## Grid GenerationQueue
Report Run Date: 03/30/2026
The California ISO Controlled Grid Generation Queue for All: Active
[6 empty] | Generating Facility | [5 empty] | MWs |  |  |  | Deliverability Status |  |  |  | Location |  | Point of Interconnection | [5 empty] | Study Availability
Project Name | Queue Position | Interconnection Request Receive Date | Queue Date | Application Status | Study Process | Type-1 | Type-2 | Type-3 | Fuel-1 | Fuel-2 | Fuel-3 | MW-1 | MW-2 | MW-3 | Net MWs to Grid | Full Capacity, Partial or Energy Only (FC/P/EO) | TPD Allocation Percentage | Off-Peak Deliverability and Economic Only | TPD Allocation Group | County | State | Utility | PTO Study Region | Station or Transmission Line | Proposed On-line Date (as filed with IR) | Current On-line Date | Suspension Status | Feasibility Study or Supplemental Review | System Impact Study or Phase I Cluster Study | Facilities Study (FAS) or Phase II Cluster Study | Optional Study (OS) | Interconnection Agreement Status
MONTEZUMA (HIGH WINDS III) | 22 | 2003-11-18 | 2003-11-18 08:00 | ACTIVE | AMEND 39 | Wind Turbine | Storage |  | Wind Turbine | Battery |  | 38 | 38 |  | 38 | Partial Capacity | 50 | Off-Peak Deliverability | Group D | SOLANO | CA | PGAE | Northern | Birds Landing 230 kV | 2005-06-30 07:00 | 2024-04-01 07:00 |  |  | Complete | Complete |  | Executed
TULE WIND | 32 | 2004-05-12 | 2004-05-24 07:00 | ACTIVE | Serial LGIP | Wind Turbine | Storage |  | Wind Turbine | Battery |  | 127.6 | 131.6 |  | 193.8 | Partial Capacity | 23 | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE | SDGE | Boulevard East Substation 138 kV | 2007-09-01 07:00 | 2030-10-31 07:00 |  | Waived | Complete | Complete | None | Executed
MIDWAY PEAKING | 54 | 2005-01-12 | 2005-01-12 08:00 | ACTIVE | Serial LGIP | Gas Turbine | Storage |  | Natural Gas | Battery |  | 119.9 | 119.9 |  | 119.9 | Full Capacity |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE | Fresno | Panoche Substation | 2008-06-01 07:00 | 2027-06-30 07:00 |  | Waived | Complete | Re-Study | None | Executed
FRESNO COGENERATION EXPANSION PROJECT | 61 | 2005-03-28 | 2005-03-30 08:00 | ACTIVE | AMEND 39 | Steam Turbine | Storage |  | Natural Gas | Battery |  | 73.27 | 18.5 |  | 73.27 | Full Capacity |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE | Fresno | Helm-Kerman 70 kV Line | 2006-05-31 07:00 | 2023-02-28 08:00 |  |  | Complete | Complete |  | Executed
LAKE ELSINORE ADVANCED PUMPED STORAGE PROJECT | 72 | 2005-04-26 | 2005-06-21 07:00 | ACTIVE | Serial LGIP | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Pumped-Storage hydro; MWs MW-1: 500 | 500 | Full Capacity |  |  |  | RIVERSIDE | CA | SDGE | SDGE | Proposed Lee Lake Substation 500 kV | 2008-12-31 08:00 | 2028-12-31 08:00 |  | Waived | Complete | Re-Study | None | Executed
BOTTLE ROCK POWER | 81 | 2005-09-13 | 2005-09-13 07:00 | ACTIVE | Serial LGIP | Steam Turbine | Storage |  | Geothermal | Battery |  | 9.435 | 47.4465 |  | 52.01 | Energy Only |  | Off-Peak Deliverability | Group A | LAKE | CA | PGAE | Kern | Geysers #17-Fulton 230 kV Line | 2006-09-01 07:00 | 2027-11-30 08:00 |  | None | Complete | Complete | None | Executed
CPC WEST | 96 | 2006-02-15 | 2006-03-01 08:00 | ACTIVE | Serial LGIP | Wind Turbine | Storage | Storage | Wind Turbine | Battery | Battery | 600 | 150 | 150 | 600 | Partial Capacity | 59.76 | Off-Peak Deliverability | Group A | KERN | CA | SCE | Northern | Tehachapi Conceptual Substation #1 | 2009-12-31 08:00 | 2026-07-05 07:00 |  | Waived | Complete | None | None | Executed
WINDSTAR I ALTERNATE | 100 | 2006-04-05 | 2006-04-05 07:00 | ACTIVE | Serial LGIP | Wind Turbine | Storage |  | Wind Turbine | Battery |  | 120 | 120 |  | 120 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Vincent Substation 230kV | 2007-12-31 08:00 | 2030-10-15 07:00 |  | Waived | Complete | None | None | Executed
SILVER RIDGE MOUNT SIGNAL | 124 | 2006-08-22 | 2006-08-22 07:00 | ACTIVE | Serial LGIP | Photovoltaic | Storage |  | Solar | Battery |  | 600 | 150 |  | 600 | Partial Capacity | 19.36 | Off-Peak Deliverability |  | IMPERIAL | CA | SDGE |  | Imperial Valley Substation 230 kV | 2011-03-01 08:00 | 2027-06-01 07:00 |  | Waived | Complete | Complete | None | Executed
SANDSTORM WIND POWER | 138 | 2006-10-23 | 2006-10-23 07:00 | ACTIVE | Serial LGIP | Wind Turbine | Storage |  | Wind Turbine | Battery |  | 60 | 90 |  | 150 | Partial Capacity | 30.44 | Off-Peak Deliverability |  | RIVERSIDE | CA | SCE | Eastern | Devers Substation 220 kV | 2008-12-31 08:00 | 2030-02-01 08:00 |  | Waived | Complete | Complete | None | Executed
MONTEZUMA II | 222 | 2007-05-23 | 2007-05-23 07:00 | ACTIVE | TC | Wind Turbine | Storage |  | Wind Turbine | Battery |  | 78 | 54 |  | 78 | Partial Capacity | 59 | Off-Peak Deliverability | Group D | SOLANO | CA | PGAE | Northern | Birds Landing 230 kV | 2010-12-31 08:00 | 2012-01-29 08:00 |  | NA | Complete | Complete | NA | Executed
TRACY COMBINED-CYCLE POWER PLANT | 268 | 2007-10-24 | 2007-10-24 07:00 | ACTIVE | Serial LGIP | Steam Turbine | Storage |  | Natural Gas | Battery |  | 145 | 40 |  | 145 | Full Capacity |  | Off-Peak Deliverability |  | SAN JOAQUIN | CA | PGAE |  | Tesla-Manteca 115kV line via Schulte Switchyard | 2012-06-01 07:00 | 2027-04-28 07:00 |  | Waived | Complete | Complete | None | Executed
AMERICAN KINGS SOLAR | 272 | 2007-11-01 | 2007-11-01 07:00 | ACTIVE | TC | Photovoltaic | Storage |  | Solar | Battery |  | 123 | 73.8 |  | 123 | Full Capacity |  | Off-Peak Deliverability | Group A | KINGS | CA | PGAE | Fresno | Henrietta 70 kV | 2012-06-01 07:00 | 2025-12-30 08:00 |  | NA | Complete | Complete | NA | Executed
ALTA VISTA SUNTOWER GENERATING STATION | 297 | 2008-01-18 | 2008-01-18 08:00 | ACTIVE | TC | Steam Turbine | Storage |  | Solar | Battery |  | 66 | 66 |  | 66 | Full Capacity |  | Off-Peak Deliverability | Group A | LOS ANGELES | CA | SCE | Northern | Neenach-Bailey 66kV line | 2009-12-01 08:00 | 2027-12-11 08:00 |  | NA | Complete | Complete | NA | Executed
LOS ESTEROS CRITICAL ENERGY FACILITY EXPANSION | 378 | 2008-05-28 | 2008-05-28 07:00 | ACTIVE | TC | Combined Cycle | Storage |  | Natural Gas | Battery |  | 120 | 3 |  | 120 | Full Capacity |  | Off-Peak Deliverability |  | SANTA CLARA | CA | PGAE | Northern | Los Esteros 115 kV | 2011-06-01 07:00 | 2023-09-01 07:00 |  | NA | Complete | Complete | NA | Executed
OCOTILLO EXPRESS | 493 | 2009-07-16 | 2009-07-31 07:00 | ACTIVE | C01 | Wind Turbine | Storage |  | Wind Turbine | Battery |  | 265.44 | 238.989 |  | 265.44 | Partial Capacity | 35 | Off-Peak Deliverability |  | IMPERIAL | CA | SDGE |  | Ocotillo Switchyard 500 kV | 2013-12-31 08:00 | 2030-05-31 07:00 |  | NA | Complete | Complete | NA | Executed
ROSAMOND WEST SOLAR | 506 | 2009-07-30 | 2009-07-31 07:00 | ACTIVE | C01 | Photovoltaic | Storage |  | Solar | Battery |  | 299.6 | 255.7 |  | 299.6 | Partial Capacity | 63.35 | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2015-07-31 07:00 | 2029-03-31 07:00 |  | NA | Complete | Complete | NA | Executed
CROW CREEK SOLAR 1 (FKA: FRONTIER SOLAR 1) (FKA AS SCATEC WESTSIDE SOLAR RANCH I AND STANISLAUS PV - PHASE 1) | 539 | 2009-12-18 | 2009-12-18 08:00 | ACTIVE | SGIP | Photovoltaic | Storage |  | Solar | Battery |  | 20 | 20 |  | 20 | Energy Only |  | Off-Peak Deliverability |  | STANISLAUS | CA | PGAE | None | Salado-Newman #1 60kV Line | 2012-10-31 07:00 | 2025-04-01 07:00 |  | None | Facilities Study | SGIA | NA | Executed
KETTLEMAN SOLAR PROJECT (FKA KETTLEMAN SOLAR FARM) | 625 | 2010-05-14 | 2010-05-14 07:00 | ACTIVE | SGIP | Photovoltaic | Storage |  | Solar | Battery |  | 20 | 20 |  | 20 | Energy Only |  | Off-Peak Deliverability |  | KINGS | CA | PGAE | Fresno | Henrietta-Tulare Lake 70 kV | 2011-12-31 08:00 | 2025-04-01 07:00 |  | None | Facilities Study | SGIA | NA | Executed
NORTH ROSAMOND SOLAR | 643R | 2010-07-30 | 2010-07-31 07:00 | ACTIVE | C03 | Photovoltaic | Storage |  | Solar | Battery |  | 153 | 100 |  | 153 | Partial Capacity | 13.95 | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Sub 230 kV Bus | 2013-06-01 07:00 | 2026-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
PUMPJACK SOLAR I (AKA PIONEER SOLAR I) | 653B | 2010-09-29 | 2010-09-29 07:00 | ACTIVE | SGIP-TC | Photovoltaic | Storage |  | Solar | Battery |  | 20 | 20 |  | 20 | Partial Capacity |  | Off-Peak Deliverability |  | KERN | CA | PGAE |  | Belridge - Temblor 115 kV | 2013-05-01 07:00 | 2027-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
EXCELSIOR SOLAR (FKA: BURFORD FIVE POINTS) | 678 | 2011-03-31 | 2011-03-31 07:00 | ACTIVE | C04 | Photovoltaic | Storage |  | Solar | Battery |  | 60 | 60 |  | 60 | Partial Capacity | 10 | Off-Peak Deliverability |  | FRESNO | CA | PGAE | Fresno | Panoche-Schindler #1 and #2 115 kV Line | 2013-09-05 07:00 | 2024-12-20 08:00 |  | NA | Complete | Complete | NA | Executed
LASSEN LODGE HYDROELECTRIC | 720 | 2011-03-31 | 2011-03-31 07:00 | ACTIVE | C04 | Generating Facility Type-1: Hydro; Generating Facility Fuel-1: Water; MWs MW-1: 4.5 | 4.5 | Energy Only |  |  |  | TEHAMA | CA | PGAE | Northern | Vota-South 60 kV | 2012-12-15 08:00 | 2027-10-15 07:00 |  | NA | Complete | Complete | NA | Executed
REDWOOD SOLAR FARM | 744 | 2011-03-31 | 2011-03-31 07:00 | ACTIVE | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 90 | 90 | Partial Capacity | 87 | Off-Peak Deliverability | Group D | KERN | CA | PGAE | Kern | Lamont 115 KV | 2014-07-01 07:00 | 2024-07-01 07:00 |  | NA | Complete | Complete | NA | Executed
BIG SKY SOLAR | 768 | 2011-03-31 | 2011-03-31 07:00 | ACTIVE | C04 | Photovoltaic | Storage |  | Solar | Battery |  | 320 | 156.02 |  | 320 | Full Capacity |  | Off-Peak Deliverability |  | LOS ANGELES | CA | SCE | Northern | Antelope Substation 230kV bus | 2014-12-31 08:00 | 2023-01-31 08:00 |  | NA | Complete | Complete | NA | Executed
WRIGHT SOLAR | 779 | 2011-03-31 | 2011-03-31 07:00 | ACTIVE | C04 | Photovoltaic | Storage |  | Solar | Battery |  | 200 | 80 |  | 200 | Partial Capacity | 49.35 | Off-Peak Deliverability |  | MERCED | CA | PGAE | Fresno | Los Banos-Panoche #1 230kV Line | 2014-01-06 08:00 | 2026-10-21 07:00 |  | NA | Complete | Complete | NA | Executed
RIO BRAVO SOLAR 1 | 900 | 2012-04-02 | 2012-04-02 07:00 | ACTIVE | C05 | Photovoltaic | Storage |  | Solar | Battery |  | 20 | 20 |  | 20 | Partial Capacity | 10 | Off-Peak Deliverability |  | KERN | CA | PGAE | None | Midway Temblor 115 kV line | 2014-12-20 08:00 | 2027-06-30 07:00 |  | NA | Complete | Complete | NA | Executed
RIO BRAVO SOLAR 2 | 972 | 2013-04-30 | 2013-04-30 07:00 | ACTIVE | C06 | Photovoltaic | Storage |  | Solar | Battery |  | 20 | 20 |  | 20 | Partial Capacity | 10 | Off-Peak Deliverability |  | KERN | CA | PGAE | None | Midway-Temblor 115kV line | 2016-12-31 08:00 | 2027-07-30 07:00 |  | NA | Complete | Complete | NA | Executed
SUNSHINE VALLEY SOLAR 1 | 993 | 2013-04-30 | 2013-04-30 07:00 | ACTIVE | C06 | Photovoltaic | Storage |  | Solar | Battery |  | 50 | 40 |  | 50 | Partial Capacity | 8 | Off-Peak Deliverability |  | NYE | NV | VEA | EOP | Valley Substation 138 kV | 2016-12-31 08:00 | 2026-12-31 08:00 |  | NA | Complete | Complete | NA | Executed
LASSEN LODGE HYDROELECTRIC 2 | 1002 | 2013-05-01 | 2013-04-30 07:00 | ACTIVE | C06 | Generating Facility Type-1: Hydro; Generating Facility Fuel-1: Water; MWs MW-1: 0.5 | 0.5 | Energy Only |  |  |  | TEHAMA | CA | PGAE | Northern | Volta-South 60 kV Line | 2015-11-15 08:00 | 2027-10-15 07:00 |  | NA | Complete | Complete | NA | Executed
LITTLE BEAR SOLAR 1 | 1028 | 2014-04-30 | 2014-04-30 07:00 | ACTIVE | C07 | Photovoltaic | Storage |  | Solar | Battery |  | 20 | 20 |  | 20 | Full Capacity |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE | Fresno | Mendota Substation 115 kV | 2016-12-01 08:00 | 2029-02-01 08:00 |  | NA | Complete | Complete | NA | Executed
LITTLE BEAR SOLAR 2 | 1029 | 2014-04-30 | 2014-04-30 07:00 | ACTIVE | C07 | Photovoltaic | Storage |  | Solar | Battery |  | 20 | 20 |  | 20 | Full Capacity |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE | Fresno | Mendota Substation 115 kV | 2018-09-01 07:00 | 2029-02-01 08:00 |  | NA | Complete | Complete | NA | Executed
CHULA VISTA ENERGY CENTER 2 | 1045 | 2014-04-30 | 2014-04-30 07:00 | ACTIVE | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 49.7 | 49.7 | Full Capacity |  |  | Group A | SAN DIEGO | CA | SDGE | SDGE | Otay Substation 69 kV | 2019-11-01 07:00 | 2026-04-28 07:00 |  | NA | Complete | Complete | NA | Executed
NORTH JOHNSON ENERGY CENTER | 1047 | 2014-04-30 | 2014-04-30 07:00 | ACTIVE | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 50 | 50 | Full Capacity |  |  | Group A | SAN DIEGO | CA | SDGE | SDGE | El Cajon Substation 69 kV | 2019-11-01 07:00 | 2026-04-01 07:00 |  | NA | Complete | Complete | NA | Executed
ESCONDIDO ENERGY CENTER 2 | 1048 | 2014-04-30 | 2014-04-30 07:00 | ACTIVE | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 33 | 33 | Full Capacity |  |  | Group A | SAN DIEGO | CA | SDGE | SDGE | Escondido Substation 69 kV | 2019-11-01 07:00 | 2030-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
WHITE WING RANCH SOLAR | 1062 | 2014-04-30 | 2014-04-30 07:00 | ACTIVE | C07 | Photovoltaic | Storage |  | Solar | Battery |  | 200 | 200 |  | 200 | Energy Only |  | Off-Peak Deliverability |  | YUMA | AZ | SDGE | SDGE | Hoodoo Wash Switchyard 500 kV | 2018-12-31 08:00 | 2026-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
ARES NEVADA | 1064 | 2014-04-30 | 2014-04-30 07:00 | ACTIVE | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Gravity via Rail; MWs MW-1: 44 | 44 | Energy Only |  |  |  | NYE | NV | GLW | None | Gamebird Substation 230 kV | 2017-01-01 08:00 | 2027-01-08 08:00 |  | NA | Complete | Complete | NA | Executed
GASKELL WEST | 1074 | 2014-04-30 | 2014-04-30 07:00 | ACTIVE | C07 | Photovoltaic | Storage |  | Solar | Battery |  | 125 | 61.62 |  | 125 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 220 kV | 2016-06-30 07:00 | 2026-12-02 08:00 |  | NA | Complete | Complete | NA | Executed
WILLOW SPRINGS SOLAR 3 | 1076 | 2014-04-30 | 2014-04-30 07:00 | ACTIVE | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 50 | 50 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230 kV | 2017-06-30 07:00 | 2026-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
ALTAMONT MIDWAY LTD | 1096 | 2015-02-24 | 2015-04-13 07:00 | ACTIVE | FT | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 5 | 5 | Energy Only |  | Off-Peak Deliverability |  | ALAMEDA | CA | PGAE | Northern | Altamont Midway 230 kV | 2015-08-31 07:00 | 2027-04-28 07:00 |  | None | NA | NA | NA | Executed
LITTLE BEAR 3 | 1127 | 2015-04-28 | 2015-04-30 07:00 | ACTIVE | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 20.44 | 20 |  | 20 | Full Capacity |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE | Fresno | Mendota Substation 115kV | 2020-08-01 07:00 | 2029-02-02 08:00 |  | NA | Complete | Complete | NA | Executed
LITTLE BEAR 4 | 1128 | 2015-04-28 | 2015-04-30 07:00 | ACTIVE | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 103.09 | 100 |  | 100 | Full Capacity |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE | Fresno | Mendota Substation 115kV | 2020-12-01 08:00 | 2029-02-02 08:00 |  | NA | Complete | Complete | NA | Executed
LUNA VALLEY SOLAR | 1129 | 2015-04-30 | 2015-04-30 07:00 | ACTIVE | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 204 | 168.5 |  | 200 | Partial Capacity | 15 | Off-Peak Deliverability |  | FRESNO | CA | PGAE | Fresno | Tranquility 230 kV | 2018-12-31 08:00 | 2028-12-29 08:00 |  | NA | Complete | Complete | NA | Executed
SCARLET | 1135 | 2015-04-29 | 2015-04-30 07:00 | ACTIVE | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 400 | 400 |  | 400 | Full Capacity |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE | Fresno | Tranquility 230 kV | 2018-12-31 08:00 | 2025-12-23 08:00 |  | NA | Complete | Complete | NA | Executed
LAKE ALPAUGH BATTERY STORAGE | 1143 | 2015-04-29 | 2015-04-30 07:00 | ACTIVE | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 10 | 10 | Full Capacity |  |  |  | TULARE | CA | PGAE | Kern | Corcoran-Olive 115 kV Line | 2017-12-31 08:00 | 2026-02-15 08:00 |  | NA | Complete | Complete | NA | Executed
FALLBROOK ENERGY STORAGE | 1169 | 2015-04-30 | 2015-04-30 07:00 | ACTIVE | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 69.6 | 69.6 | Full Capacity |  |  |  | SAN DIEGO | CA | SDGE | SDGE | Avocado Substation 69 kV | 2020-02-01 08:00 | 2026-03-06 08:00 |  | NA | Complete | Complete | NA | Executed
LECONTE ENERGY STORAGE | 1175 | 2015-04-29 | 2015-04-30 07:00 | ACTIVE | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 125 | 125 | Partial Capacity | 32 |  | Group B | IMPERIAL | CA | SDGE | SDGE | Imperial Valley Substation 230 kV | 2018-09-01 07:00 | 2026-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
ARATINA SOLAR CENTER 1 | 1204 | 2015-04-30 | 2015-04-30 07:00 | ACTIVE | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 200 | 200 |  | 200 | Partial Capacity | 19 | Off-Peak Deliverability | Group A | SAN BERNARDINO | CA | SCE | NOL | Kramer Substation 230kV | 2020-06-01 07:00 | 2026-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
SIENNA SOLAR FARM | 1207 | 2015-04-30 | 2015-04-30 07:00 | ACTIVE | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 200 | 200 |  | 200 | Partial Capacity | 93 | Off-Peak Deliverability | Group D | SAN BERNARDINO | CA | SCE | NOL | Calcite Substation 230kV | 2020-06-01 07:00 | 2027-01-28 08:00 |  | NA | Complete | Complete | NA | Executed
ANTELOPE SOLAR 2 | 1208 | 2015-04-30 | 2015-04-30 07:00 | ACTIVE | C08 | Storage | Photovoltaic |  | Battery | Solar |  | 358.88 | 423 |  | 650 | Full Capacity |  | Off-Peak Deliverability |  | LOS ANGELES | CA | SCE | Northern | Antelope Substation 220kV | 2018-12-31 08:00 | 2025-11-27 08:00 |  | NA | Complete | Complete | NA | Executed
GOLDEN FIELDS SOLAR | 1212 | 2015-04-30 | 2015-04-30 07:00 | ACTIVE | C08 | Storage | Storage |  | Battery | Battery |  | 52 | 48 |  | 100 | Full Capacity |  | Off-Peak Deliverability | Group 3 | KERN | CA | SCE | Northern | Whirlwind Substation 220kV | 2018-06-30 07:00 | 2026-12-01 08:00 |  | NA | Complete | Complete | NA | Executed
WILLOW SPRINGS SOLAR 4 | 1217 | 2015-04-28 | 2015-04-30 07:00 | ACTIVE | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 75 | 75 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2019-12-31 08:00 | 2026-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
AGUA CALIENTE SOLAR 2 | 1222 | 2016-03-01 | 2016-03-08 08:00 | ACTIVE | ISP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | Off-Peak Energy Only |  | MARICOPA | AZ | SDGE | SDGE | Hoodoo Wash Switchyard 500 kV | 2016-12-01 08:00 | 2016-12-01 08:00 |  | NA | Complete | Complete | NA
DAYLIGHT | 1223 | 2016-04-22 | 2016-05-02 07:00 | ACTIVE | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 310.707 | 300 |  | 300 | Partial Capacity | 60 | Off-Peak Deliverability | Group B | KINGS | CA | PGAE | Fresno | Mustang 230 kV | 2020-12-31 08:00 | 2028-01-19 08:00 |  | NA | Complete | Complete | NA | Executed
PLUOT | 1242 | 2016-05-03 | 2016-05-02 07:00 | ACTIVE | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 246.4 | 225 |  | 246.4 | Partial Capacity | 59 | Off-Peak Deliverability | Group B | KINGS | CA | PGAE | Fresno | Gates 230 kV | 2023-04-05 07:00 | 2026-06-30 07:00 |  | NA | Complete | Complete | NA | Executed
POMEGRANATE | 1243 | 2016-05-03 | 2016-05-02 07:00 | ACTIVE | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 254 | 225 |  | 249.7 | Full Capacity |  | Off-Peak Deliverability | Group A | KINGS | CA | PGAE | Fresno | Gates 230 kV | 2022-04-06 07:00 | 2027-12-31 08:00 |  | NA | Complete | Complete | NA | Executed
KYAN SOLAR | 1260 | 2016-04-27 | 2016-05-02 07:00 | ACTIVE | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 102 | 100 | Energy Only |  | Off-Peak Deliverability | Group B | KERN | CA | PGAE | Kern | Midway-Wheeler Ridge #2 230 kV Line | 2020-10-14 07:00 | 2027-03-02 08:00 |  | NA | Complete | Complete | NA | Executed
CORBY | 1270 | 2016-04-27 | 2016-05-02 07:00 | ACTIVE | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 313.5 | 300 | Full Capacity |  |  | Group 3 | SOLANO | CA | PGAE | Northern | Vaca-Dixon 230 kV | 2020-12-01 08:00 | 2027-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
MULQUEENEY RANCH WIND | 1277 | 2016-05-02 | 2016-05-02 07:00 | ACTIVE | C09 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 114 | 20 | Full Capacity |  | Off-Peak Deliverability |  | ALAMEDA | CA | PGAE | Northern | Tesla 230 kV | 2020-03-01 08:00 | 2026-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
DAGGETT SOLAR 3 | 1314 | 2016-04-28 | 2016-05-02 07:00 | ACTIVE | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 313.88 | 208 |  | 300 | Full Capacity |  | Off-Peak Deliverability |  | SAN BERNARDINO | CA | SCE | NOL | Kramer Substation 230kV | 2020-06-30 07:00 | 2023-08-06 07:00 |  | NA | Complete | Complete | NA | Executed
SOLAR STAR 3 | 1322 | 2016-04-25 | 2016-05-02 07:00 | ACTIVE | C09 | Storage | Photovoltaic |  | Battery | Solar |  | 24.95 | 25 |  | 24 | Full Capacity |  | Off-Peak Deliverability | Group 3 | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2021-12-31 08:00 | 2026-08-12 07:00 |  | NA | Complete | Complete | NA | Executed
SOLAR STAR 4 | 1323 | 2016-04-25 | 2016-05-02 07:00 | ACTIVE | C09 | Storage | Photovoltaic |  | Battery | Solar |  | 24.95 | 25.05 |  | 24 | Full Capacity |  | Off-Peak Deliverability | Group 3 | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2021-12-31 08:00 | 2026-08-12 07:00 |  | NA | Complete | Complete | NA | Executed
PASTORIA SOLAR | 1335 | 2016-05-02 | 2016-05-02 07:00 | ACTIVE | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 106.875 | 80 |  | 105.2 | Partial Capacity | 77 | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Pastoria Substation 230kV | 2019-09-01 07:00 | 2026-05-04 07:00 |  | NA | Complete | Complete | NA | Executed
TAHOE | 1339 | 2016-04-29 | 2016-05-02 07:00 | ACTIVE | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 300 | 300 | Partial Capacity | 93 | Off-Peak Deliverability |  | CLARK | NV | SCE | EOP | SCE owned Eldorado Bus 230kV | 2019-07-31 07:00 | 2026-05-01 07:00 |  | NA | Complete | Complete | NA | Executed
ROCCASECCA BESS | 1347 | 2016-05-02 | 2016-05-02 07:00 | ACTIVE | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 126.5934 | 126.5934 | Full Capacity |  | Off-Peak Deliverability |  | CLARK | NV | GLW | None | Sloan Canyon Switching Station 230kV | 2019-07-31 07:00 | 2027-03-01 08:00 |  | NA | Complete | Complete | NA | Executed
ARAMIS POWER PLANT | 1349 | 2017-04-28 | 2017-05-01 07:00 | ACTIVE | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 101.4 | 101.3 |  | 100 | Full Capacity |  | Off-Peak Deliverability | Group 2 | ALAMEDA | CA | PGAE | Northern | Cayetano 230 kV | 2020-12-31 08:00 | 2026-07-31 07:00 |  | NA | Complete | Complete | NA | Executed
SAND HILL C | 1363 | 2017-04-29 | 2017-05-01 07:00 | ACTIVE | C10 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 84.25 | 80.8 | Full Capacity |  | Off-Peak Deliverability |  | ALAMEDA | CA | PGAE | Northern | Delta Switching Yard-Tesla 230 kV Line | 2019-12-31 08:00 | 2027-04-28 07:00 |  | NA | Complete | Complete | NA | Executed
GONZAGA WIND FARM | 1378 | 2017-04-27 | 2017-05-01 07:00 | ACTIVE | C10 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 80 | 76.35 | Partial Capacity | 66.5 | Off-Peak Deliverability | Group 2 | MERCED | CA | PGAE | Fresno | Los Banos 70 kV | 2020-10-09 07:00 | 2026-03-31 07:00 |  | NA | Complete | Complete | NA | Executed
HEARTLAND 1 | 1379 | 2017-04-26 | 2017-05-01 07:00 | ACTIVE | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 156.04 | 72.27 |  | 150 | Partial Capacity | 46.16 | Off-Peak Deliverability |  | FRESNO | CA | PGAE | Fresno | Tranquility 230 kV | 2021-09-01 07:00 | 2028-06-30 07:00 |  | NA | Complete | Complete | NA | Executed
HEARTLAND 2 | 1380 | 2017-04-26 | 2017-05-01 07:00 | ACTIVE | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 156.05 | 72.2932 |  | 150 | Partial Capacity | 46.16 | Off-Peak Deliverability |  | FRESNO | CA | PGAE | Fresno | Tranquility 230 kV | 2021-09-01 07:00 | 2028-06-30 07:00 |  | NA | Complete | Complete | NA | Executed
LAS CAMAS 1 | 1382 | 2017-04-29 | 2017-05-01 07:00 | ACTIVE | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 102.5 | 100 |  | 100 | Partial Capacity | 65 | Off-Peak Energy Only | Group D | MERCED | CA | PGAE | Fresno | Los Banos 230 kV | 2021-11-30 08:00 | 2027-12-31 08:00 |  | NA | Complete | Complete | NA | Executed
REDUX SOLAR | 1389 | 2017-05-01 | 2017-05-01 07:00 | ACTIVE | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 128.24 | 61.25 |  | 125 | Full Capacity |  | Off-Peak Deliverability | Group 2b | FRESNO | CA | PGAE | Fresno | Gates 230 kV | 2020-12-30 08:00 | 2026-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
SONRISA | 1391 | 2017-04-29 | 2017-05-01 07:00 | ACTIVE | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 200 | 184 |  | 200 | Partial Capacity | 92 | Off-Peak Deliverability | Group 1 | FRESNO | CA | PGAE | Fresno | Tranquility 230 kV | 2021-11-30 08:00 | 2026-12-31 08:00 |  | NA | Complete | Complete | NA | Executed
DRIFTWOOD STELLA | 1394 | 2017-04-29 | 2017-05-01 07:00 | ACTIVE | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 200 | 200 |  | 200 | Energy Only |  | Off-Peak Deliverability | Group D | KERN | CA | PGAE | Kern | Midway 115 kV | 2021-11-30 08:00 | 2026-11-01 07:00 |  | NA | Complete | Complete | NA | Executed
ATLAS COMPLEX | 1402 | 2017-04-28 | 2017-05-01 07:00 | ACTIVE | C10 | Storage | Photovoltaic |  | Battery | Solar |  | 2171 | 2256 |  | 3200 | Partial Capacity | 63 | Off-Peak Deliverability | Group A | LA PAZ | AZ | DCRT | Eastern | Delaney-Colorado River 500 kV Line | 2020-12-31 08:00 | 2026-01-01 08:00 |  | NA | Complete | Complete | NA | Executed
ATHOS POWER PLANT | 1405 | 2017-04-28 | 2017-05-01 07:00 | ACTIVE | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 458 | 450 |  | 450 | Full Capacity |  | Off-Peak Deliverability | Group A | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 230kV | 2020-12-31 08:00 | 2027-05-17 07:00 |  | NA | Complete | Complete | NA | Executed
BALDY MESA | 1413 | 2017-04-29 | 2017-05-01 07:00 | ACTIVE | C10 | Storage | Photovoltaic |  | Battery | Solar |  | 75 | 150 |  | 100 | Partial Capacity | 94 | Off-Peak Deliverability | Group 2 | SAN BERNARDINO | CA | SCE | NOL | Roadway Substation 115kV bus | 2020-12-31 08:00 | 2026-11-01 07:00 |  | NA | Complete | Complete | NA | Executed
CAMINO SOLAR | 1419 | 2017-04-27 | 2017-05-01 07:00 | ACTIVE | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 44 | 11 |  | 54.28 | Full Capacity |  | Off-Peak Deliverability | Group 2 | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2020-08-15 07:00 | 2027-12-31 08:00 |  | NA | Complete | Complete | NA | Executed
MOUNT LAGUNA WIND 2 | 1429 | 2017-04-28 | 2017-05-01 07:00 | ACTIVE | C10 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 400 | 400 | Energy Only |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE | SDGE | Suncrest - Ocotillo 500 kV Line | 2020-06-01 07:00 | 2031-02-05 08:00 |  | NA | Complete | Complete | NA | Executed
STARLIGHT SOLAR | 1432 | 2017-05-01 | 2017-05-01 07:00 | ACTIVE | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 20 | 17.4 |  | 20 | Partial Capacity | 87 | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE | None | Boulevard East Substation 69 kV | 2020-06-01 07:00 | 2027-04-30 07:00 |  | NA | Complete | Complete | NA | Executed
IRONWOOD SOLAR | 1435 | 2017-04-24 | 2017-05-01 07:00 | ACTIVE | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 168 | 250 |  | 250 | Energy Only |  | Off-Peak Deliverability |  | YUMA | AZ | SDGE | SDGE | Hoodoo Wash Switchyard 500 kV | 2020-12-31 08:00 | 2030-06-30 07:00 |  | NA | Complete | Complete | NA | Executed
AJO POWER BANK | 1442 | 2018-04-05 | 2018-04-16 07:00 | ACTIVE | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 124.3 | 120 | Full Capacity |  |  |  | SANTA CLARA | CA | PGAE | Northern | Llagas-Gilroy Foods 115 kV line | 2020-12-01 08:00 | 2028-01-01 08:00 |  | NA | Complete | Complete | NA | Executed
ANGELA | 1443 | 2018-04-13 | 2018-04-16 07:00 | ACTIVE | C11 | Photovoltaic | Storage |  | Solar | Battery |  | 40 | 20 |  | 40 | Partial Capacity | 65 | Off-Peak Deliverability | Group 2a | TULARE | CA | PGAE | Kern | Olive 115 kV | 2021-11-30 08:00 | 2025-12-15 08:00 |  | NA | Complete | Complete | NA | Executed
SALOON ENERGY STORAGE | 1444 | 2018-04-04 | 2018-04-16 07:00 | ACTIVE | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 150 | 150 | Partial Capacity | 54 | Off-Peak Deliverability | Group 2 | COLUSA | CA | PGAE | Northern | Cortina 115 kV | 2022-12-01 08:00 | 2027-07-13 07:00 |  | NA | Complete | Complete | NA | Executed
HUMMINGBIRD ENERGY STORAGE | 1454 | 2018-04-09 | 2018-04-16 07:00 | ACTIVE | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 75 | 75 | Full Capacity |  |  | Group 1a | SANTA CLARA | CA | PGAE | Northern | Metcalf 115 kV | 2020-12-31 08:00 | 2025-09-25 07:00 |  | NA | Complete | Complete | NA | Executed
JANUS | 1455 | 2018-04-12 | 2018-04-16 07:00 | ACTIVE | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 80 | 83.54 |  | 80 | Full Capacity |  | Off-Peak Deliverability | Group 3 | COLUSA | CA | PGAE | Northern | Cortina 60 kV | 2021-12-31 08:00 | 2027-03-01 08:00 |  | NA | Complete | Complete | NA | Executed
LAS CAMAS 3 | 1456 | 2018-04-10 | 2018-04-16 07:00 | ACTIVE | C11 | Photovoltaic | Storage |  | Solar | Battery |  | 102.5 | 100 |  | 100 | Partial Capacity | 65 | Off-Peak Energy Only | Group D | MERCED | CA | PGAE | Fresno | Los Banos 230 kV | 2022-11-30 08:00 | 2027-12-31 08:00 |  | NA | Complete | Complete | NA | Executed
MILPA POWER BANK | 1457 | 2018-04-09 | 2018-04-16 07:00 | ACTIVE | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 3 | 3 | Full Capacity |  |  | Group 3 | SANTA CLARA | CA | PGAE | Northern | Los Esteros 115 kV | 2020-12-01 08:00 | 2025-04-29 07:00 |  | NA | Complete | Complete | NA
MULQUEENEY RANCH WIND 2 | 1459 | 2018-04-12 | 2018-04-16 07:00 | ACTIVE | C11 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 62.5 | 60 | Full Capacity |  | Off-Peak Deliverability | Group 2b | ALAMEDA | CA | PGAE | Northern | Tesla 230 kV | 2021-12-15 08:00 | 2026-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
RECLAIMED WIND | 1461 | 2018-04-04 | 2018-04-16 07:00 | ACTIVE | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 114.4 | 90.7 | Full Capacity |  | Off-Peak Deliverability | Group A | ALAMEDA | CA | PGAE | Northern | Kelso-Tesla Tap 230 kV | 2020-12-31 08:00 | 2026-12-01 08:00 |  | NA | Complete | Complete | NA | Executed
SOLANO 4 WIND | 1463 | 2018-04-04 | 2018-04-16 07:00 | ACTIVE | C11 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 92.354 | 90.8 | Full Capacity |  | Off-Peak Deliverability | Group 1 | SOLANO | CA | PGAE | Northern | Birds Landing 230 kV | 2023-03-31 07:00 | 2025-05-31 07:00 |  | NA | Complete | Complete | NA | Executed
KEY STORAGE 1 | 1479 | 2018-04-11 | 2018-04-16 07:00 | ACTIVE | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 309.3 | 300.1 | Full Capacity |  |  | Group 3 | FRESNO | CA | PGAE | Fresno | Gates 500 kV | 2022-12-01 08:00 | 2026-10-01 07:00 |  | NA | Complete | Complete | NA | Executed
AZALEA | 1493 | 2018-04-16 | 2018-04-16 07:00 | ACTIVE | C11 | Photovoltaic | Storage |  | Solar | Battery |  | 61.3 | 38 |  | 60 | Partial Capacity | 70 | Off-Peak Deliverability | Group 2 | KERN | CA | PGAE | Kern | Arco 70 kV | 2022-11-01 07:00 | 2025-09-12 07:00 |  | NA | Complete | Complete | NA | Executed
CHALAN SOLAR | 1495 | 2018-04-13 | 2018-04-16 07:00 | ACTIVE | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 25.2 | 66.6 |  | 64.9 | Full Capacity |  | Off-Peak Deliverability | Group 1a | KERN | CA | PGAE | Kern | Arco 230 kV | 2021-12-01 08:00 | 2026-04-12 07:00 |  | NA | Complete | Complete | NA | Executed
DESCENDANT RANCH 1 | 1496 | 2018-04-11 | 2018-04-16 07:00 | ACTIVE | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 510 | 513.5 |  | 500 | Energy Only |  | Off-Peak Deliverability | Group 1b | COLUSA | CA | PGAE | Northern | Delevan 230 kV | 2023-12-01 08:00 | 2034-02-27 08:00 |  | NA | Complete | Complete | NA | Executed
JASMINE | 1499 | 2018-04-16 | 2018-04-16 07:00 | ACTIVE | C11 | Photovoltaic | Storage |  | Solar | Battery |  | 71.161 | 70 |  | 70 | Partial Capacity | 92 | Off-Peak Deliverability | Group 3 | KERN | CA | PGAE | Kern | Lakeview 70 kV | 2022-11-01 07:00 | 2026-08-31 07:00 |  | NA | Complete | Complete | NA | Executed
PROSPECT ENERGY STORAGE | 1507 | 2018-04-16 | 2018-04-16 07:00 | ACTIVE | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 58.75 | 49.9 | Full Capacity |  |  | Group 1 | SACRAMENTO | CA | PGAE | Northern | Gold Hill 60 kV | 2022-06-01 07:00 | 2028-06-01 07:00 | Suspended | NA | Complete | Complete | NA | Executed
BELLEFIELD SOLAR FARM | 1510 | 2018-04-16 | 2018-04-16 07:00 | ACTIVE | C11 | Photovoltaic | Storage |  | Solar | Battery |  | 500 | 500 |  | 500 | Full Capacity |  | Off-Peak Deliverability | Group 3 | KERN | CA | SCE | Northern | Windhub Substation 230kV | 2022-10-01 07:00 | 2025-08-01 07:00 |  | NA | Complete | Complete | NA | Executed
SANBORN SOLAR 2 | 1518 | 2018-04-13 | 2018-04-16 07:00 | ACTIVE | C11 | Photovoltaic | Storage |  | Solar | Battery |  | 334 | 372.5 |  | 500 | Full Capacity |  | Off-Peak Deliverability | Group 1 | KERN | CA | SCE | Northern | Windhub Substation 230kV | 2022-12-31 08:00 | 2025-10-01 07:00 |  | NA | Complete | Complete | NA | Executed
BALDY MESA 2 | 1519 | 2018-04-15 | 2018-04-16 07:00 | ACTIVE | C11 | Photovoltaic | Storage |  | Solar | Battery |  | 50 | 75 |  | 100 | Partial Capacity | 94 | Off-Peak Deliverability | Group 2 | SAN BERNARDINO | CA | SCE | NOL | Roadway Substation 115kV | 2021-12-15 08:00 | 2026-11-01 07:00 |  | NA | Complete | Complete | NA | Executed
ARIDA SOLAR FARM | 1522 | 2018-04-16 | 2018-04-16 07:00 | ACTIVE | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 370 | 370 |  | 370 | Full Capacity |  | Off-Peak Deliverability | Group 3 | CLARK | NV | SCE | EOP | Mohave Substation 500kV | 2022-10-01 07:00 | 2027-09-15 07:00 |  | NA | Complete | Complete | NA
CENTENNIAL FLATS | 1529 | 2018-04-17 | 2018-04-16 07:00 | ACTIVE | C11 | Photovoltaic | Storage |  | Solar | Battery |  | 500 | 267 |  | 500 | Partial Capacity | 83.46 | Off-Peak Deliverability | Group 3 | LA PAZ | AZ | DCRT | Eastern | Delaney-Colorado River 500 kV Line | 2022-12-15 08:00 | 2026-04-15 07:00 |  | NA | Complete | Complete | NA | Executed
KETTLE SOLAR ONE | 1532 | 2018-04-16 | 2018-04-16 07:00 | ACTIVE | C11 | Photovoltaic | Storage |  | Solar | Battery |  | 90 | 90 |  | 90 | Full Capacity |  | Off-Peak Deliverability | Group 2 | SAN DIEGO | CA | SDGE | SDGE | Carrizo Gorge Switchyard 138 kV | 2020-12-01 08:00 | 2026-10-31 07:00 |  | NA | Complete | Complete | NA | Executed
VULCAN | 1534 | 2018-04-11 | 2018-04-16 07:00 | ACTIVE | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 250 | 250 |  | 250 | Energy Only |  | Off-Peak Deliverability | Group B | MARICOPA | AZ | SDGE | SDGE | Hassayampa Common Bus 500 kV | 2021-05-01 07:00 | 2027-12-31 08:00 |  | NA | Complete | Complete | NA
IRVING STORAGE | 1539 | 2019-03-05 | 2019-05-07 07:00 | ACTIVE | ISP | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 782.79 | 750 | Full Capacity |  |  | Other | MONTEREY | CA | PGAE | Northern | Moss Landing 500 kV | 2022-12-01 08:00 | 2025-11-30 08:00 |  | NA | Complete | Complete | NA | Executed
TANAGER STORAGE | 1550 | 2019-04-02 | 2019-04-15 07:00 | ACTIVE | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 200 | 200 | Full Capacity |  |  | Group 2 | SANTA CLARA | CA | PGAE | Northern | Los Esteros 230 kV | 2023-06-30 07:00 | 2027-12-15 08:00 |  | NA | Complete | Complete | NA | Executed
CORMORANT STORAGE | 1552 | 2019-04-02 | 2019-04-15 07:00 | ACTIVE | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 250 | 250 | Full Capacity |  |  | Group 2 | SAN FRANCISCO | CA | PGAE | Northern | Martin 115 kV | 2023-06-30 07:00 | 2027-04-15 07:00 |  | NA | Complete | Complete | NA | Executed
JEWELFLOWER STORAGE | 1553 | 2019-04-05 | 2019-04-15 07:00 | ACTIVE | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 354.88 | 350 | Full Capacity |  |  | Group 3 | SANTA CLARA | CA | PGAE | Northern | Metcalf 230 kV | 2022-12-31 08:00 | 2029-03-28 07:00 |  | NA | Complete | Complete | NA | Executed
NOOSA ENERGY STORAGE | 1557 | 2019-04-15 | 2019-04-15 07:00 | ACTIVE | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 99 | 99 | Full Capacity |  |  | Group 3 | SAN JOAQUIN | CA | PGAE | Northern | Ripon 115 kV | 2022-12-16 08:00 | 2029-04-16 07:00 |  | NA | Complete | Complete | NA | Executed
DYNAMO SOLAR | 1565 | 2019-04-08 | 2019-04-15 07:00 | ACTIVE | C12 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 24.5 | 24.5 | Full Capacity |  | Off-Peak Deliverability | Group 3 | NAPA | CA | PGAE | Northern | Tulucay 60 kV | 2023-06-30 07:00 | 2027-07-16 07:00 |  | NA | Complete | Complete | NA | Executed
AIR STATION 1 | 1568 | 2019-04-16 | 2019-04-15 07:00 | ACTIVE | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 21.05 | 21.05 |  | 40 | Energy Only |  | Off-Peak Energy Only |  | KINGS | CA | PGAE | Fresno | Henrietta-Lemoore NAS 70 kV | 2021-12-31 08:00 | 2021-12-31 08:00 |  | NA | Complete | Complete | NA | In Progress
KINGSROAD HYBRID SOLAR | 1587 | 2019-04-16 | 2019-04-15 07:00 | ACTIVE | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 101.78 | 101.78 |  | 100 | Energy Only |  | Off-Peak Energy Only | Group 2a | KERN | CA | PGAE | Kern | Arco 230 kV | 2023-11-30 08:00 | 2028-12-01 08:00 |  | NA | Complete | Complete | NA | Executed
PELICANS JAW HYBRID SOLAR | 1593 | 2019-04-09 | 2019-04-15 07:00 | ACTIVE | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 500 | 500 |  | 500 | Partial Capacity | 47.8 | Off-Peak Energy Only | Group A | KINGS | CA | PGAE | Fresno | Gates-Midway 230 kV Line | 2022-11-30 08:00 | 2028-01-24 08:00 |  | NA | Complete | Complete | NA | Executed
BUTTONBUSH SOLAR HYBRID ENERGY CENTER | 1596 | 2019-04-01 | 2019-04-15 07:00 | ACTIVE | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 818 | 818 |  | 800 | Full Capacity |  | Off-Peak Deliverability | Group 3 | KERN | CA | PGAE | Kern | Midway 500 kV | 2025-11-01 07:00 | 2026-12-01 08:00 |  | NA | Complete | Complete | NA | Executed
ARATINA SOLAR CENTER 2 | 1604 | 2019-04-01 | 2019-04-15 07:00 | ACTIVE | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 150 | 113 |  | 200 | Partial Capacity | 85.3 | Off-Peak Deliverability | Group 1a | KERN | CA | SCE | NOL | Kramer Substation 230kV | 2022-06-01 07:00 | 2026-12-31 08:00 |  | NA | Complete | Complete | NA | Executed
AVOCET STORAGE | 1608 | 2019-04-01 | 2019-04-15 07:00 | ACTIVE | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 200 | 200 | Full Capacity |  |  | Group 2 | LOS ANGELES | CA | SCE | Metro | Hinson Substation 230kV | 2023-06-30 07:00 | 2026-04-15 07:00 |  | NA | Complete | Complete | NA | Executed
COMMERCE ENERGY STORAGE | 1611 | 2019-04-09 | 2019-04-15 07:00 | ACTIVE | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 250 | 250 | Full Capacity |  |  | Group 3 | LOS ANGELES | CA | SCE | Metro | Laguna Bell Substation 230kV | 2023-01-01 08:00 | 2026-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
KESTREL STORAGE | 1615 | 2019-04-01 | 2019-04-15 07:00 | ACTIVE | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 200 | 200 | Full Capacity |  |  | Group 3 | LOS ANGELES | CA | SCE | Metro | Walnut Substation 220kV | 2023-06-30 07:00 | 2027-02-28 08:00 |  | NA | Complete | Complete | NA | Executed
LOCKHART SOLAR 2 | 1617 | 2019-04-05 | 2019-04-15 07:00 | ACTIVE | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 59.7 | 105 |  | 150 | Full Capacity |  | Off-Peak Deliverability | Group B | SAN BERNARDINO | CA | SCE | NOL | Kramer Substation 230kV | 2022-12-01 08:00 | 2026-04-01 07:00 |  | NA | Complete | Complete | NA | Executed
GOLDBACK SOLAR CENTER | 1619 | 2019-04-12 | 2019-04-15 07:00 | ACTIVE | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 500 | 500 | Full Capacity |  | Off-Peak Deliverability | Group 3 | VENTURA | CA | SCE | Northern | Moorpark Substation 230 kV | 2023-06-01 07:00 | 2026-03-31 07:00 |  | NA | Complete | Complete | NA | Executed
ANGELENO SOLAR FARM | 1625 | 2019-03-31 | 2019-04-15 07:00 | ACTIVE | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 1150 | 1150 |  | 1150 | Full Capacity |  | Off-Peak Deliverability | Group 3 | LOS ANGELES | CA | SCE | Northern | Vincent Substation 500kV | 2023-06-01 07:00 | 2028-12-31 08:00 |  | NA | Complete | Complete | NA | Executed
HUMIDOR STORAGE 1 | 1629 | 2019-04-11 | 2019-04-15 07:00 | ACTIVE | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 305 | 300 | Full Capacity |  |  | Group 3 | LOS ANGELES | CA | SCE | Northern | Vincent Substation 230 kV | 2021-12-01 08:00 | 2028-10-01 07:00 |  | NA | Complete | Complete | NA | Executed
BELLEFIELD 2 SOLAR FARM | 1631 | 2019-04-01 | 2019-04-15 07:00 | ACTIVE | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 500 | 500 |  | 500 | Full Capacity |  | Off-Peak Deliverability | Group 2a | KERN | CA | SCE | Northern | Windhub Substation 220kV | 2022-10-01 07:00 | 2024-09-01 07:00 |  | NA | Complete | Complete | NA | Executed
SANBORN HYBRID 3 | 1632 | 2019-04-05 | 2019-04-15 07:00 | ACTIVE | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 672.27 | 1420.24 |  | 1400 | Partial Capacity | 89.84 | Off-Peak Deliverability | Group 2 | KERN | CA | SCE | Northern | Windhub Substation 500kV | 2023-12-01 08:00 | 2026-12-31 08:00 |  | NA | Complete | Complete | NA | Executed
CALYPSO SOLAR | 1636 | 2019-04-04 | 2019-04-15 07:00 | ACTIVE | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 400 | 400 |  | 400 | Energy Only |  | Off-Peak Energy Only | Group D | RIVERSIDE | CA | SCE | Eastern | Colorado River Substation 230kV | 2023-12-01 08:00 | 2031-10-28 07:00 |  | NA | Complete | Complete | NA | Executed
OBERON | 1642 | 2019-04-02 | 2019-04-15 07:00 | ACTIVE | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 518.4 | 518.4 |  | 500 | Partial Capacity | 60 | Off-Peak Deliverability | Group 2a | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 500kV | 2022-12-31 08:00 | 2026-04-15 07:00 |  | NA | Complete | Complete | NA | Executed
LYCAN SOLAR | 1643 | 2019-04-04 | 2019-04-15 07:00 | ACTIVE | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 400 | 400 |  | 400 | Full Capacity |  | Off-Peak Energy Only | Group B | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 500kV | 2023-12-01 08:00 | 2030-04-01 07:00 |  | NA | Complete | Complete | NA | Executed
MENIFEE POWER BANK | 1645 | 2019-04-10 | 2019-04-15 07:00 | ACTIVE | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 680 | 680 | Full Capacity |  |  | Other | RIVERSIDE | CA | SCE | Eastern | Valley Substation 500kV | 2022-12-01 08:00 | 2025-10-01 07:00 |  | NA | Complete | Complete | NA | Executed
DOUBLE BUTTE STORAGE | 1646 | 2019-04-05 | 2019-04-15 07:00 | ACTIVE | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 507.6 | 500 | Full Capacity |  |  | Group A | RIVERSIDE | CA | SCE | Eastern | Valley Substation 500 kV | 2022-12-31 08:00 | 2030-07-01 07:00 |  | NA | Complete | Complete | NA | Executed
ARIDA 2 SOLAR FARM | 1647 | 2019-04-02 | 2019-04-15 07:00 | ACTIVE | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 700 | 700 |  | 700 | Full Capacity |  | Off-Peak Deliverability | Group 3 | CLARK | NV | SCE | EOP | Mohave Substation 500kV | 2022-10-01 07:00 | 2029-05-31 07:00 |  | NA | Complete | Complete | NA | In Progress
BONANZA SOLAR | 1649 | 2019-04-05 | 2019-04-15 07:00 | ACTIVE | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 300 | 300 |  | 300 | Partial Capacity | 73.71 | Off-Peak Deliverability | Group B | CLARK/NYE | NV | GLW | EOP | Innovation Substation 230 kV | 2023-12-01 08:00 | 2028-09-30 07:00 |  | NA | Complete | Complete | NA | Executed
ROUGH HAT HYBRID SOLAR | 1650 | 2019-04-15 | 2019-04-15 07:00 | ACTIVE | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 204 | 200 |  | 200 | Full Capacity |  | Off-Peak Deliverability | Group A | NYE | NV | GLW | EOP | Trout Canyon Substation 230 kV | 2022-11-30 08:00 | 2028-07-31 07:00 |  | NA | Complete | Complete | NA | Executed
YELLOW PINE 3 | 1654 | 2019-04-09 | 2019-04-15 07:00 | ACTIVE | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 261.954 | 254.98 |  | 250 | Full Capacity |  | Off-Peak Deliverability | Group B | CLARK | NV | GLW | EOP | Trout Canyon Substation 230 kV | 2025-03-15 07:00 | 2026-12-01 08:00 |  | NA | Complete | Complete | NA | Executed
BONANZA PEAK SOLAR FARM | 1655 | 2019-04-12 | 2019-04-12 07:00 | ACTIVE | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 200 | 441 |  | 400 | Full Capacity |  | Off-Peak Deliverability | Group D | CLARK/NYE | NV | GLW | EOP | Trout Canyon Substation 230 kV | 2022-12-16 08:00 | 2027-12-31 08:00 |  | NA | Complete | Complete | NA | Executed
SANDPIPER STORAGE | 1657 | 2019-04-02 | 2019-04-15 07:00 | ACTIVE | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 200 | 200 | Partial Capacity | 50 |  | Group 2a | ORANGE | CA | SDGE | SDGE | Talega Substation 138 kV | 2023-06-30 07:00 | 2026-04-15 07:00 |  | NA | Complete | Complete | NA | Executed
CIMARRON WIND | 1660 | 2019-03-29 | 2019-04-15 07:00 | ACTIVE | C12 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 300 | 300 | Full Capacity |  | Off-Peak Deliverability | Group A | TECATE | MX | SDGE | SDGE | East County Substation 230 kV | 2023-12-31 08:00 | 2025-12-31 08:00 |  | NA | Complete | Complete | NA | Executed
HOODINI | 1663 | 2019-04-13 | 2019-04-15 07:00 | ACTIVE | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 450 | 459.54 |  | 450 | Energy Only |  | Off-Peak Deliverability | Group 3 | YUMA | AZ | SDGE | SDGE | Hoodoo Wash Switchyard 500 kV | 2023-05-31 07:00 | 2028-01-31 08:00 |  | NA | Complete | Complete | NA | In Progress
KINGSLEY SOLAR FARM | 1665 | 2019-04-01 | 2019-04-15 07:00 | ACTIVE | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 360 | 360 |  | 360 | Partial Capacity | 20.6 | Off-Peak Deliverability | Group D | IMPERIAL | CA | SDGE | SDGE | Imperial Valley Substation 230 kV | 2023-06-01 07:00 | 2030-01-31 08:00 |  | NA | Complete | Complete | NA | Executed
SUNRISE BUTTE | 1667 | 2019-04-12 | 2019-04-15 07:00 | ACTIVE | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 0 | 150 |  | 150 | Energy Only |  | Off-Peak Deliverability | Group 3 | IMPERIAL | CA | SDGE | SDGE | Imperial Valley Substation 230 kV | 2022-12-31 08:00 | 2029-11-18 08:00 |  | NA | Complete | Complete | NA | Executed
NIGHTHAWK STORAGE | 1673 | 2019-04-02 | 2019-04-15 07:00 | ACTIVE | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 300 | 300 | Full Capacity |  |  | Group 2 | SAN DIEGO | CA | SDGE | SDGE | Sycamore Canyon Substation 138 kV | 2023-06-30 07:00 | 2026-03-01 08:00 |  | NA | Complete | Complete | NA | Executed
HARQUAHALA SUNRISE | 1678 | 2020-03-13 | 2020-04-15 07:00 | ACTIVE | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 308.926 | 308.926 |  | 300 | Full Capacity |  | Off-Peak Deliverability | Group A | MARICOPA | AZ | DCRT | Eastern | Delaney Substation 500 kV | 2022-04-01 07:00 | 2030-04-01 07:00 |  | NA | Complete | Complete | NA
CONAWAY HYBRID POWER PLANT | 1687 | 2020-04-08 | 2020-04-15 07:00 | ACTIVE | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 84.8117 | 84.9957 |  | 80 | Energy Only |  | Off-Peak Deliverability |  | YOLO | CA | PGAE | Northern | Woodland-Davis 115 kV Line | 2023-01-01 08:00 | 2023-01-01 08:00 |  | NA | Complete | Complete | NA
DENALI ENERGY STORAGE | 1690 | 2020-04-14 | 2020-04-15 07:00 | ACTIVE | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 102 | 101.2 | Partial Capacity | 92 |  | Group B | SAN JOAQUIN | CA | PGAE | Northern | Vierra 115 kV | 2023-06-15 07:00 | 2028-09-30 07:00 |  | NA | Complete | Complete | NA | Executed
POTENTIA-VIRIDI | 1702 | 2020-04-13 | 2020-04-15 07:00 | ACTIVE | C13 | Wind Turbine | Photovoltaic | Storage | Wind Turbine | Solar | Battery | 408.8 | 410.04 | 405.9 | 400 | Full Capacity |  | Off-Peak Deliverability | Group 3 | SAN JOAQUIN | CA | PGAE | Northern | Tesla 500 kV | 2024-12-15 08:00 | 2028-05-11 07:00 |  | NA | Complete | Complete | NA | Executed
ROSEMARY | 1709 | 2020-04-10 | 2020-04-15 07:00 | ACTIVE | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 36.1746 | 36.1746 |  | 35 | Full Capacity |  | Off-Peak Deliverability | Group D | FRESNO | CA | PGAE | Northern | Crescent 70 kV | 2023-12-01 08:00 | 2028-04-30 07:00 |  | NA | Complete | Complete | NA | Executed
GONZAGA HYBRID | 1718 | 2020-04-14 | 2020-04-15 07:00 | ACTIVE | C13 | Storage | Wind Turbine |  | Battery | Wind Turbine |  | 54.94 | 60.45 |  | 103.65 | Full Capacity |  | Off-Peak Deliverability | Group B | MERCED | CA | PGAE | Fresno | Los Banos 70 kV | 2024-07-01 07:00 | 2026-03-31 07:00 |  | NA | Complete | Complete | NA | Executed
ZETA | 1728 | 2020-04-10 | 2020-04-15 07:00 | ACTIVE | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 77.4774 | 77.4774 |  | 75 | Full Capacity |  | Off-Peak Deliverability | Group B | MERCED | CA | PGAE | Fresno | Mercy Springs 70 kV | 2023-12-01 08:00 | 2027-05-26 07:00 |  | NA | Complete | Complete | NA | Executed
HAWKINS SOLAR HYBRID | 1736 | 2020-04-01 | 2020-04-15 07:00 | ACTIVE | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 250 | 250 |  | 250 | Partial Capacity | 76.75 | Off-Peak Deliverability | Group D | KERN | CA | PGAE | Kern | Arco 230 kV | 2024-04-01 07:00 | 2027-05-01 07:00 |  | NA | Complete | Complete | NA | In Progress
PUFF HYBRID SOLAR | 1740 | 2020-04-14 | 2020-04-15 07:00 | ACTIVE | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 101.8 | 101.8 |  | 100 | Full Capacity |  | Off-Peak Deliverability | Group D | KERN | CA | PGAE | Kern | Arco 230 kV | 2024-11-30 08:00 | 2030-09-01 07:00 |  | NA | Complete | Complete | NA | Executed
CRYSTAL FLATS | 1744 | 2020-04-02 | 2020-04-15 07:00 | ACTIVE | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 103.455 | 51.401 |  | 100 | Energy Only |  | Off-Peak Deliverability | Group D | KERN | CA | PGAE | Kern | Lamont 115 kV | 2023-10-31 07:00 | 2030-12-26 08:00 |  | NA | Complete | Complete | NA | Executed
SUNRISE POWER IMPROVEMENT | 1745 | 2020-04-06 | 2020-04-15 07:00 | ACTIVE | C13 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 655.7 | 35 | Energy Only |  |  |  | KERN | CA | PGAE | Kern | Midway 230 kV | 2023-06-01 07:00 | 2024-05-11 07:00 |  | NA | Complete | Complete | NA
WINDWALKER OFFSHORE | 1750 | 2020-04-11 | 2020-04-15 07:00 | ACTIVE | C13 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 1028.94 | 1000 | Full Capacity |  | Off-Peak Deliverability | Group 3 | SAN LUIS OBISPO | CA | PGAE | Kern | Diablo Canyon 500 kV | 2027-03-31 07:00 | 2028-02-12 08:00 |  | NA | Complete | Complete | NA | Executed
WINSTON HYBRID PV AND BESS | 1751 | 2020-04-08 | 2020-04-15 07:00 | ACTIVE | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 102 | 204 |  | 200 | Full Capacity |  | Off-Peak Deliverability | Group A | KERN | CA | PGAE | Kern | Midway 115 kV | 2025-03-01 08:00 | 2028-12-10 08:00 |  | NA | Complete | Complete | NA | Executed
COBALT | 1757 | 2020-04-11 | 2020-04-15 07:00 | ACTIVE | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 256.202 | 256.41 |  | 250 | Energy Only |  | Off-Peak Deliverability | Group 3 | RIVERSIDE | CA | SCE | Eastern | Colorado River Substation 220kV | 2023-10-31 07:00 | 2027-05-31 07:00 |  | NA | Complete | Complete | NA | Executed
DESERT SANDS | 1758 | 2020-04-15 | 2020-04-15 07:00 | ACTIVE | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 300 | 300 | Full Capacity |  | Off-Peak Deliverability | Group B | RIVERSIDE | CA | SCE | Eastern | Devers Substation 230kV | 2024-11-30 08:00 | 2035-03-31 07:00 |  | NA | Complete | Complete | NA | Executed
GRACE ENERGY CENTER | 1761 | 2020-04-14 | 2020-04-15 07:00 | ACTIVE | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 508.56 | 508.56 |  | 500 | Partial Capacity | 10 | Off-Peak Deliverability | Group B | RIVERSIDE | CA | SCE | Eastern | Colorado River Substation 230kV | 2024-11-30 08:00 | 2027-01-13 08:00 |  | NA | Complete | Complete | NA | Executed
SAPPHIRE SOLAR | 1764 | 2020-04-07 | 2020-04-15 07:00 | ACTIVE | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 117 | 117 |  | 117 | Full Capacity |  | Off-Peak Deliverability | Group A | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 230kV | 2024-12-01 08:00 | 2034-12-31 08:00 |  | NA | Complete | Complete | NA | Executed
COMMERCE ENERGY STORAGE 2 | 1766 | 2020-04-14 | 2020-04-15 07:00 | ACTIVE | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 250 | 250 | Full Capacity |  |  | Group 3 | LOS ANGELES | CA | SCE | Metro | Laguna Bell Substation 230kV | 2023-12-01 08:00 | 2026-03-15 07:00 |  | NA | Complete | Complete | NA
ROADHOUSE STORAGE | 1768 | 2020-04-15 | 2020-04-15 07:00 | ACTIVE | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 312.96 | 300 | Full Capacity |  |  | Group 3 | SAN BERNARDINO | CA | SCE | Metro | Mira Loma Substation 230kV | 2024-11-30 08:00 | 2027-06-12 07:00 |  | NA | Complete | Complete | NA | Executed
OVERNIGHT SOLAR | 1774 | 2020-04-09 | 2020-04-15 07:00 | ACTIVE | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 150 | 150 |  | 150 | Full Capacity |  | Off-Peak Deliverability | Group A | SAN BERNARDINO | CA | SCE | NOL | Kramer Substation 230kV | 2024-10-31 07:00 | 2027-05-01 07:00 |  | NA | Complete | Complete | NA | Executed
SEGS EXPANSION 2 HYBRID | 1775 | 2020-04-11 | 2020-04-15 07:00 | ACTIVE | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 45 | 100 |  | 100 | Energy Only |  | Off-Peak Deliverability | Group B | SAN BERNARDINO | CA | SCE | NOL | Kramer Junction Substation 230kV | 2023-12-15 08:00 | 2026-11-02 08:00 |  | NA | Complete | Complete | NA | Executed
BELLEFIELD 3 SOLAR FARM | 1779 | 2020-04-01 | 2020-04-15 07:00 | ACTIVE | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 150 | 150 |  | 150 | Energy Only |  | Off-Peak Deliverability | Group B | KERN | CA | SCE | Northern | Windhub Substation 230kV | 2023-04-01 07:00 | 2027-04-01 07:00 |  | NA | Complete | Complete | NA | Executed
WILLOW ROCK ENERGY STORAGE | 1782 | 2020-04-15 | 2020-04-15 07:00 | ACTIVE | C13 | Storage | Other |  | Battery | Other |  | 108 | 512 |  | 500 | Full Capacity |  | Off-Peak Deliverability | Group 3 | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2023-06-01 07:00 | 2030-07-01 07:00 |  | NA | Complete | Complete | NA | Executed
SHOALS ENERGY STORAGE | 1783 | 2020-04-15 | 2020-04-15 07:00 | ACTIVE | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 409 | 400 | Full Capacity |  |  | Group D | VENTURA | CA | SCE | Northern | Mandalay Switchyard 220kV | 2023-07-01 07:00 | 2030-10-08 07:00 |  | NA | Complete | Complete | NA | Executed
KEYHOLE WIND | 1784 | 2020-04-06 | 2020-04-15 07:00 | ACTIVE | C13 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 100 | 100 | Full Capacity |  | Off-Peak Deliverability | Group A | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2024-12-01 08:00 | 2028-06-28 07:00 |  | NA | Complete | Complete | NA | Executed
REXFORD 2 SOLAR FARM | 1789 | 2020-04-01 | 2020-04-15 07:00 | ACTIVE | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 200 | 200 |  | 200 | Full Capacity |  | Off-Peak Deliverability | Group D | TULARE | CA | SCE | Northern | Vestal Substation 230kV | 2023-04-01 07:00 | 2027-07-01 07:00 |  | NA | Complete | Complete | NA | Executed
SANBORN HYBRID 4 | 1790 | 2020-04-10 | 2020-04-15 07:00 | ACTIVE | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 50 | 50 |  | 100 | Energy Only |  | Off-Peak Deliverability | Group B | KERN | CA | SCE | Northern | Windhub Substation 230kV | 2022-12-15 08:00 | 2025-10-01 07:00 |  | NA | Complete | Complete | NA | Executed
SANBORN 5 HYBRID | 1791 | 2020-04-10 | 2020-04-15 07:00 | ACTIVE | C13 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 560.33 | 550 | Energy Only |  |  | Group D | KERN | CA | SCE | Northern | Windhub Substation 230kV | 2024-12-15 08:00 | 2027-03-31 07:00 |  | NA | Complete | Complete | NA | Executed
SEQUOIA | 1792 | 2020-04-03 | 2020-04-15 07:00 | ACTIVE | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 200 | 200 |  | 200 | Partial Capacity | 60.6 | Off-Peak Deliverability | Group D | TULARE | CA | SCE | Northern | Vestal Substation 230 kV | 2023-10-31 07:00 | 2031-01-01 08:00 |  | NA | Complete | Complete | NA | Filed Unexecuted
ARIDA 3 SOLAR FARM | 1795 | 2020-04-01 | 2020-04-15 07:00 | ACTIVE | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 450 | 450 |  | 450 | Full Capacity |  | Off-Peak Deliverability | Group 3 | CLARK | NV | SCE | EOP | Mohave Substation 500kV | 2025-04-01 07:00 | 2030-07-01 07:00 |  | NA | Complete | Complete | NA
DELAMAR ENERGY STORAGE | 1796 | 2020-04-14 | 2020-04-15 07:00 | ACTIVE | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 256.29 | 250 | Full Capacity |  |  | Group D | CLARK | NV | SCE | EOP | Eldorado Substation 230kV | 2024-08-01 07:00 | 2027-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
CALVADA SPRINGS SOLAR | 1798 | 2020-04-08 | 2020-04-15 07:00 | ACTIVE | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 250 | 250 |  | 250 | Full Capacity |  | Off-Peak Deliverability | Group D | INYO | CA | GLW | EOP | Trout Canyon Substation 230 kV | 2022-12-16 08:00 | 2027-12-31 08:00 |  | NA | Complete | Complete | NA | Executed
ROUGH HAT 2 | 1799 | 2020-04-02 | 2020-04-15 07:00 | ACTIVE | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 203.8 | 203.8 |  | 200 | Full Capacity |  | Off-Peak Deliverability | Group A | CLARK | NV | GLW | EOP | Trout Canyon Substation 230 kV | 2024-09-30 07:00 | 2027-12-01 08:00 |  | NA | Complete | Complete | NA | Executed
PURPLE SAGE ENERGY CENTER | 1800 | 2020-03-31 | 2020-04-15 07:00 | ACTIVE | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 408.24 | 409.2 |  | 400 | Full Capacity |  | Off-Peak Deliverability | Group A | CLARK | NV | GLW | EOP | Trout Canyon Substation 230 kV | 2024-12-31 08:00 | 2028-05-01 07:00 |  | NA | Complete | Complete | NA | Executed
WATER ROCK SOLAR 1 | 1801 | 2020-04-02 | 2020-04-15 07:00 | ACTIVE | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 200 | 200 |  | 200 | Full Capacity |  | Off-Peak Deliverability | Group D | NYE | NV | GLW | EOP | Gamebird Substation 230 kV | 2025-12-01 08:00 | 2027-12-01 08:00 |  | NA | Complete | Complete | NA | Executed
CAPTIVA ENERGY STORAGE | 1806 | 2020-04-14 | 2020-04-15 07:00 | ACTIVE | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 256.875 | 250 | Full Capacity |  |  | Group 3 | ORANGE | CA | SDGE | SDGE | Trabuco - Capistrano 138 kV Line | 2024-06-01 07:00 | 2028-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
EAST FIELD ENERGY STORAGE | 1810 | 2020-04-15 | 2020-04-15 07:00 | ACTIVE | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 312.96 | 300.01 | Energy Only |  |  | Group B | SAN DIEGO | CA | SDGE | SDGE | Otay Mesa Switchyard 230 kV | 2024-11-30 08:00 | 2030-06-25 07:00 |  | NA | Complete | Complete | NA | Executed
DATELAND ENERGY COMPLEX | 1812 | 2020-04-01 | 2020-04-15 07:00 | ACTIVE | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 237.5 | 112.5 |  | 350 | Full Capacity |  | Off-Peak Deliverability | Group 3 | YUMA | AZ | SDGE | SDGE | Hoodoo Wash Switchyard 500 kV | 2024-12-01 08:00 | 2027-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
SADDLE MOUNTAIN SOLAR | 1818 | 2020-04-06 | 2020-04-15 07:00 | ACTIVE | C13 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 125 | 125 | Energy Only |  | Off-Peak Deliverability | Group B | MARICOPA | AZ | SDGE | SDGE | Hassayampa Common Bus 500 kV | 2023-02-10 08:00 | 2025-12-31 08:00 |  | NA | Complete | Complete | NA | Executed
SCAFELL STORAGE | 1820 | 2020-04-12 | 2020-04-15 07:00 | ACTIVE | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 52 | 50 | Energy Only |  |  | Group B | SAN DIEGO | CA | SDGE | SDGE | Creelman Substation 69 kV | 2022-11-15 08:00 | 2029-06-30 07:00 |  | NA | Complete | Complete | NA | In Progress
VIENTO FRONTERIZO | 1824 | 2020-04-11 | 2020-04-15 07:00 | ACTIVE | C13 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 1001 | 972.82 | Energy Only |  | Off-Peak Deliverability | Group D | MUNICIPALITY OF TECATE | MX | SDGE | SDGE | East County Substation 500 kV | 2024-09-30 07:00 | 2033-05-10 07:00 |  | NA | Complete | Complete | NA | Executed
TOLENAS | 1842 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 417.3487 | 400 | Full Capacity |  |  | Group A | SOLANO | CA | PGAE | NGBA | Lambie 230 kV | 2026-06-01 07:00 | 2031-02-18 08:00 |  | NA | Complete | Complete | NA
BRUSHY | 1843 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 400 | 400 | Full Capacity |  |  | Group D | SOLANO | CA | PGAE | NGBA | Lambie 230 kV | 2026-06-01 07:00 | 2031-02-18 08:00 |  | NA | Complete | Complete | NA
WILDHORSE ENERGY CENTER | 1846 | 2021-04-10 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 121.55 | 120 | Full Capacity |  | Off-Peak Deliverability |  | SONOMA | CA | PGAE |  | Fulton 230 kV | 2025-04-01 07:00 | 2030-05-04 07:00 |  | NA | Complete | Complete | NA
HIGH WINDS STORAGE | 1850 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 120.62 | 100 | Full Capacity |  |  | Group D | SOLANO | CA | PGAE |  | Birds Landing 230 kV | 2024-03-30 07:00 | 2031-03-16 07:00 |  | NA | Complete | Complete | NA
CORBY 2 | 1854 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 475.96 | 400 | Full Capacity |  |  | Group D | SOLANO | CA | PGAE |  | Vaca-Dixon 230 kV | 2025-11-30 08:00 | 2031-03-16 07:00 |  | NA | Complete | Complete | NA
ARGES BESS | 1856 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 102.15 | 100 | Full Capacity |  |  | Group B | SOLANO | CA | PGAE | NGBA | Vaca-Dixon 115 kV | 2024-06-01 07:00 | 2029-06-18 07:00 |  | NA | Complete | Complete | NA
MAYACAMAS GEOTHERMAL | 1859 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 53 | 53 | Full Capacity |  |  | Group A | SONOMA | CA | PGAE | NGBA | Geysers #3-Cloverdale 115 kV Line | 2024-02-01 08:00 | 2030-10-19 07:00 |  | NA | Complete | Complete | NA
TOWNSHIP POWER BANK | 1864 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 50.5 | 49 | Energy Only |  |  |  | SUTTER | CA | PGAE | NGBA | Greenleaf #1 115 kV Tap | 2025-04-01 07:00 | 2028-03-01 08:00 |  | NA | Complete | Complete | NA
SEAHAWK STORAGE | 1865 | 2021-03-24 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 203.699 | 200 | Full Capacity |  |  | Group B | SANTA CRUZ | CA | PGAE | GBA | Green Valley 115 kV | 2025-06-01 07:00 | 2029-09-18 07:00 |  | NA | Complete | Complete | NA | Executed
TOKAY STORAGE | 1866 | 2021-03-24 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 101.888 | 100 | Full Capacity |  |  | Group D | SANTA CLARA | CA | PGAE | GBA | Santa Teresa 115 kV | 2025-06-01 07:00 | 2030-03-18 07:00 |  | NA | Complete | Complete | NA | Executed
ALLEGHENY ENERGY STORAGE | 1872 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 353.2 | 325 | Full Capacity |  |  | Group D | CONTRA COSTA | CA | PGAE | GBA | Pittsburg 115 kV | 2024-08-01 07:00 | 2032-09-20 07:00 |  | NA | Complete | Complete | NA | Executed
DELILAH ENERGY STORAGE | 1875 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 504 | 500 | Full Capacity |  |  | Group D | CONTRA COSTA | CA | PGAE | GBA | Pittsburg-Tesla #1 230 kV Line | 2024-08-01 07:00 | 2032-07-19 07:00 |  | NA | Complete | Complete | NA | Executed
DOUBLE SPRINGS ENERGY STORAGE | 1876 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 101 | 100 | Full Capacity |  |  | Group D | CALAVERAS | CA | PGAE | GBA | Valley Springs 60 kV | 2024-11-29 08:00 | 2029-08-17 07:00 |  | NA | Complete | Complete | NA | Executed
PALMETTO ENERGY STORAGE | 1880 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 75.6 | 75 | Full Capacity |  |  | Group D | ALAMEDA | CA | PGAE | GBA | Oakland C 115 kV | 2024-08-01 07:00 | 2030-07-22 07:00 |  | NA | Complete | Complete | NA
SPECTRUM ENERGY STORAGE | 1881 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 504 | 500 | Full Capacity |  |  | Group D | ALAMEDA | CA | PGAE | GBA | Tesla-Newark #1 230 kV Line | 2024-08-01 07:00 | 2032-02-29 08:00 |  | NA | Complete | Complete | NA | Executed
PRESIDIO | 1887 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 356.592 | 356.592 |  | 350 | Full Capacity |  | Off-Peak Deliverability | Group A | SAN JOAQUIN | CA | PGAE | NGBA | Rancho Seco-Bellota #1 230 kV Line | 2025-06-01 07:00 | 2030-12-16 08:00 |  | NA | Complete | Complete | NA | Executed
HOLMAN | 1889 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Wind Turbine |  | Battery | Wind Turbine |  | 756.813 | 1525.172 |  | 1500 | Partial Capacity | 50 | Off-Peak Deliverability | Group B | MONTEREY | CA | PGAE | GBA | Moss Landing 500 kV | 2028-04-01 07:00 | 2034-02-17 08:00 |  | NA | Complete | Complete | NA | Executed
HARMONY STORAGE 2 | 1892 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 307.878 | 300 | Full Capacity |  |  | Group A | CONTRA COSTA | CA | PGAE | GBA | Contra Costa PP 230 kV | 2025-10-30 07:00 | 2031-06-05 07:00 |  | NA | Complete | Complete | NA
OAKDALE STORAGE | 1895 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 102.672 | 100 | Partial Capacity | 54 |  | Group A | STANISLAUS | CA | PGAE | GBA | Cottle 230 kV | 2025-10-30 07:00 | 2029-09-18 07:00 |  | NA | Complete | Complete | NA | Executed
PATHFINDER STORAGE | 1896 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 268.065 | 260 | Full Capacity |  |  | Group A | SAN JOAQUIN | CA | PGAE | GBA | Weber 60 kV | 2025-10-30 07:00 | 2031-06-05 07:00 |  | NA | Complete | Complete | NA | Executed
BAYLANDS BATTERY | 1900 | 2021-04-12 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 250 | 250 | Full Capacity |  |  | Group D | SAN MATEO | CA | PGAE | GBA | Martin 115 kV | 2025-07-27 07:00 | 2030-03-24 07:00 |  | NA | Complete | Complete | NA | Executed
GOLDEN FLATS | 1903 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 365.12 | 300 | Full Capacity |  |  | Group D | STANISLAUS | CA | PGAE | Fresno | Westly-Quinto 230 kV | 2025-11-30 08:00 | 2031-09-01 07:00 |  | NA | Complete | Complete | NA | Executed
NORTHEAST CENTRAL VALLEY | 1904 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 365.12 | 300 | Full Capacity |  |  | Group D | SAN JOAQUIN | CA | PGAE |  | Bellota 115 kV | 2025-11-30 08:00 | 2031-02-16 08:00 |  | NA | Complete | Complete | NA
ZORIN STORAGE | 1911 | 2021-04-10 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 252 | 180 | Full Capacity |  |  | Group D | ALAMEDA | CA | PGAE | GBA | Newark 230 kV | 2024-10-31 07:00 | 2034-02-19 08:00 |  | NA | Complete | Complete | NA | Executed
ESPRESSO | 1912 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 365.12 | 300 | Full Capacity |  |  | Group D | ALAMEDA | CA | PGAE |  | Tesla 230 kV | 2025-11-30 08:00 | 2031-08-18 07:00 |  | NA | Complete | Complete | NA | Executed
BLACK DIAMOND ES2 | 1914 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 179.4 | 175 | Full Capacity |  |  | Group B | CONTRA COSTA | CA | PGAE | GBA | Pittsburg 230 kV | 2024-06-01 07:00 | 2031-06-18 07:00 |  | NA | Complete | Complete | NA | Executed
SHERMAN ENERGY STORAGE | 1915 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 256.29 | 250 | Full Capacity |  |  | Group D | CONTRA COSTA | CA | PGAE | GBA | Contra Costa PP 230 kV | 2025-06-01 07:00 | 2031-06-18 07:00 |  | NA | Complete | Complete | NA
KIFER BESS 1 | 1918 | 2021-04-13 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 50 | 50 | Full Capacity |  |  | Group A | SANTA CLARA | CA | PGAE | GBA | KEN-OKJ 60 kV | 2023-10-01 07:00 | 2025-12-18 08:00 |  | NA |  | Complete | NA
SUNBEAM STORAGE | 1919 | 2021-04-10 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 100.9 | 65 | Full Capacity |  |  | Group D | SAN MATEO | CA | PGAE | GBA | Cooley Landing 60 kV | 2024-10-31 07:00 | 2034-02-19 08:00 |  | NA | Complete | Complete | NA | Executed
ZEUS BESS | 1920 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 213.55 | 200 | Partial Capacity |  |  | Group B | SAN JOAQUIN | CA | PGAE |  | Schulte 115 kV | 2024-06-01 07:00 | 2031-06-18 07:00 |  | NA | Complete | Complete | NA | Executed
ALLIUM HYBRID | 1921 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 112.386 | 112.491 |  | 110 | Full Capacity |  | Off-Peak Deliverability | Group B | SAN BENITO | CA | PGAE | GBA | Crazy Horse Canyon-Hollister 115 kV Line | 2025-06-01 07:00 | 2030-12-15 08:00 |  | NA | Complete | Complete | NA | Executed
ALTA CASA STORAGE | 1922 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 515.418 | 500 | Full Capacity |  |  | Group B | SAN JOAQUIN | CA | PGAE | GBA | Tesla 500 kV | 2025-06-01 07:00 | 2031-10-21 07:00 |  | NA | Complete | Complete | NA | Executed
EL REY POWER BANK | 1928 | 2021-04-10 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 124.3 | 120 | Energy Only |  |  |  | MONTEREY | CA | PGAE | GBA | Coburn-Basic Energy 60 kV Line | 2025-04-01 07:00 | 2029-01-02 08:00 |  | NA | Complete | Complete | NA
APACHE STORAGE | 1930 | 2021-03-24 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 203.699 | 200 | Full Capacity |  |  | Group D | FRESNO | CA | PGAE | Kern | Sanger 115 kV | 2025-06-01 07:00 | 2029-05-21 07:00 |  | NA | Complete | Complete | NA | Executed
COUGAR STORAGE | 1932 | 2021-03-24 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 203.699 | 200 | Full Capacity |  |  | Group D | MERCED | CA | PGAE | Fresno | Wilson 115 kV | 2025-06-01 07:00 | 2030-09-19 07:00 |  | NA | Complete | Complete | NA | Executed
PUMA STORAGE | 1933 | 2021-03-24 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 203.699 | 200 | Full Capacity |  |  | Group D | MADERA | CA | PGAE | Fresno | Borden 230 kV | 2025-06-01 07:00 | 2030-11-18 08:00 |  | NA | Complete | Complete | NA
LOTUS SOLAR 2 | 1934 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 203.2 | 203.2 |  | 200 | Full Capacity |  | Off-Peak Deliverability | Group D | MADERA | CA | PGAE | Fresno | Borden 230 kV | 2024-12-01 08:00 | 2030-11-17 08:00 |  | NA | Complete | Complete | NA
ELYSIAN | 1935 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 206.091 | 206.091 |  | 200 | Energy Only |  | Off-Peak Deliverability | Group D | FRESNO | CA | PGAE | Fresno | Tranquility 230 kV | 2024-11-01 07:00 | 2029-10-18 07:00 |  | NA | Complete | Complete | NA | Executed
WINGTIP SOLAR 1 | 1943 | 2021-04-02 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 1176.1 | 1176.1 |  | 1150 | Full Capacity |  | Off-Peak Deliverability | Group D | MERCED | CA | PGAE | S500 | Los Banos 500 kV | 2027-06-01 07:00 | 2032-09-18 07:00 |  | NA | Complete | Complete | NA | Executed
DARDEN | 1949 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 1182.384 | 1182.384 |  | 1150 | Full Capacity |  | Off-Peak Deliverability | Group D | FRESNO | CA | PGAE | S500 | Manning-Midway 500kV Line | 2026-12-31 08:00 | 2027-07-19 07:00 |  | NA | Complete | Complete | NA | Executed
AUSTRALIS | 1952 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 307 | 307 |  | 300 | Full Capacity |  | Off-Peak Deliverability | Group A | MERCED | CA | PGAE | Fresno | Los Banos 230 kV | 2025-06-01 07:00 | 2031-04-18 07:00 |  | NA | Complete | Complete | NA | Executed
FLORES STORAGE | 1953 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 151.7416 | 150 | Full Capacity |  | Off-Peak Deliverability | Group D | MADERA | CA | PGAE | Fresno | Gregg 230 kV | 2025-10-01 07:00 | 2031-02-18 08:00 |  | NA | Complete | Complete | NA
HUASO HYBRID | 1954 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 101.83 | 102.1 |  | 100 | Full Capacity |  | Off-Peak Deliverability | Group B | FRESNO | CA | PGAE | Fresno | Gates 230 kV | 2025-12-01 08:00 | 2026-12-03 08:00 |  | NA | Complete | Complete | NA | Executed
CIERVO MOUNTAIN HYBRID | 1955 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 127.37 | 127.57 |  | 125 | Full Capacity |  | Off-Peak Deliverability | Group B | FRESNO | CA | PGAE | Fresno | Excelsior 115 kV | 2025-12-01 08:00 | 2029-08-03 07:00 |  | NA | Complete | Complete | NA | Executed
CLARKSON | 1956 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 203.659 | 203.849 |  | 200 | Full Capacity |  | Off-Peak Deliverability | Group A | FRESNO | CA | PGAE | Fresno | Tranquility 230 kV | 2025-06-01 07:00 | 2029-09-30 07:00 |  | NA | Complete | Complete | NA | Executed
SPIKES PEAK SOLAR | 1958 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 158.9783 | 158.5678 |  | 150 | Full Capacity |  | Off-Peak Deliverability | Group B | MERCED | CA | PGAE | Fresno | Quinto 230 kV | 2025-10-01 07:00 | 2029-10-18 07:00 |  | NA | Complete | Complete | NA | Executed
CORNUCOPIA HYBRID | 1959 | 2021-04-12 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 300.951 | 303.678 |  | 300 | Partial Capacity | 95 | Off-Peak Deliverability | Group B | FRESNO | CA | PGAE | Fresno | Gates-Templeton 230 kV Line | 2025-06-16 07:00 | 2030-11-16 08:00 |  | NA | Complete | Complete | NA | Executed
LOCK STORAGE | 1962 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 508 | 500.01 | Full Capacity |  |  | Group D | FRESNO | CA | PGAE | S500 | Gates 500 kV | 2025-11-30 08:00 | 2027-12-15 08:00 |  | NA | Complete | Complete | NA | Executed
ALMANDE ENERGY STORAGE | 1963 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 256.29 | 250 | Full Capacity |  |  | Group D | MERCED | CA | PGAE | Fresno | Wilson 230 kV | 2025-06-01 07:00 | 2030-06-18 07:00 |  | NA | Complete | Complete | NA
ORLEANS | 1966 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 25.54 | 25.54 |  | 25 | Full Capacity |  |  | Group D | FRESNO | CA | PGAE | Fresno | Giffen 70 kV | 2024-12-31 08:00 | 2029-08-03 07:00 |  | NA | Complete | Complete | NA | Executed
PLUM | 1968 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 1040 | 520 |  | 1000 | Full Capacity |  | Off-Peak Deliverability |  | KINGS | CA | PGAE | Fresno | Gates 230 kV | 2024-12-10 08:00 | 2031-03-19 07:00 |  | NA | Complete | Complete | NA
PEACEFUL HOLLOW BESS | 1973 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 100 | 75 | Full Capacity |  |  | Group D | FRESNO | CA | PGAE | Fresno | Tranquility 230kV | 2024-06-01 07:00 | 2028-06-18 07:00 |  | NA | Complete | Complete | NA | Executed
TARRAGON HYBRID | 1975 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 35.979 | 35.951 |  | 35 | Full Capacity |  | Off-Peak Deliverability | Group B | FRESNO | CA | PGAE | Fresno | Crescent 70 kV | 2025-06-01 07:00 | 2028-06-01 07:00 |  | NA | Complete | Complete | NA
VALETUDO ENERGY STORAGE | 1977 | 2021-09-30 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 79.5871 | 75 | Full Capacity |  |  | Group B | MADERA | CA | PGAE | Fresno | Chowchilla 115 kV | 2022-12-31 08:00 | 2028-11-01 07:00 |  | NA | Complete | Complete | NA
ARTEMIS | 1980 | 2021-03-31 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 412.336 | 412.336 |  | 400 | Partial Capacity | 24 | Off-Peak Deliverability | Group D | KERN | CA | PGAE | Kern | Arco 230 kV | 2024-11-01 07:00 | 2029-10-18 07:00 |  | NA | Complete | Complete | NA
PHAENON | 1983 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 102.254 | 101.7635 |  | 100 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | PGAE | Kern | Shafter 115 kV | 2024-12-31 08:00 | 2029-07-18 07:00 |  | NA | Complete | Complete | NA
BUTTONBUSH SOLAR 2 | 1987 | 2021-04-03 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 358.2 | 358.2 |  | 350 | Full Capacity |  | Off-Peak Deliverability | Group D | KERN | CA | PGAE | S500 | Midway 500 kV | 2028-04-01 07:00 | 2032-03-17 07:00 |  | NA | Complete | Complete | NA | Executed
EIGER ENERGY STORAGE | 1994 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 100.9 | 100 | Full Capacity |  |  | Group D | KERN | CA | PGAE | Kern | Lamont 115 kV | 2025-01-01 08:00 | 2032-02-16 08:00 |  | NA | Complete | Complete | NA
EVEREST ENERGY STORAGE | 1995 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 201.8 | 200 | Full Capacity |  |  | Group D | KERN | CA | PGAE | Kern | Kern PP 230 kV | 2025-01-01 08:00 | 2030-10-18 07:00 |  | NA | Complete | Complete | NA
SERENA STORAGE | 2001 | 2021-04-10 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 114.264 | 110 | Full Capacity |  |  | Group A | KERN | CA | PGAE | Kern | Kern PP 230 kV | 2025-10-30 07:00 | 2029-09-18 07:00 |  | NA | Complete | Complete | NA | Executed
VALLEY SUNLIGHT REFINERY | 2004 | 2021-04-10 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 410 | 411.3018 |  | 400 | Full Capacity |  | Off-Peak Deliverability | Group D | KINGS | CA | PGAE | Kern | Gates-Midway 230 kV Line | 2025-06-10 07:00 | 2032-02-18 08:00 |  | NA | Complete | Complete | NA
CHERRY LANE HYBRID | 2015 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 310.63 | 310.63 |  | 300 | Full Capacity |  | Off-Peak Deliverability | Group B | KERN | CA | PGAE | Kern | Wheeler Ridge 230 kV | 2025-06-01 07:00 | 2031-06-19 07:00 |  | NA | Complete | Complete | NA
HIDDEN KNOLLS BESS | 2018 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 30.8 | 30 | Full Capacity |  |  | Group D | KERN | CA | PGAE | Kern | Arco-Carneras 70 kV Line | 2024-06-01 07:00 | 2028-10-18 07:00 |  | NA | Complete | Complete | NA
SOCORRO PEAK SOLAR | 2022 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 379.7505 | 376.0403 |  | 350 | Full Capacity |  | Off-Peak Deliverability | Group B | LA PAZ | AZ | DCRT | Eastern | Cielo Azul Substation 500 kV | 2025-10-01 07:00 | 2029-03-26 07:00 |  | NA | Complete | Complete | NA
JOVE SOLAR | 2023 | 2021-04-05 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 2042.4 | 2090.2 |  | 2000 | Full Capacity |  | Off-Peak Deliverability | Group D | LA PAZ | AZ | DCRT | Eastern | Cielo Azul Substation 500 kV | 2024-12-31 08:00 | 2030-01-26 08:00 |  | NA | Complete | Complete | NA
RANEGRAS PVS | 2025 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 718.81 | 718.81 |  | 700 | Full Capacity |  | Off-Peak Deliverability | Group B | LA PAZ | AZ | DCRT | Eastern | Colorado River-Delaney 500 kV line | 2025-06-01 07:00 | 2029-07-26 07:00 |  | NA | Complete | Complete | NA
HARQUAHALA FLATS 2 | 2027 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 410.76 | 410.76 |  | 400 | Full Capacity |  | Off-Peak Deliverability | Group D | MARICOPA | AZ | DCRT | Eastern | Delaney Substation 500 kV | 2025-11-30 08:00 | 2028-04-15 07:00 |  | NA | Complete | Complete | NA
HARQUAHALA SUNRISE 2 | 2029 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 169.2 | 160.98 |  | 150 | Full Capacity |  | Off-Peak Deliverability | Group A | MARICOPA | AZ | DCRT | Eastern | Delaney Substation 500 kV | 2024-11-01 07:00 | 2026-09-01 07:00 |  | NA | Complete | Complete | NA
TROLLEY | 2032 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 405.6634 | 400 | Full Capacity |  |  | Group D | SAN BERNARDINO | CA | SCE | Eastern | Etiwanda Substation 230 kV | 2024-06-30 07:00 | 2031-02-26 08:00 |  | NA | Complete | Complete | NA | Executed
CARMINE | 2033 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 291.891 | 285 | Full Capacity |  | Off-Peak Deliverability | Group D | RIVERSIDE | CA | SCE | Eastern | Colorado River Substation 230 kV | 2024-11-01 07:00 | 2031-05-01 07:00 |  | NA | Complete | Complete | NA
REDONDA | 2036 | 2021-04-05 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 273.0212 | 268.7138 |  | 250 | Full Capacity |  | Off-Peak Deliverability | Group A | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 220 kV | 2024-12-01 08:00 | 2031-01-01 08:00 |  | NA | Complete | Complete | NA | Executed
SANDRIFT STORAGE 1 | 2039 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 254.77 | 250 | Partial Capacity | 88.43 |  | Group A | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 230 kV | 2023-12-31 08:00 | 2030-12-26 08:00 |  | NA | Complete | Complete | NA | Executed
SANDRIFT STORAGE 2 | 2041 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 254.77 | 250 | Partial Capacity | 88.43 |  | Group A | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 230 kV | 2023-12-31 08:00 | 2031-03-01 08:00 |  | NA | Complete | Complete | NA | Executed
EASLEY | 2042 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 650 | 290 |  | 650 | Full Capacity |  | Off-Peak Deliverability | Group A | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 500 kV | 2024-12-31 08:00 | 2028-03-06 08:00 |  | NA | Complete | Complete | NA | Executed
INVICTUS | 2045 | 2021-04-10 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 430.192 | 430.192 |  | 300 | Full Capacity |  | Off-Peak Deliverability | Group B | RIVERSIDE | CA | SCE | Eastern | Colorado River 230 kV | 2025-12-15 08:00 | 2029-11-26 08:00 |  | NA | Complete | Complete | NA
TWIN PALMS SOLAR | 2048 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 288.144 | 288 |  | 280 | Full Capacity |  | Off-Peak Deliverability | Group A | RIVERSIDE | CA | SCE | Eastern | Colorado River Substation 230 kV | 2025-10-30 07:00 | 2030-07-06 07:00 |  | NA | Complete | Complete | NA | Executed
BOUSE SOLAR AND STORAGE PLANT | 2052 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 1009.9 | 1010.88 |  | 1000 | Full Capacity |  | Off-Peak Deliverability | Group D | LA PAZ | AZ | SCE | Eastern | Colorado River - Palo Verde 500kV | 2026-02-05 08:00 | 2033-12-26 08:00 |  | NA | Complete | Complete | NA
EUISMOD | 2055 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 623.48 | 623.48 |  | 600 | Full Capacity |  | Off-Peak Deliverability | Group B | KERN | CA | SCE | Northern | WHIRLWIND Substation 230 kV | 2024-06-30 07:00 | 2028-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
J90 ENERGY STORAGE | 2059 | 2021-04-02 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 261 | 250 | Full Capacity |  | Off-Peak Deliverability | Group B | LOS ANGELES | CA | SCE | Northern | Antelope Substation 230 kV | 2025-06-01 07:00 | 2033-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
SAGEBRUSH ENERGY STORAGE | 2060 | 2021-04-05 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 528 | 500 | Partial Capacity | 50 |  | Group D | KERN | CA | SCE | Northern | Vincent Substation 230 kV | 2025-07-01 07:00 | 2033-02-26 08:00 |  | NA | Complete | Complete | NA | Executed
JUNIPER STORAGE | 2061 | 2021-04-05 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 153.5 | 153.5 |  | 150 | Full Capacity |  | Off-Peak Deliverability |  | LOS ANGELES | CA | SCE | Northern | Vincent - Pearblossom 230 kV line | 2024-06-30 07:00 | 2033-02-26 08:00 |  | NA | Complete | Complete | NA
DORIAN STORAGE | 2062 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 213.5926 | 200 | Full Capacity |  | Off-Peak Deliverability | Group D | LOS ANGELES | CA | SCE | Northern | Antelope Substation 230 kV | 2025-10-01 07:00 | 2034-08-26 07:00 |  | NA | Complete | Complete | NA | Executed
ELION ENERGY STORAGE | 2064 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 302.4 | 300 | Full Capacity |  |  | Group D | LOS ANGELES | CA | SCE | Northern | Antelope ValleySubstation 230 kV | 2024-08-01 07:00 | 2034-05-26 07:00 |  | NA | Complete | Complete | NA | Executed
DRIFTER ENERGY STORAGE | 2066 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 504.8 | 500 | Full Capacity |  |  | Group B | VENTURA | CA | SCE | Northern | Moorpark Substation 230 kV | 2024-08-01 07:00 | 2033-03-26 07:00 |  | NA | Complete | Complete | NA | Executed
BOBOR STORAGE | 2068 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 152.1 | 150 | Full Capacity |  |  | Group D | TULARE | CA | SCE | Northern | Rector Substation 230 kV | 2025-12-15 08:00 | 2030-12-26 08:00 |  | NA | Complete | Complete | NA
SOLEIL CANTIL | 2078 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 372.3 | 225 |  | 350 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Windhub Substation 500kV | 2024-06-01 07:00 | 2033-02-26 08:00 |  | NA | Complete | Complete | NA
MINERAL KING SOLAR | 2081 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 215.4124 | 214.0983 |  | 200 | Full Capacity |  | Off-Peak Deliverability |  | TULARE | CA | SCE | Northern | Rector Substation 220 kV | 2026-12-31 08:00 | 2029-09-26 07:00 |  | NA | Complete | Complete | NA
ELECTRON | 2082 | 2021-04-12 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 300 | 300 | Energy Only |  |  |  | LOS ANGELES | CA | SCE | Northern | ANTELOPE Substation 220 kV | 2024-06-01 07:00 | 2033-01-26 08:00 |  | NA | Complete | Complete | NA | Executed
SOLSKEN | 2085 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 345 | 464.42 |  | 460 | Full Capacity |  | Off-Peak Deliverability |  | TULARE | CA | SCE | Northern | Springville Substation 230 kV | 2024-04-15 07:00 | 2033-02-26 08:00 |  | NA | Complete | Complete | NA
GREASEWOOD ENERGY STORAGE | 2089 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 513.2 | 500 | Full Capacity |  |  | Group D | KERN | CA | SCE | Northern | Whirlwind Substation 500 kV | 2025-06-01 07:00 | 2033-02-26 08:00 |  | NA | Complete | Complete | NA | Executed
ROSA STORAGE | 2092 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 511.725 | 500 | Full Capacity |  |  | Group D | VENTURA | CA | SCE | Northern | Moorpark Substation 230 kV | 2025-06-01 07:00 | 2034-06-27 07:00 |  | NA | Complete | Complete | NA
HIDALGO ENERGY STORAGE | 2096 | 2021-04-02 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 408.12 | 400 | Partial Capacity | 70 |  | Group B | SAN BERNARDINO | CA | SCE | NOL | Kramer-Lugo #1 220 kV | 2024-06-01 07:00 | 2033-09-26 07:00 |  | NA | Complete | Complete | NA | Executed
SIENNA SOLAR 2 | 2097 | 2021-04-02 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 56 | 56 |  | 55 | Full Capacity |  | Off-Peak Deliverability | Group D | SAN BERNARDINO | CA | SCE | NOL | Calcite Substation 230 kV | 2025-12-01 08:00 | 2029-03-26 07:00 |  | NA | Complete | Complete | NA | In Progress
WESTON STORAGE | 2101 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 213.5957 | 200 | Full Capacity |  | Off-Peak Deliverability | Group D | SAN BERNARDINO | CA | SCE | NOL | Kramer Substation 230 kV | 2025-10-01 07:00 | 2031-03-26 07:00 |  | NA | Complete | Complete | NA
CADY SOLAR | 2103 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 312.96 | 312.96 |  | 300 | Partial Capacity | 80 | Off-Peak Deliverability | Group D | SAN BERNARDINO | CA | SCE | NOL | Pisgah Substation 230 kV | 2025-11-30 08:00 | 2031-02-26 08:00 |  | NA | Complete | Complete | NA | Executed
DOS PALMAS | 2104 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 410.76 | 400 | Full Capacity |  |  | Group D | SAN BERNARDINO | CA | SCE | NOL | Victor Substation 230 kV | 2025-11-30 08:00 | 2031-04-26 07:00 |  | NA | Complete | Complete | NA | Executed
CONDUIT ENERGY STORAGE | 2105 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 512.58 | 500 | Full Capacity |  |  | Group D | SAN BERNARDINO | CA | SCE | NOL | Lugo Substation 500 kV |  | 2031-02-26 08:00 |  | NA | Complete | Complete | NA | Executed
FLEETWOOD | 2111 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 405.5148 | 400 | Full Capacity |  |  |  | LOS ANGELES | CA | SCE | Metro | Litehipe Substation 230 kV | 2024-06-30 07:00 | 2032-04-28 07:00 |  | NA | Complete | Complete | NA
GABRIEL STORAGE | 2113 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 405.7509 | 400 | Full Capacity |  |  | Group B | LOS ANGELES | CA | SCE | Metro | Rio Hondo Substation 230 kV | 2024-06-30 07:00 | 2033-05-15 07:00 |  | NA | Complete | Complete | NA | Executed
DIRAC | 2114 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 403.4 | 400 | Full Capacity |  |  | Group D | SAN BERNARDINO | CA | SCE | Metro | Chino Substation 230 kV | 2024-06-30 07:00 | 2031-02-26 08:00 |  | NA | Complete | Complete | NA | Executed
SIMON | 2115 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 405.7509 | 400 | Full Capacity |  |  |  | LOS ANGELES | CA | SCE | Metro | La Cienega Substation 230 kV | 2024-06-30 07:00 | 2032-04-26 07:00 |  | NA | Complete | Complete | NA
MARICI | 2116 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 405.5148 | 400 | Full Capacity |  |  | Group D | LOS ANGELES | CA | SCE | Metro | Walnut Substation 230 kV | 2024-06-30 07:00 | 2031-02-26 08:00 |  | NA | Complete | Complete | NA | Executed
CORAL REEF | 2117 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 405.6634 | 400 | Full Capacity |  |  |  | LOS ANGELES | CA | SCE | Metro | El Nido Substation 230 kV | 2024-06-30 07:00 | 2032-04-26 07:00 |  | NA | Complete | Complete | NA
GREENWOOD ENERGY STORAGE | 2121 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 252 | 250 | Full Capacity |  |  | Group D | LOS ANGELES | CA | SCE | Metro | Mesa Substation 500 kV | 2024-08-01 07:00 | 2032-05-26 07:00 |  | NA | Complete | Complete | NA | Executed
TABLA ENERGY STORAGE | 2124 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 302.4 | 300 | Full Capacity |  |  | Group D | LOS ANGELES | CA | SCE | Metro | Rio Hondo Substation 230 kV | 2024-08-01 07:00 | 2032-05-26 07:00 |  | NA | Complete | Complete | NA | Executed
TYRELL ENERGY STORAGE | 2125 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 302.4 | 300 | Full Capacity |  |  | Group D | ORANGE | CA | SCE | Metro | Viejo Substation 230kV | 2024-08-01 07:00 | 2032-05-26 07:00 |  | NA | Complete | Complete | NA | Executed
LOS NIETOS | 2129 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 102.26 | 100 | Full Capacity |  |  | Group D | ORANGE | CA | SCE | Metro | Johanna Substation 230 kV | 2024-11-01 07:00 | 2031-04-26 07:00 |  | NA | Complete | Complete | NA | Executed
MERLIN STORAGE | 2131 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 200 | 200 | Full Capacity |  |  |  | LOS ANGELES | CA | SCE | Metro | Hinson Substation 220 kV | 2023-06-01 07:00 | 2032-05-26 07:00 |  | NA | Complete | Complete | NA
HAVEN STORAGE | 2136 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 312.96 | 300 | Full Capacity |  |  | Group D | LOS ANGELES | CA | SCE | Metro | Rio Hondo Substation 230 kV | 2025-11-30 08:00 | 2031-02-26 08:00 |  | NA | Complete | Complete | NA | Executed
COMMERCE ENERGY STORAGE 3 | 2139 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 256.29 | 250 | Full Capacity |  |  | Group D | L.A | CA | SCE | Metro | Laguna Bell Substation 230 kV | 2025-06-01 07:00 | 2031-02-26 08:00 |  | NA | Complete | Complete | NA | Executed
STERLING | 2140 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 250 | 250 |  | 250 | Full Capacity |  | Off-Peak Deliverability | Group A | CLARK | NV | SCE | EOP | Mohave Substation 500 kV | 2024-12-01 08:00 | 2031-05-26 07:00 |  | NA | Complete | Complete | NA
DELAMAR ENERGY STORAGE 2 | 2141 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 256.29 | 250 | Full Capacity |  |  | Group B | CLARK | NV | SCE | EOP | SCE portion of Eldorado Substation 230 kV | 2025-06-01 07:00 | 2027-06-26 07:00 |  | NA | Complete | Complete | NA
SILVER STAR SOLAR | 2142 | 2021-03-31 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 516.7638 | 516.7638 |  | 500 | Energy Only |  | Off-Peak Deliverability | Group D | NYE | NV | GLW | EOP | Lathrop Wells Substation 230 kV | 2028-03-31 07:00 | 2028-12-01 08:00 |  | NA | Complete | Complete | NA | Executed
ROCK VALLEY ENERGY CENTER | 2144 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 515.08 | 508.56 |  | 500 | Energy Only |  | Off-Peak Deliverability | Group D | NYE | NV | GLW | EOP | Beatty Substation 230 kV | 2025-11-30 08:00 | 2029-03-15 07:00 |  | NA | Complete | Complete | NA | Executed
DANDELION HYBRID SOLAR | 2145 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 223.33 | 110.87 |  | 220 | Full Capacity |  | Off-Peak Deliverability | Group B | NYE | NV | GLW | EOP | Vista Substation 230 kV | 2024-11-30 08:00 | 2027-12-26 08:00 |  | NA | Complete | Complete | NA
WATER ROCK SOLAR 2 | 2146 | 2021-03-31 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 516.7638 | 516.7638 |  | 500 | Energy Only |  | Off-Peak Deliverability | Group D | NYE | NV | GLW | EOP | Gamebird Substation 230 kV | 2028-03-31 07:00 | 2028-12-01 08:00 |  | NA | Complete | Complete | NA
KAWICH | 2147 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 350 | 350 |  | 350 | Full Capacity |  | Off-Peak Deliverability | Group A | CLARK | NV | GLW | EOP | Innovation-Desert View 230 kV Line | 2025-06-01 07:00 | 2029-07-27 07:00 |  | NA | Complete | Complete | NA | Executed
MOSEY | 2148 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 537.0067 | 543.856 |  | 500 | Full Capacity |  | Off-Peak Deliverability | Group A | CLARK | NV | GLW | EOP | Trout Canyon Substation 230 kV | 2025-06-01 07:00 | 2029-06-27 07:00 |  | NA | Complete | Complete | NA | Executed
SUNBAKED SOLAR | 2149 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 515.08 | 508.56 |  | 500 | Energy Only |  | Off-Peak Deliverability | Group B | INYO | CA | GLW | EOP | Trout Canyon Substation 230 kV | 2025-11-30 08:00 | 2029-02-26 08:00 |  | NA | Complete | Complete | NA | Executed
LARREA SOLAR | 2150 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 307 | 307 |  | 300 | Full Capacity |  | Off-Peak Deliverability |  | CLARK | NV | GLW | EOP | Trout Canyon Substation 230 kV | 2024-09-01 07:00 | 2028-09-15 07:00 |  | NA | Complete | Complete | NA
FRIGATEBIRD STORAGE | 2153 | 2021-03-23 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 213.5487 | 200 | Full Capacity |  |  |  | SAN DIEGO | CA | SDGE | SDGE | Silvergate Substation 230 kV | 2023-06-30 07:00 | 2035-03-05 08:00 |  | NA | Complete | Complete | NA
REMY | 2154 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 308.47 | 308 |  | 300 | Full Capacity |  | Off-Peak Deliverability |  | YUMA | AZ | SDGE | SDGE | Hoodoo Wash Switchyard 500 kV | 2025-12-01 08:00 | 2029-06-30 07:00 |  | NA | Complete | Complete | NA
GNARLY OSAGE | 2157 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 304.3999 | 300 | Full Capacity |  |  |  | SAN DIEGO | CA | SDGE | SDGE | Encina Substation 138 kV | 2024-06-30 07:00 | 2027-08-07 07:00 |  | NA | Complete | Complete | NA
ALISA SOLAR ENERGY COMPLEX | 2161 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 208.494 | 208.494 |  | 200 | Energy Only |  | Off-Peak Deliverability | Group D | YUMA | AZ | SDGE | SDGE | Hoodoo Wash - North Gila 500 kV | 2024-06-01 07:00 | 2028-06-01 07:00 |  | NA | Complete | Complete | NA
SOLAR DE MEXICALI | 2162 | 2021-03-31 | 2021-04-15 07:00 | ACTIVE | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 286.13 | 286.13 |  | 275 | Full Capacity |  | Off-Peak Deliverability | Group D | BAJA CALIFORNIA | MX | SDGE | SDGE | Imperial Valley Substation 230 kV | 2027-12-31 08:00 | 2030-03-16 07:00 |  | NA | Complete | Complete | NA
UMBRIEL | 2166 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 1182.38 | 1182.38 |  | 1150 | Full Capacity |  | Off-Peak Deliverability | Group A | IMPERIAL | CA | SDGE | SDGE | North Gila - Imperial Valley 500 kV Line | 2026-12-31 08:00 | 2035-06-05 07:00 |  | NA | Complete | Complete | NA | Executed
HAMMERHEAD STORAGE | 2167 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 71.3 | 70 | Full Capacity |  |  | Group D | SAN DIEGO | CA | SDGE | SDGE | Scripps Substation 69 kV | 2024-12-15 08:00 | 2030-05-05 07:00 |  | NA | Complete | Complete | NA
DESERT JEWEL STORAGE | 2173 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 206.31 | 200 | Full Capacity |  |  | Group A | SAN DIEGO | CA | SDGE | SDGE | Boulevard East Substation 138 kV | 2025-10-30 07:00 | 2029-08-05 07:00 |  | NA | Complete | Complete | NA | Executed
YUHA DESERT BATTERY STORAGE | 2176 | 2021-04-02 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 633.1 | 600 | Full Capacity |  |  | Group D | IMPERIAL | CA | SDGE | SDGE | Imperial Valley Substation 230 kV | 2024-12-31 08:00 | 2031-11-05 08:00 |  | NA | Complete | Complete | NA
BOULDER BRUSH HYBRID | 2177 | 2021-04-13 | 2021-04-15 07:00 | ACTIVE | C14 | Wind Turbine | Storage |  | Wind Turbine | Battery |  | 105.8 | 313.9193 |  | 400 | Full Capacity |  | Off-Peak Deliverability | Group D | SAN DIEGO | CA | SDGE | SDGE | Suncrest - Ocotillo 500 kV Line | 2025-06-01 07:00 | 2031-02-05 08:00 |  | NA | Complete | Complete | NA
BELL BLUFF STORAGE | 2178 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 312.96 | 300 | Full Capacity |  |  | Group D | SAN DIEGO | CA | SDGE | SDGE | Suncrest Substation 230 kV | 2025-11-30 08:00 | 2035-03-05 08:00 |  | NA | Complete | Complete | NA
CARGO STORAGE | 2180 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 312.96 | 300 | Full Capacity |  |  | Group D | SAN DIEGO | CA | SDGE | SDGE | Otay Mesa Switchyard 230 kV | 2025-03-31 07:00 | 2036-05-05 07:00 |  | NA | Complete | Complete | NA
GATEWAY ENERGY STORAGE 2 | 2185 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 256.29 | 250 | Full Capacity |  |  | Group D | SAN DIEGO | CA | SDGE | SDGE | Otay Mesa Switchyard 230 kV | 2024-06-01 07:00 | 2035-02-05 08:00 |  | NA | Complete | Complete | NA
SANDBAR ENERGY STORAGE | 2186 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 256 | 250 | Full Capacity |  |  | Group B | SAN DIEGO | CA | SDGE | SDGE | San Luis Rey Substation 230 kV | 2025-06-01 07:00 | 2030-02-05 08:00 |  | NA | Complete | Complete | NA
|  | Legend: | ● Study Process Key: Active=project is in study through Construction phases; Complete=project is in Commercial Operation, Withdrawn=project is withdrawn
● Study Process Key: A39=Amendment 39 Procedures (Appendix W), Serial=Standard Large Generator Interconnection Procedures (Appendix U), SGIP=Small Generator Interconnection Procedure (Appendix S), Numbered Clusters=Large Generator Interconnection Procedures in a Queue Cluster Window (Appendix Y), TC=Transition Cluster (Appendix 2 to Appendix Y), ISP=Independent Study Process (Appendix Y), FT=Fast Track (Appendix Y)
● Generating Facility Type Key: CC=Combined Cycle, CT=Combustion Turbine, FC=Fuel Cell, H=Hydro, PS=Pump Storage, PV=Photovoltaic, RE=Reciprocating Engine, ST= Steam Turbine, STH=Solar Thermal, STR=Storage, WT=Wind Turbine
● Generating Facility Fuel Key: B=Biofuel, BAT=Battery, C=Coal, G=Geothermal, FW=Flywheel, HR=Heat Recovery, NG=Natural Gas, NU=Nuclear, O=Fuel Oil, S=Solar, W=Wind, WTR=Water
The contents of these pages are subject to change without notice. Decisions based on information contained within the California ISO's web site are the visitor's sole responsibility.

## Completed Generation Projects
Report Run Date: 03/30/2026
The California ISO Controlled Grid Generation Queue for All: Completed
[6 empty] | Generating Facility | [5 empty] | MWs |  |  |  | Deliverability Status |  |  |  | Location |  | Point of Interconnection |  |  |  |  | Study Availability
Project Name | Queue Position | Interconnection Request Receive Date | Queue Date | Application Status | Study Process | Type-1 | Type-2 | Type-3 | Fuel-1 | Fuel-2 | Fuel-3 | MW-1 | MW-2 | MW-3 | Net MWs to Grid | Full Capacity, Partial or Energy Only (FC/P/EO) | TPD Allocation Percentage | Off-Peak Deliverability and Economic Only | TPD Allocation Group | County | State | Utility | PTO Study Region | Station or Transmission Line | Proposed On-line Date (as filed with IR) | Actual On-line Date | Feasibility Study or Supplemental Review | System Impact Study or Phase I Cluster Study | Facilities Study (FAS) or Phase II Cluster Study | Optional Study (OS) | Interconnection Agreement Status
OTAY MESA GENERATING PROJECT | 1A | 1999-11-01 | 1999-11-01 08:00 | COMPLETED | Pre- Amend. 39 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 550 | 550 |  |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Otay Mesa Switchyard 230 kV | 2002-03-01 08:00 | 2009-10-02 07:00 |  | Complete | Complete |  | Executed
GATEWAY GENERATING FACILITY (FKA CONTRA COSTA POWER PLANT PROJECT) | 2 | 1999-08-10 | 2000-02-03 08:00 | COMPLETED | Pre- Amend. 39 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 590 | 590 |  |  | Off-Peak Deliverability |  | CONTRA COSTA | CA | PGAE |  | Contra Costa Power Plant 230 kV bus | 2007-11-28 08:00 | 2009-01-06 08:00 |  | Complete | Complete |  | Executed
CPV SENTINEL (FKA INTERGEN OCOTILLO) | 3 | 2000-04-21 | 2000-06-14 07:00 | COMPLETED | Serial LGIP | Gas Turbine | Storage |  | Natural Gas | Battery |  | 850 | 16 |  | 850 | Full Capacity |  | Off-Peak Deliverability |  | RIVERSIDE | CA | SCE | Eastern | Devers Substation 230kV Bus | 2004-01-01 08:00 | 2013-06-01 07:00 | Waived | Re-Study | Re-Study | Complete | Executed
PALOMAR ENERGY PROJECT | 4 | 2000-08-08 | 2000-08-08 07:00 | COMPLETED | Pre- Amend. 39 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 521 | 521 |  |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Palomar Energy Switchyard 230 kV | 2001-06-01 07:00 | 2005-10-14 07:00 |  | Complete | Complete |  | Executed
NRG EL SEGUNDO - TOT041 | 7 | 2000-08-16 | 2000-10-06 07:00 | COMPLETED | Pre- Amend. 39 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 570 | 570 |  |  | Off-Peak Deliverability |  | LOS ANGELES | CA | SCE | Metro | El Segundo 220 kV Bus | 2009-08-01 07:00 | 2013-07-10 07:00 |  | Complete | Complete | Complete | Executed
BLYTHE ENERGY PROJECT PHASE I | 11A | 2002-07-26 | 2002-07-26 07:00 | COMPLETED |  | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 520 | 520 | Full Capacity |  | Off-Peak Deliverability |  | RIVERSIDE | CA | SCE | Northern | Julian Hinds Substation 230kV | 2005-06-01 07:00 | 2010-07-31 07:00 | NA | Complete | Complete | NA | Executed
SHILOH I WIND PROJECT | 12 | 2002-12-16 | 2002-12-16 08:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 150 | 150 |  |  | Off-Peak Deliverability |  | SOLANO | CA | PGAE |  | Birds Landing Sub 230kV Bus | 2005-10-31 08:00 | 2006-03-30 08:00 |  | Complete | Complete |  | Executed
LAKE HODGES PUMPED STORAGE PROJECT | 13 | 2003-01-03 | 2003-01-03 08:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Water; MWs MW-1: 40 | 40 |  |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Lake Hodges Metering Switchyard 69 kV | 2007-07-01 07:00 | 2012-08-26 07:00 |  | Complete | Complete |  | Executed
OTAY MESA | 14 | 2003-01-07 | 2003-01-07 08:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 65 | 65 |  |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Otay Mesa Switchyard 230 kV | 2004-12-31 08:00 | 2009-10-02 07:00 |  | Complete | Complete |  | Executed
KUMEYAAY/CAMPO WIND FARM | 19 | 2003-06-04 | 2003-06-18 07:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 46 | 46 |  |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Crestwood Substation 69 kV | 2005-12-31 08:00 | 2005-09-30 07:00 |  | Complete | Complete |  | Executed
MANZANA WIND | 20 | 2003-08-19 | 2003-09-04 07:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Other; Generating Facility Fuel-1: Other; MWs MW-1: 189 | 189 |  |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind 220kV | 2006-12-31 08:00 | 2018-11-14 08:00 |  | Complete | Complete
BUENA VISTA REPOWER | 21 | 2003-10-03 | 2003-10-23 07:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 37.55 | 37.55 |  |  | Off-Peak Deliverability |  | CONTRA COSTA | CA | PGAE |  | Windmaster/Buena Vista Sub | 2004-07-01 07:00 | 2006-12-28 08:00 |  | N/A |  |  | Executed
MOUNTAINVIEW POWER PROJECT | 23 | 2003-11-17 | 2003-11-24 08:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 72 | 72 |  |  | Off-Peak Deliverability |  | SAN BERNARDINO | CA | SCE | Eastern | San Bernadino 220+M127 kV | 2004-11-01 08:00 | 2005-10-01 07:00 |  | Complete | Complete |  | Executed
SHILOH WIND FARM II | 24 | 2004-01-30 | 2004-01-30 08:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 150 | 150 |  |  | Off-Peak Deliverability |  | SOLANO | CA | PGAE |  | High Winds/Contra Costa PP | 2006-12-31 08:00 | 2009-01-26 08:00 |  | Complete | Complete |  | Executed
TERRA-GEN DIXIE VALLEY EXPANSION (FKA CAITHNESS DIXIE VALLEY) | 33 | 2004-07-09 | 2004-07-12 07:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 10 | 10 |  |  | Off-Peak Deliverability |  | CHURCHILL | NV | SCE |  | Bishop Control Substation 115 kV | 1988-07-14 07:00 | 2006-05-30 07:00 |  | Complete | Complete |  | Executed
HUMBOLDT BAY POWER PLANT REPOWERING PROJECT | 38 | 2004-10-19 | 2004-11-11 08:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Combustion Turbine; MWs MW-1: 146.4 | 146.4 |  |  | Off-Peak Deliverability |  | HUMBOLDT | CA | PGAE |  | Humboldt Power Plant Substation | 2008-08-01 07:00 | 2010-09-29 07:00 |  | Complete | Complete |  | Executed
SHILOH III | 39 | 2004-11-11 | 2004-11-11 08:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 200 | 200 |  |  | Off-Peak Deliverability |  | SOLANO | CA | PGAE |  | Birds Landing Switching Station 230kV | 2008-12-31 08:00 | 2012-12-04 08:00 |  | Complete | Complete |  | Executed
RUSSELL CITY ENERGY CENTER | 45 | 2004-12-01 | 2004-12-01 08:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Combustion Turbine; MWs MW-1: 354 | 354 |  |  | Off-Peak Deliverability |  | ALAMEDA | CA | PGAE |  | Eastshore Substation 230kV | 2006-07-31 07:00 | 2013-08-08 07:00 |  | Complete | Re-Study |  | Executed
INLAND EMPIRE ENERGY CENTER | 50 | 2004-12-21 | 2004-12-21 08:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 810 | 810 |  |  | Off-Peak Deliverability |  | RIVERSIDE | CA | SCE | Eastern | SCE Valley Substation 500 kV | 2008-05-31 07:00 | 2010-06-07 07:00 |  | Complete | Complete |  | Executed
FRESNO COGEN ICE UNIT | 51 | 2004-12-20 | 2004-12-21 08:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Combustion Turbine; MWs MW-1: 0.55 | 0.55 |  |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE |  | Kerman-Helm 70kV line | 2005-04-30 07:00 | 2006-05-30 07:00 |  | N/A |  |  | Executed
PANOCHE ENERGY CENTER | 52 | 2004-12-01 | 2004-12-21 08:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 401 | 401 |  |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE |  | Panoche Substation | 2008-06-30 07:00 | 2009-05-28 07:00 | Waived | Complete | Complete | None | Executed
CPV COLUSA | 57 | 2004-12-01 | 2005-02-08 08:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 715 | 715 |  |  | Off-Peak Deliverability |  | COLUSA | CA | PGAE |  | Between Cottonwood and Vaca-Dixon | 2010-01-01 08:00 | 2010-12-22 08:00 |  | Complete | Complete |  | Executed
WALNUT CREEK ENERGY PARK - PHASE 1 | 66 | 2005-05-06 | 2005-05-06 07:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Combustion Turbine; MWs MW-1: 500.5 | 500.5 |  |  | Off-Peak Deliverability |  | LOS ANGELES | CA | SCE | Metro | Walnut Substation 220kV | 2007-09-01 07:00 | 2013-03-21 07:00 |  | Complete | Complete |  | Executed
RUSSELL CITY ENERGY CENTER EXPANSION | 67 | 2005-03-28 | 2005-05-09 07:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 245 | 245 |  |  | Off-Peak Deliverability |  | ALAMEDA | CA | PGAE |  | Eastshore Substation 230kV | 2008-07-31 07:00 | 2013-08-08 07:00 |  | Complete | Re-Study |  | Executed
OX MOUNTAIN LANDFILL GAS GENERATION | 70 | 2005-05-09 | 2005-06-14 07:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Combustion Turbine; MWs MW-1: 12.6 | 12.6 |  |  | Off-Peak Deliverability |  | SAN MATEO | CA | PGAE |  | Hillsdale Junction-Half Moon Bay 60 kV line | 2005-12-23 08:00 | 2009-03-31 07:00 |  | Complete | Complete |  | Executed
PACIFIC WIND | 73 | 2005-06-06 | 2005-06-27 07:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 141.3 | 141.3 |  |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Sub 230kV Bus | 2007-12-31 08:00 | 2012-07-20 07:00 | Waived | Complete | Complete | None | Executed
HATCHET RIDGE WIND FARM PROJECT | 74 | 2005-07-12 | 2005-07-12 07:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 102 | 102 |  |  | Off-Peak Deliverability |  | SHASTA | CA | PGAE | None | Pit #3-Round Mountain 230kV Line | 2007-12-15 08:00 | 2010-11-18 08:00 | Required | Complete | Re-Study | None | Executed
CHOWCHILLA BIOMASS | 75 | 2005-04-28 | 2005-07-15 07:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Biofuel; MWs MW-1: 10.5 | 10.5 |  |  | Off-Peak Deliverability |  | MADERA | CA | PGAE |  | Le Grand-Chowcilla 115 kV | 2005-12-31 08:00 | 2009-05-19 07:00 |  | Complete | Complete |  | Executed
EL NIDO | 76 | 2005-04-28 | 2005-07-15 07:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Biofuel; MWs MW-1: 10.5 | 10.5 |  |  | Off-Peak Deliverability |  | MERCED | CA | PGAE |  | Merced #1 70 kV circuit | 2006-07-01 07:00 | 2009-05-18 07:00 |  | Complete | Complete |  | Executed
AVALON HYBRID | 84 | 2005-11-22 | 2005-12-01 08:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Sub 230kV Bus | 2009-12-31 08:00 | 2019-11-09 08:00 | Waived | Complete | Complete | None | Executed
VOYAGER WIND | 93 | 2006-02-15 | 2006-03-01 08:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 220 | 220 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Windhub Substation 220kV bus | 2008-12-31 08:00 | 2021-04-26 07:00 | Waived | Complete | Complete | None | Executed
CPC EAST | 95 | 2006-02-10 | 2006-03-01 08:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 550 | 550 |  |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Windhub Substation 220kV bus | 2009-12-31 08:00 | 2012-02-14 08:00 | Waived | Complete | Complete | None | Executed
DIABLO CANYON P.P. UNIT 1 | 98 | 2006-03-09 | 2006-03-09 08:00 | COMPLETED | TC | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Nuclear; MWs MW-1: 37 | 37 | Full Capacity |  | Off-Peak Deliverability |  | SAN LUIS OBISPO | CA | PGAE |  | Diablo Canyon Substation Cirvuit Breakers 532 and 632 | 2005-12-08 08:00 | 2005-12-31 08:00 | NA | Complete | None | NA
DIABLO CANYON P.P. UNIT 2 | 99 | 2006-03-29 | 2006-03-29 08:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 45 | 45 |  |  | Off-Peak Deliverability |  | SAN LUIS OBISPO | CA | PGAE |  | Diablo Canyon Substation Circuit Breakers 542 and 642 | 2006-06-08 07:00 | 2006-06-07 07:00 | None | None | None | None
SOLANO WIND PROJECT - PHASE 3 (230KV) | 108 | 2006-06-09 | 2006-06-09 07:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 128 | 128 |  |  | Off-Peak Deliverability |  | SOLANO | CA | PGAE |  | Lambie-Contra Costa 230 kV | 2011-03-01 08:00 | 2012-03-04 08:00 | Required | Complete | Complete | Complete | Executed
VOYAGER WIND 2 | 119 | 2006-08-08 | 2006-08-08 07:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 500 | 500 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Windhub Sub 230kV Bus | 2013-12-31 08:00 | 2021-04-26 07:00 | Required | Complete | Complete | None | Executed
MIRAMAR ENERGY FACILITY II | 121 | 2006-08-16 | 2006-08-17 07:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49 | 49 |  |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Miramar GT Substation 69 kV | 2009-03-31 07:00 | 2009-08-07 07:00 | Waived | Complete | Complete | None | Executed
MOJAVE SOLAR (FKA HARPER LAKE SOLAR) | 125 | 2006-08-22 | 2006-08-22 07:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 | Full Capacity |  | Off-Peak Deliverability |  | SAN BERNARDINO | CA | SCE | NOL | Coolwater-Kramer 230kv line | 2010-08-01 07:00 | 2014-12-04 08:00 | Required | Complete | Complete | Complete | Executed
DPT 1 | 131 | 2006-09-25 | 2006-09-25 07:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 132 | 132 |  |  | Off-Peak Deliverability |  | SAN BERNARDINO | CA | SCE | NOL | Eldorado-Baker-Cool Water-Dunn Siding-Mountain Pass 115kV line | 2010-06-30 07:00 | 2013-12-30 08:00 | Required | Complete | Complete | None | Executed
NORTH SKY RIVER WIND | 132 | 2006-09-27 | 2006-09-27 07:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 162 | 162 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Highwind Substation 230kV bus | 2010-12-31 08:00 | 2012-12-07 08:00 | Required | Complete | Complete | Complete | Executed
CARLSBAD 1 | 137 | 2006-10-16 | 2006-10-17 07:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 211 | 211 |  |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Encina Substation 230 kV | 2017-08-01 07:00 | 2018-11-19 08:00 | Waived | Complete | Complete | None | Executed
DESERT SUNLIGHT PV I | 146 | 2006-11-16 | 2006-11-16 08:00 | COMPLETED | Serial LGIP | Photovoltaic | Storage |  | Solar | Battery |  | 250 | 230 |  | 250 | Partial Capacity | 65 | Off-Peak Deliverability |  | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 230kV | 2008-12-01 08:00 |  | Required | Complete | Complete | None | Executed
DESERT SUNLIGHT PV II | 147 | 2006-11-16 | 2006-11-16 08:00 | COMPLETED | Serial LGIP | Photovoltaic | Storage |  | Solar | Battery |  | 300 | 230 |  | 300 | Partial Capacity | 65 | Off-Peak Deliverability |  | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 230kV | 2010-02-01 08:00 |  | Required | Complete | Complete | None | Executed
ENERGIA SIERRA JUAREZ WIND | 159A | 2006-12-06 | 2006-12-22 08:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 256 | 256 | Full Capacity |  | Off-Peak Deliverability |  | BAJA CALIFORNIA | MX | SDGE |  | East County Substation 230 kV | 2009-06-01 07:00 | 2022-01-13 08:00 | Required | Complete | Complete | None | Executed
DPT 2 | 162 | 2007-01-05 | 2007-01-05 08:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 126 | 126 |  |  | Off-Peak Deliverability |  | SAN BERNARDINO | CA | SCE | NOL | Eldorado-Baker-Cool Water-Dunn Siding-Mountain Pass 115kV line | 2010-06-30 07:00 | 2013-12-30 08:00 | Waived | Complete | Complete | None | Executed
DESERT STATELINE PROJECT | 163 | 2007-01-09 | 2007-01-09 08:00 | COMPLETED | TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 300 | 300 | Full Capacity |  | Off-Peak Deliverability |  | SAN BERNARDINO | CA | SCE | EOP | Mountain Pass Substation 115kV | 2010-12-31 08:00 | 2016-08-30 07:00 | NA | Complete | Complete | NA | Executed
CALIFORNIA VALLEY PV | 166 | 2007-01-23 | 2007-01-23 08:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 210 | 210 |  |  | Off-Peak Deliverability |  | SAN LUIS OBISPO | CA | PGAE |  | Midway-Morrow Bay 230kV line | 2010-12-31 08:00 | 2014-10-27 07:00 | Required | Re-Study | Complete | None | Executed
RISING TREE WIND FARM (FKA HOMESTEAD WIND FARM) | 188 | 2007-03-23 | 2007-03-23 07:00 | COMPLETED | TC | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 198 | 198 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Windhub Substation 230kV | 2013-12-15 08:00 | 2015-06-25 07:00 | NA | Complete | Complete | NA | Executed
CARLSBAD 2 | 189 | 2007-03-30 | 2007-03-30 07:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 105.8 | 105.8 | Full Capacity |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Encina Substation 138 kV | 2010-05-01 07:00 | 2019-06-10 07:00 | Waived | Complete | Complete | None | Executed
GENESIS MCCOY | 193 | 2007-03-19 | 2007-04-04 07:00 | COMPLETED | TC | Steam Turbine | Storage |  | Solar | Battery |  | 500 | 230 |  | 500 | Partial Capacity | 68.3 | Off-Peak Deliverability |  | RIVERSIDE | CA | SCE | Eastern | Colorado River Substation 500kV | 2010-12-31 08:00 | 2021-06-30 07:00 | NA | Complete | Complete | NA | Executed
CARRIZO PLAIN SOLAR | 194 | 2007-04-05 | 2007-04-05 07:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 190 | 190 |  |  | Off-Peak Deliverability |  | SAN LUIS OBISPO | CA | PGAE |  | Morro Bay-Midway #1 & #2 lines 230kV | 2010-12-31 08:00 | 2014-10-27 07:00 | Required | Complete | Complete | None | Executed
ORANGE GROVE | 201 | 2007-04-02 | 2007-04-19 07:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 99 | 99 |  |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Pala Substation 69 kV | 2008-05-31 07:00 | 2010-06-16 07:00 | Waived | Complete | Complete | None | Executed
IVANPAH SEGS 3 | 233 | 2007-06-27 | 2007-06-27 07:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 132 | 132 |  |  | Off-Peak Deliverability |  | SAN BERNARDINO | CA | SCE | NOL | Ivanpah Substation 115kV | 2013-06-30 07:00 | 2013-12-30 08:00 | Waived | Complete | Complete | None | Executed
CALIFORNIA VALLEY SOLAR RANCH (FKA CARRIZO SOLAR FARM II) | 239 | 2007-07-11 | 2007-07-11 07:00 | COMPLETED | TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 | Full Capacity |  | Off-Peak Deliverability |  | SAN LUIS OBISPO | CA | PGAE |  | Midway-Morro Bay 230kV line | 2010-12-01 08:00 | 2014-02-13 08:00 | NA | Complete | Complete | NA | Executed
DESERT TOPAZ PV 2 | 242 | 2007-07-13 | 2007-07-13 07:00 | COMPLETED | TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | Off-Peak Deliverability |  | SAN LUIS OBISPO | CA | PGAE |  | Morro Bay-Midway 230kV line | 2012-09-01 07:00 | 2014-10-27 07:00 | NA | Complete | Complete | NA | Executed
AES REDONDO BEACH UNIT 7 | 252 | 2007-07-11 | 2007-08-06 07:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 25.96 | 25.96 |  |  | Off-Peak Deliverability |  | LOS ANGELES | CA | SCE | Metro | Redondo Beach Generating Station 220kV switchyard | 2007-05-23 07:00 | 2010-02-07 08:00 | Waived | None | None | None | Executed
CALRENEW-1(A) | 261A | 2007-10-09 | 2007-10-09 07:00 | COMPLETED | AMEND 39 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 5 | 5 |  |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE |  | Mendota-San Joaquin-Helm 70kV line | 2009-04-15 07:00 | 2010-04-20 07:00 |  |  |  |  | Executed
LODI ENERGY CENTER | 267 | 2007-10-23 | 2007-10-23 07:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 280 | 280 |  |  | Off-Peak Deliverability |  | SAN JOAQUIN | CA | PGAE |  | Gold Hill-Eight Mile 230kV lines | 2012-04-16 07:00 | 2012-07-16 07:00 | Required | Unexpected | Complete | None | Executed
PALOMAR ENERGY CENTER EXPANSION | 274 | 2007-11-05 | 2007-11-05 08:00 | COMPLETED | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 54 | 54 |  |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Palomar Energy Switchyard 230 kV | 2008-08-25 07:00 | 2008-08-24 07:00 | Waived | Complete | Complete | None | Executed
DRACKER SOLAR | 294 | 2008-01-15 | 2008-01-16 08:00 | COMPLETED | TC | Photovoltaic | Storage |  | Solar | Battery |  | 485 | 340 |  | 485 | Partial Capacity | 75.2 | Off-Peak Deliverability |  | RIVERSIDE | CA | SCE | None | Colorado River Substation 220kV | 2012-06-01 07:00 |  | NA | Complete | Complete | NA | Executed
ALPAUGH PV SOLAR GENERATION FACILITY | 304 | 2008-02-28 | 2008-02-28 08:00 | COMPLETED | TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 | Full Capacity |  | Off-Peak Deliverability |  | TULARE | CA | PGAE | None | Smyrna-Alpaugh 115kV line | 2010-05-03 07:00 | 2013-03-08 08:00 | NA | Complete | Complete | NA | Executed
MARSH LANDING GENERATION STATION - SIMPLE CYCLE UNITS | 320 | 2008-03-12 | 2008-03-12 07:00 | COMPLETED | TC | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 100 | 100 | Full Capacity |  | Off-Peak Deliverability |  | CONTRA COSTA | CA | PGAE |  | Contra Costa Substation 230kV switchyard | 2013-05-01 07:00 | 2013-05-01 07:00 | NA | Complete | Complete | NA | Executed
MARIPOSA ENERGY PROJECT (FKA DGC KELSO CT) | 334 | 2008-04-04 | 2008-04-04 07:00 | COMPLETED | TC | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 195.9 | 195.9 | Full Capacity |  | Off-Peak Deliverability |  | ALAMEDA | CA | PGAE |  | Kelso Substation 230kV bus | 2012-06-01 07:00 | 2012-06-30 07:00 | NA | Complete | Complete | NA | Executed
BORREGO SOLAR I | 337 | 2008-04-02 | 2008-04-18 07:00 | COMPLETED | TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 26 | 25.75 | Full Capacity |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Borrego Substation 69 kV | 2011-04-01 07:00 | 2013-02-12 08:00 | NA | Complete | Complete | NA | Executed
ATWELL ISLAND PV SOLAR GENERATING FACILITY | 340 | 2008-04-02 | 2008-04-22 07:00 | COMPLETED | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | TULARE | CA | PGAE |  | Smyrna-Alpaugh 115kV line | 2010-05-01 07:00 | 2013-03-08 08:00 | System Impact Study | Facilities Study | SGIA | NA | Executed
CUYAMA SOLAR | 356 | 2008-04-28 | 2008-04-28 07:00 | COMPLETED | TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 40 | 40 | Full Capacity |  | Off-Peak Deliverability |  | SAN LUIS OBISPO | CA | PGAE | None | Taft-Cuyama #1 70kV line | 2012-04-01 07:00 | 2017-11-30 08:00 | NA | Complete | Complete | NA | Executed
ALMASOL | 365 | 2008-05-06 | 2008-05-12 07:00 | COMPLETED | TC | Photovoltaic | Storage |  | Solar | Battery |  | 457 | 50 |  | 457 | Full Capacity |  | Off-Peak Deliverability |  | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 230kV | 2013-12-28 08:00 | 2022-06-27 07:00 | NA | Complete | Complete | NA | Executed
SOLAR STAR 1 | 407 | 2008-05-30 | 2008-05-30 07:00 | COMPLETED | TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 310 | 310 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Cottonwind-Whirlwind 230kV line | 2012-07-01 07:00 | 2015-06-08 07:00 | NA | Complete | Complete | NA | Executed
SOLAR STAR 2 | 408 | 2008-05-30 | 2008-05-30 07:00 | COMPLETED | TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 276 | 276 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Cottonwind-Whirlwind 230kV line | 2012-07-01 07:00 | 2015-06-25 07:00 | NA | Complete | Complete | NA | Executed
AV SOLAR ONE PROJECT | 412 | 2008-05-30 | 2008-05-30 07:00 | COMPLETED | TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 | Full Capacity |  | Off-Peak Deliverability |  | LOS ANGELES | CA | SCE | Northern | Whirlwind Substation 230kV | 2012-08-01 07:00 | 2014-06-19 07:00 | NA | Complete | Complete | NA | Executed
SLOTH | 421 | 2008-05-30 | 2008-05-30 07:00 | COMPLETED | TC | Photovoltaic | Storage |  | Solar | Battery |  | 49.5 | 15 |  | 49.5 | Partial Capacity |  | Off-Peak Energy Only |  | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 220kV | 2012-02-01 08:00 | 2024-03-26 07:00 | NA | Complete | Complete | NA | Executed
WISTARIA RANCH SOLAR ENERGY | 429 | 2008-05-30 | 2008-05-30 07:00 | COMPLETED | TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | Off-Peak Deliverability |  | IMPERIAL | CA | SDGE |  | Imperial Valley Substation 230 kV | 2014-07-01 07:00 | 2018-11-06 08:00 | NA | Complete | Complete | NA | Executed
CENTINELA SOLAR ENERGY | 442 | 2008-05-30 | 2008-05-30 07:00 | COMPLETED | TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 125 | 125 | Full Capacity |  | Off-Peak Deliverability |  | IMPERIAL | CA | SDGE |  | Imperial Valley Substation 230 kV | 2013-10-01 07:00 | 2014-07-30 07:00 | NA | Complete | Complete | NA | Executed
SILVER STATE SOUTH SOLAR PROJECT | 467 | 2008-05-30 | 2008-06-02 07:00 | COMPLETED | TC | Steam Turbine | Storage |  | Solar | Battery |  | 230 | 200 |  | 230 | Full Capacity |  | Off-Peak Deliverability |  | CLARK | NV | SCE | EOP | Eldorado-Ivanpah 230kV line | 2012-08-01 07:00 | 2016-08-23 07:00 | NA | Complete | Complete | NA | Executed
AGUA CALIENTE | 468 | 2008-05-30 | 2008-06-02 07:00 | COMPLETED | TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 290 | 290 | Energy Only |  | Off-Peak Deliverability |  | YUMA | AZ | SDGE |  | Hoodoo Wash Switchyard 500 kV | 2012-08-01 07:00 | 2014-06-10 07:00 | NA | Complete | Complete | NA | Executed
BLUE LAKE POWER | 472 | 2010-11-20 | 2008-08-11 07:00 | COMPLETED | SGIP | Steam Turbine | Steam Turbine |  | Biofuel | Biofuel |  | 11 | 0 |  | 0 | Full Capacity |  | Off-Peak Deliverability |  |  |  | PGAE |  | Blue Lake Power Substation | 2008-12-20 08:00 | 2010-09-09 07:00 | None | None | None | NA | Executed
ALPAUGH NORTH PV SOLAR GENERATING FACILITY | 473 | 2008-09-03 | 2008-09-12 07:00 | COMPLETED | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | TULARE | CA | PGAE |  | Smyrna-Alpaugh 115kV line | 2010-05-01 07:00 | 2013-03-08 08:00 | None | Facilities Study | SGIA | NA | Executed
AMERESCO BUTTE COUNTY LANDFILL | 477 | 2009-02-02 | 2009-02-06 08:00 | COMPLETED | SGIP | Generating Facility Type-1: Reciprocating Engine; Generating Facility Fuel-1: Biofuel; MWs MW-1: 4 | 4 | Energy Only |  | Off-Peak Deliverability |  | BUTTE | CA | PGAE |  | Centerville-Table Mountain 60kV line | 2010-03-31 07:00 | 2012-05-15 07:00 | None | None | SGIA | NA | Executed
CORCORAN PV GENERATION FACILITY | 478 | 2009-02-17 | 2009-02-17 08:00 | COMPLETED | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | KINGS | CA | PGAE |  | Corcoran-Kingsburg 115kV #2 line | 2011-11-01 07:00 | 2013-08-14 07:00 | None | Facilities Study | SGIA | NA | Executed
WHITE RIVER PV 20MVA SOLAR GENERATION FACILITY | 479 | 2009-03-13 | 2009-03-13 07:00 | COMPLETED | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | TULARE | CA | PGAE |  | Smyrna-Alpaugh 115kV line | 2011-10-01 07:00 | 2013-06-25 07:00 | None | Facilities Study | SGIA | NA | Executed
BVBP REPOWERING PROJECT | 481 | 2009-04-06 | 2009-04-20 07:00 | COMPLETED | SGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Biofuel; MWs MW-1: 18.4 | 18.4 | Energy Only |  | Off-Peak Deliverability |  | AMADOR | CA | PGAE |  | Valley Springs-Martel #2 60kV line | 2010-04-01 07:00 | 2012-01-30 08:00 | None | Facilities Study | SGIA | NA | Executed
ATWELL WEST PV SOLAR GENERATING FACILITY | 482 | 2009-04-24 | 2009-04-24 07:00 | COMPLETED | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | TULARE | CA | PGAE |  | Smyrna-Alpaugh 115kV line | 2012-08-01 07:00 | 2015-06-11 07:00 | None | Facilities Study | SGIA | NA | Executed
LOST HILLS SOLAR | 484 | 2009-06-11 | 2009-06-11 07:00 | COMPLETED | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | SAN FRANCISCO | CA | PGAE |  | Arco-Carneras 70 kV Line | 2013-12-31 08:00 | 2015-04-10 07:00 | None | Facilities Study | SGIA | NA | Executed
TULLOCH POWERHOUSE | 495 | 2009-07-24 | 2009-07-31 07:00 | COMPLETED | C01 | Generating Facility Type-1: Hydro; Generating Facility Fuel-1: Water; MWs MW-1: 7.2 | 7.2 | Full Capacity |  | Off-Peak Deliverability |  | TUOLUMNE | CA | PGAE |  | Tulloch 115kV tap | 2011-10-01 07:00 | 2012-03-31 07:00 | NA | Complete | Complete | NA | Executed
SILVER STATE SOUTH SOLAR PROJECT (FKA SILVER STATE SOLAR II) | 502 | 2009-07-28 | 2009-07-31 07:00 | COMPLETED | C01 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | CLARK | NV | SCE | EOP | Eldorado-Ivanpah 230kV line | 2016-05-01 07:00 | 2016-08-23 07:00 | NA | Complete | Complete | NA | Executed
CMS2 (FKA BOULDER CITY PV) | 503 | 2009-07-28 | 2009-07-31 07:00 | COMPLETED | C01 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 155 | 155 | Full Capacity |  | Off-Peak Deliverability |  | CLARK | NV | SDGE |  | Merchant Switchyard 230 kV | 2016-01-01 08:00 | 2015-06-14 07:00 | NA | Complete | Complete | NA | Executed
EL CAJON ENERGY CENTER | 509 | 2009-07-31 | 2009-07-31 07:00 | COMPLETED | C01 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49.9 | 49.9 | Full Capacity |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | El Cajon Substation 69 kV | 2010-06-15 07:00 | 2010-10-31 07:00 | NA | Complete | None | NA | Executed
IV SUBSTATION SOUTH | 510 | 2009-07-31 | 2009-07-31 07:00 | COMPLETED | C01 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 130 | 130 | Full Capacity |  | Off-Peak Deliverability |  | IMPERIAL | CA | SDGE |  | Imperial Valley Substation 230 kV | 2012-07-01 07:00 | 2013-10-11 07:00 | NA | Complete | Complete | NA | Executed
OLD RIVER 1 | 517 | 2009-08-19 | 2009-08-19 07:00 | COMPLETED | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | PGAE |  | Kern-Old River #1 70kV line | 2012-12-31 08:00 | 2014-12-30 08:00 | None | Facilities Study | SGIA | NA | Executed
PAIGE SOLAR | 526 | 2009-09-11 | 2009-09-11 07:00 | COMPLETED | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE | None | Schindler-Coalinga #2 70kV line | 2012-01-01 08:00 | 2017-03-09 08:00 | None | Facilities Study | SGIA | NA | Executed
FRESHWATER SOLAR GENERATING FACILITY (FKA SWEETWATER PV 20MVA SOLAR GENERATING FACILITY) | 529 | 2009-10-19 | 2009-10-19 07:00 | COMPLETED | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | Off-Peak Deliverability |  | KINGS | CA | PGAE |  | Corcoran- Kingsburg #1 115kV line | 2013-08-01 07:00 | 2016-01-15 08:00 | None | Facilities Study | SGIA | NA | Executed
WHITNEY POINT SOLAR | 532 | 2009-11-02 | 2009-11-02 08:00 | COMPLETED | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE | None | Schindler-Huron-Gates 70kV line | 2012-01-01 08:00 | 2017-04-15 07:00 | None | Facilities Study | SGIA | NA | Executed
VEGA SOLAR (FKA: FRV VEGA SOLAR) | 548 | 2009-11-19 | 2010-01-15 08:00 | COMPLETED | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | Off-Peak Deliverability |  | KINGS | CA | PGAE | None | Mercy Springs Substation 70kV | 2011-10-31 07:00 | 2015-03-23 07:00 | None | Facilities Study | SGIA | NA | Executed
WHITE RIVER 2 (FKA:WHITE RIVER WEST 19.75 MW PV GENERATION FACILTY) | 557 | 2010-01-27 | 2010-02-01 08:00 | COMPLETED | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 19.75 | 19.75 | Full Capacity |  | Off-Peak Deliverability |  | TULARE | CA | PGAE |  | Smyrna-Alpaugh 115kV line | 2013-04-01 07:00 | 2014-10-01 07:00 | NA | Complete | Complete | NA | Executed
CORCORAN 2 GENERATING FACILITY (FKA: CORCORAN WEST 19.75 MW PV GENERATION FACILTY) | 558 | 2010-01-27 | 2010-02-01 08:00 | COMPLETED | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 19.75 | 19.75 | Full Capacity |  | Off-Peak Deliverability |  | KINGS | CA | PGAE |  | Corcoran-Kingsburg #2 115kV | 2013-06-01 07:00 | 2015-05-20 07:00 | NA | Complete | Complete | NA | Executed
REGULUS SOLAR (FKA FRV REGULUS SOLAR) | 559 | 2010-01-27 | 2010-02-01 08:00 | COMPLETED | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 60 | 60 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | PGAE |  | Wheeler Ridge-Lamont 115kV | 2012-07-01 07:00 | 2014-11-11 08:00 | NA | Complete | Complete | NA | Executed
RUSSELL CITY ENERGY CENTER FD3 UPGRADE | 568 | 2010-01-28 | 2010-02-01 08:00 | COMPLETED | C02 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 25 | 25 | Full Capacity |  | Off-Peak Deliverability |  | ALAMEDA | CA | PGAE |  | Eastshore Substation 230kV Bus | 2013-05-01 07:00 | 2013-08-08 07:00 | NA | Complete | Complete | NA | Executed
PIO PICO ENERGY CENTER | 574 | 2010-01-29 | 2010-02-01 08:00 | COMPLETED | C02 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 308 | 308 | Full Capacity |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Otay Mesa Switchyard 230 kV | 2013-05-01 07:00 | 2016-11-03 07:00 | NA | Complete | Complete | NA | Executed
BLYTHE MESA SOLAR | 576 | 2010-01-29 | 2010-02-01 08:00 | COMPLETED | C02 | Photovoltaic | Storage |  | Solar | Battery |  | 224 | 112 |  | 224 | Full Capacity |  | Off-Peak Deliverability |  | RIVERSIDE | CA | SCE | Eastern | Colorado River Sub 230kV Bus | 2013-12-31 08:00 | 2022-12-22 08:00 | NA | Complete | Complete | NA | Executed
SOLAR STAR CALIFORNIA XIII (QUINTO) | 577 | 2010-01-29 | 2010-02-01 08:00 | COMPLETED | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 110 | 110 | Full Capacity |  | Off-Peak Deliverability |  | MERCED | CA | PGAE |  | Los Banos-Westley 230kV | 2013-12-31 08:00 | 2015-11-30 08:00 | NA | Complete | Complete | NA | Executed
HENRIETTA SOLAR (FKA SUNPOWER HENRIETTA SOLAR) | 581 | 2010-01-29 | 2010-02-01 08:00 | COMPLETED | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | Off-Peak Deliverability |  | KINGS | CA | PGAE | None | Henrietta-GWF 115 kV Line | 2013-05-01 07:00 | 2016-08-15 07:00 | NA | Complete | Complete | NA | Executed
CAMPO VERDE SOLAR (FKA USS WIXOM SOLAR 1) | 590 | 2010-01-29 | 2010-02-01 08:00 | COMPLETED | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 147 | 147 | Full Capacity |  | Off-Peak Deliverability |  | IMPERIAL | CA | SDGE |  | Imperial Valley Substation 230 kV | 2012-12-31 08:00 | 2013-10-22 07:00 | NA | Complete | Complete | NA | Executed
CATALINA SOLAR | 602 | 2010-01-30 | 2010-02-01 08:00 | COMPLETED | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 145.44 | 145.44 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2013-07-01 07:00 | 2022-12-29 08:00 | NA | Complete | Complete | NA | Executed
TRACY - ADDITIONAL CAPACITY | 606 | 2010-02-01 | 2010-02-01 08:00 | COMPLETED | C02 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | SAN JOAQUIN | CA | PGAE |  | Schulte Switching Station 115kV bus | 2012-06-01 07:00 | 2012-05-31 07:00 | NA | Complete | Complete | NA | Executed
NORTH STAR SOLAR 1 | 607 | 2010-02-01 | 2010-02-01 08:00 | COMPLETED | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 60 | 60 | Full Capacity |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE |  | Mendota Substation 115 kV bus | 2012-10-01 07:00 | 2015-06-20 07:00 | NA | Complete | Complete | NA | Executed
IMPERIAL VALLEY WEST | 608 | 2010-02-01 | 2010-02-01 08:00 | COMPLETED | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | Off-Peak Deliverability |  | IMPERIAL | CA | SDGE |  | Imperial Valley Substation 230 kV | 2013-05-01 07:00 | 2016-01-21 08:00 | NA | Complete | Complete | NA | Executed
MARICOPA WEST SOLAR PV (FKA COPUS SOLAR ONE) | 620 | 2010-04-26 | 2010-04-26 07:00 | COMPLETED | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | PGAE |  | Copus Road Sub 70kV bus | 2014-12-31 08:00 | 2015-12-12 08:00 | None | Facilities Study | SGIA | NA | Executed
ORION SOLAR I (FKA: FRV ORION KERN SOLAR) | 621A | 2010-05-05 | 2010-05-05 07:00 | COMPLETED | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | PGAE |  | Weedpatch - San Bernard 70 KV line | 2012-04-02 07:00 | 2014-06-26 07:00 | None | Facilities Study | SGIA | NA | Executed
ADOBE SOLAR (FKA FRV ADOBE SOLAR) | 622B | 2010-05-05 | 2010-05-05 07:00 | COMPLETED | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | PGAE |  | Wheeler Ridge-Lamont 115 kv | 2012-03-31 07:00 | 2014-05-21 07:00 | None | Facilities Study | SGIA | NA | Executed
ADAMS EAST | 632 | 2010-05-25 | 2010-05-25 07:00 | COMPLETED | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 19 | 19 | Full Capacity |  | Off-Peak Deliverability | Group A | FRESNO | CA | PGAE |  | Wesix 70kV Tap | 2012-12-31 08:00 | 2014-12-13 08:00 | None | Facilities Study | SGIA | NA | Executed
SUMMER WHEAT SOLAR FARM | 632B | 2010-06-01 | 2010-06-01 07:00 | COMPLETED | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 18.5 | Full Capacity |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE | None | Stroud switching station 70kV | 2012-12-01 08:00 | 2018-10-11 07:00 | NA | Complete | Complete | NA | Executed
WESTLANDS SOLAR FARM PV1 | 633 | 2010-06-02 | 2010-06-02 07:00 | COMPLETED | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 18 | 18 | Full Capacity |  | Off-Peak Deliverability | Group A | FRESNO | CA | PGAE | None | Gates-Coalinga 70 kV Line #1 | 2012-11-30 08:00 | 2014-02-14 08:00 | None | Facilities Study | SGIA | NA | Executed
KANSAS | 636 | 2010-07-02 | 2010-07-06 07:00 | COMPLETED | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | KINGS | CA | PGAE | None | Leprino Food (Lemoore) 115 kV Tap Line | 2012-12-31 08:00 | 2014-12-18 08:00 | None | Facilities Study | SGIA | NA | Executed
KANSAS SOUTH | 637 | 2010-07-02 | 2010-07-06 07:00 | COMPLETED | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability | Group A | KINGS | CA | PGAE | None | Henrietta-Jacobs Corner 70kV | 2012-12-31 08:00 | 2013-06-06 07:00 | None | Facilities Study | SGIA | NA | Executed
DESERT HARVEST | 643AE | 2010-07-30 | 2010-07-31 07:00 | COMPLETED | C03 | Photovoltaic | Storage |  | Solar | Battery |  | 150 | 35 |  | 150 | Partial Capacity | 65 | Off-Peak Deliverability |  | RIVERSIDE | CA | SCE | Eastern | Red Bluff Sub 230kV Bus | 2014-01-01 08:00 | 2020-12-11 08:00 | NA | Complete | Complete | NA | Executed
WILLOW SPRINGS 2 | 643AJ | 2010-07-30 | 2010-07-31 07:00 | COMPLETED | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Sub 230 kV Bus | 2013-06-01 07:00 | 2019-01-29 08:00 | NA | Complete | Complete | NA | Executed
CENTINELA SOLAR ENERGY EXPANSION (45 MW) | 643AM | 2010-07-30 | 2010-07-31 07:00 | COMPLETED | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 45 | 45 | Full Capacity |  | Off-Peak Deliverability |  | IMPERIAL | CA | SDGE |  | Imperial Valley Substation 230 kV | 2014-03-01 08:00 | 2014-08-15 07:00 | NA | Complete | Complete | NA | Executed
SPI ANDERSON 2 | 643G | 2010-07-20 | 2010-07-31 07:00 | COMPLETED | C03 | Steam Turbine | Steam Turbine |  | Biofuel | Biofuel |  | 27.15 | 27.15 |  | 27.15 | Full Capacity |  | Off-Peak Deliverability |  |  |  | PGAE |  | Cascade-Cottonwood 115 kV | 2012-03-01 08:00 | 2015-09-09 07:00 | NA | Complete | Complete | NA | Executed
MESQUITE SOLAR 1 (FKA MESQUITE GENERATION) | 643T | 2010-07-30 | 2010-07-31 07:00 | COMPLETED | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 165 | 165 | Full Capacity |  | Off-Peak Deliverability |  | MARICOPA | AZ | SDGE |  | Hassayampa Common Bus 500 kV | 2015-10-31 07:00 | 2014-01-01 08:00 | NA | Complete | None | NA | Executed
RE MUSTANG | 643W | 2010-07-08 | 2010-07-31 07:00 | COMPLETED | C03 | Photovoltaic | Storage |  | Solar | Battery |  | 100 | 75 |  | 100 | Full Capacity |  | Off-Peak Deliverability |  | KINGS | CA | PGAE | None | Gates-Gregg 230 kV and Gates-McCall 230 kV | 2014-06-30 07:00 | 2021-10-29 07:00 | NA | Complete | Complete | NA | Executed
RE TRANQUILLITY | 643X | 2010-07-30 | 2010-07-31 07:00 | COMPLETED | C03 | Photovoltaic | Storage |  | Solar | Battery |  | 200 | 72 |  | 200 | Full Capacity |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE | None | Helm-Panoche 230 kV and Panoche-Kearney 230kV | 2014-06-30 07:00 | 2022-03-16 07:00 | NA | Complete | Complete | NA | Executed
CHOWCHILLA SOLAR PROJECT | 644 | 2010-08-16 | 2010-08-16 07:00 | COMPLETED | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | Off-Peak Deliverability |  | MADERA | CA | PGAE |  | Dairyland - Legrand 115 kV | 2012-01-03 08:00 | 2015-12-23 08:00 | NA | Complete | Complete | NA | Executed
JACUMBA SOLAR FARM | 644A | 2010-08-17 | 2010-08-17 07:00 | COMPLETED | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | East County Substation 138 kV | 2012-05-01 07:00 | 2017-07-25 07:00 | NA | Complete | Complete | NA | Executed
KENT SOUTH | 650AB | 2010-09-08 | 2010-09-08 07:00 | COMPLETED | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability | Group A | KINGS | CA | PGAE |  | Henrietta-Tulare Lake 70kV | 2012-12-31 08:00 | 2014-12-24 08:00 | NA | Complete | Complete | NA | Executed
WEST ANTELOPE SOLAR (FKA: TA - ACACIA) | 651A | 2010-09-21 | 2010-09-21 07:00 | COMPLETED | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | LOS ANGELES | CA | SCE | None | Antlelope Sub 66 kV Bus | 2012-06-30 07:00 | 2014-11-13 08:00 | NA | Complete | Complete | NA | Executed
SOUTH KERN SOLAR PV PLANT | 653EA | 2010-09-30 | 2010-09-30 07:00 | COMPLETED | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | PGAE |  | Copus-Old River 70 kV | 2012-04-01 07:00 | 2015-04-07 07:00 | NA | Complete | Complete | NA | Executed
WESTERN ANTELOPE DRY RANCH | 653H | 2010-10-20 | 2010-10-20 07:00 | COMPLETED | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 10 | 10 | Full Capacity |  | Off-Peak Deliverability |  | LOS ANGELES | CA | SCE | Northern | Antelope Sub 66 kV Bus | 2013-12-31 08:00 | 2016-12-01 08:00 | NA | Complete | Complete | NA | Executed
WILDWOOD SOLAR I (FKA GOOSE LAKE SOLAR I) | 654 | 2010-10-25 | 2010-10-25 07:00 | COMPLETED | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | PGAE | None | Semitropic-Midway #2 115kV | 2013-05-01 07:00 | 2015-02-19 08:00 | NA | Complete | Complete | NA | Executed
CENTRAL ANTELOPE SOLAR (FKA WESTERN ANTELOPE BLUE SKY RANCH B) | 659 | 2010-12-15 | 2010-12-15 08:00 | COMPLETED | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | LOS ANGELES | CA | SCE | Northern | Antelope Sub 66 kV Bus | 2013-12-31 08:00 | 2016-05-06 07:00 | NA | Complete | Complete | NA | Executed
WESTERN ANTELOPE BLUE SKY RANCH A | 660 | 2010-12-15 | 2010-12-15 08:00 | COMPLETED | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | LOS ANGELES | CA | SCE | Northern | Antelope Sub 66 kV Bus | 2013-12-31 08:00 | 2014-11-14 08:00 | NA | Complete | Complete | NA | Executed
SIERRA SOLAR GWX (FKA SILVER SUN GREENWORKS) | 662 | 2010-12-15 | 2010-12-15 08:00 | COMPLETED | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | LOS ANGELES | CA | SCE | Northern | Antelope Sub 66 kV Bus | 2013-12-31 08:00 | 2015-11-30 08:00 | NA | Complete | Complete | NA | Executed
BURFORD GIFFEN | 679 | 2011-03-31 | 2011-03-31 07:00 | COMPLETED | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE | None | Giffen substation 70 KV | 2013-09-05 07:00 | 2017-06-16 07:00 | NA | Complete | Complete | NA | Executed
COLUMBIA SOLAR ENERGY 2 FKA COLUMBIA SOLAR ENERGY II | 687 | 2011-03-31 | 2011-03-31 07:00 | COMPLETED | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Partial Capacity | 10 | Off-Peak Deliverability | Group D | CONTRA COSTA | CA | PGAE | Northern | Pittsburg-Kirker-Columbia Steel 115 kV Line | 2012-12-31 08:00 | 2015-10-21 07:00 | NA | Complete | Complete | NA | Executed
FRONTIER SOLAR | 705 | 2011-03-28 | 2011-03-31 07:00 | COMPLETED | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | PGAE | None | Arco-Carneras 70 kV line | 2013-09-05 07:00 | 2019-02-05 08:00 | NA | Complete | Complete | NA | Executed
GOLDEN HILLS 2 WIND | 709 | 2011-03-31 | 2011-03-31 07:00 | COMPLETED | C04 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 36 | 36 | Full Capacity |  | Off-Peak Deliverability |  | ALAMEDA | CA | PGAE |  | Tesla Sub 115 KV | 2013-12-31 08:00 | 2015-12-18 08:00 | NA | Complete | Complete | NA | Executed
LOTUS SOLAR FARM | 723 | 2011-03-31 | 2011-03-31 07:00 | COMPLETED | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 | Full Capacity |  | Off-Peak Deliverability |  | MADERA | CA | PGAE |  | Borden 70kV | 2014-07-01 07:00 | 2020-05-30 07:00 | NA | Complete | Complete | NA | Executed
RE ASTORIA | 746 | 2011-03-31 | 2011-03-31 07:00 | COMPLETED | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 175 | 175 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 220kV | 2014-12-31 08:00 | 2016-10-31 07:00 | NA | Complete | Complete | NA | Executed
MORELOS DEL SOL (FKA TWISSLEMAN I) | 775 | 2011-03-31 | 2011-03-31 07:00 | COMPLETED | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 15 | 15 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | PGAE |  | Arco-Twisselman 70 KV | 2014-07-10 07:00 | 2015-11-25 08:00 | NA | Complete | Complete | NA | Executed
NORTH LANCASTER SOLAR (FKA WESTERN ANTELOPE DRY RANCH ADDITION) | 778 | 2011-03-31 | 2011-03-31 07:00 | COMPLETED | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | Off-Peak Deliverability |  | LOS ANGELES | CA | SCE | Northern | Antelope Substation 66 kV bus | 2013-12-31 08:00 | 2016-12-31 08:00 | NA | Complete | Complete | NA | Executed
KINGBIRD SOLAR A (FKA AV SOLAR RANCH 2-A) | 795 | 2011-03-31 | 2011-03-31 07:00 | COMPLETED | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230 kV bus | 2013-08-30 07:00 | 2016-04-30 07:00 | NA | Complete | Complete | NA | Executed
KINGBIRD SOLAR B (FKA AV SOLAR RANCH 2-B | 796 | 2011-03-31 | 2011-03-31 07:00 | COMPLETED | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230 kV bus | 2013-08-30 07:00 | 2016-04-30 07:00 | NA | Complete | Complete | NA | Executed
PV2 PANOCHE VALLEY SOLAR (AKA SGE PANOCHE VALLEY SOLAR) | 829 | 2011-03-31 | 2011-03-31 07:00 | COMPLETED | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 140 | 140 | Full Capacity |  | Off-Peak Deliverability |  | SAN BENITO | CA | PGAE |  | Moss-Panoche and Coburn-Panoche 230 KV | 2015-12-30 08:00 | 2018-11-26 08:00 | NA | Complete | Complete | NA | Executed
BLUE HORNET SOLAR | 838 | 2011-03-31 | 2011-03-31 07:00 | COMPLETED | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | Off-Peak Deliverability |  | IMPERIAL | CA | SDGE |  | Imperial Valley Substation 230 kV | 2015-12-31 08:00 | 2022-11-04 07:00 | NA | Complete | Complete | NA | Executed
COPPER MOUNTAIN SOLAR 4 | 855 | 2011-03-31 | 2011-03-31 07:00 | COMPLETED | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 92 | 92 | Full Capacity |  | Off-Peak Deliverability |  | CLARK | NV | SDGE |  | Merchant Switchyard 230 kV | 2013-02-28 08:00 | 2016-12-02 08:00 | NA | Complete | Complete | NA | Executed
VASCO WIND PROJECT | 860 | 2011-03-31 | 2011-03-31 07:00 | COMPLETED | ISP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 3.1 | 3.1 | Partial Capacity | 40.12 | Off-Peak Deliverability | Group B | CONTRA COSTA | CA | PGAE | None | Lone Tree-Cayetano at the Jackson Substation | 2011-12-01 08:00 | 2011-11-30 08:00 | NA | Complete | Complete | NA
CALIFORNIA FLATS SOLAR | 877 | 2012-03-23 | 2012-04-02 07:00 | COMPLETED | C05 | Photovoltaic | Storage |  | Solar | Battery |  | 280 | 60 |  | 280 | Full Capacity |  | Off-Peak Deliverability |  | MONTEREY | CA | PGAE | None | Morro-Gates 230kV line | 2015-10-30 07:00 | 2019-03-05 08:00 | NA | Complete | Complete | NA | Executed
SKIC SOLAR | 885 | 2012-04-02 | 2012-04-02 07:00 | COMPLETED | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 10 | 10 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | PGAE | None | Copus-Old River 70 kV line | 2015-01-01 08:00 | 2017-01-05 08:00 | NA | Complete | Complete | NA | Executed
WILDWOOD SOLAR 2 | 901 | 2012-04-02 | 2012-04-02 07:00 | COMPLETED | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 15 | 15 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | PGAE | None | Semitropic-Midway 115 kV line | 2015-12-20 08:00 | 2017-01-11 08:00 | NA | Complete | Complete | NA | Executed
MOJAVE SOLAR | 909 | 2012-04-02 | 2012-04-02 07:00 | COMPLETED | C05 | Generating Facility Type-1: Solar Thermal; Generating Facility Fuel-1: Solar; MWs MW-1: 25 | 25 | Energy Only |  | Off-Peak Deliverability |  | SAN BERNARDINO | CA | SCE | NOL | Sandlot Substation 220kV | 2014-02-11 08:00 | 2015-10-22 07:00 | NA | Complete | Complete | NA | In Progress
PASTORIA ENERGY FACILITY | 911 | 2012-04-02 | 2012-04-02 07:00 | COMPLETED | C05 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 50 | 50 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Pastoria Substation 220kV | 2014-01-01 08:00 | 2016-04-01 07:00 | NA | Complete | Complete | NA | Executed
LECU | 945 | 2013-04-18 | 2013-04-30 07:00 | COMPLETED | C06 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 24 | 24 | Full Capacity |  | Off-Peak Deliverability |  | SAN JOAQUIN | CA | PGAE | None | Lodi STIG 230 kV Substation | 2014-01-08 08:00 | 2017-04-24 07:00 | NA | Complete | Complete | NA | Executed
NORTHERN ORCHARD SOLAR | 946 | 2013-04-23 | 2013-04-30 07:00 | COMPLETED | C06 | Photovoltaic | Storage |  | Solar | Battery |  | 100 | 92 |  | 100 | Partial Capacity | 60 | Off-Peak Deliverability |  | KERN | CA | PGAE | Kern | Midway-Wheeler Ridge #2 230 kV Line | 2015-12-01 08:00 | 2025-04-22 07:00 | NA | Complete | Complete | NA | Executed
MESQUITE SOLAR 2 | 952 | 2013-04-29 | 2013-04-30 07:00 | COMPLETED | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100.81 | 100.81 | Partial Capacity | 98 | Off-Peak Deliverability |  | MARICOPA | AZ | SDGE |  | Hassayampa Common Bus 500 kV | 2016-11-30 08:00 | 2017-10-12 07:00 | NA | Complete | Complete | NA | Executed
FIFTH STANDARD SOLAR | 954 | 2013-04-29 | 2013-04-30 07:00 | COMPLETED | C06 | Photovoltaic | Storage |  | Solar | Battery |  | 150 | 117 |  | 150 | Partial Capacity | 25 | Off-Peak Deliverability |  | FRESNO | CA | PGAE | Fresno | Gates Substation 230 kV | 2016-07-01 07:00 | 2023-09-30 07:00 | NA | Complete | Complete | NA | Executed
LOS MEDANOS ENERGY CENTER | 963 | 2013-04-30 | 2013-04-30 07:00 | COMPLETED | C06 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 72 | 72 | Full Capacity |  | Off-Peak Deliverability |  | CONTRA COSTA | CA | PGAE | None | Pittsburg Substation 115 kV bus | 2014-01-03 08:00 | 2019-03-04 08:00 | NA | Complete | Complete | NA | Executed
JAVA SOLAR | 965 | 2013-04-30 | 2013-04-30 07:00 | COMPLETED | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 13.5 | 13.5 | Full Capacity |  | Off-Peak Deliverability |  | KINGS | CA | PGAE | None | Henrietta-GWF 115 kV Line | 2016-10-01 07:00 | 2022-11-18 08:00 | NA | Complete | Complete | NA | Executed
PALOMAR ENERGY CENTER 2 | 968 | 2013-04-30 | 2013-04-30 07:00 | COMPLETED | C06 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 35 | 35 | Full Capacity |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Palomar Energy Switchyard 230 kV | 2015-03-01 08:00 | 2021-07-30 07:00 | NA | Complete | Complete | NA | Executed
GARLAND | 971 | 2013-04-30 | 2013-04-30 07:00 | COMPLETED | C06 | Photovoltaic | Storage |  | Solar | Battery |  | 200 | 88 |  | 200 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 220kV | 2016-05-30 07:00 | 2021-08-19 07:00 | NA | Complete | Complete | NA | Executed
SUNSHINE VALLEY SOLAR 2 | 994 | 2013-05-01 | 2013-04-30 07:00 | COMPLETED | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 | Full Capacity |  | Off-Peak Deliverability |  | NYE | NV | VEA |  | Valley Substation 138kV | 2016-12-31 08:00 | 2019-12-18 08:00 | NA | Complete | Complete | NA | Executed
PEARBLOSSOM SOLAR | 1003A | 2014-08-07 | 2013-04-30 07:00 | COMPLETED | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 9.5 | 9.5 | Full Capacity |  | Off-Peak Deliverability |  | LOS ANGELES | CA | SCE | Northern | Vincent Substation 230kV | 2016-10-01 07:00 | 2016-12-29 08:00 | NA | None | Complete | NA | Executed
MERCED POWER | 1005 | 2014-01-21 | 2014-03-11 07:00 | COMPLETED | FT | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Biofuel; MWs MW-1: 0.5 | 0.5 | Energy Only |  | Off-Peak Deliverability |  | MERCED | CA | PGAE |  | Merced #1 70kV Line | 2014-04-29 07:00 | 2014-07-30 07:00 | None | NA | NA | NA | Executed
DYER SUMMIT WIND REPOWER | 1010 | 2014-04-28 | 2014-04-30 07:00 | COMPLETED | C07 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 46.1 | 44.8 | Full Capacity |  | Off-Peak Deliverability |  | SAN JOAQUIN | CA | PGAE | None | Vasco-Herdlyn 60kV line | 2015-12-01 08:00 | 2022-04-05 07:00 | NA | Complete | Complete | NA | Executed
RICHMOND STEAM TURBINE | 1016 | 2014-04-25 | 2014-04-30 07:00 | COMPLETED | C07 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 0.01 | 0 | Energy Only |  | Off-Peak Deliverability |  | CONTRA COSTA | CA | PGAE |  | Standard Oil Switching Station 115kV | 2018-04-30 07:00 | 2019-04-11 07:00 | NA | Complete | Complete | NA | Executed
BLACKBRIAR | 1027 | 2014-05-01 | 2014-04-30 07:00 | COMPLETED | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20 | Full Capacity |  |  |  | FRESNO | CA | PGAE | Fresno | Gates Substation 230kV | 2016-06-01 07:00 | 2023-09-15 07:00 | NA | Complete | Complete | NA | Executed
TRANQUILLITY 8 | 1032 | 2014-04-30 | 2014-04-30 07:00 | COMPLETED | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 206.2 | 200 | Full Capacity |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE | None | Tranquillity Switchyard 230kV | 2016-09-30 07:00 | 2018-04-17 07:00 | NA | Complete | Complete | NA | Executed
MUSTANG 2 | 1036 | 2014-04-30 | 2014-04-30 07:00 | COMPLETED | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 153.4 | 150 | Full Capacity |  | Off-Peak Deliverability |  | KINGS | CA | PGAE | None | Mustang Switchyard 230 kV | 2016-09-30 07:00 | 2020-11-18 08:00 | NA | Complete | Complete | NA | Executed
ARLINGTON VALLEY SOLAR ENERGY 2 | 1040 | 2014-04-29 | 2014-04-30 07:00 | COMPLETED | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 127 | 127 | Full Capacity |  | Off-Peak Deliverability |  | MARICOPA | AZ | SDGE |  | Hassayampa Common Bus 500 kV | 2014-01-03 08:00 | 2014-01-03 08:00 | NA | Complete | Complete | NA | Executed
MESQUITE SOLAR 3 | 1053 | 2014-04-30 | 2014-04-30 07:00 | COMPLETED | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 152 | 152 | Full Capacity |  | Off-Peak Deliverability |  | MARICOPA | AZ | SDGE |  | Hassayampa Common Bus 500 kV | 2019-11-30 08:00 | 2019-10-17 07:00 | NA | Complete | Complete | NA | Executed
PIO PICO CAPACITY INCREASE (FKA PIO PICO ENERGY CENTER 2) | 1058 | 2014-04-30 | 2014-04-30 07:00 | COMPLETED | C07 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 10 | 10 | Full Capacity |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Otay Mesa Switchyard 230 kV | 2016-05-01 07:00 | 2016-12-14 08:00 | NA | Complete | Complete | NA | Executed
VISTA ENERGY STORAGE | 1061 | 2014-04-29 | 2014-04-30 07:00 | COMPLETED | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Melrose Substation 69 kV | 2016-06-01 07:00 | 2018-06-26 07:00 | NA | Complete | Complete | NA | Executed
BEAR CANYON ENERGY STORAGE | 1097 | 2015-04-29 | 2015-04-30 07:00 | COMPLETED | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 13.25 | 13 | Full Capacity |  |  |  | LAKE | CA | PGAE | Northern | Geysers #12-Fulton 230 kV Line | 2018-01-01 08:00 | 2024-07-24 07:00 | NA | Complete | Complete | NA | Executed
CENTRAL 40 | 1103 | 2015-04-30 | 2015-04-30 07:00 | COMPLETED | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 40 | 40 | Full Capacity |  | Off-Peak Deliverability |  | STANISLAUS | CA | PGAE | None | Miller #1 115 kV line | 2017-08-01 07:00 | 2021-02-23 08:00 | NA | Complete | Complete | NA | Executed
NORTH CENTRAL VALLEY | 1109 | 2015-04-30 | 2015-04-30 07:00 | COMPLETED | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 132 | 132 | Full Capacity |  |  |  | SAN JOAQUIN | CA | PGAE | Northern | Belotta 115 kV | 2021-06-01 07:00 | 2023-08-30 07:00 | NA | Complete | Complete | NA | Executed
BLACK DIAMOND ENERGY STORAGE | 1111 | 2015-04-30 | 2015-04-30 07:00 | COMPLETED | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 200 | 200 | Full Capacity |  |  |  | CONTRA COSTA | CA | PGAE | None | Pittsburgh Substation 230kV | 2018-06-01 07:00 | 2022-03-17 07:00 | NA | Complete | Complete | NA | Executed
ULTRAPOWER CHINESE STATION BESS | 1116 | 2015-04-30 | 2015-04-30 07:00 | COMPLETED | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 10 | 10 | Full Capacity |  |  |  | TUOLUMNE | CA | PGAE | Northern | Melones-Curtis 115 kV Line | 2017-03-31 07:00 |  | NA | Complete | Complete | NA | Executed
AQUAMARINE WESTSIDE | 1117 | 2015-04-30 | 2015-04-30 07:00 | COMPLETED | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 | Full Capacity |  | Off-Peak Deliverability |  | KINGS | CA | PGAE |  | Gates Substation 230 kV | 2019-06-18 07:00 | 2021-12-08 08:00 | NA | Complete | Complete | NA | Executed
CHESTNUT WESTSIDE | 1120 | 2015-04-30 | 2015-04-30 07:00 | COMPLETED | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 152 | 135 |  | 150 | Full Capacity |  | Off-Peak Deliverability | Group A | KINGS | CA | PGAE | Fresno | Gates 230 kV | 2021-04-19 07:00 | 2023-12-14 08:00 | NA | Complete | Complete | NA | Executed
WESTLANDS ALMOND | 1136 | 2015-04-30 | 2015-04-30 07:00 | COMPLETED | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 19.88 | 19.88 | Energy Only |  | Off-Peak Deliverability |  | KINGS | CA | PGAE | Fresno | Kent 70 kV | 2016-11-14 08:00 | 2023-09-26 07:00 | NA | Complete | Complete | NA | Executed
WESTLANDS SOLAR BLUE | 1139 | 2015-04-30 | 2015-04-30 07:00 | COMPLETED | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 252.04 | 225 |  | 250 | Full Capacity |  | Off-Peak Deliverability | Group A | KINGS | CA | PGAE | Fresno | Gates 230 kV | 2020-04-20 07:00 | 2023-12-13 08:00 | NA | Complete | Complete | NA | Executed
SLATE | 1158 | 2015-04-29 | 2015-04-30 07:00 | COMPLETED | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 308.5 | 308.7 |  | 300 | Full Capacity |  | Off-Peak Deliverability |  | KINGS | CA | PGAE | Fresno | Mustang Switching Station 230kV | 2018-12-31 08:00 | 2022-03-15 07:00 | NA | Complete | Complete | NA | Executed
BIG ROCK SOLAR FARM | 1166 | 2015-04-30 | 2015-04-30 07:00 | COMPLETED | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 200 | 200 | Partial Capacity | 50 | Off-Peak Deliverability | Group D | IMPERIAL | CA | SDGE | SDGE | Imperial Valley Substation 230 kV | 2020-06-01 07:00 | 2025-05-28 07:00 | NA | Complete | Complete | NA | Executed
GATEWAY ENERGY STORAGE | 1170 | 2015-04-30 | 2015-04-30 07:00 | COMPLETED | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 250 | 250 | Full Capacity |  |  |  | SAN DIEGO | CA | SDGE |  | Otay Mesa Switchyard 230 kV | 2018-09-01 07:00 | 2025-04-22 07:00 | NA | Complete | Complete | NA | Executed
MCFARLAND SOLAR | 1171 | 2015-04-30 | 2015-04-30 07:00 | COMPLETED | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 500 | 435 |  | 500 | Partial Capacity | 87 | Off-Peak Deliverability |  | YUMA | AZ | SDGE |  | Hoodoo Wash Switchyard 500 kV | 2018-12-31 08:00 | 2025-04-09 07:00 | NA | Complete | Complete | NA | Executed
SUN STREAMS SOLAR 2 | 1189 | 2015-04-28 | 2015-04-30 07:00 | COMPLETED | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | Off-Peak Deliverability |  | MARICOPA | AZ | SDGE |  | Hassayampa Common Bus 500 kV | 2020-01-31 08:00 | 2021-06-25 07:00 | NA | Complete | Complete | NA | Executed
VALLEY CENTER ENERGY STORAGE | 1191 | 2015-04-30 | 2015-04-30 07:00 | COMPLETED | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 119 | 119 | Partial Capacity | 87 | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Valley Center Substation 69 kV | 2018-10-01 07:00 | 2021-12-16 08:00 | NA | Complete | Complete | NA | Executed
CRIMSON | 1192 | 2015-04-29 | 2015-04-30 07:00 | COMPLETED | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 350 | 350 | Full Capacity |  | Off-Peak Deliverability |  | RIVERSIDE | CA | SCE | Eastern | Colorado River Substation 230kV | 2020-12-31 08:00 | 2022-10-28 07:00 | NA | Complete | Complete | NA | Executed
ARLINGTON | 1196 | 2015-04-30 | 2015-04-30 07:00 | COMPLETED | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 409.9 | 242 |  | 400 | Partial Capacity | 96.5 | Off-Peak Deliverability |  | RIVERSIDE | CA | SCE | Eastern | Colorado River Substation 230kV | 2021-07-01 07:00 | 2023-10-20 07:00 | NA | Complete | Complete | NA | Executed
QUARTZITE SOLAR 8 | 1198 | 2015-04-28 | 2015-04-30 07:00 | COMPLETED | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 150 | 75 |  | 150 | Full Capacity |  | Off-Peak Deliverability |  | RIVERSIDE | CA | SCE | Eastern | Colorado River Substation 220kV | 2020-12-01 08:00 | 2024-12-17 08:00 | NA | Complete | Complete | NA | Executed
VICTORY PASS SOLAR | 1200 | 2015-04-30 | 2015-04-30 07:00 | COMPLETED | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 200 | 50 |  | 200 | Partial Capacity |  | Off-Peak Deliverability |  | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 230kV | 2018-12-31 08:00 | 2024-03-26 07:00 | NA | Complete | Complete | NA | Executed
ROSAMOND SOUTH EAST | 1211 | 2015-04-30 | 2015-04-30 07:00 | COMPLETED | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 100 | 92 |  | 101.7 | Partial Capacity | 90.46 | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2018-06-30 07:00 | 2025-08-12 07:00 | NA | Complete | Complete | NA | Executed
ANTELOPE VALLEY COMPLEX | 1215 | 2015-04-28 | 2015-04-30 07:00 | COMPLETED | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 100 | 70 |  | 150 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2019-12-31 08:00 | 2025-05-08 07:00 | NA | Complete | Complete | NA | Executed
PROXIMA SOLAR | 1244 | 2016-04-30 | 2016-05-02 07:00 | COMPLETED | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 190 | 162 |  | 300 | Partial Capacity | 56.67 | Off-Peak Deliverability |  | STANISLAUS | CA | PGAE | Fresno | Fink 230 kV | 2020-03-10 07:00 | 2024-06-11 07:00 | NA | Complete | Complete | NA | Executed
NORTHERN ORCHARD SOLAR 2 | 1259 | 2016-04-27 | 2016-05-02 07:00 | COMPLETED | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 | Energy Only |  | Off-Peak Deliverability | Group B | KERN | CA | PGAE | Kern | Midway-Wheeler Ridge #2 230 kV Line | 2020-12-16 08:00 | 2025-04-22 07:00 | NA | Complete | Complete | NA | Executed
CASCADE ENERGY STORAGE | 1272 | 2016-05-02 | 2016-05-02 07:00 | COMPLETED | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 25.2 | 25 | Full Capacity |  |  |  | SAN JOAQUIN | CA | PGAE | Northern | Weber 60 kV | 2018-05-31 07:00 | 2023-12-14 08:00 | NA | Complete | Complete | NA | Executed
KOLA | 1275 | 2016-04-26 | 2016-05-02 07:00 | COMPLETED | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 400 | 400 | Full Capacity |  |  |  | ALAMEDA | CA | PGAE | Northern | Tesla 230 kV | 2020-12-01 08:00 |  | NA | Complete | Complete | NA | Executed
SPI SONORA | 1283 | 2016-04-28 | 2016-05-02 07:00 | COMPLETED | C09 | Generating Facility Type-1: Cogeneration; Generating Facility Fuel-1: Biofuel; MWs MW-1: 10.9 | 7.5 | Full Capacity |  | Off-Peak Deliverability |  | TUOLUMNE | CA | PGAE | Northern | Donnels-Curtis at PG&E switch 183 115vK | 2017-06-05 07:00 | 2018-04-12 07:00 | NA | Complete | Complete | NA
MESQUITE SOLAR 4 | 1291 | 2016-04-28 | 2016-05-02 07:00 | COMPLETED | C09 | Storage | Photovoltaic |  | Battery | Solar |  | 10 | 52.5 |  | 52.5 | Full Capacity |  | Off-Peak Deliverability |  | MARICOPA | AZ | SDGE | SDGE | Hassayampa Common Bus 500 kV | 2023-04-28 07:00 | 2024-01-26 08:00 | NA | Complete | Complete | NA | Executed
VISTA ENERGY STORAGE 2 | 1294 | 2016-04-30 | 2016-05-02 07:00 | COMPLETED | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20 | Full Capacity |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Melrose Substation 69 kV | 2019-08-01 07:00 | 2018-06-26 07:00 | NA | Complete | Complete | NA | Executed
MARVEL | 1295 | 2016-04-26 | 2016-05-02 07:00 | COMPLETED | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 405.85 | 400 | Full Capacity |  |  |  | RIVERSIDE | CA | SCE | Eastern | Devers Substation 230kV | 2022-04-01 07:00 | 2024-04-24 07:00 | NA | Complete | Complete | NA | Executed
SOL CATCHER BESS | 1302 | 2016-05-03 | 2016-05-02 07:00 | COMPLETED | C09 | Storage | Photovoltaic |  | Battery | Solar |  | 121 | 213.5 |  | 213.5 | Partial Capacity |  | Off-Peak Energy Only |  | RIVERSIDE | CA | SCE | Eastern | Red Bluff 220 kV | 2019-05-31 07:00 | 2024-04-02 07:00 | NA | Complete | Complete | NA | Executed
DAGGETT SOLAR 1 | 1312 | 2016-04-28 | 2016-05-02 07:00 | COMPLETED | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 113.5 | 113.5 | Full Capacity |  | Off-Peak Deliverability |  | SAN BERNARDINO | CA | SCE | NOL | Coolwater Substation 115kV | 2020-06-30 07:00 | 2025-09-09 07:00 | NA | Complete | Complete | NA | Executed
DAGGETT SOLAR 2 | 1313 | 2016-04-28 | 2016-05-02 07:00 | COMPLETED | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 169 | 131 |  | 182 | Full Capacity |  | Off-Peak Deliverability |  | SAN BERNARDINO | CA | SCE | NOL | Kramer Substation 230kV | 2020-06-30 07:00 | 2023-11-22 08:00 | NA | Complete | Complete | NA | Executed
WILLY 9 | 1319 | 2016-04-25 | 2016-05-02 07:00 | COMPLETED | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 174 | 164 |  | 250 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2020-12-31 08:00 | 2025-05-08 07:00 | NA | Complete | Complete | NA | Executed
EDSAN 1 | 1324 | 2016-04-27 | 2016-05-02 07:00 | COMPLETED | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 118 | 266 |  | 300 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Windhub Substation 230kV | 2019-12-31 08:00 | 2023-11-23 08:00 | NA | Complete | Complete | NA | Executed
SAGEBRUSH SOLAR 2 | 1325 | 2016-04-27 | 2016-05-02 07:00 | COMPLETED | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 179 | 179 | Full Capacity |  | Off-Peak Deliverability | Group A | KERN | CA | SCE | Northern | Vincent Substation 230kV | 2019-12-31 08:00 | 2024-09-16 07:00 | NA | Complete | Complete | NA | Executed
CYCLONE SOLAR | 1327 | 2016-04-29 | 2016-05-02 07:00 | COMPLETED | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 40 | 25 |  | 40 | Full Capacity |  | Off-Peak Deliverability | Group 3 | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2019-07-01 07:00 | 2025-08-01 07:00 | NA | Complete | Complete | NA | Executed
TROPICO SOLAR | 1329 | 2016-04-29 | 2016-05-02 07:00 | COMPLETED | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 112.266 | 40 |  | 110 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230 kV | 2021-12-01 08:00 | 2022-12-27 08:00 | NA | Complete | Complete | NA | Executed
YELLOW PINE 2 | 1341 | 2016-04-26 | 2016-05-02 07:00 | COMPLETED | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 250 | 150 |  | 250 | Full Capacity |  | Off-Peak Deliverability |  | CLARK | NV | GLW | None | Crazy Eyes Substation 230 kV | 2019-12-01 08:00 |  | NA | Complete | Complete | NA | Executed
PIO PICO PLUS | 1348 | 2017-02-03 | 2017-02-06 08:00 | COMPLETED | ISP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 18 | 18 | Full Capacity |  | Off-Peak Deliverability |  | USA | CA | SDGE |  | Otay Mesa Switchyard 230 kV | 2017-11-05 07:00 | 2017-10-17 07:00 | NA |  |  | NA | Executed
PAULSELL SOLAR ENERGY CENTER | 1350 | 2017-05-01 | 2017-05-01 07:00 | COMPLETED | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 20 | 15 |  | 20 | Partial Capacity | 70 | Off-Peak Deliverability |  | STANISLAUS | CA | PGAE | Northern | Crow Creek 60 kV | 2019-12-31 08:00 | 2024-06-20 07:00 | NA | Complete | Complete | NA | Executed
WEST FORD FLAT ENERGY STORAGE | 1367 | 2017-04-28 | 2017-05-01 07:00 | COMPLETED | C10 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 26.25 | 25 | Full Capacity |  |  |  | LAKE | CA | PGAE | Northern | Fulton 230 kV | 2020-01-01 08:00 | 2024-07-25 07:00 | NA | Complete | Complete | NA | Executed
ELKHORN ENERGY STORAGE | 1374 | 2017-05-01 | 2017-05-01 07:00 | COMPLETED | C10 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 189 | 182.5 | Full Capacity |  | Off-Peak Deliverability |  | MONTEREY | CA | PGAE | Fresno | Moss Landing Substation 115kV | 2020-10-31 07:00 | 2022-04-07 07:00 | NA | Complete | Complete | NA | Filed Unexecuted
SANDRINI SOL 1 | 1397 | 2017-04-29 | 2017-05-01 07:00 | COMPLETED | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 100 | 92 |  | 100 | Partial Capacity | 92 | Off-Peak Deliverability | Group 2 | KERN | CA | PGAE | Kern | Wheeler Ridge 70 kV | 2021-11-30 08:00 |  | NA | Complete | Complete | NA | Executed
SANDRINI SOL 2 | 1398 | 2017-04-29 | 2017-05-01 07:00 | COMPLETED | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 | Full Capacity |  | Off-Peak Deliverability | Group 1 | KERN | CA | PGAE | Kern | Wheeler Ridge 230 kV | 2021-11-30 08:00 | 2024-11-05 08:00 | NA | Complete | Complete | NA | Executed
MOUNTAINVIEW GENERATING STATION PMAX INCREASE | 1407 | 2017-04-06 | 2017-05-01 07:00 | COMPLETED | C10 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 38 | 38 | Full Capacity |  | Off-Peak Deliverability |  | SAN BERNARDINO | CA | SCE | Eastern | San Bernardino Substation 230kV | 2019-03-01 08:00 | 2019-10-17 07:00 | NA | Complete | Complete | NA | Executed
HIGH 5 SOLAR | 1414 | 2017-04-28 | 2017-05-01 07:00 | COMPLETED | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 100 | 50 |  | 100 | Full Capacity |  | Off-Peak Deliverability |  | SAN BERNARDINO | CA | SCE | NOL | Victor Substation 230kV | 2019-12-29 08:00 | 2021-12-08 08:00 | NA | Complete | Complete | NA | Executed
EDSAN 2 | 1424 | 2017-04-28 | 2017-05-01 07:00 | COMPLETED | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 357 | 196 |  | 500 | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Windhub Substation 230kV | 2020-12-31 08:00 | 2023-11-10 08:00 | NA | Complete | Complete | NA | Executed
TOP GUN ENERGY STORAGE | 1434 | 2017-04-28 | 2017-05-01 07:00 | COMPLETED | C10 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 30 | 30 | Full Capacity |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Miramar GT Substation 69 kV | 2019-12-31 08:00 | 2021-06-30 07:00 | NA | Complete | Complete | NA | Executed
WIND WALL MONOLITH 1 | 1439 | 2018-04-30 | 2018-04-17 07:00 | COMPLETED | FT | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 4.96 | 4.96 | Full Capacity |  | Off-Peak Deliverability | Group A |  |  | SCE | Northern | Vincent Substation 220kV | 2019-12-15 08:00 | 2021-03-30 07:00 | Offered | NA | NA | NA | Executed
WIND WALL MONOLITH 2 | 1440 | 2018-04-30 | 2018-04-17 07:00 | COMPLETED | FT | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 3.7 | 3.7 | Full Capacity |  | Off-Peak Deliverability | Group A | KERN | CA | SCE | Northern | Vincent Substation 220kV | 2019-12-15 08:00 | 2021-03-30 07:00 | Offered | NA | NA | NA | Executed
CABALLERO STORAGE | 1470 | 2018-04-13 | 2018-04-16 07:00 | COMPLETED | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 106.2 | 99.7 | Full Capacity |  |  | Group 2a | SAN LUIS OBISPO | CA | PGAE | Kern | Mesa 230 kV | 2021-12-01 08:00 | 2025-02-05 08:00 | NA | Complete | Complete | NA | Executed
DALLAS ENERGY STORAGE | 1472 | 2018-04-11 | 2018-04-18 07:00 | COMPLETED | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 500 | 400 | Full Capacity |  | Off-Peak Deliverability |  | MONTEREY | CA | PGAE | Fresno | Moss Landing Substation 500kV | 2020-12-01 08:00 | 2021-07-28 07:00 | NA | Complete | Complete | NA | Executed
PANOCHE ENERGY CENTER C11 | 1484 | 2018-04-10 | 2018-04-16 07:00 | COMPLETED | C11 | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 427 | 427 | Full Capacity |  |  |  | FRESNO | CA | PGAE | Fresno | Panoche 230 kV | 2020-07-01 07:00 | 2024-09-04 07:00 | NA | Complete | Complete | NA
REXFORD SOLAR FARM | 1516 | 2018-04-16 | 2018-04-16 07:00 | COMPLETED | C11 | Photovoltaic | Storage |  | Solar | Battery |  | 300 | 240 |  | 300 | Full Capacity |  | Off-Peak Deliverability | Group 3 | TULARE | CA | SCE | Northern | Vestal Substation 230kV | 2022-10-01 07:00 | 2025-11-15 08:00 | NA | Complete | Complete | NA | Executed
QUARTZITE SOLAR 11 | 1526 | 2018-04-11 | 2018-04-16 07:00 | COMPLETED | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 75 | 150 |  | 150 | Full Capacity |  | Off-Peak Deliverability | Group 2 | RIVERSIDE | CA | SCE | Eastern | Colorado River Substation 230kV | 2022-12-30 08:00 | 2024-12-17 08:00 | NA | Complete | Complete | NA | Executed
BATERIA DEL SUR | 1531 | 2018-04-16 | 2018-04-16 07:00 | COMPLETED | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 350 | 350 | Full Capacity |  |  | Group A | IMPERIAL | CA |  |  | Imperial Valley Substation 230 kV | 2022-05-01 07:00 | 2025-07-01 07:00 | NA | Complete | Complete | NA | Executed
PLANO STORAGE | 1540 | 2019-03-05 | 2019-05-07 07:00 | COMPLETED | ISP | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 365 | 350 | Full Capacity |  |  |  | MONTEREY | CA | PGAE | Northern | Moss Landing Substation 500kV | 2021-12-01 08:00 | 2023-06-02 07:00 | NA | Complete | Complete | NA | Executed
RAMPA | 1641 | 2019-04-05 | 2019-04-15 07:00 | COMPLETED | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 100.98 | 100 | Full Capacity |  |  | Group 3 | SAN BERNARDINO | CA | SCE | Eastern | Etiwanda Substation 230kV | 2022-12-31 08:00 | 2024-09-20 07:00 | NA | Complete | Complete | NA | Executed
VENTASSO ENERGY STORAGE | 1662 | 2019-04-06 | 2019-04-15 07:00 | COMPLETED | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 50.774 | 50 | Full Capacity |  |  | Group 3 | SAN DIEGO | CA | SDGE |  | El Cajon Substation 69 kV | 2022-11-30 08:00 | 2026-03-12 07:00 | NA | Complete | Complete | NA | Executed
POME BESS | 1669 | 2019-04-13 | 2019-04-15 07:00 | COMPLETED | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 100 | 100 | Full Capacity |  |  | Group 3 | SAN DIEGO | CA | SDGE | SDGE | Pomerado Substation 69 kV | 2023-05-31 07:00 | 2025-09-26 07:00 | NA | Complete | Complete | NA | Executed
PEREGRINE STORAGE | 1670 | 2019-04-01 | 2019-04-15 07:00 | COMPLETED | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 200 | 200 | Partial Capacity | 50 |  | Group 2 | SAN DIEGO | CA |  |  | Silvergate Substation 230 kV | 2023-06-30 07:00 | 2025-04-09 07:00 | NA | Complete | Complete | NA | Executed
RESAVA ENERGY STORAGE | 1675 | 2019-04-05 | 2019-04-15 07:00 | COMPLETED | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20 | Energy Only |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Valley Center Substation 69 kV | 2021-12-31 08:00 | 2021-12-16 08:00 | NA | Complete | Complete | NA
POINT WIND FAST TRACK | 1679 | 2020-03-30 | 2020-04-14 07:00 | COMPLETED | FT | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 1.62 | 1.5374 | Energy Only |  | Off-Peak Energy Only |  | KERN | CA | SCE | Northern | Vincent Sub | 2020-11-01 07:00 | 2021-03-30 07:00 |  | NA | NA | NA | Executed
RE GARLAND | 1680 | 2020-01-29 | 2020-05-13 07:00 | COMPLETED | FT | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 5 | 3 | Energy Only |  | Off-Peak Energy Only |  | KERN | CA | SCE | Northern | Whirlwind Substation | 2019-08-03 07:00 | 2021-08-19 07:00 |  | NA | NA | NA
LEAD | 1713 | 2020-04-15 | 2020-04-15 07:00 | COMPLETED | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 32.7 | 32 | Partial Capacity |  |  | Group B | KINGS | CA | PGAE | Fresno | GWF Hanford 115 kV | 2023-08-01 07:00 |  | NA | Complete | Complete | NA | Executed
HIGH DESERT POWER PLANT UPDATE | 1829 | 2020-11-11 | 2020-12-14 08:00 | COMPLETED | ISP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 100 | 100 | Partial Capacity | 51 |  | Group 1a | SAN BERNARDINO | CA | SCE | NOL | Victor Substation | 2021-07-01 07:00 | 2021-08-09 07:00 | NA |  |  | NA | Executed
CHULA VISTA ENERGY CENTER EXPANSION | 1834 | 2021-03-02 | 2021-03-02 08:00 | COMPLETED | FT | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 2.8 | 2.8 | Energy Only |  |  | Group C | SAN DIEGO | CA | SDGE |  | Otay Substation 69 kV | 2021-05-14 07:00 | 2022-05-14 07:00 |  | NA | NA | NA | Executed
CASCADE ENERGY STORAGE EXPANSION | 1835 | 2021-02-26 | 2021-05-03 07:00 | COMPLETED | ISP | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20.25 | 20 | Full Capacity |  |  | Group D | SAN JOAQUIN | CA | PGAE | Northern | Weber 60 kV | 2022-12-01 08:00 |  | NA | Complete | Complete | NA
The contents of these pages are subject to change without notice. Decisions based on information contained within the California ISO's web site are the visitor's sole responsibility.

## Withdrawn Generation Projects
Report Run Date: 03/30/2026
The California ISO Controlled Grid Generation Queue for All: Withdrawn
[7 empty] | Generating Facility | [5 empty] | MWs |  |  |  | Deliverability Status |  | Location |  | Point of Interconnection |  |  |  | Study Availability
Project Name - Confidential | Queue Position | Interconnection Request Receive Date | Queue Date | Application Status | Withdrawn Date | Study Process | Type-1 | Type-2 | Type-3 | Fuel-1 | Fuel-2 | Fuel-3 | MW-1 | MW-2 | MW-3 | Net MWs to Grid | Full Capacity, Partial or Energy Only (FC/P/EO) | Off-Peak Deliverability and Economic Only | County | State | Utility | Station or Transmission Line | Proposed On-line Date (as filed with IR) | Current On-line Date | Feasibility Study or Supplemental Review | System Impact Study or Phase I Cluster Study | Facilities Study (FAS) or Phase II Cluster Study | Optional Study (OS) | Interconnection Agreement Status | Reason for Withdrawal
ENCINA GENERATING PROJECT (PH. 1 AND 2) | 5 | 2000-08-09 | 2000-08-09 07:00 | WITHDRAWN |  | Pre- Amend. 39 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 900 | 900 |  |  | SAN DIEGO | CA | SDGE | Encina Power Plant Switchyard | 2003-06-30 07:00 | 2008-06-01 07:00 |  | Complete
TESLA POWER PLANT | 6 | 2007-08-24 | 2000-08-23 07:00 | WITHDRAWN | 2011-06-16 17:57 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 1156 | 1156 |  |  | SAN JOAQUIN | CA | PGAE | Tesla Sub 230kV Bus E | 2008-06-01 07:00 | 2014-11-30 08:00 | Waived | Complete | Complete | Complete
SAN DIEGO COMMUNITY POWER GENERATING STATION | 8 | 2000-11-28 | 2000-11-28 08:00 | WITHDRAWN |  | Pre- Amend. 39 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 750 | 750 |  |  | SAN DIEGO | CA | SDGE | Sycamore Canyon Substation | 2004-06-01 07:00 | 2010-12-31 08:00 |  | Complete | Re-Study |  | In Progress
MORRO BAY MODERNIZATION PROJECT | 9 | 2000-12-01 | 2000-12-01 08:00 | WITHDRAWN |  | Pre- Amend. 39 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 1200 | 1200 |  |  | SAN LUIS OBISPO | CA | PGAE | Morro Bay Substation | 2008-01-01 08:00 | 2008-01-01 08:00 |  | Complete | Complete |  | Executed
AVENAL ENERGY PROJECT | 10 | 2001-05-02 | 2001-05-02 07:00 | WITHDRAWN |  | Pre- Amend. 39 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 620 | 620 |  |  | KINGS | CA | PGAE | Gates Substation (Arco - Gates 230 kV line) | 2009-01-01 08:00 | 2009-07-01 07:00 |  | Complete | Complete |  | Executed
DESERT POWER WIND PROJECT | 11 | 2002-10-14 | 2002-10-23 07:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 63 | 63 |  |  | SAN BERNARDINO | CA | SCE | Wheaton Substation | 2004-12-01 08:00 | 2008-03-01 08:00 |  | Complete | Complete |  | Executed
ARGONAUT WIND PROJECT | 15 | 2002-12-31 | 2003-01-17 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 50 | 50 |  |  | SAN BERNARDINO | CA | SCE | Mountain Pass | 2004-09-01 07:00 | 2010-01-01 08:00 |  | Complete | Complete
PACIFIC RENEWABLE ENERGY GENERATION LLC (FKA LOMPOC WIND POWER PROJECT) | 16 | 2003-03-11 | 2003-03-11 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 55.5 | 55.5 |  |  | SANTA BARBARA | CA | PGAE | Divide-Cabrillo #2 115kV line tap | 2006-06-01 07:00 | 2015-12-31 08:00 |  | Complete | Complete |  | Executed
SONORAN 2 | 17 | 2003-03-18 | 2003-03-18 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 520 | 520 |  |  | RIVERSIDE | CA | SCE | Colorado River Substation 500kV bus | 2006-01-01 08:00 | 2021-01-02 08:00 |  | Complete | Complete |  | Executed
FAIRMONT WIND GENERATION PROJECT | 18 | 2003-04-15 | 2003-04-15 07:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 200 | 200 |  |  | LOS ANGELES | CA | SCE | Antelope | 2005-12-31 08:00 | 2007-12-12 08:00 |  | Complete | Complete |  | In Progress
CUYAPAIPE WIND POWER PROJECT | 25 | 2004-02-05 | 2004-02-05 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 117 | 117 |  |  | SAN DIEGO | CA | SDGE | Crestwood | 2005-06-06 07:00 | 2007-06-01 07:00
SAN DIEGO WIND #2 - PHASE I | 26 | 2004-02-12 | 2004-02-12 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 36 | 36 |  |  | SAN DIEGO | CA | SDGE | Crestwood | 2006-04-01 08:00 | 2008-01-01 08:00
SOUTH BAY REPLACEMENT - OPTION 1 | 27 | 2004-02-23 | 2004-02-23 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 650 | 650 |  |  | SAN DIEGO | CA | SDGE | 230/138/69 kV South Bay (650 MW CC) | 2010-01-01 08:00 | 2010-01-01 08:00 |  | Complete | Complete |  | In Progress
S. F. ELECTRIC RELIABILITY GENERATING PLANT | 28 | 2004-02-25 | 2004-02-25 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 145.1 | 145.1 |  |  | SAN FRANCISCO | CA | PGAE | Potrero 115 kV Sub | 2006-12-01 08:00 | 2008-06-01 07:00 |  | Complete | Complete |  | Executed
GEYSERS WIND PROJECT | 29 | 2004-03-08 | 2004-03-29 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 201 | 201 |  |  | LAKE/SONOMA | CA | PGAE | Collector Sub at Geysers #17 Fulton 230 kV line | 2006-12-01 08:00 | 2009-07-01 07:00 |  | Complete | Re-Study |  | In Progress
SAN FRANCISCO AIRPORT ELECTRIC RELIABILITY PLANT | 30 | 2004-04-26 | 2004-04-26 07:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 48.7 | 48.7 |  |  | SAN FRANCISCO | CA | PGAE | SF Airport Substation | 2006-06-01 07:00 | 2008-06-01 07:00 |  | Complete | Complete |  | Executed
BARREN RIDGE WIND PROJECT | 31 | 2004-04-12 | 2004-05-11 07:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 201 | 201 |  |  | KERN | CA | SCE | Monolith Substation | 2007-12-31 08:00 | 2010-06-01 07:00 |  | Complete
BARREN RIDGE II | 34 | 2004-07-19 | 2004-07-19 07:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 300 | 300 |  |  | KERN | CA | SCE | Monolith Substation | 2007-07-01 07:00 | 2011-07-01 07:00 |  | Complete
WELLHEAD POWER FIREBAUGH | 35 | 2004-10-25 | 2004-10-25 07:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49.9 | 49.9 |  |  | FRESNO | CA | PGAE | 115 KV Panoche Sub | 2006-05-31 07:00 | 2006-05-31 07:00 |  | Complete | Complete |  | In Progress
WELLHEAD POWER LATHROP | 36 | 2004-11-01 | 2004-11-01 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 99.9 | 99.9 |  |  | STANISLAUS | CA | PGAE | 115 kV Tesla - Stockton Cogen Trans. Line. | 2006-05-31 07:00 | 2006-05-31 07:00 |  | Complete | Complete |  | In Progress
RIPON GENERATION | 37 | 2004-11-08 | 2004-11-08 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 74.9 | 74.9 |  |  | SAN JOAQUIN | CA | PGAE | Tesla Substation | 2007-01-01 08:00 | 2011-12-31 08:00 |  | Complete | Complete |  | Executed
EASTSHORE ENERGY FACILITY PROJECT | 40 | 2004-10-19 | 2004-11-11 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 118 | 118 |  |  | ALAMEDA | CA | PGAE | Eastshore Substation | 2007-05-01 07:00 | 2009-10-01 07:00 |  | Complete | Complete |  | Executed
PASTORIA EXPANSION | 41 | 2004-11-09 | 2004-11-18 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 157 | 157 |  |  | KERN | CA | SCE | Pastoria Substation | 2006-07-31 07:00 | 2011-06-01 07:00 |  | Complete | Complete
WELLHEAD POWER MCCALL | 42 | 2004-11-24 | 2004-11-26 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 300 | 300 |  |  | FRESNO | CA | PGAE | McCall Substation | 2007-05-31 07:00 | 2013-03-31 07:00 |  | Complete | Complete |  | Executed
ALBION P3 | 43 | 2004-11-29 | 2004-11-29 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 168.7 | 168.7 |  |  | SAN JOAQUIN | CA | PGAE | Tesla-Bellota 230 kV line | 2008-01-01 08:00 | 2007-10-01 07:00 |  | Complete |  |  | In Progress
LOWLANDS P3 | 44 | 2004-11-29 | 2004-11-29 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 126.5 | 126.5 |  |  | MADERA | CA | PGAE | Borden Substation 230 kV Bus | 2008-01-01 08:00 | 2007-10-01 07:00 |  | Complete | Complete
EAST ALTAMONT ENERGY CENTER - OPTION 2 | 46 | 2004-12-01 | 2004-12-01 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 531 | 531 |  |  | CONTRA COSTA | CA | PGAE | Tesla-Tracy #1 230 kV Line - Tracy Sub | 2006-07-31 07:00 | 2008-07-31 07:00 |  | Complete | Complete
BULLARD ENERGY CENTER | 47 | 2004-12-01 | 2004-12-01 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 200.6 | 200.6 |  |  | FRESNO | CA | PGAE | Herndon - Kearney 230 kV line | 2008-06-30 07:00 | 2008-06-30 07:00 |  | Complete | Complete |  | In Progress
BRIDGEVIEW ENERGY FACILITY | 48 | 2004-12-01 | 2004-12-01 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 590 | 590 |  |  | CONTRA COSTA | CA | PGAE | Contra Costa Power Plant 230 kV Substation | 2008-01-01 08:00 | 2008-10-01 07:00 |  | Complete | Complete |  | In Progress
ROCKLIN PEAKER | 53 | 2004-12-01 | 2004-12-22 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 116.8 | 116.8 |  |  | PLACER | CA | PGAE | Pleasant Grove Sub Station | 2008-06-01 07:00 | 2008-06-01 07:00 |  | Complete | Complete |  | In Progress
COPPER MOUNTAIN PROJECT | 56 | 2004-12-21 | 2005-01-25 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 634 | 634 |  |  | CLARK | NV | SCE | El Dorado 230 kV Substation | 2007-06-01 07:00 | 2009-08-01 07:00 |  | Complete | Complete
GREEN BORDERS GEOTHERMAL | 58 | 2005-01-25 | 2005-02-22 08:00 | WITHDRAWN | 2013-10-11 07:00 | AMEND 39 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 62 | 62 |  |  | MINERAL | NV | SCE | Control 115kV Substation | 2007-10-07 07:00 | 2012-02-01 08:00 |  | Complete | Complete |  | Executed | IC Request
HENRIETTA II | 59 | 2005-03-25 | 2005-03-28 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 97.2 | 97.2 |  |  | KINGS | CA | PGAE | Henrietta Substantion 70 kV | 2008-01-01 08:00 | 2008-01-01 08:00 |  | Complete | Complete |  | In Progress
SOUTH KERN FRONT COGEN | 60 | 2005-03-28 | 2005-03-28 08:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 94 | 94 |  |  | KERN | CA | PGAE | Kern Oil Substation 115 kV | 2007-03-31 07:00 | 2015-10-31 07:00 |  | Complete | Complete |  | Executed
WELLHEAD POWER HUMBOLDT | 62 | 2005-03-28 | 2005-04-13 07:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 166.5 | 166.5 |  |  | HUMBOLDT | CA | PGAE | Humboldt Bay-Humboldt #1 115 kV | 2007-05-31 07:00 | 2007-06-01 07:00
WILBUR POWER CC | 63 | 2005-03-25 | 2005-04-18 07:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 158 | 158 |  |  | CONTRA COSTA | CA | PGAE | Contra Costa (230 kV) | 2008-01-01 08:00 | 2008-01-01 08:00 |  | Complete | Re-Study |  | In Progress
HUMBOLDT ENERGY FACILITY (AGILE ENERGY) | 64 | 2005-03-30 | 2005-04-28 07:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 147 | 147 |  |  | HUMBOLDT | CA | PGAE | Humboldt Bay Power Plant Sub | 2008-05-01 07:00 | 2008-03-01 08:00 |  | Complete
LONG BEACH PEAKER PROJECT | 65 | 2005-05-06 | 2005-05-06 07:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 424.8 | 424.8 |  |  | LOS ANGELES | CA | SCE | Long Beach Gen Station 220kv switchyard | 2007-01-01 08:00 | 2010-06-01 07:00 |  | Complete | Complete
K ROAD CALICO SOLAR LLC (KRCS) (FKA CALICO SOLAR 1; SES SOLAR ONE) | 68 | 2005-03-30 | 2005-05-11 07:00 | WITHDRAWN | 2013-06-04 22:43 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 850 | 850 |  |  | SAN BERNARDINO | CA | SCE | Pisgah Sub 230 kV Bus | 2009-12-31 08:00 | 2013-03-31 07:00 | Waived | Complete | Complete | Complete |  | None
FONTANA ENERGY CENTER | 69 | 2005-05-06 | 2005-06-07 07:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 527 | 527 |  |  | SAN BERNARDINO | CA | SCE | Etiwanda 230kV Substation | 2008-08-01 07:00 | 2008-08-01 07:00 |  | Complete
RELIANT ENERGY BIGHORN | 71 |  | 2005-06-15 07:00 | WITHDRAWN | 2006-01-11 08:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 591 | 591 |  |  | CLARK | NV | SCE | Eldorado 500/230kV Substation | 2007-02-28 08:00 | 2007-01-31 08:00 | None | None | None | None
BARREN RIDGE II ALTERNATIVE | 77 | 2010-12-14 | 2005-08-22 07:00 | WITHDRAWN | 2011-02-08 08:00 | TC | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 300 | 300 | Full Capacity |  | KERN | CA | SCE | TBD Bakersfield | 2007-11-30 08:00 | 2007-11-30 08:00 | NA | None | None | NA
SES SOLAR TWO) | 78 | 2005-08-31 | 2005-08-31 07:00 | WITHDRAWN | 2012-03-02 20:50 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 300 | 300 |  |  | IMPERIAL | CA | SDGE | Imperial Valley Sub 230kV Bus | 2009-12-31 08:00 | 2012-05-31 07:00 | Waived | Complete | Complete | None
VERNON POWER PLANT | 80 | 2005-09-12 | 2005-09-12 07:00 | WITHDRAWN | 2009-09-28 07:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 610 | 610 |  |  | LOS ANGELES | CA | SCE | Laguna Bell Sub 230 kV Bus | 2008-07-31 07:00 | 2012-05-31 07:00 | Required | Complete | Re-Study | None
PALCO | 82 | 2005-06-10 | 2005-09-14 07:00 | WITHDRAWN | 2011-08-05 19:34 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Biofuel; MWs MW-1: 6.8 | 6.8 |  |  | HUMBOLDT | CA | PGAE | Rio Dell Substation 60kV | 2006-01-01 08:00 | 2006-01-01 08:00 | None | Complete | None | None
WEST FRY WIND ENERGY PROJECT | 83 | 2005-09-16 | 2005-09-16 07:00 | WITHDRAWN | 2008-10-08 07:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 60 | 60 |  |  | SAN BERNARDINO | CA | SCE | Lugo-Pisgah No. 2 230 kV tran line | 2008-12-31 08:00 | 2010-06-01 07:00 | Required | Complete | None | None
WINDSTAR I | 85 | 2005-12-28 | 2005-12-28 08:00 | WITHDRAWN | 2008-03-26 07:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 120 | 120 |  |  | KERN | CA | SCE | Segment 3 230 Collector Loop Tehachapi | 2007-12-31 08:00 | 2009-12-31 08:00 | Waived | Complete | Withdrawn | None
CAITHNESS 251 WIND REPOWER | 86A | 2006-01-20 | 2006-01-20 08:00 | WITHDRAWN | 2012-12-04 19:39 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 33.1 | 33.1 |  |  | KERN | CA | SCE | Vincent Substation | 2008-01-01 08:00 | 2015-01-01 08:00 | Waived | Complete | Complete | None
CAITHNESS RIDGETOP WIND REPOWER | 86B | 2006-01-20 | 2006-01-20 08:00 | WITHDRAWN | 2012-12-04 19:39 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 34 | 34 |  |  | KERN | CA | SCE | Canwind Substation 66kV | 2008-01-01 08:00 | 2015-01-01 08:00 | Waived | Complete | Complete | None
DIABLO CANYON P.P. #1 UNIT | 87 | 2010-12-14 | 2006-02-03 08:00 | WITHDRAWN | 2010-12-14 08:00 | TC | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Nuclear; MWs MW-1: 28 | 28 | Full Capacity |  | SAN LUIS OBISPO | CA | PGAE | Diablo Canyon Substation Circuit Breakers 532 and 632 | 2005-12-08 08:00 | 2005-12-08 08:00 | NA | None | None | NA
CARSON HYDROGEN POWER PROJECT (CHPP) | 88 | 2006-02-10 | 2006-02-10 08:00 | WITHDRAWN | 2008-02-14 08:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 613.5 | 613.5 |  |  | LOS ANGELES | CA | SCE | Hinson Sub 230 kV bus | 2011-07-01 07:00 | 2011-07-01 07:00 | Waived | Re-Study | None | None
VICTORVILLE 2 | 89 | 2006-02-13 | 2006-02-13 08:00 | WITHDRAWN | 2010-10-07 07:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 570 | 570 |  |  | SAN BERNARDINO | CA | SCE | Victorville Substation | 2009-07-01 07:00 | 2012-07-01 07:00 | Required | Re-Study | Complete | None
MMC CHULA VISTA EXPANSION | 90 | 2006-09-13 | 2006-02-16 08:00 | WITHDRAWN | 2009-10-26 07:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 93 | 93 |  |  | SAN DIEGO | CA | SDGE | Existing radial 69kV gen-tie line to TL6929 | 2007-06-01 07:00 | 2009-06-01 07:00 | Required | Complete | Complete | None
PALMDALE POWER PLANT | 92 | 2006-02-23 | 2006-02-23 08:00 | WITHDRAWN | 2019-07-22 07:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 570 | 570 | Full Capacity |  | LOS ANGELES | CA | SCE | Vincent Sub 230 kV Bus | 2009-07-01 07:00 | 2022-04-01 07:00 | Waived | Complete | Complete | None | Executed | Failure to Cure Deficiency
ALTA Q94 (FKA LEHIGH) | 94 | 2006-02-15 | 2006-03-01 08:00 | WITHDRAWN | 2014-02-04 16:08 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 180 | 180 |  |  | KERN | CA | SCE | Highwind Sub 220kV Bus | 2011-12-31 08:00 | 2016-12-31 08:00 | Waived | Complete | Complete | None
ALTA Q97 (FKA ALTA 5 AND LUCCHESE) | 97 | 2006-02-15 | 2006-03-01 08:00 | WITHDRAWN | 2014-09-29 07:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 160 | 160 |  |  | KERN | CA | SCE | Whirlwind Sub 220kV bus | 2013-12-31 08:00 | 2016-12-31 08:00 | Waived | Complete | Complete | None |  | None
RMU PLANT | 101 | 2006-04-07 | 2006-04-07 07:00 | WITHDRAWN | 2006-04-07 07:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 100 | 100 |  |  | KERN | CA | PGAE | PG&E Kern Oil-Vedder 115kV line | 2008-03-01 08:00 | 2008-03-01 08:00 | None | None | None | None
WILDHORSE | 102 | 2006-04-19 | 2006-04-19 07:00 | WITHDRAWN | 2008-01-17 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 210 | 210 |  |  | MONTEREY | CA | PGAE | Coburn Sub 230 kV Bus | 2008-11-30 08:00 | 2008-11-30 08:00 | Required | Complete | Complete | None
LOMPOC WIND PROJECT II | 102A | 2010-08-05 | 2006-04-21 07:00 | WITHDRAWN | 2011-07-08 18:26 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 100 | 100 |  |  | KERN | CA | PGAE | Cabrill0-Divide 115kV | 2009-12-31 08:00 | 2009-12-31 08:00 | None | None | None | None
BME OTAY MESA BIOMASS FACILITY | 103 | 2006-05-02 | 2006-05-02 07:00 | WITHDRAWN | 2016-12-22 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Biofuel; MWs MW-1: 27 | 27 |  |  | SAN DIEGO | CA | SDGE | Border Substation 69 kV | 2008-12-01 08:00 | 2017-12-30 08:00 | Required | Complete | Complete | None | Executed | FERC Order
VERNON POWER PLANT EXPANSION PROJECT | 104 | 2006-04-14 | 2006-05-03 07:00 | WITHDRAWN | 2009-09-28 07:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 304 | 304 |  |  | LOS ANGELES | CA | SCE | Laguna Bell Sub 230 kV Bus | 2009-07-31 07:00 | 2009-07-31 07:00 | Required | Re-Study | Re-Study | None
BEAR RIVER WIND FARM | 105 | 2006-05-04 | 2006-05-04 07:00 | WITHDRAWN | 2011-08-05 20:02 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 100 | 100 |  |  | HUMBOLDT | CA | PGAE | Between Rio Del Junction and Bridgeville | 2009-10-30 07:00 | 2009-10-30 07:00 | None | None | None | None
MOJAVE SOLAR PARK 1 | 106 | 2006-05-26 | 2006-05-26 07:00 | WITHDRAWN | 2008-10-13 07:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 635 | 635 |  |  | SAN BERNARDINO | CA | SCE | Mohave 500 kV Switchyard | 2009-12-31 08:00 | 2010-12-31 08:00 | Required | None | None | None
TECATE HYBRID | 106A | 2006-05-01 | 2006-06-06 07:00 | WITHDRAWN | 2019-12-04 08:00 | Serial LGIP | Photovoltaic | Storage |  | Solar | Battery |  | 50 | 50 |  | 100 | Full Capacity |  | SAN DIEGO | CA | SDGE | Boulevard East Substation 138kV | 2008-06-30 07:00 | 2022-12-31 08:00 | Required | Complete | Complete | None | Executed | IC Request
SOLANO WIND PROJECT - PHASE 3 (115KV) | 107 | 2006-06-09 | 2006-06-09 07:00 | WITHDRAWN | 2011-08-05 20:05 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 128 | 128 |  |  | SOLANO | CA | PGAE | Brighton-Contra Costa 115 kV | 2011-03-01 08:00 | 2011-03-01 08:00 | None | None | None | None
SAN LUIS OBISPO SOLAR I | 108A | 2006-06-14 | 2006-06-14 07:00 | WITHDRAWN | 2006-11-16 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 300 | 300 |  |  | KERN | CA | PGAE | Morro Bay - Midway 230kV line | 2010-03-01 08:00 | 2010-03-01 08:00 | None | None | None | None
SES SOLAR THREE | 109 | 2006-06-14 | 2006-06-16 07:00 | WITHDRAWN | 2011-03-31 18:39 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 550 | 550 |  |  | SAN BERNARDINO | CA | SCE | Pisgah Substation | 2011-03-01 08:00 | 2011-03-01 08:00 | Required | None | None | None
SES SOLAR SIX | 110 | 2006-06-14 | 2006-06-16 07:00 | WITHDRAWN | 2011-03-31 18:42 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 1400 | 1400 |  |  | SAN BERNARDINO | CA | SCE | Pisgah Substation | 2013-03-01 08:00 | 2013-03-01 08:00 | Required | None | None | None
LIBERTY V LOST HILLS | 111 | 2006-06-23 | 2006-06-26 07:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Biofuel; MWs MW-1: 16 | 16 |  |  | KERN | CA | PGAE | Tap of Chevron 70kv tran line | 2009-08-31 07:00 | 2016-12-31 08:00 |  | Complete | Complete |  | Executed
TULE II | 112 | 2006-06-28 | 2006-06-28 07:00 | WITHDRAWN | 2009-05-01 07:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 300 | 300 |  |  | SAN DIEGO | CA | SDGE | 500 kV Imperial Valley-Miguel trans line | 2008-10-31 07:00 | 2008-10-31 07:00 | Required | Complete | None | None
COLLINSVILLE WIND | 113 | 2006-06-29 | 2006-06-30 07:00 | WITHDRAWN | 2014-10-24 22:28 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 30 | 30 |  |  | SOLANO | CA | PGAE | Birds Landing Switching Station 230kV bus | 2009-04-03 07:00 | 2014-12-31 08:00 | Required | Complete | None | None | Executed
MOJAVE WINDS | 114 | 2006-06-29 | 2006-07-12 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 150 | 150 |  |  | SAN BERNARDINO | CA | SCE | Victor 230 kV | 2008-07-01 07:00 | 2008-07-01 07:00 | Required | None | None | None
UPC GRAND VIEW WINDS | 115 | 2006-06-29 | 2006-07-12 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 150 | 150 |  |  | SAN BERNARDINO | CA | SCE | Lugo-Pisgah 230kV line | 2008-07-01 07:00 | 2008-07-01 07:00 | Required | None | None | None
INDIGO WINDS | 116 | 2006-06-29 | 2006-07-12 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 50 | 50 |  |  | SAN BERNARDINO | CA | SCE | Lugo-Pisgah 230kV line | 2008-07-01 07:00 | 2008-07-01 07:00 | Required | None | None | None
BEAR RIVER WIND FARM Q=117 | 117 | 2006-05-04 | 2006-07-20 07:00 | WITHDRAWN | 2011-08-05 19:58 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 70 | 70 |  |  | HUMBOLDT | CA | PGAE | Rio Del Junction - Bridgeville | 2009-10-30 07:00 | 2009-10-30 07:00 | None | None | None | None
SOUTH POINT ENERGY CENTER | 118 | 2006-08-02 | 2006-08-04 07:00 | WITHDRAWN | 2007-11-28 08:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 550 | 550 |  |  | MOHAVE | AZ | SCE | SCE Mohave Substation | 2009-01-08 08:00 | 2009-01-08 08:00 | Required | None | None | None
SES SOLAR SEVEN | 120 | 2006-08-09 | 2006-08-09 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 1200 | 1200 |  |  | SAN BERNARDINO | CA | SCE | Mojave 500 kV Switchyard | 2011-03-01 08:00 | 2011-03-01 08:00 | Required | None | None | None
MARGARITA ENERGY CENTER | 122 | 2006-08-16 | 2006-08-17 07:00 | WITHDRAWN | 2007-01-16 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 99 | 99 |  |  | ORANGE | CA | SDGE | SDG&E Margarita Substation | 2009-03-31 07:00 | 2008-06-30 07:00 | Waived | None | None | None
PALA ENERGY CENTER | 123 |  | 2006-08-17 07:00 | WITHDRAWN | 2007-01-16 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 99 | 99 |  |  | SAN DIEGO | CA | SDGE | SDG&E Pala Substation | 2009-03-31 07:00 | 2008-06-30 07:00 | None | None | None | None
SEARCHLIGHT 1 | 126 | 2006-08-31 | 2006-08-31 07:00 | WITHDRAWN | 2012-06-12 23:21 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 1500 | 1500 |  |  | CLARK | NV | SCE | Eldorado Substation 220kV bus | 2011-12-31 08:00 | 2011-12-31 08:00 | Required | Complete | Re-Study | None
CONTRA COSTA CARBON PLANT RECONNECT (CCCPR) | 127 | 2006-08-22 | 2006-09-01 07:00 | WITHDRAWN | 2007-07-11 07:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Other; MWs MW-1: 27.2 | 27.2 |  |  | CONTRA COSTA | CA | PGAE | 115kV Oleum Switchyard | 2008-08-01 07:00 | 2008-08-01 07:00 | Waived | Complete | None | None
KRCD COMMUNITY POWER PLANT | 128 | 2006-09-01 | 2006-09-01 07:00 | WITHDRAWN | 2009-08-06 07:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 600 | 600 |  |  | FRESNO | CA | PGAE | McCall Substation | 2010-12-01 08:00 | 2012-12-01 08:00 | Required | Re-Study | Re-Study | None
AMBOY | 129 |  | 2006-09-13 07:00 | WITHDRAWN | 2006-10-24 07:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 400 | 400 |  |  | SAN BERNARDINO | CA | SCE | Pisgah 230kV Substation | 2010-03-01 08:00 | 2010-03-01 08:00 | None | None | None | None
MOJAVE SOLAR PARK 2 | 130 | 2006-09-13 | 2006-09-13 07:00 | WITHDRAWN | 2008-04-01 07:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 565 | 565 |  |  | SAN BERNARDINO | CA | SCE | Mohave Generating Station | 2010-12-31 08:00 | 2010-12-31 08:00 | Required | None | None | None
CROSSROADS WIND | 133 |  | 2006-10-03 07:00 | WITHDRAWN | 2006-12-21 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 140 | 140 |  |  | SAN BERNARDINO | CA | SCE | Pisgah-Lugo 230kV | 2010-03-01 08:00 | 2010-03-01 08:00 | None | None | None | None
PASTORIA EXPANSION II | 134 |  | 2006-10-09 07:00 | WITHDRAWN | 2007-01-31 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 200 | 200 |  |  | KERN | CA | SCE | Pastoria Substation | 2010-05-31 07:00 | 2010-05-31 07:00 | None | None | None | None
GRANITE MOUNTAIN WIND FARM | 135 | 2006-10-10 | 2006-10-10 07:00 | WITHDRAWN | 2013-10-08 16:43 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 60 | 60 |  |  | SAN BERNARDINO | CA | SCE | Lugo-Pisgah 230kV line | 2008-09-30 07:00 | 2015-12-31 08:00 | Required | Complete | Complete | Complete | Executed
FONTANA ENERGY CENTER | 136 | 2006-10-16 | 2006-10-16 07:00 | WITHDRAWN | 2010-08-03 07:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 300 | 300 |  |  | SAN BERNARDINO | CA | SCE | Etiwanda 230kV Substation | 2010-01-01 08:00 | 2010-01-01 08:00 | Waived | Complete | Complete | None
ETIWANDA CCGT | 139 | 2006-10-24 | 2006-10-24 07:00 | WITHDRAWN | 2010-09-22 07:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 698 | 698 |  |  | SAN BERNARDINO | CA | SCE | SCE Rancho Vista 500kV Sub | 2010-06-01 07:00 | 2013-06-01 07:00 | Waived | Complete | Complete | None
NAVY 1 | 140 | 2006-10-31 | 2006-10-31 08:00 | WITHDRAWN | 2007-02-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 75 | 75 |  |  | INYO | CA | SCE | Coso-Kramer 230 kV | 2011-08-18 07:00 | 2011-08-18 07:00 | None | None | None | None
ETIWANDA SCGT EXPANSION | 141 | 2006-11-03 | 2006-11-03 08:00 | WITHDRAWN | 2007-12-11 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 504 | 504 |  |  | SAN BERNARDINO | CA | SCE | Rancho Vista 500 kV Substation | 2010-06-01 07:00 |  | Waived | None | None | None
KM ACQUISITIONS | 142 | 2006-11-06 | 2006-11-06 08:00 | WITHDRAWN | 2017-01-09 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 80 | 80 |  |  | SAN BERNARDINO | CA | SCE | Kramer Substation 220kV | 2009-12-31 08:00 | 2016-12-01 08:00 | Required | Complete | Complete | None | Executed | IC Request
HDLA SOLAR | 143 | 2006-11-06 | 2006-11-06 08:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 80 | 80 |  |  | SAN BERNARDINO | CA | SCE | Kramer Substation | 2009-12-31 08:00 | 2009-12-31 08:00 | Required | None | None | None
LUZ SOLAR PARTNERS | 144 | 2006-11-06 | 2006-11-06 08:00 | WITHDRAWN | 2009-12-07 21:21 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 320 | 320 |  |  | SAN BERNARDINO | CA | SCE | Kramer Substation | 2009-12-31 08:00 | 2009-12-31 08:00 | Required | None | None | None |  | None
BIGHORN | 145 | 2006-11-08 | 2006-11-08 08:00 | WITHDRAWN | 2008-10-23 07:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 591 | 591 |  |  | CLARK | NV | SCE | Eldorado 500 kV Substation | 2010-06-01 07:00 | 2010-06-01 07:00 | Required | None | None | None
GREEN BORDERS GEOTHERMAL PHASE II | 148 |  | 2006-11-16 08:00 | WITHDRAWN | 2007-02-01 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 90 | 90 |  |  | CHURCH | NV | SCE | Oxbow 230kV Substation | 2011-10-01 07:00 | 2011-10-01 07:00 | None | None | None | None
NORTH SKY RIVER II WIND | 149 | 2006-11-16 | 2006-11-16 08:00 | WITHDRAWN | 2008-10-20 07:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 362 | 362 |  |  | KERN | CA | SCE | SCE Highwind Sub #2 (proposed) 230 kV | 2010-12-31 08:00 | 2010-12-31 08:00 | Required | None | None | None
LARKSPUR 3 | 150 | 2006-11-16 | 2006-11-16 08:00 | WITHDRAWN | 2016-03-24 00:57 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 47.4 | 47.4 |  |  | SAN DIEGO | CA | SDGE | Border Substation 69 kV | 2014-05-15 07:00 | 2016-11-15 08:00 | Required | Re-Study | Complete | None
TRANSCANADA PEAKER | 151 | 2006-11-17 | 2006-11-17 08:00 | WITHDRAWN | 2006-12-11 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 510 | 510 |  |  | SAN BERNARDINO | CA | SCE | Chino Substation 230kV Line | 2011-05-01 07:00 | 2011-05-01 07:00 | Required | None | None | None
POINT SAL WIND | 152 | 2006-11-22 | 2006-11-22 08:00 | WITHDRAWN | 2008-10-29 07:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 105 | 105 |  |  | SANTA BARBARA | CA | PGAE | Mesa-Divide #1 115kV line | 2009-12-31 08:00 | 2009-12-31 08:00 | Required | Complete | None | None
ALTA Q153 (FKA ALTA 7) | 153 | 2006-11-22 | 2006-11-22 08:00 | WITHDRAWN | 2014-09-29 07:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 100 | 100 |  |  | KERN | CA | SCE | Whirlwind Substation 230kV | 2008-05-30 07:00 | 2016-12-31 08:00 | Waived | Complete | Complete | None | In Progress | None
FLYING WING SOLAR (FKA GENESIS SOLAR) | 154 | 2006-11-28 | 2006-11-30 08:00 | WITHDRAWN | 2013-04-18 07:00 | TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 | Full Capacity |  | KERN | CA | SCE | Windhub 230 kV Substation | 2009-12-31 08:00 | 2015-06-01 07:00 | NA | Complete | Complete | NA
LSP OAKLAND | 155 | 2006-12-01 | 2006-12-01 08:00 | WITHDRAWN | 2009-01-02 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 300 | 300 |  |  | ALAMEDA | CA | PGAE | Oakland C 115kV substation | 2010-05-31 07:00 | 2012-05-31 07:00 | Required | Re-Study | None | None
DAGGETT WIND PROJECT II | 156 | 2006-12-05 | 2006-12-05 08:00 | WITHDRAWN | 2012-03-13 22:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 201 | 201 |  |  | SAN BERNARDINO | CA | SCE | Lugo-Pisgah 230kV line | 2009-03-01 08:00 | 2012-03-01 08:00 | Required | Complete | None | None
ALTA 8 | 157 | 2006-12-15 | 2006-12-15 08:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 100 | 100 |  |  | KERN | CA | SCE | 66kV Rosamond-Antelope line | 2014-12-31 08:00 | 2014-12-31 08:00 | Required | None | None | None
ALTA 9 | 158 | 2006-12-15 | 2006-12-15 08:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 100 | 100 |  |  | KERN | CA | SCE | 66kV Rosamond-Delsur line | 2013-12-31 08:00 | 2013-12-31 08:00 | Required | None | None | None
ALTA 10 | 159 | 2006-12-15 | 2006-12-15 08:00 | WITHDRAWN | 2009-12-15 22:53 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 100 | 100 |  |  | KERN | CA | SCE | Antelope-Magunden #1 220kV line | 2013-12-31 08:00 | 2013-12-31 08:00 | Required | None | None | None
CALIFORNIA SOLAR ONE | 160 | 2007-02-01 | 2006-12-29 08:00 | WITHDRAWN | 2007-09-17 07:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 220 | 220 |  |  | SAN BERNARDINO | CA | SCE | Kramer | 2009-01-01 08:00 | 2009-01-01 08:00 | Required | None | None | None
HARBOR II | 161 | 2006-12-27 | 2007-01-04 08:00 | WITHDRAWN | 2011-06-23 07:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 220 | 220 |  |  | LOS ANGELES | CA | SCE | Harborgen Substation | 2009-05-01 07:00 | 2012-03-01 08:00 | Waived | Re-Study | None | None
BAJANORTE WIND FACILITY | 164 | 2007-01-12 | 2007-01-12 08:00 | WITHDRAWN | 2008-11-19 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 1000 | 1000 |  |  | BAJA CALIFORNIA | MX | SDGE | Imperial Valley 230kV switchyard | 2010-10-01 07:00 | 2010-10-01 07:00 | Required | None | None | None
DPT BROADWELL LAKE | 165 | 2007-01-16 | 2007-01-16 08:00 | WITHDRAWN | 2010-05-21 07:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 400 | 400 |  |  | SAN BERNARDINO | CA | SCE | Pisgah 230kV Substation bus | 2011-06-30 07:00 | 2011-06-30 07:00 | Waived | Complete | None | None
BLYTHE III | 167 |  | 2007-01-25 08:00 | WITHDRAWN | 2007-05-16 07:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 700 | 700 |  |  | RIVERSIDE | CA | SCE | 500kV line to Midpoint Switching Station | 2012-06-01 07:00 | 2012-06-01 07:00 | None | None | None | None
VIENTO MEXICANA | 168 | 2007-02-01 | 2007-02-02 08:00 | WITHDRAWN | 2011-03-31 21:31 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 1000 | 1000 |  |  | BAJA CALIFORNIA | MX | SDGE | Imperial Valley 500kV bus | 2011-12-31 08:00 | 2011-12-31 08:00 | Required | None | None | None
IMPERIAL SOLEIL | 169 | 2007-02-01 | 2007-02-02 08:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 211.6 | 211.6 |  |  | IMPERIAL | CA | SDGE | Imperial Valley 230kV bus | 2011-12-31 08:00 | 2011-12-31 08:00 | Required | None | None | None
MOJAVE SOLEIL | 170 | 2007-02-02 | 2007-02-02 08:00 | WITHDRAWN | 2009-12-07 21:16 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 |  |  | KERN | CA | SCE | Substation 5 (aka Whirlwind) | 2011-12-31 08:00 | 2013-07-31 07:00 | Required | None | None | None
DELTA WIND II | 171 | 2007-02-09 | 2007-02-09 08:00 | WITHDRAWN | 2011-03-31 21:54 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 500 | 500 |  |  | SOLANO | CA | PGAE | Vaca-Tesla 500kV line | 2011-12-31 08:00 | 2011-03-31 07:00 | Required | None | None | None
STOCKTON GENERATION | 172 | 2007-02-08 | 2007-02-15 08:00 | WITHDRAWN | 2015-07-01 21:14 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 508 | 508 |  |  | SAN JOAQUIN | CA | PGAE | Tesla-Bellota 230kV lines | 2011-05-15 07:00 | 2014-05-01 07:00 | Required | Complete | Complete | None
WELLHEAD POWER PALA | 173 | 2007-02-16 | 2007-02-16 08:00 | WITHDRAWN | 2009-01-27 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49.9 | 49.9 |  |  | SAN DIEGO | CA | SDGE | Pala 69kV Substation | 2011-05-01 07:00 | 2011-05-01 07:00 | Waived | Complete | Complete | None
PAINTED HILLS II | 174 | 2007-02-16 | 2007-02-16 08:00 | WITHDRAWN | 2007-06-12 07:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 30 | 30 |  |  | RIVERSIDE | CA | SCE | Devers-Venwind 115kV line | 2008-12-01 08:00 | 2008-12-01 08:00 | Required | None | None | None
ALTA Q175 (FKA ALTA 11) | 175 | 2007-02-21 | 2007-02-21 08:00 | WITHDRAWN | 2015-06-12 07:00 | TC | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 650 | 650 | Full Capacity |  | KERN | CA | SCE | Whirlwind Substation 230kV | 2008-09-30 07:00 | 2017-12-31 08:00 | NA | Complete | Complete | NA
WELLHEAD POWER MARGARITA | 176 | 2007-02-23 | 2007-02-23 08:00 | WITHDRAWN | 2008-04-29 07:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49.9 | 49.9 |  |  | ORANGE | CA | SDGE | Margarita 138kV Substation | 2008-05-01 07:00 | 2010-06-15 07:00 | Waived | Complete | Complete | None
CARQUINEZ WIND | 177 | 2007-02-27 | 2007-02-28 08:00 | WITHDRAWN | 2009-01-21 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 100 | 100 |  |  | CONTRA COSTA | CA | PGAE | Bahia Moraga 230 kV Line | 2011-12-31 08:00 | 2011-12-31 08:00 | Required | Complete | None | None
PACHECO WIND | 178 | 2007-02-27 | 2007-02-28 08:00 | WITHDRAWN | 2007-11-19 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 100 | 100 |  |  | MERCED | CA | PGAE | Los Banos 230kV bus near Pacheco Pass | 2011-12-31 08:00 | 2011-12-31 08:00 | Required | None | None | None
BAJA WIND | 178A | 2007-02-27 | 2007-02-28 08:00 | WITHDRAWN | 2008-11-24 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 500 | 500 |  |  | MEXICALI/ENSENADA/TECATE | MX | SDGE | Miguel 230kV Bus | 2011-07-01 07:00 | 2011-07-01 07:00 | Required | None | None | None
MEXICO WIND | 178B | 2007-02-27 | 2007-02-28 08:00 | WITHDRAWN | 2011-03-31 22:07 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 500 | 500 |  |  | MEXICALI/ENSENADA/TECATE | MX | SDGE | Imperial Valley 230kV Substation | 2010-07-01 07:00 | 2010-06-15 07:00 | Required | None | None | None
EAGLE MOUNTAIN | 179 | 2007-02-15 | 2007-03-01 08:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 300 | 300 |  |  | RIVERSIDE | CA | SCE | Julian Hinds 230kV Substation | 2010-12-31 08:00 | 2010-12-31 08:00 | Required | None | None | None
CPV CALIFORNIA I | 180 | 2007-03-06 | 2007-03-02 08:00 | WITHDRAWN | 2008-05-01 07:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 564 | 564 |  |  | SAN BERNARDINO | CA | SCE | New 230kV Switchyard on the Mira Loma-Vista #2 line | 2011-05-01 07:00 | 2011-05-01 07:00 | Required | None | None | None
CPV CALIFORNIA II | 181 | 2007-03-06 | 2007-03-02 08:00 | WITHDRAWN | 2008-05-01 07:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 400 | 400 |  |  | SAN BERNARDINO | CA | SCE | New 230kV switchyard on the Chino-Serrano line | 2010-03-01 08:00 | 2010-03-01 08:00 | Required | None | None | None
DESERT SAPPHIRE PV | 182 | 2007-03-05 | 2007-03-05 08:00 | WITHDRAWN | 2009-12-07 23:59 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 500 | 500 |  |  | KERN | CA | SCE | Windhub Substation | 2010-12-31 08:00 | 2015-07-01 07:00 | Required | None | None | None
ESJ PHASE II PROJECT (FKA RUMOROSA WIND ENERGY PHASE II PROJECT) | 183 | 2007-03-05 | 2007-03-05 08:00 | WITHDRAWN | 2017-10-10 07:00 | TC | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 300 | 300 | Energy Only |  | BAJA CALIFORNIA | MX | SDGE | East County (ECO) Substation 230kV | 2009-11-01 07:00 | 2019-06-30 07:00 | NA | Complete | Complete | NA |  | IC Request
WESTERN GEOPOWER UNIT 1 | 184 | 2007-03-05 | 2007-03-05 08:00 | WITHDRAWN | 2013-08-14 20:40 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 32 | 32 |  |  | SONOMA | CA | PGAE | Geysers #3-Cloverdale 115 kV line | 2010-01-01 08:00 | 2015-10-01 07:00 | Required | Complete | Complete | None
GREEN BORDERS GEOTHERMAL PHASE 2 | 185 | 2007-03-06 | 2007-03-06 08:00 | WITHDRAWN | 2011-01-03 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 150 | 150 |  |  | MINERAL | NV | SCE | Control Sub | 2011-08-01 07:00 | 2011-01-01 08:00 | Waived | Complete | None | None
STOCKTON PEAKERS PROJECT | 186 | 2007-03-07 | 2007-03-07 08:00 | WITHDRAWN | 2007-11-28 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 211 | 211 |  |  | SAN JOAQUIN | CA | PGAE | Stockton¿A¿-Lockeford-Bellota 115kV #1&#2 lines & Tesla-Tracy 115kV line | 2009-12-31 08:00 | 2009-12-31 08:00 | Required | None | None | None
NEW GEYSERS | 187 | 2007-03-14 | 2007-03-14 07:00 | WITHDRAWN | 2008-06-06 07:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 50 | 50 |  |  | SONOMA | CA | PGAE | Geysers-Fulton 230kV transmission line | 2011-01-01 08:00 | 2011-01-01 08:00 | Required | Complete | None | None
DOGHOUSE JUNCTION ENERGY CENTER | 190 | 2007-03-31 | 2007-03-30 07:00 | WITHDRAWN | 2011-05-31 21:18 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 330 | 330 |  |  | SAN DIEGO | CA | SDGE | Otay Mesa Energy Center 230kV Substation | 2011-03-01 08:00 | 2013-05-01 07:00 | Required | Complete | Complete | None
CPV CALIFORNIA III | 191 | 2007-04-02 | 2007-04-02 07:00 | WITHDRAWN | 2007-10-01 07:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 315 | 315 |  |  | SAN DIEGO | CA | SDGE | Penasquistos Old Town 230kV transmission line | 2010-03-01 08:00 | 2010-03-01 08:00 | Required | None | None | None
CPV CALIFORNIA IV | 192 | 2007-04-02 | 2007-04-02 07:00 | WITHDRAWN | 2007-10-01 07:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 315 | 315 |  |  | SAN DIEGO | CA | SDGE | San Luis Rey¿Mission 230kV transmission line | 2010-03-01 08:00 | 2010-03-01 08:00 | Required | None | None | None
BPAE KERN FRONT | 195 | 2007-04-06 | 2007-04-06 07:00 | WITHDRAWN | 2007-09-21 07:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 725 | 725 |  |  | KERN | CA | SCE | Springerville Mugunden 230kV Line | 2013-01-01 08:00 | 2013-01-01 08:00 | Waived | None | None | None
MADERA ENERGY CENTER | 196 | 2007-04-13 | 2007-04-13 07:00 | WITHDRAWN | 2011-04-01 14:26 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 210 | 210 |  |  | MADERA | CA | PGAE | Borden Substation 230kV Bus | 2011-07-01 07:00 | 2014-06-15 07:00 | Required | None | None | None
CPV CALIFORNIA V | 197 | 2007-04-16 | 2007-04-16 07:00 | WITHDRAWN | 2007-12-03 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 315 | 315 |  |  | SAN DIEGO | CA | SDGE | Otay Mesa 230kV switchyard | 2011-12-01 08:00 | 2011-12-01 08:00 | Required | None | None | None
STAR GENERATION | 198 | 2007-04-18 | 2007-04-18 07:00 | WITHDRAWN | 2008-01-11 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 400 | 400 |  |  | SAN DIEGO | CA | SDGE | OMEC interconnection substation | 2010-02-28 08:00 | 2010-02-28 08:00 | Required | None | None | None
STOCKTON REPOWERING PROJECT | 199 | 2007-04-19 | 2007-04-19 07:00 | WITHDRAWN | 2008-03-03 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 50 | 50 |  |  | SAN JOAQUIN | CA | PGAE | 60kV bus at Posdef QF facility | 2009-12-31 08:00 | 2009-12-31 08:00 | Required | Complete | None | None
MILLIKEN | 200 | 2007-04-02 | 2007-04-19 07:00 | WITHDRAWN | 2007-05-14 07:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 200 | 200 |  |  | RIVERSIDE | CA | SCE | Mira Loma Substation | 2010-05-31 07:00 | 2010-05-31 07:00 | None | None | None | None
CALICO MOUNTAINS WIND ENERGY | 202 | 2007-04-19 | 2007-04-19 07:00 | WITHDRAWN | 2008-11-12 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 198.65 | 198.65 |  |  | SAN BERNARDINO | CA | SCE | Cool Water-Kramer #1 230kV line | 2013-11-15 08:00 | 2013-11-15 08:00 | Required | None | None | None
CAMP ROCK WIND | 203 | 2007-04-19 | 2007-04-19 07:00 | WITHDRAWN | 2011-04-01 14:52 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 198.65 | 198.65 |  |  | SAN BERNARDINO | CA | SCE | Cool Water-SEGS2-Tortilla 115kV line | 2013-12-15 08:00 | 2013-12-15 08:00 | Required | None | None | None
IRON MOUNTAIN WIND ENERGY | 204 | 2007-04-19 | 2007-04-19 07:00 | WITHDRAWN | 2008-12-19 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 149.4 | 149.4 |  |  | SAN BERNARDINO | CA | SCE | Tortilla-Kramer 115 kV line | 2013-11-15 08:00 | 2013-11-15 08:00 | Required | None | None | None
EL DORADO SOLAR GENERATING STATION PROJECT | 205 | 2007-04-20 | 2007-04-20 07:00 | WITHDRAWN | 2014-01-03 08:00 | TC | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 5 | 5 | Full Capacity |  | CLARK | NV | SCE | El Dorado 220kV Switchyard | 2010-12-31 08:00 | 2014-12-31 08:00 | NA | Complete | Complete | NA
EL SEGUNDO 3 & 4 RE-POWER II | 206 | 2007-04-26 | 2007-04-23 07:00 | WITHDRAWN | 2007-06-20 07:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 |  |  | LOS ANGELES | CA | SCE | El Sequndo 230kV Switchyard | 2013-01-30 08:00 | 2013-01-30 08:00 | None | None | None | None
LONG BEACH 5, 6, 7 & 8 | 207 | 2007-04-26 | 2007-04-26 07:00 | WITHDRAWN | 2008-03-06 08:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 557.3 | 557.3 |  |  | LOS ANGELES | CA | SCE | Long Beach Substation | 2013-08-30 07:00 |  | Required | None | None | None
GV1 | 208 | 2007-04-20 | 2007-05-03 07:00 | WITHDRAWN |  | AMEND 39 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 2 | 2 |  |  | ALAMEDA | CA | PGAE | Tracy-Herdlyn 69kV line | 2008-06-01 07:00 | 2008-09-01 07:00 |  | Waived
CONCEPCION II WIND GENERATION | 209 | 2007-05-02 | 2007-05-03 07:00 | WITHDRAWN | 2009-12-17 19:15 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 400 | 400 |  |  | BAJA CALIFORNIA | MX | SDGE | New 230/500kV substation near the 500kV IV-ML line | 2010-12-31 08:00 | 2010-12-31 08:00 | Required | None | None | None
DESERT SUNLIGHT PV III | 210 | 2007-05-03 | 2007-05-03 07:00 | WITHDRAWN | 2009-12-08 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 500 | 500 |  |  | RIVERSIDE | CA | SCE | Red Bluff Substation 230kV switchyard | 2012-12-31 08:00 | 2016-12-01 08:00 | Required | None | None | None
HORSE LAKE WIND PROJECT | 211 | 2007-05-14 | 2007-05-04 07:00 | WITHDRAWN | 2008-12-11 23:43 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 201 | 201 |  |  | LASSEN | CA | PGAE | Caribou 230kV Substation | 2008-10-31 07:00 | 2008-10-31 07:00 | Required | None | None | None
BEAR RIVER RIDGE WIND FARM | 212 | 2007-05-09 | 2007-05-09 07:00 | WITHDRAWN | 2012-07-23 21:16 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 50 | 50 |  |  | HUMBOLDT | CA | PGAE | Rio Dell Substation 60kV | 2010-10-30 07:00 | 2013-12-15 08:00 | Required | Complete | Complete | None | In Progress
DESERT WIND | 213 | 2007-05-07 | 2007-05-09 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 180 | 180 |  |  | SAN BERNARDINO | CA | SCE | Coolwater 220kV bus | 2010-11-15 08:00 | 2010-11-15 08:00 | Required | None | None | None
WATERMAN MOUNTAINS WIND ENERGY PROJECT | 214 | 2007-05-10 | 2007-05-10 07:00 | WITHDRAWN | 2008-11-12 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 49.25 | 49.25 |  |  | SAN BERNARDINO | CA | SCE | Coolwater-Kramer 115 kV line | 2013-12-15 08:00 | 2013-12-15 08:00 | Required | None | None | None
ESJ EXPANSION PROJECT (FKA RUMOROSA WIND EXPANSION) | 215 | 2007-05-21 | 2007-05-21 07:00 | WITHDRAWN | 2017-10-10 07:00 | TC | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 420 | 420 | Energy Only |  | BAJA CALIFORNIA | MX | SDGE | East County (ECO) Substation 230kV | 2011-05-01 07:00 | 2019-06-30 07:00 | NA | Complete | Complete | NA |  | IC Request
LONESTAR | 216 | 2007-05-22 | 2007-05-22 07:00 | WITHDRAWN | 2007-07-24 07:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 98.8 | 98.8 |  |  | SAN DIEGO | CA | SDGE | Otay Mesa Energy Center | 2010-03-31 07:00 | 2010-03-31 07:00 | None | None | None | None
OCEANSIDE | 217 |  | 2007-05-22 07:00 | WITHDRAWN | 2007-07-24 07:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 98.8 | 98.8 |  |  | SAN DIEGO | CA | SDGE | San Luis Rey-Melrose 69kV | 2010-03-31 07:00 | 2010-03-31 07:00 | None | None | None | None
OLYMPUS POWER | 218 | 2007-05-22 | 2007-05-22 07:00 | WITHDRAWN | 2007-07-24 07:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 98.8 | 98.8 |  |  | SAN DIEGO | CA | SDGE | Loop Talega-Escondido 230kV line | 2010-03-31 07:00 | 2010-03-31 07:00 | None | None | None | None
SONORAN | 219 | 2007-05-07 | 2007-05-23 07:00 | WITHDRAWN | 2019-03-25 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 |  |  | RIVERSIDE | CA | SCE | Colorado River Substation 500kV bus | 2012-06-01 07:00 | 2021-01-02 08:00 | Required | None | None | None | Executed | IC Request
DESERT GARNET PV | 220 | 2007-05-23 | 2007-05-23 07:00 | WITHDRAWN | 2009-12-07 21:22 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 450 | 450 |  |  | SAN BERNARDINO | CA | SCE | BLM West-Kramer 230kV line | 2011-12-01 08:00 | 2016-10-01 07:00 | Required | None | None | None
DESERT ONYX PV | 221 | 2007-05-23 | 2007-05-23 07:00 | WITHDRAWN | 2009-12-07 23:54 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 450 | 450 |  |  | SAN BERNARDINO | CA | SCE | Cool Water-Kramer #1 230kV line | 2011-12-01 08:00 | 2015-11-01 07:00 | Required | None | None | None
NOBLE WELL WIND GENERATION PROJECT | 223 | 2007-05-24 | 2007-05-29 07:00 | WITHDRAWN | 2008-08-15 16:34 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 170 | 170 |  |  | SAN BERNARDINO | CA | SCE | Cool Water-Kramer #1 230kV line | 2010-12-31 08:00 | 2010-12-31 08:00 | Required | None | None | None
BORDER II | 224 | 2007-05-23 | 2007-05-30 07:00 | WITHDRAWN | 2007-07-23 07:00 | Serial LGIP | Generating Facility Type-1: Reciprocating Engine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 99 | 99 |  |  | SAN DIEGO | CA | SDGE | 69kV line next to Calpeak Border site | 2010-05-01 07:00 | 2010-05-01 07:00 | None | None | None | None
BLYTHE III (REVISED) | 225 | 2007-05-23 | 2007-06-04 07:00 | WITHDRAWN | 2011-04-01 22:34 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 640 | 640 |  |  | RIVERSIDE | CA | SCE | 500kV line to the new Midpoint switching station | 2012-06-01 07:00 | 2015-05-31 07:00 | Required | None | None | None
RAINBOW ENERGY FACILITY | 226 | 2007-05-16 | 2007-06-05 07:00 | WITHDRAWN | 2008-04-03 07:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 620 | 620 |  |  | SAN DIEGO | CA | SDGE | New double circuit 230kV line into Escondido Substation | 2012-03-30 07:00 | 2012-03-30 07:00 | Required | None | None | None
BODEGA BAY PROJECT | 227 | 2007-06-18 | 2007-06-14 07:00 | WITHDRAWN | 2008-03-10 07:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 175 | 175 |  |  | MARIN | CA | PGAE | Fulton-Ignacio 230kV #2 line | 2010-12-31 08:00 | 2010-12-31 08:00 | Required | None | None | None
CPV CALIFORNIA VI | 228 | 2007-06-20 | 2007-06-20 07:00 | WITHDRAWN | 2007-10-22 07:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 630 | 630 |  |  | ALAMEDA | CA | PGAE | Newark Substation 230kV bus | 2011-06-01 07:00 | 2011-06-01 07:00 | Required | None | None | None
DESERT OPAL III PV | 229 | 2007-06-21 | 2007-06-21 07:00 | WITHDRAWN | 2009-12-07 23:55 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 1000 | 1000 |  |  | SAN BERNARDINO | CA | SCE | Devers Substation | 2013-12-31 08:00 | 2016-12-31 08:00 | Required | None | None | None
DESERT RUBY PV | 230 | 2007-06-21 | 2007-06-21 07:00 | WITHDRAWN | 2009-12-07 23:58 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 1000 | 1000 |  |  | SAN BERNARDINO | CA | SCE | Devers Substation | 2013-12-31 08:00 | 2013-12-31 08:00 | Required | None | None | None
PAINTED HILLS III | 231 | 2007-06-13 | 2007-06-25 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 50 | 50 |  |  | RIVERSIDE | CA | SCE | Venwind portion of Devers-Garnett-Venwind line | 2009-12-01 08:00 | 2009-12-01 08:00 | Required | None | None | None
RAMCO ENERGY CENTER | 232 | 2007-06-26 | 2007-06-26 07:00 | WITHDRAWN | 2007-08-06 07:00 | Serial LGIP | Generating Facility Type-1: Reciprocating Engine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 99 | 99 |  |  | SAN DIEGO | CA | SDGE | Interconnection on Site | 2010-05-15 07:00 |  | None | None | None | None
JEAN LAKE SOLAR | 234 | 2007-06-27 | 2007-06-27 07:00 | WITHDRAWN | 2011-04-04 15:27 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 400 | 400 |  |  | CLARK | NV | SCE | Proposed Eldorado-Ivanpah 230kV line | 2013-06-30 07:00 | 2013-06-30 07:00 | Required | None | None | None
CPV CALIFORNIA VII | 235 | 2007-06-29 | 2007-06-29 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 630 | 630 |  |  | CONTRA COSTA | CA | PGAE | Tesla-Tracy #1 230kV line | 2011-06-01 07:00 | 2011-06-01 07:00 | Required | None | None | None
CPV CALIFORNIA VIII | 236 | 2007-06-29 | 2007-06-29 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 630 | 630 |  |  | SAN JOAQUIN | CA | PGAE | Tesla Substation 230kV bus | 2011-06-01 07:00 | 2011-06-01 07:00 | Required | None | None | None
COPPER MOUNTAIN II | 237 | 2007-06-12 | 2007-07-02 07:00 | WITHDRAWN | 2008-11-24 08:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 634 | 634 |  |  | CLARK | NV | SCE | Eldorado 220kV switchyard | 2011-05-01 07:00 | 2011-05-01 07:00 | Waived | None | None | None
CARRIZO SOLAR FARM I | 238 | 2007-07-12 | 2007-07-11 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 45 | 45 |  |  | SAN LUIS OBISPO | CA | PGAE | Temblor-San Luis Obispo 115kV line | 2008-12-01 08:00 | 2008-12-01 08:00 | Required | None | None | None
SIBERIA PHASE I SEGS (FKA DPT BROADWELL LAKE II) | 240 | 2007-07-12 | 2007-07-12 07:00 | WITHDRAWN | 2013-11-06 16:32 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 400 | 400 |  |  | SAN BERNARDINO | CA | SCE | Pisgah Sub 230kV | 2014-06-30 07:00 | 2018-01-01 08:00 | Waived | Complete | Complete | None
SIBERIA PHASE II SEGS (FKA DPT 9) | 241 | 2007-07-12 | 2007-07-12 07:00 | WITHDRAWN | 2014-01-10 21:40 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 400 | 400 |  |  | SAN BERNARDINO | CA | SCE | Pisgah Sub 230kV | 2015-06-30 07:00 | 2015-06-30 07:00 | Waived | Complete | Complete | None
SOUTH BRISTOL MOUNTAINS WIND FARM | 243 | 2007-07-16 | 2007-07-16 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 429 | 429 |  |  | SAN BERNARDINO | CA | SCE | Pisgah 230kV Substation | 2010-12-30 08:00 | 2010-12-30 08:00 | Required | None | None | None
LITTLE LAKE SOUTH WIND FARM | 244 | 2007-07-16 | 2007-07-16 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 120 | 120 |  |  | KERN/INYO | CA | SCE | Control-Haiwee-Inyokern 115kV line | 2010-12-15 08:00 | 2010-12-15 08:00 | Required | None | None | None
SHAVERS VALLEY WIND FARM | 245 | 2007-07-16 | 2007-07-16 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 228 | 228 |  |  | RIVERSIDE | CA | SCE | Devers-Mirage-Julian Hinds 230kV line | 2010-12-15 08:00 | 2010-12-15 08:00 | Required | None | None | None
LAUREL MOUNTAIN WIND FARM | 246 | 2007-07-17 | 2007-07-17 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 120 | 120 |  |  | KERN | CA | SCE | Kramer-Inyokern-Randsburg #3 115kV line | 2010-12-15 08:00 | 2010-12-15 08:00 | Required | None | None | None
MADERA ENERGY CENTER EXPANSION | 247 | 2007-07-30 | 2007-07-30 07:00 | WITHDRAWN | 2011-04-07 21:21 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 67 | 67 |  |  | MADERA | CA | PGAE | Borden Substation 230kV Bus | 2011-07-01 07:00 | 2012-04-15 07:00 | Waived | None | None | None
STOCKTON GENERATION EXPANSION | 248 | 2007-07-30 | 2007-07-30 07:00 | WITHDRAWN | 2015-07-01 21:15 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 67 | 67 |  |  | SAN JOAQUIN | CA | PGAE | Tesla-Bellota 230kV line | 2011-05-15 07:00 | 2014-05-01 07:00 | Waived | Complete | Complete | None
SOLEDAD WIND ENERGY PARK | 249 | 2007-07-30 | 2007-07-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 105 | 105 |  |  | MONTEREY | CA | PGAE | Moss-Linding-Salinas-Soledad 115kV #1 and #2 lines #1 line & Tap N/O Moss Landing-Salinas-Soledad #2 | 2010-11-01 07:00 | 2010-11-01 07:00 | Required | None | None | None
WALKER RIDGE WIND ENERGY PARK | 250 | 2007-08-04 | 2007-07-30 07:00 | WITHDRAWN | 2013-06-04 07:00 | TC | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 66.2 | 66.2 | Full Capacity |  | LAKE/COLUSA | CA | PGAE | Redbud-Cortina 115kV line | 2009-08-01 07:00 | 2014-08-03 07:00 | NA | Complete | Complete | NA
CHUCKWALLA SOLAR I | 251 | 2007-08-01 | 2007-08-01 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 |  |  | RIVERSIDE | CA | SCE | Eagle Mountain-Blythe 161kV line | 2009-12-15 08:00 | 2009-12-15 08:00 | Required | None | None | None
CENTRAL COAST | 253 | 2007-08-13 | 2007-08-13 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 40 | 40 |  |  | SANTA BARBARA | CA | PGAE | Cabrillo Substation 115kV | 2011-12-31 08:00 | 2011-12-31 08:00 | Required | None | None | None
AVENAL ENERGY PROJECT | 254 | 2007-08-21 | 2007-08-21 07:00 | WITHDRAWN | 2015-08-24 07:00 | TC | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 600 | 600 | Full Capacity |  | KINGS | CA | PGAE | Gates Substation 230kV bus | 2012-06-01 07:00 | 2017-06-01 07:00 | NA | Complete | Complete | NA
RIDGECREST SOLAR II (FKA MOJAVE SOLAR PEAKING POWER) | 255 | 2010-11-20 | 2007-08-23 07:00 | WITHDRAWN | 2011-01-26 08:00 | TC | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 | Full Capacity |  | KERN | CA | SCE | Inyokern Substation | 2013-12-28 08:00 | 2013-07-01 07:00 | NA | Complete | Complete | NA
CALRENEW-1 | 256 | 2007-08-23 | 2007-08-23 07:00 | WITHDRAWN | 2007-09-24 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 30 | 30 |  |  | FRESNO | CA | PGAE | Mendota Biomass Substation | 2009-04-15 07:00 | 2009-04-15 07:00 | None | None | None | None
FAIRFIELD ENERGY CENTER | 257 | 2007-07-10 | 2007-09-10 07:00 | WITHDRAWN | 2011-04-21 16:06 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 575 | 575 |  |  | SOLANO | CA | PGAE | New Fairfield Substation 230kV bus | 2011-06-01 07:00 | 2011-06-01 07:00 | Required | None | None | None
OAKLEY GENERATING STATION | 258 | 2007-09-12 | 2007-09-12 07:00 | WITHDRAWN | 2018-08-28 07:00 | TC | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 651 | 651 | Energy Only |  | CONTRA COSTA | CA | PGAE | Contra Costa Substation 230kV bus | 2012-02-01 08:00 | 2020-12-31 08:00 | NA | Complete | Complete | NA | Executed
PALERMO GENERATING STATION | 259 | 2007-09-14 | 2007-09-12 07:00 | WITHDRAWN | 2008-12-11 23:51 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 345 | 345 |  |  | SUTTER | CA | PGAE | Rio Oso Substation 115kV bus | 2012-02-01 08:00 | 2012-02-01 08:00 | Required | None | None | None
LODI GENERATING STATION | 260 | 2007-09-14 | 2007-09-12 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 260 | 260 |  |  | SAN JOAQUIN | CA | PGAE | Loop Gold Hill-Eight Mile Road 230kV line | 2012-02-01 08:00 | 2012-02-01 08:00 | Required | None | None | None
TESORO REFINERY COGENERATION | 261 | 2007-09-28 | 2007-09-28 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 104 | 104 |  |  | LOS ANGELES | CA | SCE | Hinson Substation 220kV | 2010-10-01 07:00 | 2010-10-01 07:00 | Required | None | None | None
BIRDS LANDING ENERGY CENTER | 262 | 2007-10-11 | 2007-10-10 07:00 | WITHDRAWN | 2008-06-03 07:00 | Serial LGIP | Generating Facility Type-1: Reciprocating Engine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 390.6 | 390.6 |  |  | SOLANO | CA | PGAE | Birds Landing Substation 230 kV Bus | 2012-04-15 07:00 | 2012-04-15 07:00 | Required | None | None | None
COPPER MOUNTAIN II ALTERNATE | 263 | 2007-10-10 | 2007-10-10 07:00 | WITHDRAWN | 2008-02-13 08:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 634 | 634 |  |  | CLARK | NV | SCE | Eldorado Switchyard 220kV & NCP Merchant Substation 230kV | 2011-05-01 07:00 | 2011-05-01 07:00 | Waived | None | None | None
HOMER MOUNTAIN WIND FARM | 264 | 2007-10-15 | 2007-10-15 07:00 | WITHDRAWN | 2009-12-17 19:16 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 300 | 300 |  |  | SAN BERNARDINO | CA | SCE | Lugo-Mohave 500kV line | 2010-12-30 08:00 | 2010-12-30 08:00 | Required | None | None | None
PALEN DRY LAKE PV | 265 | 2007-10-16 | 2007-10-16 07:00 | WITHDRAWN | 2007-12-05 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 25 | 25 |  |  | RIVERSIDE | CA | SCE | Eagle Mountain Blythe 161kV line | 2009-12-01 08:00 | 2009-12-01 08:00 | Required | None | None | None
RIO OSO GENERATING STATION | 266 | 2007-10-19 | 2007-10-19 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 325 | 325 |  |  | SUTTER | CA | PGAE | Rio Oso Substation 230 kV Bus | 2012-02-01 08:00 | 2012-02-01 08:00 | Required | None | None | None
PATTERSON PASS ENERGY CENTER | 269 | 2007-10-30 | 2007-10-31 07:00 | WITHDRAWN | 2011-04-07 21:53 | Serial LGIP | Generating Facility Type-1: Reciprocating Engine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 371.3 | 371.3 |  |  | SAN JOAQUIN | CA | PGAE | Tesla-Westley 230 KV lines | 2012-04-15 07:00 | 2015-05-01 07:00 | Required | None | None | None
DESERT QUARTZSITE PV | 270 | 2007-11-01 | 2007-11-01 07:00 | WITHDRAWN | 2009-12-07 23:56 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 700 | 700 |  |  | RIVERSIDE | CA | SCE | Proposed Midpoint Substation 230kV | 2011-12-01 08:00 | 2015-12-01 08:00 | Required | None | None | None
DESERT JASPER PV | 271 | 2007-11-01 | 2007-11-01 07:00 | WITHDRAWN | 2009-12-07 22:19 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 400 | 400 |  |  | SAN BERNARDINO | CA | SCE | Lugo-Pisgah 230kV line | 2012-12-01 08:00 | 2016-09-01 07:00 | Required | None | None | None
GWF HANFORD | 273 | 2007-11-01 | 2007-11-01 07:00 | WITHDRAWN | 2008-01-25 08:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 99 | 99 |  |  | KINGS | CA | PGAE | Hanford Switchyard 115kV bus | 2010-05-01 07:00 | 2010-05-01 07:00 | Waived | None | None | None
CPV CALIFORNIA IX | 275 | 2007-11-07 | 2007-11-07 08:00 | WITHDRAWN | 2011-04-07 22:04 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 630 | 630 |  |  | SOLANO | CA | PGAE | Loop Vaca Dixon-Peabody & Vaca Dixon-Lambie 230 kV lines | 2012-09-01 07:00 | 2013-05-01 07:00 | Required | None | None | None
ANTIOCH GENERATING STATION | 276 | 2007-11-09 | 2007-11-09 08:00 | WITHDRAWN | 2008-11-18 08:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 650 | 650 |  |  | CONTRA COSTA | CA | PGAE | Contra Costa Substation | 2012-01-15 08:00 | 2012-01-15 08:00 | Required | None | None | None
RIO SECO WIND | 277 | 2007-11-15 | 2007-11-15 08:00 | WITHDRAWN | 2008-03-06 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 75 | 75 |  |  | SAN BERNARDINO | CA | SCE | Coolwater-Dunn Siding 115kV line | 2010-11-15 08:00 | 2010-11-15 08:00 | Required | None | None | None
HUMBOLDT WAVECONNECT PROJECT | 279 | 2007-11-30 | 2007-11-30 08:00 | WITHDRAWN | 2008-02-29 08:00 | Serial LGIP | Generating Facility Type-1: Hydro; Generating Facility Fuel-1: Water; MWs MW-1: 40 | 40 |  |  | HUMBOLDT | CA | PGAE | Fairhaven Substation 60kV bus | 2012-06-01 07:00 | 2012-06-01 07:00 | Required | None | None | None
MENDOCINO WAVECONNECT PROJECT | 280 | 2007-11-30 | 2007-11-30 08:00 | WITHDRAWN | 2008-11-18 08:00 | Serial LGIP | Generating Facility Type-1: Hydro; Generating Facility Fuel-1: Water; MWs MW-1: 40 | 40 |  |  | MENDOCINO | CA | PGAE | Fort Bragg Substation 60kV bus | 2012-06-01 07:00 | 2012-06-01 07:00 | Required | None | None | None
ROUGH & READY ISLAND ENERGY PARK PROJECT | 281 | 2007-12-03 | 2007-12-03 08:00 | WITHDRAWN | 2008-05-27 07:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 500 | 500 |  |  | SAN JOAQUIN | CA | PGAE | Loop Tesla-Stagg and Tesla-Eight Mile 230kV lines | 2010-12-31 08:00 | 2010-12-31 08:00 | Required | None | None | None
MADERA POWER | 282 | 2007-12-12 | 2007-12-12 08:00 | WITHDRAWN | 2014-12-03 08:00 | TC | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Biofuel; MWs MW-1: 29 | 29 | Full Capacity |  | MADERA | CA | PGAE | Dairyland-Mendota 115 kV line tap | 2008-05-31 07:00 | 2011-06-30 07:00 | NA | Complete | Complete | NA | Executed
BETHEL 7 & 8 SOLAR THERMAL HYBRID PROJECT | 283 | 2007-12-12 | 2007-12-12 08:00 | WITHDRAWN | 2011-04-12 19:50 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Biofuel; MWs MW-1: 106.8 | 106.8 |  |  | FRESNO | CA | PGAE | Gates Substation 230kV bus | 2010-03-01 08:00 | 2012-09-30 07:00 | Required | None | None | None
UKIAH ENERGY CENTER | 284 | 2007-12-13 | 2007-12-13 08:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Reciprocating Engine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 115 | 115 |  |  | MENDOCINO | CA | PGAE | Ukiah Substation 115kV bus | 2012-04-15 07:00 | 2012-04-15 07:00 | Required | None | None | None
TROY LAKE WIND | 285 | 2007-12-13 | 2007-12-13 08:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 150 | 150 |  |  | SAN BERNARDINO | CA | SCE | Pisgah Substation 230kV | 2011-12-31 08:00 | 2011-12-31 08:00 | Required | None | None | None
EL CENTRO 1 | 286 | 2007-12-20 | 2007-12-20 08:00 | WITHDRAWN | 2008-05-07 07:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 375 | 375 |  |  | IMPERIAL | CA | SDGE | Southwest Power Link 500kV line | 2012-07-01 07:00 | 2012-07-01 07:00 | Required | None | None | None
SUNTOWER GASKELL GENERATING STATION | 287 | 2007-12-21 | 2007-12-21 08:00 | WITHDRAWN | 2011-04-12 19:59 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 231 | 231 |  |  | KERN | CA | SCE | Antelope-Magunden 230kV | 2011-04-01 07:00 | 2011-04-01 07:00 | Waived | None | None | None
CARRIZO 1 | 288 | 2007-12-20 | 2007-12-21 08:00 | WITHDRAWN | 2008-05-14 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 375 | 375 |  |  | SAN LUIS OBISPO | CA | PGAE | Morro Bay-Midway #2 230kV line | 2011-07-01 07:00 | 2012-07-01 07:00 | Required | None | None | None
ECP I | 289 | 2007-12-20 | 2007-12-21 08:00 | WITHDRAWN | 2008-05-29 07:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 375 | 375 |  |  | SAN BERNARDINO | CA | SCE | El Dorado-Ivanpah 115kV line | 2011-07-01 07:00 | 2011-07-01 07:00 | Required | None | None | None
TRILOBITE SOLAR PROJECT | 290 | 2007-12-27 | 2007-12-27 08:00 | WITHDRAWN | 2009-12-07 21:18 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 750 | 750 |  |  | SAN BERNARDINO | CA | SCE | Pisgah Substation 230kV | 2015-06-01 07:00 | 2012-12-31 08:00 | Required | None | None | None
MESQUITE LAKE | 291 | 2007-12-27 | 2007-12-27 08:00 | WITHDRAWN | 2008-11-20 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 |  |  | SAN BERNARDINO | CA | SCE | Ivanpah Substation 230kV | 2015-06-01 07:00 | 2015-06-01 07:00 | Required | None | None | None
FREEMAN JUNCTION SOLAR PROJECT | 292 | 2007-12-27 | 2007-12-27 08:00 | WITHDRAWN | 2008-02-06 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 |  |  | KERN | CA | SCE | SCE portion of Kramer BLM West 230kV line | 2014-06-01 07:00 | 2014-06-01 07:00 | Required | None | None | None
WELLHEAD POWER PROJECT 5 | 293 | 2007-12-31 | 2008-01-03 08:00 | WITHDRAWN | 2008-12-09 08:00 | Serial LGIP | Generating Facility Type-1: Reciprocating Engine; Generating Facility Fuel-1: Biofuel; MWs MW-1: 5.2 | 5.2 |  |  | FRESNO | CA | PGAE | Helm-Kerman 70kV line | 2009-06-01 07:00 | 2009-06-01 07:00 | Required | None | None | None
TROY LAKE SOLEIL | 295 | 2008-01-17 | 2008-01-17 08:00 | WITHDRAWN | 2009-12-07 21:17 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 300 | 300 |  |  | SAN BERNARDINO | CA | SCE | Pisgah Substation 220kV | 2011-12-31 08:00 | 2011-12-31 08:00 | Required | None | None | None
BIG ROCK SUNTOWER GENERATING STATION | 296 | 2008-01-18 | 2008-01-18 08:00 | WITHDRAWN | 2008-05-23 07:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 33 | 33 |  |  | LOS ANGELES | CA | SCE | Antelope-Piute 66kV line | 2009-12-01 08:00 | 2009-12-01 08:00 | Waived | None | None | None
EL DORADO SOLAR ALTERNATE | 298 | 2008-01-23 | 2008-01-23 08:00 | WITHDRAWN | 2008-11-19 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 140 | 140 |  |  | CLARK | NV | SCE | El Dorado 220kV switchyard | 2011-11-01 07:00 | 2011-11-01 07:00 | Required | None | None | None
GWF HANFORD COMBINED CYCLE POWER PLANT | 299 | 2010-11-20 | 2008-01-29 08:00 | WITHDRAWN | 2011-01-26 08:00 | TC | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 27 | 27 | Full Capacity |  | KINGS | CA | PGAE | Hanford Switchyard 115kV bus | 2010-05-01 07:00 | 2013-05-01 07:00 | NA | Complete | Complete | NA
HYDROGEN ENERGY CALIFORNIA | 300 | 2010-11-20 | 2008-02-04 08:00 | WITHDRAWN | 2011-05-17 07:00 | TC | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 400 | 400 | Full Capacity |  | KERN | CA | PGAE | Midway-Wheeler Ridge #1 and #2 230kV line | 2014-09-01 07:00 | 2015-09-01 07:00 | NA | Complete | Complete | NA
LUCERNE VALLEY SOLAR PROJECT, PHASE 2 | 301 | 2008-02-08 | 2008-02-08 08:00 | WITHDRAWN | 2008-10-27 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 500 | 500 |  |  | SAN BERNARDINO | CA | SCE | Lugo-Pisgah Line 220kV line | 2016-01-01 08:00 | 2016-01-01 08:00 | Required | None | None | None |  | None
LUCERNE VALLEY SOLAR PROJECT, PHASE 1 | 302 | 2008-02-19 | 2008-02-19 08:00 | WITHDRAWN | 2008-04-07 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 |  |  | SAN BERNARDINO | CA | SCE | Lugo-Pisgah 220kV line | 2010-02-01 08:00 | 2010-02-01 08:00 | Required | None | None | None
AUBANEL WIND PROJECT | 303 | 2008-02-27 | 2008-02-27 08:00 | WITHDRAWN | 2008-10-27 07:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 500 | 500 |  |  | BAJA CALIFORNIA | MX | SDGE | Imperial Valley - Miguel 500kV line | 2011-12-31 08:00 | 2011-12-31 08:00 | Required | None | None | None
MARSH LANDING GENERATING STATION - COMBINED CYCLE UNITS | 305 | 2008-03-18 | 2008-03-10 07:00 | WITHDRAWN | 2010-12-08 17:45 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 611 | 611 |  |  | CONTRA COSTA | CA | PGAE | Contra Costa Substation 230kV Switchyard | 2012-07-30 07:00 | 2012-07-30 07:00 | Required | None | None | None
ZEPHYR POWER STATION | 306 | 2008-03-11 | 2008-03-11 07:00 | WITHDRAWN | 2008-11-20 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 200 | 200 |  |  | SAN JOAQUIN | CA | PGAE | Tesla-Belota 230kV and Tesla-Webber 230kV lines | 2012-05-01 07:00 | 2012-05-01 07:00 | Required | None | None | None
PV REDMAN-LANCASTER | 307 | 2008-03-11 | 2008-03-11 07:00 | WITHDRAWN | 2008-04-24 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | LOS ANGELES | CA | SCE | Lancaster Redman 66kV line | 2009-05-01 07:00 | 2009-05-01 07:00 | Required | None | None | None
PV LITTLE ROCK-PALMDALE | 308 | 2008-03-11 | 2008-03-11 07:00 | WITHDRAWN | 2008-04-24 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | LOS ANGELES | CA | SCE | Helijet-Little Rock-Palmdale-Rockair 66kV line | 2009-05-01 07:00 | 2009-05-01 07:00 | Required | None | None | None
PV-3 (FKA PV ANTELOPE-DEL SUR) | 309 | 2010-11-20 | 2008-03-11 07:00 | WITHDRAWN | 2011-03-23 18:19 | TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | LOS ANGELES | CA | SCE | Antelope Substation 66kV | 2009-05-01 07:00 | 2013-07-01 07:00 | NA | None | None | NA
PV DEL SUR-LANCASTER | 310 | 2008-03-11 | 2008-03-11 07:00 | WITHDRAWN | 2008-04-24 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | LOS ANGELES | CA | SCE | Del-Dur-Lancaster-Rite Aid 66kV line | 2009-05-01 07:00 | 2009-05-01 07:00 | Required | None | None | None | In Progress
PV PIUTE-LANCASTER | 311 | 2008-03-11 | 2008-03-11 07:00 | WITHDRAWN | 2008-04-24 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | LOS ANGELES | CA | SCE | Lancaster-Little Rock-Piute 66kV line | 2009-05-01 07:00 | 2009-05-01 07:00 | Required | None | None | None
PV PALMDALE-TORTOISE | 312 | 2008-03-11 | 2008-03-11 07:00 | WITHDRAWN | 2008-05-06 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | LOS ANGELES | CA | SCE | Oasis-Tortoise 66kV line | 2009-05-01 07:00 | 2009-05-01 07:00 | Required | None | None | None
PV REDMAN-PIUTE | 313 | 2008-03-11 | 2008-03-11 07:00 | WITHDRAWN | 2008-04-24 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | LOS ANGELES | CA | SCE | Piute-Redman 66kV line | 2009-05-01 07:00 | 2009-05-01 07:00 | Required | None | None | None
PV PIUTE-LITTLE ROCK | 314 | 2008-03-11 | 2008-03-11 07:00 | WITHDRAWN | 2008-04-24 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | LOS ANGELES | CA | SCE | Lancaster-Little Rock-Piute 66kV line | 2009-05-01 07:00 | 2009-05-01 07:00 | Required | None | None | None
PV PALMDALE-ROCKAIR | 315 | 2008-03-11 | 2008-03-11 07:00 | WITHDRAWN | 2008-04-24 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | LOS ANGELES | CA | SCE | Helijet-Little Rock-Palmdale-Rockair 66kV line | 2009-05-01 07:00 | 2009-05-01 07:00 | Required | None | None | None
PV ROSAMOND-ANTELOPE | 316 | 2008-03-11 | 2008-03-11 07:00 | WITHDRAWN | 2008-04-24 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | LOS ANGELES | CA | SCE | Antelope-Rosamond 66kV line | 2009-05-01 07:00 | 2009-05-01 07:00 | Required | None | None | None
PV-11 (FKA PV ROSAMOND-DEL SUR) | 317 | 2010-11-20 | 2008-03-11 07:00 | WITHDRAWN | 2011-03-23 17:42 | TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | LOS ANGELES | CA | SCE | Antelope Substation 66kV | 2009-05-01 07:00 | 2013-06-01 07:00 | NA | None | None | NA
PV GOLDTOWN-LANCASTER | 318 | 2008-03-11 | 2008-03-11 07:00 | WITHDRAWN | 2008-04-24 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | KERN | CA | SCE | Goldtown-Lancaster 66kV line | 2009-05-01 07:00 | 2009-05-01 07:00 | Required | None | None | None
PV GOLDTOWN-CORUM | 319 | 2008-03-11 | 2008-03-11 07:00 | WITHDRAWN | 2008-04-24 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | LOS ANGELES | CA | SCE | Corum-Goldtown 66kV line | 2009-05-01 07:00 | 2009-05-01 07:00 | Required | None | None | None
NE WIND PROJECT | 321 | 2008-03-18 | 2008-03-18 07:00 | WITHDRAWN | 2010-12-08 18:53 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 100 | 100 |  |  | PLUMAS | CA | PGAE | Caribou Substation 230kV switchyard | 2013-12-15 08:00 | 2013-12-01 08:00 | Required | None | None | None
PITTSBURG POWER PLANT - CCU | 322 | 2008-03-17 | 2008-03-18 07:00 | WITHDRAWN | 2010-12-08 16:42 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 611 | 611 |  |  | CONTRA COSTA | CA | PGAE | Pittsburg 230kV switchyard | 2012-09-30 07:00 | 2012-09-30 07:00 | Required | None | None | None
PV ROSAMOND-CORUM | 323 | 2008-03-27 | 2008-03-27 07:00 | WITHDRAWN | 2008-04-24 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | KERN | CA | SCE | Coram-Rosemond 66kV line | 2009-05-01 07:00 | 2009-05-01 07:00 | Required | None | None | None
PV COOLWATER-DUNN SIDING | 324 | 2008-03-27 | 2008-03-27 07:00 | WITHDRAWN | 2008-04-24 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 |  |  | SAN BERNARDINO | CA | SCE | Eldorado Baker Cool Water Dunn Siding Mountain Pass 115kV line | 2009-05-01 07:00 | 2009-05-01 07:00 | Required | None | None | None
PV COOLWATER - KRAMER | 325 | 2008-03-27 | 2008-03-27 07:00 | WITHDRAWN | 2008-04-24 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | KERN | CA | SCE | Kramer-Cool Water 115kV line | 2009-05-01 07:00 | 2009-05-01 07:00 | Required | None | None | None
PV TORTILLA-KRAMER | 326 | 2008-03-27 | 2008-03-27 07:00 | WITHDRAWN | 2008-04-24 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | KERN | CA | SCE | Kramer-Tortilla 115kV line | 2009-05-01 07:00 | 2009-05-01 07:00 | Required | None | None | None
PV KRAMER-INYOKERN #1 | 327 | 2008-03-25 | 2008-03-27 07:00 | WITHDRAWN | 2008-11-21 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | KERN | CA | SCE | Kramer-Inyokern-Randsberg No. 1 115kV line | 2009-05-01 07:00 | 2009-05-01 07:00 | Required | None | None | None
PV KRAMER-INYOKERN #2 | 328 | 2008-03-27 | 2008-03-27 07:00 | WITHDRAWN | 2008-04-24 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | KERN | CA | SCE | Kramer-Inyokern-Randsberg No. 3 115kV line | 2009-05-01 07:00 | 2009-05-01 07:00 | Required | None | None | None
GASKELL SOLAR GENERATING STATION | 329 | 2008-03-31 | 2008-03-31 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 264 | 264 |  |  | KERN | CA | SCE | Whirlwind Substation 230kV | 2012-08-01 07:00 | 2012-08-01 07:00 | None | None | None | None
TUMBLEWEED SOLAR GENERATING STATION | 330 | 2008-03-31 | 2008-03-31 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 33 | 33 |  |  | LOS ANGELES | CA | SCE | Antelope-Calcement 66kV line | 2009-12-01 08:00 | 2009-12-01 08:00 | None | None | None | None
WILLOW SPRINGS SOLAR GENERATING STATION | 331 | 2008-03-31 | 2008-03-31 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 231 | 231 |  |  | KERN | CA | SCE | Windhub Substation | 2010-05-01 07:00 | 2010-05-01 07:00 | None | None | None | None
WILLOW SPRINGS SOLAR GENERATING STATION II | 332 | 2008-03-31 | 2008-03-31 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 264 | 264 |  |  | KERN | CA | SCE | Windhub Substation | 2011-09-01 07:00 | 2011-09-01 07:00 | None | None | None | None
PHOENIX SOLAR GENERATING STATION | 333 | 2008-03-31 | 2008-03-31 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 33 | 33 |  |  | SAN BERNARDINO | CA | SCE | Cool Water-Kramer 115kV line | 2009-07-01 07:00 | 2009-07-01 07:00 | None | None | None | None
DGC KELSO RE | 335 | 2008-04-04 | 2008-04-04 07:00 | WITHDRAWN | 2008-05-05 07:00 | Serial LGIP | Generating Facility Type-1: Reciprocating Engine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 99 | 99 |  |  | ALAMEDA | CA | PGAE | Kelso Substation 230kV bus | 2012-06-01 07:00 | 2012-06-01 07:00 | None | None | None | None
BORREGO STARLIGHT 1 | 336 | 2008-04-07 | 2008-04-07 07:00 | WITHDRAWN | 2008-11-21 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 75 | 75 |  |  | SAN DIEGO | CA | SDGE | Borrego Substation 69kV | 2010-12-31 08:00 | 2010-12-31 08:00 | None | None | None | None
FRESNO COGENERATION CTG-4 | 338 | 2008-04-17 | 2008-04-17 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 10 | 10 |  |  | FRESNO | CA | PGAE | Kerman-Helms 70kV line | 2010-06-01 07:00 | 2010-06-01 07:00 | None | None | None | None
SANGEN | 339 | 2008-04-18 | 2008-04-18 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 50 | 50 |  |  | SAN FRANCISCO | CA | PGAE | Mission Substation | 2011-06-01 07:00 | 2011-06-01 07:00 | None | None | None | None
APG WILSON STATION | 341 | 2008-04-23 | 2008-04-23 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 525 | 525 |  |  | MERCED | CA | PGAE | Wilson Substation 230kV Bus | 2012-03-01 08:00 | 2012-03-01 08:00 | None | None | None | None
PV-7 | 343 | 2008-04-25 | 2008-04-25 07:00 | WITHDRAWN | 2008-11-21 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 40 | 40 |  |  | LOS ANGELES | CA | SCE | Piute-Redman 66kV Line | 2011-05-01 07:00 | 2011-05-01 07:00 | None | None | None | None
PV-8 | 344 | 2008-05-05 | 2008-04-25 07:00 | WITHDRAWN | 2010-07-12 20:12 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 40 | 40 |  |  | LOS ANGELES | CA | SCE | Lancaster-Little Rock-Piute 66kV line | 2011-05-01 07:00 | 2011-05-01 07:00 | Waived | None | None | None |  | None
PV-5 | 345 | 2008-04-25 | 2008-04-25 07:00 | WITHDRAWN | 2008-11-21 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 40 | 40 |  |  | LOS ANGELES | CA | SCE | Lancaster-Little Rock-Piute 66kV Line (Lancaster side of Tap 72) | 2011-05-01 07:00 | 2011-05-01 07:00 | None | None | None | None
PV-1 | 346 | 2008-04-25 | 2008-04-25 07:00 | WITHDRAWN | 2008-11-21 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 30 | 30 |  |  | LOS ANGELES | CA | SCE | Lancaster-Redman 66kV Line | 2011-05-01 07:00 | 2011-05-01 07:00 | None | None | None | None
PV-9 | 347 | 2008-04-25 | 2008-04-25 07:00 | WITHDRAWN | 2010-07-12 20:12 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 |  |  | LOS ANGELES | CA | SCE | Helijet-Little Rock-Palmdale-Rockair 66kV line (primary: Palmdale side of Tap 62; Aternate: Little Rock side of Tap 62) | 2011-05-01 07:00 | 2011-05-01 07:00 | None | None | None | None
PV-31 | 350 | 2008-04-25 | 2008-04-25 07:00 | WITHDRAWN | 2010-07-12 20:10 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 80 | 80 |  |  | SAN BERNARDINO | CA | SCE | Eldorado-Baker- Coolwater-Dunn Siding-Mountain Pass 115 kV line | 2013-05-01 07:00 | 2013-05-01 07:00 | Waived | None | None | None
WELLHEAD POWER WINTERS | 351 | 2008-04-25 | 2008-04-25 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49 | 49 |  |  | YOLO | CA | PGAE | Tap Vaca-Rio Oso 115 kV line | 2009-07-01 07:00 | 2009-07-01 07:00 | None | None | None | None
WELLHEAD POWER SALADO | 352 | 2008-04-25 | 2008-04-25 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49 | 49 |  |  | STANISLAUS | CA | PGAE | Salado Substation 115 kV | 2009-07-01 07:00 | 2009-07-01 07:00 | None | None | None | None
WELLHEAD POWER FIREBAUGH 2 | 353 | 2008-04-25 | 2008-04-25 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49 | 49 |  |  | FRESNO | CA | PGAE | Panoche Substation 115 kV bus | 2009-07-01 07:00 | 2009-07-01 07:00 | None | None | None | None
WELLHEAD POWER HELM | 354 | 2008-04-25 | 2008-04-25 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49 | 49 |  |  | FRESNO | CA | PGAE | Tap Helm-Valley Nitrogen 70 kV line | 2009-07-01 07:00 | 2009-07-01 07:00 | None | None | None | None
PV-41 | 355 | 2008-04-28 | 2008-04-28 07:00 | WITHDRAWN | 2008-11-20 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | SAN LUIS OBISPO | CA | PGAE | San Luis Obispo-Tremblor 115kV line | 2011-05-01 07:00 | 2011-05-01 07:00 | None | None | None | None
PV-43 | 357 | 2008-04-28 | 2008-04-28 07:00 | WITHDRAWN | 2010-12-07 23:18 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | KERN | CA | PGAE | Midway Substation via Midway-Sunset Gen-Tie 230 kV line | 2010-05-01 07:00 | 2013-12-01 08:00 | None | None | None | None
PV-46 | 358 | 2008-04-30 | 2008-04-30 07:00 | WITHDRAWN | 2008-11-20 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | KERN | CA | PGAE | Midway Sunset via Midway-Sunset Gen-Tie 230 kV line | 2011-05-01 07:00 | 2011-05-01 07:00 | None | None | None | None
SODA MOUNTAIN SOLAR PROJECT | 359 | 2008-05-02 | 2008-05-01 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 350 | 350 |  |  | SAN BERNARDINO | CA | SCE | Eldorado-Baker-Cool Water-Dunn Siding-Mountain Pass 115kV line | 2011-03-01 08:00 | 2011-03-01 08:00 | Required | None | None | None
WILLIAMS ENERGY CENTER | 360 | 2008-05-05 | 2008-05-01 07:00 | WITHDRAWN | 2008-07-11 07:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 200 | 200 |  |  | COLUSA | CA | PGAE | Cortina Substation 230kV Bus | 2012-06-01 07:00 | 2012-06-01 07:00 | None | None | None | None
PVV-K SOLAR I | 361 | 2008-05-02 | 2008-05-02 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 |  |  | RIVERSIDE | CA | SCE | Blythe-Eagle Mountain 161 kV line | 2012-08-30 07:00 | 2012-08-30 07:00 | Required | None | None | None
PVV-M SOLAR I | 362 | 2008-05-02 | 2008-05-02 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 300 | 300 |  |  | RIVERSIDE | CA | SCE | Midpoint Substation | 2012-08-30 07:00 | 2012-08-30 07:00 | Required | None | None | None
PV-47 | 363 | 2008-05-05 | 2008-05-06 07:00 | WITHDRAWN | 2010-07-12 20:11 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 700 | 700 |  |  | KERN | CA | SCE | Windhub Substation 230 kV | 2013-05-01 07:00 | 2011-05-01 07:00 | Waived | None | None | None
PV-48 | 364 | 2008-05-05 | 2008-05-06 07:00 | WITHDRAWN | 2008-11-21 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 700 | 700 |  |  | KERN | CA | SCE | Windhub Substation 230 kV | 2014-05-01 07:00 | 2013-05-01 07:00 | None | None | None | None
DGC KELSO RE 115.5 | 366 | 2008-04-25 | 2008-05-12 07:00 | WITHDRAWN | 2008-10-30 07:00 | Serial LGIP | Generating Facility Type-1: Reciprocating Engine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 115.5 | 115.5 |  |  | ALAMEDA | CA | PGAE | Kelso Substation | 2012-06-01 07:00 | 2012-06-01 07:00 | None | None | None | None
CUYAMA SOLAR I | 367 | 2008-05-12 | 2008-05-12 07:00 | WITHDRAWN | 2008-11-24 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 |  |  | SANTA BARBARA | CA | PGAE | 69kV proximate to the Cuyama Substation | 2009-12-31 08:00 | 2009-12-31 08:00 | None | None | None | None
GOAL LINE | 368 | 2008-05-09 | 2008-05-16 07:00 | WITHDRAWN | 2008-11-20 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 150 | 150 |  |  | SAN DIEGO | CA | SDGE | Escondido Substation 69 kV | 2010-06-01 07:00 | 2010-06-01 07:00 | None | None | None | None
EAGLE MOUNTAIN PUMPED STORAGE PROJECT | 369 | 2008-05-16 | 2008-05-16 07:00 | WITHDRAWN | 2008-10-24 07:00 | Serial LGIP | Generating Facility Type-1: Hydro; Generating Facility Fuel-1: Water; MWs MW-1: 1300 | 1300 |  |  | RIVERSIDE | CA | SCE | Midpoint Substation 500 kV | 2014-06-01 07:00 | 2014-06-01 07:00 | None | None | None | None
SOLANO ENERGY CENTER | 370 | 2008-05-05 | 2008-05-19 07:00 | WITHDRAWN | 2008-11-24 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 390.4 | 390.4 |  |  | SOLANO | CA | PGAE | Lambie-Contra Costa Substation 230 kV bus | 2012-06-01 07:00 | 2012-06-01 07:00 | Required | None | None | None
KES KINGSBURG | 371 | 2008-05-09 | 2008-05-23 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 337.5 | 337.5 |  |  | FRESNO | CA | PGAE | McCall-Kingsburg #1 & #2 115 kV lines | 2010-12-01 08:00 | 2010-12-01 08:00 | None | None | None | None
JACOB CANAL SOLAR FARM | 372 | 2008-05-21 | 2008-05-21 07:00 | WITHDRAWN | 2013-09-10 19:33 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KINGS | CA | PGAE | Jacobs Corner Substation 70kV bus | 2010-11-01 07:00 | 2012-04-02 07:00 | None | Facilities Study | SGIA | NA
ISLAND ENERGY CENTER | 373 | 2008-05-27 | 2008-05-27 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 315 | 315 |  |  | SAN JOAQUIN | CA | PGAE | Loop Tesla Stagg and Tesla-Eight Mile 230 kV lines | 2012-07-01 07:00 | 2012-07-01 07:00 | None | None | None | None
WELLHEAD POWER LOGAN CREEK | 374 | 2008-05-27 | 2008-05-27 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49 | 49 |  |  | GLENN | CA | PGAE | Tap Cottonwood-Logan Creek-Vaca Dixon 230kV line | 2010-06-01 07:00 | 2010-06-01 07:00 | None | None | None | None
CAL-ZEPP 1 | 375 | 2008-05-28 | 2008-05-28 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49.9 | 49.9 |  |  | KERN | CA | PGAE | Famoso Substation | 2011-06-02 07:00 | 2011-06-02 07:00 | None | None | None | None
MOJAVE SOLAR PARK 4 - JOHNSON VALLEY | 376 | 2008-05-28 | 2008-05-28 07:00 | WITHDRAWN | 2008-12-19 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 612 | 612 |  |  | SAN BERNARDINO | CA | SCE | Pisgah-Lugo 230kV Line | 2012-12-01 08:00 | 2012-12-01 08:00 | Waived | None | None | None
EAST ALTAMONT ENERGY CENTER | 377 | 2008-05-28 | 2008-05-28 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 600 | 600 |  |  | ALAMEDA | CA | PGAE | Tracy Substation 230 kV | 2013-05-01 07:00 | 2013-05-01 07:00 | None | None | None | None
SUTTER ENERGY CENTER | 379 | 2008-05-28 | 2008-05-28 07:00 | WITHDRAWN | 2010-12-07 21:18 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 600 | 600 |  |  | SUTTER | CA | PGAE | Table Mountain-Tesla 500kV line | 2012-05-01 07:00 | 2014-01-01 08:00 | None | None | None | None
ARROWHEAD JUNCTION SOLAR PROJECT | 380 | 2008-05-29 | 2008-05-29 07:00 | WITHDRAWN | 2008-11-12 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 145 | 145 |  |  | SAN BERNARDINO | CA | SCE | Lugo-Mohave 500 kV Line | 2013-05-01 07:00 | 2013-05-01 07:00 | None | None | None | None
MCCULLOUGH PASS SOLAR PROJECT | 381 | 2008-05-29 | 2008-05-29 07:00 | WITHDRAWN | 2009-12-07 21:20 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 240 | 240 |  |  | CLARK | NV | SCE | Eldorado Subsation 230kV | 2013-05-01 07:00 | 2013-05-01 07:00 | None | None | None | None
MESQUITE HILLS SOLAR PROJECT | 382 | 2008-05-29 | 2008-05-29 07:00 | WITHDRAWN | 2009-12-07 21:19 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 290 | 290 |  |  | SAN BERNARDINO | CA | SCE | Lugo-Eldorado 500 kV line | 2013-05-01 07:00 | 2013-05-01 07:00 | None | None | None | None
WATSON COGENERATION | 383 | 2008-05-29 | 2008-05-29 07:00 | WITHDRAWN | 2014-11-18 08:00 | TC | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 85 | 85 | Full Capacity |  | LOS ANGELES | CA | SCE | Arco Gen #1 & #2 230kV lines | 2012-05-31 07:00 | 2012-12-01 08:00 | NA | Complete | Complete | NA
CADIZ WEST | 384 | 2008-05-29 | 2008-05-29 07:00 | WITHDRAWN | 2009-11-02 22:10 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 900 | 900 |  |  | SAN BERNARDINO | CA | SCE | Lugo-Mojave 500 kV Line | 2012-02-01 08:00 | 2015-02-01 08:00 | Waived | None | None | None
CADIZ EAST | 385 | 2008-05-29 | 2008-05-29 07:00 | WITHDRAWN | 2009-11-02 22:09 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 600 | 600 |  |  | SAN BERNARDINO | CA | SCE | Lugo-Mojave 500kV Line | 2011-02-01 08:00 | 2014-02-01 08:00 | None | None | None | None
OGILBY | 386 | 2008-05-29 | 2008-05-29 07:00 | WITHDRAWN | 2011-03-22 21:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 600 | 600 |  |  | IMPERIAL | CA | SDGE | New Substation on North Gila-Imperial Valley 500 kV line | 2012-01-01 08:00 | 2014-10-01 07:00 | Waived | None | None | None
LA POSA | 387 | 2008-05-29 | 2008-05-29 07:00 | WITHDRAWN | 2011-03-22 20:58 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 900 | 900 |  |  | LA PAZ | AZ | SCE | Devers-Palo Verde 500 kV Line | 2015-02-01 08:00 | 2015-02-01 08:00 | Waived | None | None | None
RANEGRAS EAGLETAIL | 388 | 2008-05-29 | 2008-05-29 07:00 | WITHDRAWN | 2011-03-22 20:55 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 900 | 900 |  |  | LA PAZ/MARICOPA | AZ | SCE | Devers-Palo Verde 500 kV Line | 2014-06-01 07:00 | 2014-06-01 07:00 | Waived | None | None | None
AZ BIGHORN | 389 | 2008-05-29 | 2008-05-29 07:00 | WITHDRAWN | 2009-12-17 19:14 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 900 | 900 |  |  | MARICOPA | AZ | SCE | Devers-Palo Verde Line 500 kV line | 2015-05-01 07:00 | 2015-05-01 07:00 | None | None | None | None
HYDER | 390 | 2008-05-29 | 2008-05-29 07:00 | WITHDRAWN | 2009-12-17 19:18 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 300 | 300 |  |  | MARICOPA | AZ | SDGE | North Gila-Hassayampa 500 kV line | 2011-05-01 07:00 | 2012-03-01 08:00 | Waived | None | None | None
COSO #1 | 391 | 2010-11-20 | 2008-05-29 07:00 | WITHDRAWN | 2011-02-07 08:00 | TC | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 15 | 15 | Full Capacity |  | INYO | CA | SCE | Kramer Substation 230kV | 2010-01-11 08:00 | 2010-01-11 08:00 | NA | Complete | Complete | NA
COSO #3 | 392 | 2010-11-20 | 2008-05-29 07:00 | WITHDRAWN | 2011-02-07 08:00 | TC | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 15 | 15 | Full Capacity |  | INYO | CA | SCE | BLM Substation 230kV | 2019-03-13 07:00 | 2010-01-11 08:00 | NA | Complete | Complete | NA
COSO #2 | 393 | 2010-11-20 | 2008-05-29 07:00 | WITHDRAWN | 2011-02-07 08:00 | TC | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 15 | 15 | Full Capacity |  | INYO | CA | SCE | Inyokern Substation 115kV | 2011-08-19 07:00 | 2010-01-11 08:00 | NA | Complete | Complete | NA
NYC #1 | 394 | 2010-11-20 | 2008-05-29 07:00 | WITHDRAWN | 2011-02-08 08:00 | TC | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 60.7 | 60.7 | Full Capacity |  | CHURCHILL | NV | SCE | Control Substation 115kV bus | 2012-12-01 08:00 | 2015-12-01 08:00 | NA | Complete | Complete | NA
NYC #2 | 395 | 2008-05-29 | 2008-05-29 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 52.5 | 52.5 |  |  | CHURCHILL | NV | SCE | Bishop Substation | 2012-12-01 08:00 | 2012-12-01 08:00 | None | None | None | None
DIXIE MEADOWS #1 | 396 | 2010-11-20 | 2008-05-29 07:00 | WITHDRAWN | 2011-02-08 08:00 | TC | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 60.7 | 60.7 | Full Capacity |  | CHURCHILL | NV | SCE | Control Substation 115kV bus | 2013-06-01 07:00 | 2016-06-01 07:00 | NA | Complete | Complete | NA
DIXIE MEADOWS #2 | 397 | 2008-05-29 | 2008-05-29 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 52.5 | 52.5 |  |  | CHURCHILL | NV | SCE | Bishop Substation | 2013-06-01 07:00 | 2013-06-01 07:00 | None | None | None | None
TGDV #1 | 398 | 2010-11-20 | 2008-05-29 07:00 | WITHDRAWN | 2011-02-08 08:00 | TC | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 60.7 | 60.7 | Full Capacity |  | CHURCHILL | NV | SCE | Control Substation 115kV bus | 2012-06-01 07:00 | 2012-06-01 07:00 | NA | Complete | Complete | NA
TGDV#2 | 399 | 2010-11-20 | 2008-05-29 07:00 | WITHDRAWN | 2011-03-22 20:13 | TC | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 60.7 | 60.7 | Full Capacity |  | CHURCHILL | NV | SCE | Control Substation 115kV bus | 2012-06-01 07:00 | 2013-06-01 07:00 | NA | None | None | NA
PV-49 | 400 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-07-22 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 700 | 700 |  |  | KERN | CA | SCE | Windhub Substation | 2011-05-01 07:00 | 2011-05-01 07:00 | None | None | None | None
D TRAIN | 401 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-07-28 07:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49.85 | 49.85 |  |  | LOS ANGELES | CA | SCE | ChevGen Substation | 2010-09-01 07:00 | 2010-09-01 07:00 | None | None | None | None
LA PALOMA II | 402 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-08-19 07:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 600 | 600 |  |  | KERN | CA | PGAE | Midway Substation 230kV line | 2012-06-01 07:00 | 2012-06-01 07:00 | None | None | None | None
SUNGEN 1 | 403 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2010-12-07 20:55 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 30 | 30 |  |  | KERN | CA | PGAE | Midway Substation 230 kV Bus | 2012-06-01 07:00 | 2011-12-31 08:00 | None | None | None | None
LA PALOMA PEAKING | 404 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-08-19 07:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 450 | 450 |  |  | KERN | CA | PGAE | Midway Substation 230kV line | 2011-06-01 07:00 | 2011-06-01 07:00 | None | None | None | None
YUHA BASIN HYBRID SOLAR ENERGY PROJECT | 405 | 2008-05-15 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 450 | 450 |  |  | IMPERIAL | CA | SDGE | Imperial Valley Substation | 2012-12-31 08:00 | 2012-12-31 08:00 | Waived | None | None | None
MILAGRO WIND | 406 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 130 | 130 |  |  | SAN DIEGO | CA | SDGE | Boulevard Substation | 2011-06-01 07:00 | 2011-06-01 07:00 | Waived | None | None | None
RED MOUNTAIN RIDGE | 409 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2012-04-24 23:11 | TC | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 150 | 150 | Energy Only |  | KERN | CA | SCE | Highwind Substation 230kV | 2011-10-01 07:00 | 2012-12-31 08:00 | NA | Complete | Complete | NA
MIDPOINT SOLAR 1 | 410 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 49.5 | 49.5 |  |  | RIVERSIDE | CA | SCE | Midpoint Substation 500kV | 2012-08-01 07:00 | 2012-08-01 07:00 | None | None | None | None
MIDPOINT SOLAR 2 | 411 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 49.5 | 49.5 |  |  | RIVERSIDE | CA | SCE | Midpoint Substation 500 kV | 2012-08-01 07:00 | 2012-08-01 07:00 | None | None | None | None
LUDLOW SOLAR 1 | 413 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-21 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 280 | 280 |  |  | SAN BERNARDINO | CA | SCE | Pisgah Substation 230 kV | 2012-08-01 07:00 | 2012-08-01 07:00 | None | None | None | None
IMPERIAL SOLAR 1 | 414 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-21 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 280 | 280 |  |  | IMPERIAL | CA | SDGE | Imperial Valley Substation 230kV bus | 2012-07-01 07:00 | 2012-07-01 07:00 | None | None | None | None
PALEN VALLEY SOLAR 1 | 415 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-21 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 280 | 280 |  |  | RIVERSIDE | CA | SCE | Devers-Palo Verde 500 kV Line | 2012-08-01 07:00 | 2012-08-01 07:00 | None | None | None | None
MCCOY SOLAR 1 | 416 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-21 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 280 | 280 |  |  | RIVERSIDE | CA | SCE | Midpoint Substation 230 kV | 2012-08-01 07:00 | 2012-08-01 07:00 | None | None | None | None
TRES VAQUEROS WIND FARM | 417 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2013-12-04 08:00 | TC | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 14 | 14 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Pittsburg-Tesla 230kV line | 2010-09-30 07:00 | 2015-05-30 07:00 | NA | Complete | Complete | NA
PATTERSON PASS GT PROJECT | 418 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 400 | 400 |  |  | SAN JOAQUIN | CA | PGAE | Tesla Substation 230 KV bus | 2012-11-01 07:00 | 2012-11-01 07:00 | None | None | None | None
WEST VALLEY ENERGY CENTER | 419 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 188 | 188 |  |  | FRESNO | CA | PGAE | Panoche Substation 230kV Bus | 2011-03-01 08:00 | 2011-03-01 08:00 | None | None | None | None
BORREGO SOLAR 2 | 420 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2009-12-11 18:06 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 49.5 | 49.5 |  |  | SAN DIEGO | CA | SDGE | Borrego Substation 69kV | 2013-02-01 08:00 | 2013-02-01 08:00 | None | None | None | None
IRON MOUNTAIN SOLAR 1 | 422 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 49.5 | 49.5 |  |  | RIVERSIDE | CA | SCE | Camino-Iron Mountain 230kV line | 2012-02-01 08:00 | 2012-02-01 08:00 | None | None | None | None
IRON MOUNTAIN SOLAR 2 | 423 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 49.5 | 49.5 |  |  | RIVERSIDE | CA | SCE | Camino-Iron Mountain 230kV line | 2012-02-01 08:00 | 2012-02-01 08:00 | None | None | None | None
AJ SOLAR ENERGY | 424 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 |  |  | SAN BERNARDINO | CA | SCE | Mohave switchyard | 2014-07-01 07:00 | 2014-07-01 07:00 | Waived | None | None | None
COLORADO RIVER ENERGY 2 | 425 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 |  |  | RIVERSIDE | CA | SCE | Colorado River Substation | 2014-07-01 07:00 | 2014-07-01 07:00 | Waived | None | None | None
CAMPOS SOLAR ENERGY | 426 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 |  |  | CLARK | NV | SCE | Mohave Switchyard | 2014-07-01 07:00 | 2014-07-01 07:00 | None | None | None | None
CANTIL SOLAR ENERGY | 427 | 2008-04-30 | 2008-05-30 07:00 | WITHDRAWN | 2009-12-17 19:14 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 |  |  | KERN | CA | SCE | Antelope Substation | 2014-07-01 07:00 | 2014-07-01 07:00 | Waived | None | None | None
DC SOLAR ENERGY | 428 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 |  |  | SAN BERNARDINO | CA | SCE | Eagle Mountain Substation | 2014-07-01 07:00 | 2014-07-01 07:00 | Waived | None | None | None
RANDSBURG SOLAR ENERGY | 430 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2011-03-22 17:02 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 |  |  | KERN | CA | SCE | Kramer Substation | 2014-07-01 07:00 | 2014-07-01 07:00 | Waived | None | None | None
RICE SOLAR ENERGY | 431 | 2010-11-20 | 2008-05-30 07:00 | WITHDRAWN | 2011-01-07 08:00 | TC | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | RIVERSIDE | CA | SCE | Midpoint Substation 220kV | 2014-07-01 07:00 | 2014-07-01 07:00 | NA | Complete | Complete | NA
WARD VALLEY SOLAR ENERGY 1 | 432 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2011-04-21 16:17 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 |  |  | RIVERSIDE | CA | SCE | Colorado River Substation 230 kV | 2014-07-01 07:00 | 2014-07-01 07:00 | Waived | None | None | None
WARD VALLEY SOLAR ENERGY 2 | 433 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 |  |  | SAN BERNARDINO | CA | SCE | Iron Mountain Substation | 2015-05-29 07:00 | 2015-05-29 07:00 | Waived | None | None | None
WARD VALLEY SOLAR ENERGY 3 | 434 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 500 | 500 |  |  | SAN BERNARDINO | CA | SCE | Mohave switchyard | 2015-05-29 07:00 | 2015-05-29 07:00 | None | None | None | None
QUARTZSITE SOLAR ENERGY | 435 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2011-04-21 16:18 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 |  |  | LA PAZ | AZ | SCE | Palo Verde Devers #2 line | 2014-07-01 07:00 | 2014-07-01 07:00 | Waived | None | None | None
CALIENTE SOLAR ENERGY | 436 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 |  |  | MARICOPA | AZ | SCE | Palo Verde Devers #2 line | 2014-07-01 07:00 | 2014-07-01 07:00 | Waived | None | None | None
ROUND MOUNTAIN WIND PROJECT | 437 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-10-24 07:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 350 | 350 |  |  | SHASTA | CA | PGAE | Pit #3 Round Mountain 230kV line | 2011-06-01 07:00 | 2011-06-01 07:00 | None | None | None | None
AVALON II | 438 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 500 | 500 |  |  | KERN | CA | SCE | Windhub Substation | 2011-12-31 08:00 | 2011-12-31 08:00 | None | None | None | None
BLYTHE SOLEIL | 439 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 500 | 500 |  |  | RIVERSIDE | CA | SCE | Midpoint Substation | 2011-12-31 08:00 | 2011-12-31 08:00 | Waived | None | None | None
MOJAVE SOLEIL II | 440 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 500 | 500 |  |  | KERN | CA | SCE | Whirlwind Substation | 2011-12-31 08:00 | 2011-12-31 08:00 | Waived | None | None | None
BINKLEY POWER PROJECT | 441 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 50 | 50 |  |  | LAKE | CA | PGAE | Geyers 17- Fulton #2 230kV line | 2012-07-31 07:00 | 2012-07-31 07:00 | None | None | None | None
WELLHEAD POWER RAINBOW | 443 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49 | 49 |  |  | SAN DIEGO | CA | SDGE | Telega - Escondido 230kV Line | 2009-07-01 07:00 | 2009-07-01 07:00 | Waived | None | None | None
WELLHEAD POWER LILAC | 444 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49 | 49 |  |  | SAN DIEGO | CA | SDGE | Lilac Rincon 69kV | 2009-07-01 07:00 | 2009-07-01 07:00 | Waived | None | None | None
WELLHEAD POWER COUSER CANYON | 445 | 2008-06-07 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49 | 49 |  |  | SAN DIEGO | CA | SDGE | Pala - lilac 69kV line | 2009-07-01 07:00 | 2009-07-01 07:00 | Waived | None | None | None
WELLHEAD POWER CLEMENTE | 446 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49 | 49 |  |  | ORANGE | CA | SDGE | Talega San Mateo 69kV line | 2009-07-01 07:00 | 2009-07-01 07:00 | Waived | None | None | None |  | None
WELLHEAD POWER ASH VALLEY | 447 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49 | 49 |  |  | SAN DIEGO | CA | SDGE | Ash - Valley Center 69kV line | 2009-07-01 07:00 | 2009-07-01 07:00 | Waived | None | None | None
WELLHEAD POWER LONESTAR | 448 | 2008-06-07 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49 | 49 |  |  | SAN DIEGO | CA | SDGE | Border Substation 69 kV | 2009-07-01 07:00 | 2009-07-01 07:00 | Waived | None | None | None
BIG MARIA VISTA SOLAR GENERATING STATION | 449 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-12-19 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 |  |  | RIVERSIDE | CA | SCE | Midpoint Substation 500 kV | 2012-07-01 07:00 | 2012-07-01 07:00 | None | None | None | None
ALTA 12 | 450 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 1150 | 1150 |  |  | LOS ANGELES/KERN | CA | SCE | Whirlwind Substation 230 kV | 2013-05-30 07:00 | 2013-05-30 07:00 | None | None | None | None
ALTA 13 | 451 | 2008-05-30 | 2008-05-30 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 1150 | 1150 |  |  | SAN BERNARDINO | CA | SCE | Pisgah Substation 230 kV | 2013-05-30 07:00 | 2013-05-30 07:00 | None | None | None | None
FAIRFIELD ENERGY CENTER - 730 MW | 452 | 2008-06-02 | 2008-06-02 07:00 | WITHDRAWN | 2008-11-24 08:00 | Serial LGIP | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 730 | 730 |  |  | SOLANO | CA | PGAE | Loop Lakesville-Sobrante and Lakesville-Ignacio 230kV Lines | 2012-06-15 07:00 | 2012-06-15 07:00 | None | None | None | None
PARKER SOLAR ENERGY | 453 | 2008-06-02 | 2008-06-02 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 |  |  | LA PAZ | AZ | SCE | Mohave Switchyard | 2014-07-01 07:00 | 2014-07-01 07:00 | None | None | None | None
SONORA SOLAR GENERATING STATION | 454 | 2008-05-30 | 2008-06-02 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 84 | 84 |  |  | IMPERIAL | CA | SDGE | Imperial Valley Substation 230 kV | 2011-02-01 08:00 | 2011-02-01 08:00 | Waived | None | None | None
FAIRMONT SOLAR GENERATING STATION | 455 | 2008-05-30 | 2008-06-02 07:00 | WITHDRAWN | 2011-03-22 14:32 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 141 | 141 |  |  | LOS ANGELES | CA | SCE | Whirlwind Substation 230 kV | 2013-10-01 07:00 | 2013-10-01 07:00 | Waived | None | None | None |  | None
CLEARWATER SOLAR GENERATING STATION | 456 | 2008-05-30 | 2008-06-02 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 840 | 840 |  |  | LOS ANGELES | CA | SCE | Vincent Substation | 2014-09-01 07:00 | 2014-09-01 07:00 | None | None | None | None
VICTOR SOLAR I | 457 | 2008-06-02 | 2008-06-02 07:00 | WITHDRAWN | 2008-11-26 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 55 | 55 |  |  | RIVERSIDE | CA | SCE | Victor substation 115kV | 2010-06-15 07:00 | 2010-06-15 07:00 | Waived | None | None | None
ROSAMOND SOLAR I | 458 | 2008-06-02 | 2008-06-02 07:00 | WITHDRAWN | 2008-08-01 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 |  |  | RIVERSIDE | CA | SCE | Antelope Cal Cement 60kV line | 2010-06-15 07:00 | 2010-06-15 07:00 | None | None | None | None
CAMERON SOLAR I | 459 | 2008-06-02 | 2008-06-02 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 |  |  | SAN DIEGO | CA | SDGE | Cameron Substation 69 kV | 2009-12-15 08:00 | 2009-12-15 08:00 | Waived | None | None | None
INYOKERN SOLAR I | 460 | 2008-06-02 | 2008-06-02 07:00 | WITHDRAWN | 2008-09-10 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 40 | 40 |  |  | KERN | CA | SCE | Inyokern Substation115 kV bus | 2010-12-01 08:00 | 2010-12-01 08:00 | None | None | None | None
DUNN SIDING SOLAR I | 461 | 2008-06-02 | 2008-06-02 07:00 | WITHDRAWN | 2008-09-10 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 40 | 40 |  |  | SAN BERNARDINO | CA | SCE | Dunn Siding Cool Water 115 kV Line | 2010-12-01 08:00 | 2010-12-01 08:00 | None | None | None | None
GREENLIGHT SOLAR I | 462 | 2008-06-02 | 2008-06-02 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 58.8 | 58.8 |  |  | SAN DIEGO | CA | SDGE | Borrego Substation 69 kV | 2010-06-15 07:00 | 2010-06-15 07:00 | Waived | None | None | None
WARNER SOLAR I | 463 | 2008-06-02 | 2008-06-02 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 58.8 | 58.8 |  |  | SAN DIEGO | CA | SDGE | Warner Substation 69 kV | 2010-06-30 07:00 | 2010-06-30 07:00 | Waived | None | None | None
REDMAN SOLAR I | 464 | 2008-06-02 | 2008-06-02 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 40 | 40 |  |  | KERN | CA | SCE | Redman Substation 69 kV bus | 2010-12-01 08:00 | 2010-12-01 08:00 | None | None | None | None
LITTLE ROCK SOLAR I | 465 | 2008-06-02 | 2008-06-02 07:00 | WITHDRAWN | 2008-11-25 08:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 40 | 40 |  |  | KERN | CA | SCE | Little Rock Substation 69 kV bus | 2010-12-01 08:00 | 2010-12-01 08:00 | None | None | None | None
BAKER SOLAR I | 466 | 2008-06-02 | 2008-06-02 07:00 | WITHDRAWN | 2008-08-01 07:00 | Serial LGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 |  |  | RIVERSIDE | CA | SCE | Baker Substation 115kV | 2010-06-15 07:00 | 2010-06-15 07:00 | None | None | None | None
RENEGY IONE | 469 | 2010-12-01 | 2008-07-14 07:00 | WITHDRAWN | 2008-11-18 08:00 | SGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 16.3 | 16.3 | Energy Only |  | AMADOR | CA | PGAE | Valley Springs Martel #2 60kV line | 2008-12-31 08:00 | 2008-12-31 08:00 | None | None | None | NA
LAUREL WEST SOLAR FARM | 470 | 2008-07-30 | 2008-07-30 07:00 | WITHDRAWN | 2013-09-10 19:31 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KINGS | CA | PGAE | Jacobs Corner Substation 70kV bus | 2011-03-01 08:00 | 2012-05-01 07:00 | None | Facilities Study | SGIA | NA
LAUREL EAST SOLAR FARM | 471 | 2008-07-30 | 2008-07-30 07:00 | WITHDRAWN | 2013-09-10 19:30 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KINGS | CA | PGAE | Jacobs Corner Substation 70kV bus | 2011-07-01 07:00 | 2012-06-01 07:00 | None | Facilities Study | SGIA | NA
AFTON CANYON PV | 474 | 2008-09-11 | 2008-09-15 07:00 | WITHDRAWN | 2011-08-26 07:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 19.9 | 19.9 | Energy Only |  | SAN BERNARDINO | CA | SCE | Dunn Siding Substation | 2011-06-01 07:00 | 2011-06-01 07:00 | None | Facilities Study | None | NA
PAINTED HILLS IV | 475 | 2010-12-01 | 2008-10-08 07:00 | WITHDRAWN | 2009-10-26 07:00 | SGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 20 | 20 | Energy Only |  | RIVERSIDE | CA | SCE | Devers-Garnet-Venwind 115 kV line | 2009-12-01 08:00 | 2010-12-01 08:00 | None | None | None | NA
REDWOOD LANDFILL | 476 | 2008-10-23 | 2008-10-23 07:00 | WITHDRAWN | 2014-05-29 21:06 | SGIP | Generating Facility Type-1: Reciprocating Engine; Generating Facility Fuel-1: Biofuel; MWs MW-1: 9.9 | 9.9 | Energy Only |  | MARIN | CA | PGAE | Lakeville #2 60 kV line | 2010-05-29 07:00 | 2014-07-15 07:00 | None | Facilities Study | SGIA | NA
20 MW SOLAR PROJECT #1 | 480 | 2009-03-16 | 2009-03-16 07:00 | WITHDRAWN | 2013-06-12 16:32 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | SAN DIEGO | CA | SDGE | Borrego Substation 69kV | 2010-12-31 08:00 | 2014-06-30 07:00 | None | Facilities Study | SGIA | NA
GE TEHACHAPI SOLAR PROJECT | 483 | 2009-04-29 | 2009-04-29 07:00 | WITHDRAWN | 2011-08-18 17:45 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 10 | 10 | Energy Only |  | KERN | CA | SCE | Vincent Substation | 2010-06-01 07:00 | 2010-06-01 07:00 | None | None | None | NA
FULL CIRCLE | 485 | 2011-03-16 | 2009-06-18 07:00 | WITHDRAWN | 2011-08-24 07:00 | SGIP-TC | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | SCE | Winhub 230 KV via Highwind 66 KV | 2012-12-15 08:00 | 2012-12-15 08:00 | NA | None | None | NA
RUBY SOLAR PROJECT | 486 | 2009-06-29 | 2009-06-29 07:00 | WITHDRAWN | 2012-07-18 16:58 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KERN | CA | SCE | Antelope-Neenach 66kV line | 2012-01-01 08:00 | 2013-11-01 07:00 | System Impact Study | Facilities Study | SGIA | NA
MARICOPA SOLAR | 487 | 2010-11-20 | 2009-07-31 07:00 | WITHDRAWN | 2010-10-15 07:00 | C01 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 600 | 600 | Full Capacity |  | KERN | CA | PGAE | Midway-Wheeler Ridge 230kV double circuit line | 2015-12-01 08:00 | 2015-12-01 08:00 | NA | None | None | NA
NEVADA SOLAR II (NS2) | 488 | 2009-04-06 | 2009-07-31 07:00 | WITHDRAWN | 2012-01-10 08:00 | C01 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 92 | 92 | Full Capacity |  | CLARK | NV | SCE | Eldorado Substation 230kV | 2012-09-30 07:00 | 2012-09-30 07:00 | NA | Complete | Complete | NA
MONTEZUMA II EXPANSION | 489 | 2009-05-26 | 2009-07-31 07:00 | WITHDRAWN | 2012-02-24 00:42 | C01 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 98.9 | 98.9 | Full Capacity |  | SOLANO | CA | PGAE | Birds Landing Substation 230kV | 2011-05-31 07:00 | 2014-05-31 07:00 | NA | Complete | None | NA
SONGS HIGH PRESSURE TURBINE RETROFIT | 490 | 2009-06-03 | 2009-07-31 07:00 | WITHDRAWN | 2013-12-17 08:00 | C01 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Nuclear; MWs MW-1: 48 | 48 | Full Capacity |  | SAN DIEGO | CA | SCE | San Onofre Nuclear Generating Station 230kV switchyard | 2012-12-31 08:00 | 2012-12-31 08:00 | NA | Complete | Complete | NA
RIVER BLUFF SOLAR ENERGY PARK | 491 | 2009-06-04 | 2009-07-31 07:00 | WITHDRAWN | 2011-12-14 08:00 | C01 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 230 | 230 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Coolwater-Dunn Siding 115kV line | 2014-06-01 07:00 | 2014-04-01 07:00 | NA | Complete | Complete | NA
WEST MOJAVE ENERGY | 492 | 2010-11-20 | 2009-07-31 07:00 | WITHDRAWN | 2009-11-02 08:00 | C01 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 350 | 350 | Full Capacity |  | KERN | CA | SCE | Windhub Substation 230kV | 2015-12-01 08:00 | 2015-12-01 08:00 | NA | None | None | NA
ORO VERDE SOLAR PROJECT (FKA GATEWAY SOLAR ENERGY PROJECT) | 494 | 2009-07-20 | 2009-07-31 07:00 | WITHDRAWN | 2015-01-13 08:00 | C01 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | KERN | CA | SCE | Windhub Substation 230kV | 2015-12-01 08:00 | 2016-10-01 07:00 | NA | Complete | Complete | NA
JEEP WRANGLER | 496 | 2009-08-04 | 2009-07-31 07:00 | WITHDRAWN | 2010-10-01 07:00 | Serial LGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 960 | 960 |  |  | YUMA | AZ | SDGE | 500 kV collector station 40 mi east of NGila sub and 4.5 mi w of proposed Agua Caliente sub | 2014-01-01 08:00 | 2014-01-01 08:00 | None | None | None | None
IVANPAH 1- EXPANSION | 497 | 2010-11-20 | 2009-07-31 07:00 | WITHDRAWN | 2010-11-20 00:23 | C01 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 6 | 6 | Full Capacity |  | SAN BERNARDINO | CA | SCE | New Ivanpah Substation 115kV | 2012-03-31 07:00 | 2012-03-31 07:00 | NA | None | None | NA
IVANPAH 2 - EXPANSION | 498 | 2010-11-20 | 2009-07-31 07:00 | WITHDRAWN | 2010-11-20 00:23 | C01 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | SAN BERNARDINO | CA | SCE | New Ivanpah Substation 115kV | 2012-09-30 07:00 | 2012-09-30 07:00 | NA | None | None | NA
IVANPAH SEGS 3 - EXPANSION | 499 | 2010-11-20 | 2009-07-31 07:00 | WITHDRAWN | 2010-07-12 07:00 | C01 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 40 | 40 | Full Capacity |  | SAN BERNARDINO | CA | SCE | New Ivanpah Substation 115kV | 2013-03-31 07:00 | 2013-03-31 07:00 | NA | None | None | NA
COYOTE SPRINGS | 500 | 2010-11-20 | 2009-07-31 07:00 | WITHDRAWN | 2011-03-16 19:20 | C01 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 960 | 960 | Full Capacity |  | LINCOLN | NV | SCE | Eldorado Substation 500kV | 2014-01-01 08:00 | 2015-01-01 08:00 | NA | None | None | NA
PALOMAS SOLAR | 501 | 2010-11-20 | 2009-07-31 07:00 | WITHDRAWN | 2010-09-30 07:00 | C01 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 750 | 750 | Full Capacity |  | YUMA | AZ | SDGE | Hassayampa-North Gila 500kV switching station | 2015-06-30 07:00 | 2015-06-30 07:00 | NA | Complete | None | NA
CITY OF VERNON RENEWABLE PROJECT 1 | 504 | 2009-09-21 | 2009-07-31 07:00 | WITHDRAWN | 2009-11-02 22:13 | Serial LGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 688 | 688 |  |  | KERN | CA | SCE | Highwind Substation 230kV bus | 2013-03-11 07:00 | 2013-03-11 07:00 | None | None | None | None
CITY OF VERNON RENEWABLE PROJECT 2 | 505 | 2010-11-20 | 2009-07-31 07:00 | WITHDRAWN | 2010-11-19 08:00 | C01 | Photovoltaic | Wind Turbine |  | Solar | Wind Turbine |  | 975 | 125 |  | 1100 | Full Capacity |  | KERN | CA | SCE | Highwind-Windhub 230kV line | 2012-11-30 08:00 | 2012-11-30 08:00 | NA | None | None | NA
CONTRA COSTA GENERATING STATION EXPANSION | 507 | 2010-12-01 | 2009-07-31 07:00 | WITHDRAWN | 2009-12-04 08:00 | C01 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 131 | 131 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Contra Costa Substation 230kV bus | 2013-12-01 08:00 | 2017-12-31 08:00 | NA | None | None | NA
ALGONQUIN POWER SANGER (OLD) | 508 | 2010-11-20 | 2009-07-31 07:00 | WITHDRAWN | 2010-10-15 07:00 | C01 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 58.3 | 58.3 | Full Capacity |  | FRESNO | CA | PGAE | Sanger-Reedley 115kV line | 2011-03-15 07:00 | 2011-03-15 07:00 | NA | Complete | None | NA
FALLBROOK ROSAMOND SUNTOWER | 511 | 2010-11-20 | 2009-07-31 07:00 | WITHDRAWN | 2009-11-30 08:00 | C01 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 92.6 | 92.6 | Full Capacity |  | KERN | CA | SCE | Goldtown-Lancaster 66kV line | 2012-12-31 08:00 | 2012-12-31 08:00 | NA | None | None | NA
ALPINE SUNTOWER GENERATION STATION | 512 | 2009-07-31 | 2009-07-31 07:00 | WITHDRAWN | 2015-11-05 08:00 | C01 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 2 | 2 | Full Capacity |  | LOS ANGELES | CA | SCE | Neenach Substation 66kV | 2012-02-15 08:00 | 2020-10-01 07:00 | NA | Complete | Complete | NA
DESERT VIEW SUNTOWER | 513 | 2009-07-31 | 2009-07-31 07:00 | WITHDRAWN | 2015-11-05 08:00 | C01 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 141 | 141 | Full Capacity |  | LOS ANGELES | CA | SCE | Whirlwind Substation 230kV | 2013-08-01 07:00 | 2017-12-31 08:00 | NA | Complete | Complete | NA
WELLHEAD POWER OTAY MESA | 513A | 2009-07-31 | 2009-07-31 07:00 | WITHDRAWN | 2009-11-02 22:11 | Serial LGIP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 190 | 190 |  |  | SAN DIEGO | CA | SDGE | Otay Mesa Energy Center Substation 230 kV | 2013-05-01 07:00 | 2013-05-01 07:00 | Waived | None | None | None
ARCO SOLAR 1 PROJECT | 514 | 2009-07-31 | 2009-07-31 07:00 | WITHDRAWN | 2014-09-26 20:53 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KERN | CA | PGAE | Arco Substation 69kV bus | 2010-12-15 08:00 | 2016-10-30 07:00 | None | Facilities Study | SGIA | NA
KJ SOLAR ENERGY CENTER | 515 | 2009-08-12 | 2009-08-12 07:00 | WITHDRAWN | 2011-10-07 07:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | SCE | Kramer-Ransburg 115kV line | 2011-04-01 07:00 | 2012-04-01 07:00 | NA | None | None | NA
FRV PEGASUS SOLAR PROJECT | 516 | 2010-12-01 | 2009-08-21 07:00 | WITHDRAWN | 2010-05-25 07:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | SAN DIEGO | CA | SDGE | Borrego Substation 69kV | 2011-01-01 08:00 | 2011-01-01 08:00 | None | None | None | NA
OLD RIVER 2 | 518 | 2009-08-19 | 2009-08-19 07:00 | WITHDRAWN | 2010-06-07 07:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KERN | CA | PGAE | Kern Old River #2 70kV line | 2014-12-31 08:00 | 2014-12-31 08:00 | None | None | None | NA
ACACIA | 519 | 2009-08-19 | 2009-08-19 07:00 | WITHDRAWN | 2011-07-01 16:32 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KERN | CA | PGAE | Elk Hills Taft 70kV line | 2014-12-31 08:00 | 2014-12-31 08:00 | None | None | None | NA
BLACKWELL SOLAR 1 | 520 | 2009-08-19 | 2009-08-19 07:00 | WITHDRAWN | 2010-06-23 07:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KERN | CA | PGAE | Blackwell-Carneras 70kV line | 2014-12-31 08:00 | 2014-12-31 08:00 | None | None | None | NA
TEHACHAPI SOLAR | 522C | 2009-08-19 | 2009-08-19 07:00 | WITHDRAWN | 2012-05-01 20:26 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KERN | CA | SCE | Kern River-Cummings 66kV line | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
KINGSOLAR (FKA QUAY VALLEY 20MW SOLAR PV) | 523 | 2009-08-21 | 2009-08-21 07:00 | WITHDRAWN | 2012-07-31 07:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KINGS | CA | PGAE | Arco Substation 70kV bus | 2011-10-30 07:00 | 2013-06-30 07:00 | None | Facilities Study | SGIA | NA
SANBORN SOLAR | 523A | 2010-11-20 | 2009-08-26 07:00 | WITHDRAWN | 2011-01-24 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 19.9 | 19.9 | Energy Only |  | KERN | CA | SCE | Goldtown-Corum 66kV line | 2010-12-31 08:00 | 2010-12-31 08:00 | None | None | None | NA
LUCERNE SOLAR ENERGY CENTER | 524 | 2010-11-20 | 2009-09-02 07:00 | WITHDRAWN | 2010-12-15 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | SAN BERNARDINO | CA | SCE | Eldorado-Pisgah #2 230kV line | 2011-12-01 08:00 | 2011-12-01 08:00 | None | None | None | NA |  | None
WAGON WHEEL MT. SOLAR 1 | 525 | 2010-11-30 | 2009-09-11 07:00 | WITHDRAWN | 2010-11-30 22:45 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KERN | CA | PGAE | Arco Caneras 70kV line | 2011-04-30 07:00 | 2010-12-31 08:00 | None | None | None | NA
INYOKERN POWER PLANT | 527 | 2010-11-20 | 2009-09-23 07:00 | WITHDRAWN | 2010-07-06 07:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | INYO | CA | SCE | Control-Haiwee-Inyokern #2 115kV line | 2011-06-01 07:00 | 2011-06-01 07:00 | None | None | None | NA
PREMIER POWER RUSSELL SOLAR | 528 | 2009-10-05 | 2009-10-05 07:00 | WITHDRAWN | 2010-01-20 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | SOLANO | CA | PGAE | Birds Landing Substation 230kV bus | 2011-06-01 07:00 | 2011-06-01 07:00 | None | None | None | NA
WELLHEAD RENEWABLES FRESNO | 529A | 2009-10-23 | 2009-10-23 07:00 | WITHDRAWN | 2014-10-13 21:56 | SGIP | Generating Facility Type-1: Reciprocating Engine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 14.5 | 14.5 | Energy Only |  | FRESNO | CA | PGAE | Helm-Kerman 70kV line | 2011-04-01 07:00 | 2014-06-15 07:00 | System Impact Study | Facilities Study | SGIA | NA
ANGIOLA WATER DISTRICT SOLAR PROJECT | 530 | 2009-10-29 | 2009-10-29 07:00 | WITHDRAWN | 2011-11-08 18:08 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | TULARE | CA | PGAE | Alpaugh 115kV substation | 2011-07-01 07:00 | 2011-07-01 07:00 | None | Facilities Study | SGIA | NA
WHITE RANCH DISTRICT SOLAR PROJECT | 531 | 2011-03-16 | 2009-10-29 07:00 | WITHDRAWN | 2010-01-29 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 16 | 16 | Energy Only |  | TULARE | CA | PGAE | Corcoran Smyrna 115 kV line | 2011-07-01 07:00 | 2011-07-01 07:00 | None | None | None | NA
CANAL POWER PLANT | 531B | 2010-11-20 | 2009-10-29 07:00 | WITHDRAWN | 2011-01-23 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | LOS ANGELES | CA | SCE | Neenach Substation 69kV | 2011-06-01 07:00 | 2011-06-01 07:00 | None | None | None | NA
BUTTONWOOD SOLAR | 533 | 2009-11-11 | 2009-11-11 08:00 | WITHDRAWN | 2010-04-19 07:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KERN | CA | PGAE | Semitropic Midway #2 115kV line | 2012-01-01 08:00 | 2012-01-01 08:00 | None | None | None | NA
PANOCHE VALLEY SOLAR FARM | 534 | 2009-08-04 | 2009-11-13 08:00 | WITHDRAWN | 2011-04-25 07:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | SAN BENITO | CA | PGAE | Moss Landing-Panoche #2 230kV line | 2011-06-30 07:00 | 2011-06-30 07:00 | None | Facilities Study | None | NA
FRV ALDEBARAN SOLAR | 536 | 2010-11-30 | 2009-11-19 08:00 | WITHDRAWN | 2010-03-04 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | MERCED | CA | PGAE | Mercy Springs 70kV Line | 2011-12-31 08:00 | 2011-12-31 08:00 | None | None | None | NA
CLEARVISTA ENERGY | 537A | 2010-11-23 | 2009-11-23 08:00 | WITHDRAWN | 2014-06-09 14:40 | SGIP | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 19.5 | 19.5 | Energy Only |  | KERN | CA | SCE | Highwind Substation 220kV bus | 2011-04-01 07:00 | 2015-07-01 07:00 | None | Facilities Study | SGIA | NA
HUDSON SOLAR | 538 | 2009-12-16 | 2009-12-16 08:00 | WITHDRAWN | 2011-06-15 07:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | FRESNO | CA | PGAE | Oro Loma-Mendota 69kV line | 2012-01-01 08:00 | 2012-01-01 08:00 | None | None | None | NA
BLUE DIAMOND SOLAR | 540 | 2009-12-22 | 2009-12-22 08:00 | WITHDRAWN | 2013-05-07 16:28 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | LOS ANGELES | CA | SCE | Little Rock-Piute 69kV line | 2012-05-01 07:00 | 2015-06-30 07:00 | None | Facilities Study | SGIA | NA
BRANNON SOLAR | 541 | 2010-01-05 | 2010-01-05 08:00 | WITHDRAWN | 2014-09-09 07:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | FRESNO | CA | PGAE | Panoche-Oro Loma 115kV Line | 2012-01-03 08:00 | 2016-03-31 07:00 | NA | Complete | Complete | NA
SUNSHINE TWO | 541A | 2010-11-20 | 2010-01-05 08:00 | WITHDRAWN | 2011-01-18 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | LOS ANGELES | CA | SCE | Antelope-Neenach 66kV | 2011-06-01 07:00 | 2011-06-01 07:00 | None | None | None | NA
SUNSHINE FOUR | 541B | 2010-11-20 | 2010-01-05 08:00 | WITHDRAWN | 2010-12-27 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | LOS ANGELES | CA | SCE | Antelope-Neenach 66kV | 2011-06-01 07:00 | 2011-06-01 07:00 | None | None | None | NA
EXCELSIOR SOLAR | 542 | 2010-01-06 | 2010-01-06 08:00 | WITHDRAWN | 2013-10-30 15:50 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | FRESNO | CA | PGAE | Schindler Sub 115kV bus | 2012-01-01 08:00 | 2016-12-01 08:00 | None | Facilities Study | SGIA | NA
SCHINDLER SOUTH SOLAR | 543 | 2010-01-06 | 2010-01-06 08:00 | WITHDRAWN | 2011-08-18 07:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | FRESNO | CA | PGAE | Schindler Sub 70kV bus | 2012-01-01 08:00 | 2012-01-01 08:00 | None | None | None | NA
FRV CYGNUS SOLAR | 544 | 2010-01-06 | 2010-01-06 08:00 | WITHDRAWN | 2010-04-19 07:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KERN | CA | PGAE | Lamont Substation 115kV bus | 2011-10-31 07:00 | 2011-10-31 07:00 | None | None | None | NA
FRV CENTAURI SOLAR | 545 | 2010-01-06 | 2010-01-06 08:00 | WITHDRAWN | 2012-03-26 07:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | PGAE | Wheeler Ridge-Lakeview 70kV | 2011-10-31 07:00 | 2011-10-31 07:00 | None | None | None | NA
GAUGAMELA | 546 | 2010-01-06 | 2010-01-06 08:00 | WITHDRAWN | 2012-12-17 23:24 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 15 | 15 | Energy Only |  | LOS ANGELES | CA | SCE | Redman-Piute 66kV Tap | 2012-12-01 08:00 | 2012-12-01 08:00 | None | Facilities Study | SGIA | NA
WATERLOO | 547 | 2010-01-06 | 2010-01-06 08:00 | WITHDRAWN | 2012-12-17 23:24 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | LOS ANGELES | CA | SCE | Loop Redman-Lancaster 66kV | 2012-12-01 08:00 | 2012-12-01 08:00 | None | Facilities Study | SGIA | NA
FRV ORION SOLAR | 549 | 2009-11-19 | 2010-01-15 08:00 | WITHDRAWN | 2010-06-04 07:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | MERCED | CA | PGAE | Mercy Springs Oro Loma 70kV line | 2012-03-31 07:00 | 2012-03-31 07:00 | None | None | None | NA
CAL SP V | 550 | 2009-12-04 | 2010-01-19 08:00 | WITHDRAWN | 2016-08-10 07:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | MERCED | CA | PGAE | Merced #1 70 kV | 2011-12-15 08:00 | 2018-05-31 07:00 | None | Facilities Study | SGIA | NA |  | None
FRV RIGEL SOLAR | 551 | 2010-01-27 | 2010-01-27 08:00 | WITHDRAWN | 2012-03-02 08:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | PGAE | Wheeler Ridge Sub 70kV bus | 2011-10-31 07:00 | 2011-10-31 07:00 | NA | None | Complete | NA
ORD MOUNTAIN | 552 | 2009-10-02 | 2010-02-01 08:00 | WITHDRAWN | 2021-07-28 07:00 | C02 | Photovoltaic | Storage |  | Solar | Battery |  | 60 | 60 |  | 60 | Energy Only | Off-Peak Energy Only | SAN BERNARDINO | CA | SCE | Calcite Substation 220kV | 2012-03-01 08:00 | 2022-09-06 07:00 | NA | Complete | Complete | NA | Executed | IC Request
PANOCHE VALLEY SOLAR FARM EXPANSION | 553 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2011-03-30 17:58 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 400 | 400 | Full Capacity |  | SAN BENITO | NV | PGAE | Moss Landing-Panoche #2 & Coburn-Panoche #2 230 kV | 2013-12-15 08:00 | 2013-12-15 08:00 | NA | Complete | None | NA
TIMBER HILLS WIND (FKA HILLCREST WIND POWER 1) | 554 | 2010-01-26 | 2010-02-01 08:00 | WITHDRAWN | 2011-10-03 07:00 | C02 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 138 | 138 | Full Capacity |  | SHASTA | CA | PGAE | Pit River 1-Cottonwood 230kV | 2013-10-31 07:00 | 2013-12-31 08:00 | NA | Complete | None | NA
JEWEL VALLEY PROJECT (FKA JORDAN WIND POWER) | 555 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2011-10-26 18:17 | C02 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 92 | 92 | Full Capacity |  | SAN DIEGO | CA | SDGE | Boulevard Substation 138kV | 2013-11-22 08:00 | 2014-12-30 08:00 | NA | None | Complete | NA
MAYACMAS WIND POWER | 556 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2010-04-09 07:00 | C02 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 126 | 126 | Energy Only |  | MENDOCINO | CA | PGAE | Eagle Rock Substation 115 kV | 2013-10-31 07:00 | 2013-10-31 07:00 | NA | None | None | NA
FRV LEO SOLAR | 560 | 2010-01-27 | 2010-02-01 08:00 | WITHDRAWN | 2013-11-22 08:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | MERCED | CA | PGAE | Los Banos-Dos Amigos 230kV | 2012-07-01 07:00 | 2013-03-31 07:00 | NA | Complete | Complete | NA
MOUNT SIGNAL SOLAR FARM | 561 | 2010-01-27 | 2010-02-01 08:00 | WITHDRAWN | 2013-07-11 07:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley Substation 230kV | 2013-02-01 08:00 | 2014-12-01 08:00 | NA | Complete | Complete | NA
BARSTOW SOLAR II | 562 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2010-05-26 07:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 420 | 420 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Victor Substation 230kV | 2013-10-01 07:00 | 2013-10-01 07:00 | NA | None | None | NA
PV-11 EXPANSION | 563 | 2010-01-29 | 2010-02-01 08:00 | WITHDRAWN | 2010-03-26 07:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 22 | 22 | Full Capacity |  | LOS ANGELES | CA | SCE | Antelope Substation 66kV | 2013-06-01 07:00 | 2013-06-01 07:00 | NA | None | None | NA
PV-03 EXPANSION | 564 | 2010-01-29 | 2010-02-01 08:00 | WITHDRAWN | 2010-03-26 07:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 23 | 23 | Full Capacity |  | LOS ANGELES | CA | SCE | Antelope Substation 66kV | 2013-07-01 07:00 | 2013-07-01 07:00 | NA | None | None | NA
QUAIL BRUSH POWER PROJECT (FKA SAN DIEGO COMMUNITY POWER PROJECT 2) | 565 | 2010-01-29 | 2010-02-01 08:00 | WITHDRAWN | 2015-07-06 07:00 | C02 | Generating Facility Type-1: Reciprocating Engine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 100 | 100 | Full Capacity |  | SAN DIEGO | CA | SDGE | Mission-Carlton Hills 138kV Line | 2014-05-31 07:00 | 2017-01-29 08:00 | NA | Complete | Complete | NA
SANBORN II SOLAR | 566 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2010-12-22 08:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 21 | 21 | Full Capacity |  | KERN | CA | SCE | Rosamond-Corum 66kV | 2013-12-01 08:00 | 2013-12-01 08:00 | NA | None | None | NA
EAGLE MOUNTAIN PUMP STORAGE #2 | 567 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2010-12-22 08:00 | C02 | Generating Facility Type-1: Hydro; Generating Facility Fuel-1: Water; MWs MW-1: 1400 | 1400 | Full Capacity |  | RIVERSIDE | CA | SCE | Red Bluff Substation 230kV | 2016-06-01 07:00 | 2016-06-01 07:00 | NA | None | None | NA
SUTTER ENERGY CENTER 2 | 569 | 2010-01-28 | 2010-02-01 08:00 | WITHDRAWN | 2014-01-22 08:00 | C02 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 600 | 600 | Full Capacity |  | SUTTER | CA | PGAE | Table Mountain-Tesla 500kV | 2013-05-01 07:00 | 2018-05-01 07:00 | NA | Complete | Complete | NA
PARADISE PEAK WIND POWER PROJECT | 570 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2010-09-27 07:00 | C02 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 102 | 102 | Full Capacity |  | SHASTA/TRINITY | CA | PGAE | Trinity-Cottonwood 115 kV Line | 2012-11-22 08:00 | 2012-11-22 08:00 | NA | None | None | NA
FRV EAFB SOLAR | 571 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2011-02-15 08:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 450 | 450 | Full Capacity |  | KERN | CA | SCE | Windhub Substation 500kV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | Complete | None | NA
FRV DIAMOND VALLEY SOLAR | 572 | 2010-01-28 | 2010-02-01 08:00 | WITHDRAWN | 2010-06-14 07:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 110 | 110 | Full Capacity |  | RIVERSIDE | CA | SCE | Valley Substation 500 kV bus | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
SUNSHINE THREE EXPANSION | 573 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2011-02-07 08:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 | Full Capacity |  | KERN | CA | SCE | Antelope-Cal Cement 66kV | 2013-06-01 07:00 | 2013-06-01 07:00 | NA | Complete | None | NA
POTRERO HILLS ENERGY | 575 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2010-11-20 00:24 | C02 | Generating Facility Type-1: Reciprocating Engine; Generating Facility Fuel-1: Biofuel; MWs MW-1: 9.6 | 9.6 | Full Capacity |  | SOLANO | CA | PGAE | Brighton-Davis 115 kV Line | 2013-06-30 07:00 | 2013-06-30 07:00 | NA | None | None | NA
SOLAR STAR XI | 578 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2010-03-31 07:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 70 | 70 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Cottonwood-Savage 115kV line | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
MADERA SOLAR PV I (FKA WHEELER RIDGE SOLAR PV1) | 579 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2011-02-15 19:06 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 220 | 220 | Full Capacity |  | MADERA | CA | PGAE | Borden Sub 230kV bus | 2013-05-01 07:00 | 2013-12-31 08:00 | NA | None | None | NA
BLYTHE SOLAR PV I | 580 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2010-04-16 07:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 170 | 170 | Full Capacity |  | RIVERSIDE | CA | SCE | Blythe-Eagle Mountain 161kV line | 2012-12-31 08:00 | 2012-12-31 08:00 | NA | None | None | NA
CPA MARICOPA SOLAR | 582 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2011-02-17 08:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 500 | 500 | Full Capacity |  | KERN | CA | SCE | Midway - Vincent #1 & #2 500kV | 2013-07-01 07:00 | 2013-07-01 07:00 | NA | Complete | None | NA
MANZANITA WIND | 583 | 2010-01-29 | 2010-02-01 08:00 | WITHDRAWN | 2015-11-23 08:00 | C02 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 57.5 | 57.5 | Energy Only |  | SAN DIEGO | CA | SDGE | Boulevard East Substation 138kV | 2012-12-31 08:00 | 2017-01-29 08:00 | NA | Complete | Complete | NA
ANTELOPE VALLEY RENEWABLE ENERGY FARM - SOLAR | 584 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2011-02-07 08:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Energy Only |  | LOS ANGELES | CA | SCE | Antelope Sub 220kV Bus | 2013-02-28 08:00 | 2013-02-28 08:00 | NA | Complete | None | NA
ANTELOPE VALLEY RENEWABLE ENERGY FARM - WIND | 585 | 2010-01-29 | 2010-02-01 08:00 | WITHDRAWN | 2012-03-02 19:40 | C02 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 150 | 150 | Energy Only |  | LOS ANGELES | CA | SCE | Antelope Sub 220kV Bus | 2013-02-28 08:00 | 2014-08-12 07:00 | NA | Complete | Complete | NA
CPN WILD HORSE GEOTHERMAL | 586 | 2010-01-29 | 2010-02-01 08:00 | WITHDRAWN | 2014-08-05 07:00 | C02 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 42 | 42 | Full Capacity |  | SONOMA | CA | PGAE | Geysers #17-Fulton 230kV | 2013-06-01 07:00 | 2017-07-01 07:00 | NA | Complete | Complete | NA
SAN JOAQUIN 1 & 2 | 587 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2010-03-22 07:00 | C02 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 106.8 | 106.8 | Energy Only |  | FRESNO | CA | PGAE | Gates Substation | 2012-09-30 07:00 | 2012-09-30 07:00 | NA | None | None | NA
NRG RED BLUFF SOLAR 1 (FKA NRG BLYTHE SOLAR 2) | 588 | 2010-01-29 | 2010-02-01 08:00 | WITHDRAWN | 2015-08-19 07:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 1 | 1 | Full Capacity |  | RIVERSIDE | CA | SCE | Red Bluff Substation 230kV | 2012-12-01 08:00 | 2017-11-01 07:00 | NA | Complete | Complete | NA
NRG SOLAR VICTOR 1 | 589 | 2010-01-29 | 2010-02-01 08:00 | WITHDRAWN | 2015-08-19 07:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 1 | 1 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Victor Substation 115kV | 2012-12-01 08:00 | 2017-01-29 08:00 | NA | Complete | Complete | NA
BORREGO SPRINGS SOLAR SOUTH | 591 | 2010-01-29 | 2010-02-01 08:00 | WITHDRAWN | 2010-04-21 07:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 40 | 40 | Full Capacity |  | SAN DIEGO | CA | SDGE | Borrego Substation 60kV | 2011-06-01 07:00 | 2011-06-01 07:00 | NA | None | None | NA
KINGSOLAR II | 592 | 2010-01-29 | 2010-02-01 08:00 | WITHDRAWN | 2012-03-02 08:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 | Full Capacity |  | KINGS | CA | PGAE | Midway-Gates & Arco-Gates 230kV lines | 2012-12-31 08:00 | 2013-02-28 08:00 | NA | Complete | None | NA
FORT MOJAVE SOLAR | 593 | 2010-01-30 | 2010-02-01 08:00 | WITHDRAWN | 2019-05-15 07:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 310 | 310 | Full Capacity |  | MOJAVE | AZ | SCE | Mohave Generating Station 500kV bus | 2014-07-07 07:00 | 2019-12-01 08:00 | NA | Complete | Complete | NA | In Progress | IC Request
BIO VERDE PV - HOOGENDM | 594 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2010-11-20 00:24 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | MERCED | CA | PGAE | Merced Substation 70 kV | 2012-12-31 08:00 | 2012-12-31 08:00 | NA | None | None | NA
BIO VERDE PV - KETTLEMAN 1 | 595 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2010-11-19 08:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 15 | 15 | Full Capacity |  | KINGS | CA | PGAE | Henrietta - Tulare 70kV line | 2012-12-31 08:00 | 2012-12-31 08:00 | NA | None | None | NA
BIO VERDE PV - KETTLEMAN 3 | 596 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2010-11-19 08:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KINGS | CA | PGAE | Henrietta Tulare 70kV line | 2012-12-31 08:00 | 2012-12-31 08:00 | NA | None | None | NA
BIO VERDE PV - VLOT | 597 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2010-11-20 00:24 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 15 | 15 | Full Capacity |  | MADERA | CA | PGAE | Merced #1 70 kV line (El Nido Bonita segment) | 2012-12-31 08:00 | 2012-12-31 08:00 | NA | None | None | NA
BIO VERDE PV - KETTLEMAN 2 | 598 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2010-11-20 00:24 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 17.75 | 17.75 | Full Capacity |  | KINGS | CA | PGAE | Henrietta Tulare 70kV line | 2012-12-31 08:00 | 2012-12-31 08:00 | NA | None | None | NA
BIO VERDE PV - SAN JOAQUIN | 599 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2010-03-04 08:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Corral Substation 70 kV | 2012-12-31 08:00 | 2012-12-31 08:00 | NA | None | None | NA
BIO VERDE PV - VANDER WOUDE | 600 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2011-03-30 17:45 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | MERCED | CA | PGAE | Merced #1 70 kV | 2012-12-31 08:00 | 2012-12-31 08:00 | NA | Complete | None | NA
ROSINA BIO VERDE | 601 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2010-11-20 00:24 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 10 | 10 | Full Capacity |  | KINGS | CA | PGAE | Tulare Henrietta 70kV line | 2012-12-31 08:00 | 2012-12-31 08:00 | NA | None | None | NA
MOJAVALON I | 603 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2010-04-20 07:00 | C02 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 146 | 146 | Full Capacity |  | KERN | CA | SCE | Whirlwind Substation 230kV | 2013-07-01 07:00 | 2013-07-01 07:00 | NA | None | None | NA
IMPERIAL VALLEY GENERATION PROJECT | 604 | 2010-01-30 | 2010-02-01 08:00 | WITHDRAWN | 2010-11-24 08:00 | C02 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 600 | 600 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley Substation 230kV | 2014-04-01 07:00 | 2014-04-01 07:00 | NA | None | None | NA
EL DORADO VALLEY GENERATION | 605 | 2010-11-20 | 2010-02-01 08:00 | WITHDRAWN | 2010-11-30 08:00 | C02 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 600 | 600 | Full Capacity |  | CLARK | NV | SCE | Eldorado Substation 230kV | 2014-04-01 07:00 | 2014-04-01 07:00 | NA | Complete | None | NA
SUN HARVESTER SOLAR PROJECT | 610 | 2010-02-04 | 2010-02-05 08:00 | WITHDRAWN | 2012-03-01 08:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | Stroud SW STA-Schindler 70kV | 2012-12-01 08:00 | 2012-12-01 08:00 | NA | None | Complete | NA
FAIRFAX SOLAR PROJECT | 611 | 2010-02-17 | 2010-02-17 08:00 | WITHDRAWN | 2011-02-15 17:18 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | FRESNO | CA | PGAE | Oro Loma-El Nido 115kV | 2012-01-01 08:00 | 2012-01-01 08:00 | None | None | None | NA
THREE ROCKS SOLAR | 612 | 2010-02-19 | 2010-02-19 08:00 | WITHDRAWN | 2016-04-22 20:25 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 13 | 13 | Energy Only |  | FRESNO | CA | PGAE | Panoche-Schindler #2 115kV Line | 2013-07-15 07:00 | 2017-12-01 08:00 | None | Facilities Study | SGIA | NA
PLACER SOLAR | 613 | 2010-02-19 | 2010-02-19 08:00 | WITHDRAWN | 2014-04-23 20:21 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | FRESNO | CA | PGAE | Helm 70kV bus | 2014-02-10 08:00 | 2015-04-01 07:00 | None | Facilities Study | SGIA | NA
SAND CANYON OF TEHACHAPI | 613A | 2010-02-24 | 2010-02-24 08:00 | WITHDRAWN | 2012-03-03 00:02 | SGIP-TC | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 20 | 20 | Energy Only |  | KERN | CA | SCE | Cal Cement - Monolith - Windland - Arwind 66 kV line | 2012-06-30 07:00 | 2012-06-30 07:00 | NA | None | None | NA
EL PECO SOLAR FARM | 614 | 2010-03-02 | 2010-03-02 08:00 | WITHDRAWN | 2013-12-26 23:04 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | FRESNO | CA | PGAE | Merced-Madera 70kV | 2011-05-01 07:00 | 2014-12-15 08:00 | None | Facilities Study | SGIA | NA
FRV MOJAVE SOLAR | 614A | 2010-03-04 | 2010-03-04 08:00 | WITHDRAWN | 2012-03-03 00:01 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | SCE | Goldtown-Lancaster 66kV | 2013-12-01 08:00 | 2013-12-01 08:00 | NA | None | Complete | NA
SUN STREAM | 615 | 2010-11-20 | 2010-03-10 08:00 | WITHDRAWN | 2011-01-19 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KERN | CA | SCE | Zondwind Sub 66kV Bus | 2012-12-30 08:00 | 2012-12-30 08:00 | None | None | None | NA
SUNLITE STATION | 616 | 2010-11-20 | 2010-03-17 07:00 | WITHDRAWN | 2011-01-19 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | RIVERSIDE | CA | SCE | Eagle Mountain-Blythe 161kV | 2012-07-01 07:00 | 2012-07-01 07:00 | None | None | None | NA
CROCKER SOLAR POWER - UNIT ONE | 617 | 2010-03-22 | 2010-03-22 07:00 | WITHDRAWN | 2013-11-25 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | SAN JOAQUIN | CA | PGAE | Tesla-Tracy 115kV | 2012-06-01 07:00 | 2016-05-01 07:00 | None | Facilities Study | SGIA | NA
LA-SOLAR-20 | 617A | 2010-03-30 | 2010-03-30 07:00 | WITHDRAWN | 2013-05-06 22:24 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | LOS ANGELES | CA | SCE | Piute-Redmond 66kV | 2012-12-01 08:00 | 2014-05-01 07:00 | None | Facilities Study | SGIA | NA
US SOLAR DESERT CENTER PV 1 | 617AA | 2010-11-20 | 2010-03-26 07:00 | WITHDRAWN | 2011-01-20 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | RIVERSIDE | CA | SCE | Eagle Mountain-Blythe SCE 161 kV | 2011-03-01 08:00 | 2011-03-01 08:00 | None | None | None | NA
GREAT VALLEY SOLAR | 617B | 2010-03-31 | 2010-03-31 07:00 | WITHDRAWN | 2011-03-28 18:36 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 19.7 | 19.7 | Energy Only |  | TULARE | CA | PGAE | Corcoran-Smyrna 115kV | 2012-12-01 08:00 | 2012-12-01 08:00 | None | None | None | NA
OASIS SOLAR ENERGY | 617C | 2010-11-20 | 2010-03-31 07:00 | WITHDRAWN | 2010-06-23 07:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 19.993 | 19.993 | Energy Only |  | MONO | CA | SCE | Control-Silverpeak 55 kV | 2012-12-01 08:00 | 2012-12-01 08:00 | None | None | None | NA
SKUNK HOLLOW SPGS1 | 618 | 2010-04-01 | 2010-04-01 07:00 | WITHDRAWN | 2010-12-27 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | FRESNO | CA | PGAE | Coalinga-Mendota Road 69kV | 2012-08-01 07:00 | 2012-08-01 07:00 | None | None | None | NA
FIVE POINTS SOLAR | 618A | 2010-04-19 | 2010-04-19 07:00 | WITHDRAWN | 2010-12-02 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | FRESNO | CA | PGAE | Helms-Schindler 70kV | 2012-01-01 08:00 | 2012-01-01 08:00 | None | None | None | NA
JEFFERSON SOLAR | 618B | 2010-03-19 | 2010-04-19 07:00 | WITHDRAWN | 2010-12-02 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 10 | 10 | Energy Only |  | FRESNO | CA | PGAE | Kerman-San Joaquin 70kv | 2012-01-01 08:00 | 2012-01-01 08:00 | None | None | None | NA
EAST LANCASTER POWER PLANT | 619 | 2010-11-20 | 2010-04-22 07:00 | WITHDRAWN | 2011-01-19 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 14 | 14 | Energy Only |  | LOS ANGELES | CA | SCE | Piute-Lancaster 66kV | 2012-01-01 08:00 | 2012-01-01 08:00 | None | None | None | NA
MARICOPA EAST SOLAR PV (FKA LAKEVIEW SOLAR ONE) | 620A | 2010-04-26 | 2010-04-26 07:00 | WITHDRAWN | 2014-02-27 20:58 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KERN | CA | PGAE | Lakeview Sub 70kV bus | 2014-12-31 08:00 | 2014-12-31 08:00 | None | Facilities Study | SGIA | NA
OCOTILLO SOL PROJECT | 621 | 2010-03-03 | 2010-04-26 07:00 | WITHDRAWN | 2016-02-16 08:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | IMPERIAL | CA | SDGE | Imperial Valley Sub 12kV Bus | 2012-08-01 07:00 | 2017-03-03 08:00 | NA | None | Complete | NA
PV ROSINA 1 SG | 622 | 2009-12-21 | 2010-05-06 07:00 | WITHDRAWN | 2011-08-18 07:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 10 | 10 | Energy Only |  | KERN | CA | PGAE | Temblor-King Ellis 70kV | 2011-12-01 08:00 | 2011-12-01 08:00 | None | None | None | NA
ROSAMOND SOLAR FACILITY | 623 | 2010-11-20 | 2010-05-10 07:00 | WITHDRAWN | 2011-01-18 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KERN | CA | SCE | Cal Cement-Antelope 66kV | 2013-12-31 08:00 | 2013-12-31 08:00 | None | None | None | NA
ROUGH ACRES SOLAR | 623A | 2010-11-20 | 2010-05-10 07:00 | WITHDRAWN | 2010-12-02 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 10.4 | 10.4 | Energy Only |  | SAN DIEGO | CA | SDGE | Boulevard Sub 138 kV Bus | 2011-06-01 07:00 | 2011-06-01 07:00 | None | None | None | NA
SUN SEEKER SOLAR ENERGY CENTER | 624 | 2010-11-20 | 2010-05-14 07:00 | WITHDRAWN | 2010-09-03 07:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 |  |  | KERN | CA | PGAE | Maricopa Substation 70 kV bus | 2012-12-01 08:00 | 2012-12-01 08:00 | None | None | None | NA
STRATFORD SOLAR FARM | 626 | 2010-05-17 | 2010-05-17 07:00 | WITHDRAWN | 2014-02-05 17:47 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KINGS | CA | PGAE | Henrietta-Guernsey 70kV | 2011-12-31 08:00 | 2017-06-15 07:00 | None | Facilities Study | SGIA | NA
FRV MOJAVE SOLAR 2 | 627 | 2010-11-20 | 2010-05-18 07:00 | WITHDRAWN | 2010-10-12 07:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | LOS ANGELES | CA | SCE | Neenach-Antelope 66kV | 2013-12-31 08:00 | 2013-12-31 08:00 | None | None | None | NA
SALADO SOLAR | 629 | 2010-05-20 | 2010-05-20 07:00 | WITHDRAWN | 2011-02-09 23:18 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | STANISLAUS | CA | PGAE | Salado-Miller 115kV line | 2011-12-01 08:00 | 2011-12-01 08:00 | None | None | None | NA
PURDY AVE PV | 630 | 2010-11-20 | 2010-05-20 07:00 | WITHDRAWN | 2011-02-09 23:16 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 4.9 | 4.9 | Energy Only |  | KERN | CA | SCE | Goldtown Substation 66kV | 2010-12-01 08:00 | 2010-12-01 08:00 | None | None | None | NA
KAMM | 631 | 2010-05-24 | 2010-05-24 07:00 | WITHDRAWN | 2013-08-27 18:23 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | FRESNO | CA | PGAE | Strout SW Station 70kV | 2014-06-30 07:00 | 2016-02-15 08:00 | None | Facilities Study | SGIA | NA
WORLD SUN PV PROJECT | 632A | 2011-03-16 | 2010-05-27 07:00 | WITHDRAWN | 2011-03-16 07:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | STANISLAUS | CA | PGAE | Salado-Miller 115 kV | 2011-12-01 08:00 | 2011-12-01 08:00 | NA | None | None | NA
SAN JOAQUIN 2A | 632C | 2010-06-01 | 2010-06-01 07:00 | WITHDRAWN | 2015-06-11 07:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | Stroud switching station 70kV | 2012-12-01 08:00 | 2017-05-30 07:00 | NA | Complete | Complete | NA
GRANGEVILLE | 634 | 2010-06-30 | 2010-06-30 07:00 | WITHDRAWN | 2014-01-31 18:18 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KINGS | CA | PGAE | Camden Junction-Lemoore Tap 70kV | 2013-06-30 07:00 | 2015-12-15 08:00 | None | Facilities Study | SGIA | NA
CAL SP XII | 635 | 2010-07-01 | 2010-07-01 07:00 | WITHDRAWN | 2012-03-05 21:12 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | MERCED | CA | PGAE | Oro Loma-Canal 70kV | 2012-06-15 07:00 | 2012-06-15 07:00 | NA | None | None | NA
JAYNE EAST | 638 | 2010-07-08 | 2010-07-08 07:00 | WITHDRAWN | 2013-08-27 18:24 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 10 | 10 | Energy Only |  | FRESNO | CA | PGAE | Coalinga 1-Gates 70kV | 2012-12-31 08:00 | 2014-12-31 08:00 | None | Facilities Study | SGIA | NA
SEPV-15 | 638A | 2011-03-09 | 2010-07-09 07:00 | WITHDRAWN | 2011-01-28 08:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 12 | 12 | Energy Only |  | FRESNO | CA | PGAE | Coalinga CoGen 70 kV Tap & Tornado Dist | 2011-12-31 08:00 | 2011-12-31 08:00 | NA | None | None | NA
LANCASTER SOLAR FARM | 639 | 2010-05-26 | 2010-07-15 07:00 | WITHDRAWN | 2012-02-17 16:25 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | LOS ANGELES | CA | SCE | Redman-Piute 66kV | 2011-11-01 07:00 | 2013-01-01 08:00 | NA | None | None | NA
BFO PV-06 | 640 | 2010-05-26 | 2010-07-15 07:00 | WITHDRAWN | 2012-02-17 16:30 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | SCE | Rosamond 66kV - Tap 52 | 2011-11-01 07:00 | 2013-01-01 08:00 | NA | None | None | NA
GRAHAM SOLAR FARM I | 640A | 2010-07-20 | 2010-07-20 07:00 | WITHDRAWN | 2012-03-06 08:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | Schindler Sub 115 kV Bus | 2011-12-15 08:00 | 2011-12-15 08:00 | NA | None | Complete | NA
PDD WHR SOLAR FARM I | 640B | 2010-07-20 | 2010-07-20 07:00 | WITHDRAWN | 2012-03-06 08:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | MERCED | CA | PGAE | Oro Loma 115kV | 2011-12-25 08:00 | 2011-12-25 08:00 | NA | None | Complete | NA
REPOWERED MCKITTRICK COGEN PLANT | 641 | 2010-11-20 | 2010-07-23 07:00 | WITHDRAWN | 2010-12-23 08:00 | SGIP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 11.2 | 11.2 | Energy Only |  | KERN | CA | PGAE | Midsun-Midway 115 kV | 2011-12-31 08:00 | 2011-12-31 08:00 | None | None | None | NA
THUNDERHILL SOLAR POWER | 642 | 2010-07-30 | 2010-07-30 07:00 | WITHDRAWN | 2012-07-09 07:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | GLENN | CA | PGAE | Elk Creek 60kV Tap | 2011-07-01 07:00 | 2011-07-01 07:00 | NA | Complete | Complete | NA
PACHECO PASS WIND ENERGY CENTER | 643 | 2010-07-26 | 2010-07-31 07:00 | WITHDRAWN | 2011-09-02 07:00 | C03 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 149.5 | 149.5 | Full Capacity |  | FRESNO | CA | PGAE | Los Banos-San Luis PGP #1 230 kV | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | None | None | NA
ARCO SOLAR STATION | 643A | 2010-07-29 | 2010-07-31 07:00 | WITHDRAWN | 2011-07-11 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 300 | 300 | Full Capacity |  | KERN | CA | PGAE | Arco Sub 230 kV Bus | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | None | None | NA
BLUE SKY WIND ENERGY CENTER | 643AA | 2010-07-26 | 2010-07-31 07:00 | WITHDRAWN | 2013-05-03 07:00 | C03 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 200.1 | 200.1 | Full Capacity |  | LOS ANGELES | CA | SCE | Antelope Sub 230kV Bus | 2012-12-31 08:00 | 2012-12-31 08:00 | NA | Complete | Complete | NA
BRIGHTSOURCE AV PROJECT | 643AB | 2010-11-20 | 2010-07-31 07:00 | WITHDRAWN | 2010-07-26 07:00 | C03 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 260 | 260 | Full Capacity |  | LOS ANGELES | CA | SCE | Whirlwind Substation 230kV Bus | 2015-01-01 08:00 | 2015-01-01 08:00 | NA | Complete | None | NA
PALO VERDE MESA (FKA BRIGHTSOURCE MIDPOINT SOLAR) | 643AC | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2013-02-21 08:00 | C03 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 750 | 750 | Full Capacity |  | RIVERSIDE | CA | SCE | Colorado River Sub 220 kV Bus | 2015-01-01 08:00 | 2015-01-01 08:00 | NA | Complete | Complete | NA
COSO 2 SWAP (COSO FINANCE PARTNERS) | 643AD | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2011-06-27 07:00 | C03 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 95 | 95 | Full Capacity |  | INYO | CA | SCE | Kramer Sub 220kV Bus | 2012-07-01 07:00 | 2012-07-01 07:00 | NA | None | None | NA
GILA SOLAR | 643AF | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2010-09-09 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 500 | 500 | Full Capacity |  | RIVERSIDE | CA | SCE | Colorado River Sub 220kV Bus | 2015-10-30 07:00 | 2015-10-30 07:00 | NA | Complete | None | NA
HAY RANCH SOLAR ENERGY PARK | 643AG | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2011-06-27 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 | Full Capacity |  | INYO | CA | SCE | Control-Inyokern 115 kV | 2014-01-01 08:00 | 2014-01-01 08:00 | NA | None | None | NA
LOMA VERDE SOLAR ENERGY PARK | 643AH | 2010-07-29 | 2010-07-31 07:00 | WITHDRAWN | 2010-09-09 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 170 | 170 | Full Capacity |  | RIVERSIDE | CA | SCE | Red Bluff Sub 230 kV Bus | 2014-01-01 08:00 | 2014-01-01 08:00 | NA | Complete | None | NA
NEVADA 300 | 643AI | 2010-07-29 | 2010-07-31 07:00 | WITHDRAWN | 2013-05-09 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 300 | 300 | Full Capacity |  | CLARK | NV | SCE | Eldorado Sub 220 kV Bus | 2014-11-30 08:00 | 2014-11-30 08:00 | NA | Complete | Complete | NA |  | None
TERRA GEN DIXIE VALLEY EXPANSION | 643AK | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2011-07-28 18:09 | C03 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 5.6 | 5.6 | Full Capacity |  | CHURCHILL | NV | SCE | Control Sub 115 kV Bus | 2011-12-31 08:00 | 2011-12-31 08:00 | NA | None | None | NA
WILDCAT QUARTSZITE | 643AL | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2011-09-09 07:00 | C03 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 1000 | 1000 | Full Capacity |  | YUMA | AZ | SCE | Palo Verde-Devers #1 500kV | 2015-01-01 08:00 | 2015-01-01 08:00 | NA | Complete | None | NA
JORDAN II RENEWABLE POWER PROJECT (20/66MW) | 643AN | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2011-07-19 07:00 | C03 | Photovoltaic | Wind Turbine |  | Solar | Wind Turbine |  | 66 | 20 |  | 86 | Full Capacity |  | SAN DIEGO | CA | SDGE | Boulevard Sub 138kV Bus | 2013-11-22 08:00 | 2013-11-22 08:00 | NA | None | None | NA
MOUNT SIGNAL SOLAR FARM II | 643AO | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2011-08-11 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley 230 kV Switchyard | 2014-06-01 07:00 | 2014-06-01 07:00 | NA | None | None | NA
OCOTILLO EXPRESS PHASE II | 643AP | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2012-12-07 08:00 | C03 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 16.1 | 16.1 | Full Capacity |  | IMPERIAL | CA | SDGE | Sunrise Powerlink 500 kV | 2012-12-31 08:00 | 2013-12-31 08:00 | NA | Complete | None | NA
PALMAS (FKA HYDER SOLAR) | 643AQ | 2010-07-31 | 2010-07-31 07:00 | WITHDRAWN | 2011-09-09 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 238 | 238 | Full Capacity |  | YUMA | AZ | SDGE | Hassayampa-North Gila 500kV line | 2013-06-01 07:00 | 2013-06-01 07:00 | NA | None | None | NA
TGP NNP | 643AR | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2011-06-27 07:00 | C03 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 364.2 | 364.2 | Full Capacity |  | CHURCHILL/PERSHING | CA | SCE | Control Sub 115 kV Bus | 2016-06-01 07:00 | 2016-06-01 07:00 | NA | None | None | NA
AIRPORT SOLAR PV 1 | 643AS | 2010-07-31 | 2010-07-31 07:00 | WITHDRAWN | 2011-09-09 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 | Full Capacity |  | RIVERSIDE | CA | SCE | Colorado River Substation | 2013-06-01 07:00 | 2013-06-01 07:00 | NA | Complete | None | NA
COPPER MOUNTAIN SOLAR III (BLACK HILLS) | 643AT | 2010-11-20 | 2010-07-31 07:00 | WITHDRAWN | 2011-06-10 19:58 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 242 | 242 | Full Capacity |  | CLARK | NV | SCE | Mead-Eldorado 230kV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
AUBANEL I WIND PROJECT | 643B | 2010-11-20 | 2010-07-31 07:00 | WITHDRAWN | 2010-11-26 08:00 | C03 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 300 | 300 | Energy Only |  | BAJA CALIFORNIA | MX | SDGE | Imperial Valley Sub 230 kV Bus | 2012-06-30 07:00 | 2012-06-30 07:00 | NA | None | None | NA
AUBANEL II WIND PROJECT | 643C | 2010-11-20 | 2010-07-31 07:00 | WITHDRAWN | 2010-11-01 07:00 | C03 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 540 | 540 | Energy Only |  | BAJA CALIFORNIA | MX | SDGE | ECO Sub 230 kV Bus | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
ANGIOLA VALLEY SOLAR RANCH | 643D | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2013-05-03 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | KINGS | CA | PGAE | Angiola Sub 70 kV Bus | 2014-12-31 08:00 | 2016-12-31 08:00 | NA | Complete | None | NA
LAGUNA SOLAR FARM | 643E | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2013-05-03 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 | Full Capacity |  | FRESNO | CA | PGAE | Schindler Sub 115 kV Bus | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | Complete | None | NA
PLACER SOLAR PV I | 643F | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2013-05-14 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 220 | 220 | Full Capacity |  | PLACER | CA | PGAE | Rio Oso-Lockford 230 kV | 2014-03-01 08:00 | 2014-03-01 08:00 | NA | Complete | Complete | NA
VALLEY OAK SOLAR | 643H | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2011-09-13 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 600 | 600 | Full Capacity |  | KINGS | CA | PGAE | Gates-Gregg 230 kV | 2015-05-01 07:00 | 2015-05-01 07:00 | NA | None | None | NA
WESTLANDS SOLAR PV I | 643I | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2013-05-03 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 | Full Capacity |  | FRESNO | CA | PGAE | Mendota-Dairyland 115 kV | 2014-03-01 08:00 | 2014-03-01 08:00 | NA | Complete | Complete | NA
WRE - COALINGA (49/120MW) | 643J | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2013-09-30 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 1 | 1 | Full Capacity |  | FRESNO | CA | PGAE | Coalinga #2-Schindler 70 kV | 2017-04-01 07:00 | 2017-04-01 07:00 | NA | Complete | None | NA
WRE - MENDOTA | 643K | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2011-09-13 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 289 | 289 | Full Capacity |  | FRESNO | CA | PGAE | Mendota-San Joaquin-Helm 70 kV | 2017-04-01 07:00 | 2017-04-01 07:00 | NA | None | None | NA
WRE - PANOCHE | 643L | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2011-09-13 07:00 | C03 | Photovoltaic | Combustion Turbine |  | Solar | Natural Gas |  | 240 | 49 |  | 289 | Full Capacity |  | FRESNO | CA | PGAE | Panoche-Schindler #1 & #2 115 kV | 2017-04-01 07:00 | 2017-04-01 07:00 | NA | None | None | NA
WRE - SCHINDLER | 643M | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2011-09-13 07:00 | C03 | Photovoltaic | Combustion Turbine |  | Solar | Natural Gas |  | 240 | 49 |  | 289 | Full Capacity |  | FRESNO | CA | PGAE | Panoche-Schindler #1 & #2 115 kV | 2017-04-01 07:00 | 2017-04-01 07:00 | NA | None | None | NA
WRE - STROUD | 643N | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2011-09-13 07:00 | C03 | Photovoltaic | Combustion Turbine |  | Solar | Natural Gas |  | 120 | 49 |  | 169 | Full Capacity |  | FRESNO | CA | PGAE | Helm-Stroud Sw Sta 70 kV | 2017-04-01 07:00 | 2017-04-01 07:00 | NA | None | None | NA
YOLO SOLAR PV I | 643O | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2013-05-03 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | YOLO | CA | PGAE | Brighton-Davis 115 kV | 2014-03-01 08:00 | 2015-05-01 07:00 | NA | Complete | Complete | NA
RRG SOLAR | 643P | 2010-11-20 | 2010-07-31 07:00 | WITHDRAWN | 2010-11-16 08:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 480 | 480 | Full Capacity |  | KERN/LOS ANGELES | CA | SCE | Whirlwind Sub 500 kV Bus | 2014-10-30 07:00 | 2014-10-30 07:00 | NA | None | None | NA
VOYAGER SOLAR ENERGY | 643Q | 2010-11-20 | 2010-07-31 07:00 | WITHDRAWN | 2010-11-23 08:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 80 | 80 | Full Capacity |  | KERN | CA | SCE | Windhub Sub 220 kV Bus | 2014-11-01 07:00 | 2014-11-01 07:00 | NA | None | None | NA
WRE - VESTAL (49/480MW) | 643S | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2011-09-09 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 320 | 320 | Full Capacity |  | FRESNO | CA | SCE | Vestal Sub 230 kV Bus | 2013-06-01 07:00 | 2013-06-01 07:00 | NA | Complete | None | NA
RE AUSTIN | 643U | 2010-07-31 | 2010-07-31 07:00 | WITHDRAWN | 2011-09-09 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 500 | 500 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley Sub 230 kV Bus | 2014-01-30 08:00 | 2014-01-30 08:00 | NA | None | None | NA
SILVER LEAF SOLAR | 643V | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2011-09-09 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley Sub 230 kV Bus | 2013-09-30 07:00 | 2013-09-30 07:00 | NA | None | None | NA
SOLCEN SOLAR PROJECT | 643Y | 2010-07-30 | 2010-07-31 07:00 | WITHDRAWN | 2011-09-14 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 80 | 80 | Full Capacity |  | KINGS | CA | PGAE | Henrietta-Leprino Food 115 kV | 2013-07-01 07:00 | 2013-07-01 07:00 | NA | None | None | NA |  | None
ALTA 14 | 643Z | 2010-07-31 | 2010-07-31 07:00 | WITHDRAWN | 2011-07-29 07:00 | C03 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | KERN | CA | SCE | Whirlwind - Windhub 500 kV | 2013-11-01 07:00 | 2014-07-01 07:00 | NA | None | None | NA
MONTEREY SOLAR FARM (FKA BFO PV -09) | 645 | 2010-08-19 | 2010-08-19 07:00 | WITHDRAWN | 2012-02-17 08:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | MONTEREY | CA | PGAE | Jolon 60 kV sub | 2012-02-01 08:00 | 2012-02-01 08:00 | NA | None | None | NA
SIRIUS SOLAR | 645A | 2010-08-23 | 2010-08-23 07:00 | WITHDRAWN | 2016-07-07 07:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | PGAE | Weedpatch-Wheeler Ridge 70kV | 2012-12-01 08:00 | 2017-08-23 07:00 | NA | Complete | Complete | NA |  | None
BRJ | 646 | 2010-08-25 | 2010-08-25 07:00 | WITHDRAWN | 2012-07-11 17:50 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 8 | 8 | Full Capacity |  | FRESNO | CA | PGAE | Chaney #1 115kV Tap | 2013-03-01 08:00 | 2013-03-01 08:00 | NA | Complete | Complete | NA
ENRICO MATSON 2 | 647 | 2010-08-25 | 2010-08-25 07:00 | WITHDRAWN | 2012-07-09 07:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | Panoche - Oro Loma 115 KV | 2012-04-01 07:00 | 2012-04-30 07:00 | NA | Complete | Complete | NA
ORO LOMA 4 ( FKA ENRICO MATSON 4) | 648 | 2010-08-25 | 2010-08-25 07:00 | WITHDRAWN | 2016-11-21 08:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | Panoche-Oro Loma 115kV Tap | 2012-04-30 07:00 | 2018-12-31 08:00 | NA | Complete | Complete | NA | Executed | IC Request
DES | 649 | 2010-08-25 | 2010-08-25 07:00 | WITHDRAWN | 2012-07-09 07:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 11.75 | 11.75 | Full Capacity |  | FRESNO | CA | PGAE | Helm 70kV | 2013-12-01 08:00 | 2013-12-01 08:00 | NA | Complete | Complete | NA
PEABODY JAC | 649A | 2010-09-15 | 2010-10-25 07:00 | WITHDRAWN | 2012-07-09 07:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 14 | 14 | Energy Only |  | SOLANO | CA | PGAE | Dixon-Vaca #2 60kV | 2013-03-01 08:00 | 2013-03-01 08:00 | NA | Complete | Complete | NA
GRAHAM - WESTLANDS PROJECT | 650 | 2010-09-07 | 2010-09-07 07:00 | WITHDRAWN | 2011-01-20 08:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | FRESNO | CA | PGAE | Westlands 138 kV Tap | 2011-12-25 08:00 | 2011-12-25 08:00 | NA | None | None | NA
SIERRA SOLAR GREENWORKS | 650A | 2010-09-08 | 2010-09-08 07:00 | WITHDRAWN | 2012-04-05 14:50 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | LOS ANGELES | CA | SCE | Lancaster-Purify-Redman 66 kV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | Complete | None | NA
ORION | 650AC | 2010-09-08 | 2010-09-08 07:00 | WITHDRAWN | 2013-05-06 07:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KINGS | CA | PGAE | Henrietta-Tulare Lake 70kV line | 2012-12-31 08:00 | 2014-12-31 08:00 | NA | Complete | Complete | NA
GYPSUM | 650B | 2010-11-20 | 2010-09-13 07:00 | WITHDRAWN | 2010-11-17 08:00 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | RIVERSIDE | CA | SCE | Line to be constructed 1 mile south & tie into SCE 69kV | 2012-02-28 08:00 | 2012-02-28 08:00 | None | None | None | NA
INDECK YUBA ENERGY CENTER | 651 | 2010-09-16 | 2010-09-16 07:00 | WITHDRAWN | 2012-07-17 07:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 15 | 15 | Energy Only |  | YUBA | CA | PGAE | Nicolaus-Marysville 60kV | 2012-06-01 07:00 | 2012-08-01 07:00 | NA | Complete | Complete | NA
SOLARPACK PROMO III | 652 | 2010-09-23 | 2010-09-23 07:00 | WITHDRAWN | 2012-02-27 08:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | Woodward-Sanger 115kV | 2013-06-15 07:00 | 2013-06-15 07:00 | NA | None | None | NA
SOUTH DOME SOLAR | 653 | 2010-09-29 | 2010-09-29 07:00 | WITHDRAWN | 2012-08-10 07:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KINGS | CA | PGAE | Arco 70 kV | 2013-01-15 08:00 | 2013-01-15 08:00 | NA | Complete | Complete | NA
LAS LOMAS SOLAR | 653A | 2010-09-29 | 2010-09-29 07:00 | WITHDRAWN | 2012-08-10 07:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KERN | CA | PGAE | Arco Sub 70 kV Bus | 2013-01-15 08:00 | 2013-01-15 08:00 | NA | Complete | Complete | NA
RE TEHACHAPI SOLAR 2 | 653BA | 2010-09-29 | 2010-09-29 07:00 | WITHDRAWN | 2012-05-01 07:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KERN | CA | SCE | Kern River-Cummings 66kV | 2012-12-31 08:00 | 2012-12-31 08:00 | NA | None | None | NA
BFO PV-18 | 653C | 2011-01-25 | 2010-09-30 07:00 | WITHDRAWN | 2011-01-28 17:22 | SGIP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | SANTA BARBARA | CA | PGAE | Taft-Cuyama#1 70kV | 2012-07-01 07:00 | 2012-07-01 07:00 | None | None | None | NA
ANNEDALE SOLAR PROJECT | 653D | 2010-09-30 | 2010-09-30 07:00 | WITHDRAWN | 2012-07-09 07:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | FRESNO | CA | PGAE | Panoche-Mendota 115kV | 2012-01-01 08:00 | 2012-06-01 07:00 | NA | Complete | Complete | NA
ROSE SOLAR PROJECT | 653E | 2010-09-30 | 2010-09-30 07:00 | WITHDRAWN | 2013-07-29 07:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | FRESNO | CA | PGAE | Helm Sub 70 kV Bus | 2012-01-03 08:00 | 2014-02-10 08:00 | NA | Complete | Complete | NA
SUNGEN I 20MW SOLAR PV PLANT | 653EB | 2010-09-30 | 2010-09-30 07:00 | WITHDRAWN | 2012-03-06 08:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | PGAE | Midway 230 KV bus via Midway-La Paloma 230kV #1 | 2013-05-01 07:00 | 2013-05-01 07:00 | NA | None | Complete | NA
ORION KERN COUNTY SOLAR I | 653EC | 2011-03-08 | 2010-09-30 07:00 | WITHDRAWN | 2011-03-08 08:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KINGS/KERN | CA | PGAE | Arco Sub 70 kV Bus | 2012-07-01 07:00 | 2012-07-01 07:00 | NA | None | None | NA
LANEAST SOLAR FARM (FKA EASTLAND SOLAR FARM) | 653ED | 2010-09-30 | 2010-09-30 07:00 | WITHDRAWN | 2015-02-13 08:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | SAN DIEGO | CA | SDGE | Boulevard East Substation 69 kV | 2013-10-31 07:00 | 2016-05-31 07:00 | NA | Complete | Complete | NA
SAND CANYON CREEK | 653EF | 2010-10-05 | 2010-10-05 07:00 | WITHDRAWN | 2012-03-03 00:02 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KERN | CA | SCE | Cal Cement-Monolith-Windland 66 kV | 2011-06-30 07:00 | 2011-06-30 07:00 | NA | None | None | NA
APPARENT FIRST HYBRID | 653F | 2010-10-07 | 2010-10-13 07:00 | WITHDRAWN | 2025-04-02 07:00 | SGIP-TC | Photovoltaic | Storage |  | Solar | Battery |  | 12 | 12.1 |  | 12 | Energy Only | Off-Peak Energy Only | YOLO | CA | PGAE | Woodland-Davis 115 kV Line | 2012-05-01 07:00 | 2022-05-30 07:00 | NA | Complete | Complete | NA | Executed | FERC Order
PIUTE #2 | 653FA | 2010-10-13 | 2010-10-13 07:00 | WITHDRAWN | 2012-01-24 00:28 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | LOS ANGELES | CA | SCE | Lancaster-Little Rock-Piute 66kV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
PIUTE | 653FB | 2010-10-13 | 2010-10-13 07:00 | WITHDRAWN | 2012-01-24 00:28 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | LOS ANGELES | CA | SCE | Lancaster-Little Rock-Piute 66kV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | Complete | NA
IFS | 653G | 2010-10-20 | 2010-10-20 07:00 | WITHDRAWN | 2012-03-06 08:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | Mendota - San Joaquin - Helm 70 KV line | 2012-12-30 08:00 | 2013-03-01 08:00 | NA | None | None | NA
RIO BRAVO SOLAR I | 655 | 2011-03-09 | 2010-11-11 08:00 | WITHDRAWN | 2011-03-09 08:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KERN | CA | PGAE | Westpark-Magunden 115 kV | 2013-05-02 07:00 | 2013-05-02 07:00 | NA | None | None | NA
ELK HILLS | 656 | 2010-11-11 | 2010-11-11 08:00 | WITHDRAWN | 2011-06-29 07:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 10 | 10 | Full Capacity |  | KERN | CA | PGAE | Taft-Elk Hills 70 kV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
MERIDIAN & MUNJAR SOLAR PROJECT | 657 | 2011-03-08 | 2010-11-12 08:00 | WITHDRAWN | 2011-01-28 08:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | BUTTE | CA | PGAE | Glenn #3 60 kV | 2012-03-01 08:00 | 2012-03-01 08:00 | NA | None | None | NA
SIERRA VIEW SOLAR IV | 657A | 2010-11-15 | 2010-11-15 08:00 | WITHDRAWN | 2012-03-02 08:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | LOS ANGELES | CA | SCE | Antelope-Neenach 66kV | 2013-12-01 08:00 | 2013-12-20 08:00 | NA | None | None | NA
SIERRA VIEW SOLAR V | 657B | 2010-11-19 | 2010-11-19 08:00 | WITHDRAWN | 2012-03-02 08:00 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | SCE | Goldtown-Corum 66 kV | 2013-12-01 08:00 | 2013-12-20 08:00 | NA | None | None | NA
DESERT VISTA GREENWORKS B | 663 | 2010-12-15 | 2010-12-15 08:00 | WITHDRAWN | 2012-05-03 22:53 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | LOS ANGELES | CA | SCE | Lancaster-Redman-Purify 66KV | 2013-07-01 07:00 | 2013-12-31 08:00 | NA | Complete | None | NA
DESERT SUN RANCH | 664 | 2010-12-15 | 2010-12-15 08:00 | WITHDRAWN | 2012-03-03 00:06 | SGIP-TC | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | LOS ANGELES | CA | SCE | Piute Sub 66 kV Bus | 2012-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
GALE AVENUE SOLAR | 665 | 2011-02-25 | 2011-03-31 07:00 | WITHDRAWN | 2012-09-19 07:00 | FT | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 5 | 5 | Energy Only |  | FRESNO | CA | PGAE | Coalinga #1-Tornado 70kV line; pole number 4/3 | 2012-01-12 08:00 | 2012-01-12 08:00 | None | NA | NA | NA
COLUMBIA SOLAR ENERGY | 666 | 2011-02-28 | 2011-03-31 07:00 | WITHDRAWN | 2012-10-03 07:00 | FT | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 5 | 5 | Energy Only |  | CONTRA COSTA | CA | PGAE | Pittsburg - Kirker - Columbia Steel 115 KV line | 2012-12-31 08:00 | 2012-12-31 08:00 | None | NA | NA | NA
ACORN GREENWORKS | 667 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2018-06-19 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley Substation 230kV | 2014-12-31 08:00 | 2021-12-31 08:00 | NA | Complete | Complete | NA | Executed
ADAME 1 | 668 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-17 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 118 | 118 | Full Capacity |  | FRESNO | CA | PGAE | Mendota 115 kV | 2014-09-01 07:00 | 2014-09-01 07:00 | NA | Complete | None | NA
ALTA 15 | 669 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-07 00:36 | C04 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 502 | 502 | Full Capacity |  | KERN | CA | SCE | Highwind Substation 230kV Bus | 2014-11-15 08:00 | 2014-11-15 08:00 | NA | None | None | NA
APOLLO SOLAR | 672 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-07-06 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 51.2 | 51.2 | Full Capacity |  | KERN | CA | SCE | Whirlwind Substation 66kV | 2013-03-31 07:00 | 2013-03-31 07:00 | NA | None | None | NA
ARLINGTON VALLEY SOLAR ENERGY II | 673 | 2011-03-30 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-30 15:51 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 | Energy Only |  | MARICOPA | AZ | SDGE | Hassayampa - N. Gila 500 kV line | 2015-05-01 07:00 | 2015-05-01 07:00 | NA | Complete | None | NA
AS LH PV 20MW | 674 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-02-21 08:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | PGAE | Arco - Polonios Pass 70kV | 2013-11-01 07:00 | 2013-11-01 07:00 | NA | None | None | NA
BELLOTA SOLAR FARM | 675 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-02-23 08:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Bellota - Tesla 230 kV Tap | 2014-06-01 07:00 | 2014-06-01 07:00 | NA | None | None | NA
BIG HORN 30MW PV PROJECT | 676 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-02-01 14:45 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 30 | 30 | Full Capacity |  | SAN DIEGO | CA | SDGE | Borrego Substation 69kV Bus | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | None | None | NA
BLACK ROCK 1,2,3,4, & 5,6 | 677 | 2010-12-15 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-20 07:00 | C04 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 470 | 470 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley Sub | 2015-06-16 07:00 | 2015-06-16 07:00 | NA | None | None | NA
KERN SOLAR RANCH (FKA CALIFORNIA SOLAR RANCH) | 680 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2013-05-15 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 1000 | 1000 | Full Capacity |  | KERN | CA | PGAE | Diablo Canyon - Midway #3 500 KV Line | 2018-03-31 07:00 | 2018-03-31 07:00 | NA | Complete | None | NA
CALAVERAS WIND PROJECT (100/383MW) | 681 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-02-23 08:00 | C04 | Photovoltaic | Wind Turbine |  | Solar | Wind Turbine |  | 100 | 383 |  | 483 | Full Capacity |  | KERN | CA | SCE | SCE Highwind Substation 230kV | 2015-05-01 07:00 | 2015-05-01 07:00 | NA | None | None | NA
CALRENEW-1 EXPANSION | 682 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-02 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 1.25 | 1.25 | Full Capacity |  | FRESNO | CA | PGAE | Mendota Biomass Tap line 70 KV | 2013-02-01 08:00 | 2013-01-01 08:00 | NA | None | None | NA
CAMDEN 1 | 683 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-17 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 14 | 14 | Full Capacity |  | FRESNO | CA | PGAE | Camden Substation 70kV Bus | 2014-07-10 07:00 | 2014-07-10 07:00 | NA | None | None | NA
CAMDEN 2 | 684 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-17 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 7 | 7 | Full Capacity |  | FRESNO | CA | PGAE | Caruthers - Kingsburg 70kV | 2014-07-10 07:00 | 2014-07-10 07:00 | NA | Complete | None | NA
CENTINELA SOLAR ENERGY EXPANSION II - 45 MW EXPANSION | 685 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-10 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 45 | 45 | Energy Only |  | IMPERIAL | CA | SDGE | Imperial Valley 230 kV bus | 2014-09-01 07:00 | 2014-09-01 07:00 | NA | Complete | None | NA
COLORADO RIVER 48 MW | 686 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-26 15:59 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 48 | 48 | Full Capacity |  | RIVERSIDE | CA | SCE | Colorado River Substation 230kV | 2014-09-01 07:00 | 2014-09-01 07:00 | NA | None | None | NA
COSTA | 688 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2013-05-02 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 19.2 | 19.2 | Full Capacity |  | KINGS | CA | PGAE | Henrietta - Lemoore 70 kV | 2013-08-30 07:00 | 2014-09-01 07:00 | NA | Complete | Complete | NA
COWBOY MESA WIND | 689 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-08-10 07:00 | C04 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 1700 | 1700 | Full Capacity |  | LINCOLN | NM | SCE | Four Corners Sub 345kV Bus | 2016-05-01 07:00 | 2016-05-01 07:00 | NA | None | None | NA
CPV NORTH CITY | 690 | 2011-05-23 | 2011-03-31 07:00 | WITHDRAWN | 2011-06-14 16:04 | C04 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 300 | 300 | Full Capacity |  | SAN DIEGO | CA | SDGE | Approx 4 mi south of the Penasquitos sub along the East side of the Penasquitos-Old Town 230kV line | 2015-06-30 07:00 | 2015-06-30 07:00 | NA | None | None | NA
CREED ENERGY CENTER | 691 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-12-29 00:03 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 3 | 3 | Full Capacity |  | SOLANO | CA | PGAE | Lambie Switching Station 230 KV | 2013-11-30 08:00 | 2013-10-30 07:00 | NA | None | None | NA
DEADHORSE WELLS GEOTHERMAL PROJECT | 692 | 2011-04-15 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-28 07:00 | C04 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 27 | 27 | Full Capacity |  | MINERAL | NV | SCE | Control Substation 115kV Bus | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | Complete | None | NA
DEL SUR SOLAR | 693 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-13 22:29 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 38 | 38 | Full Capacity |  | LOS ANGELES | CA | SCE | Del Sur Substation 66kV Bus | 2012-06-01 07:00 | 2013-03-01 08:00 | NA | Complete | None | NA
DESERT BELL SOLAR | 694 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-07-15 21:04 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 | Full Capacity |  | RIVERSIDE | CA | SCE | Keim Substation, 500kV, 7.1 miles northeast of Colorado River Station | 2014-01-01 08:00 |  | NA | None | None | NA
DIXIE-COMSTOCK GEOTHERMAL PROJECT | 695 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2013-05-03 07:00 | C04 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 38 | 38 | Full Capacity |  | CHURCHILL | NV | SCE | Control Sub 115kV Bus | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | Complete | Complete | NA
DUNNIGAN | 696 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-17 07:00 | C04 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 301.35 | 301.35 | Full Capacity |  | YOLO | CA | PGAE | Cortina - Vaca 230; Delevan - Vaca #1 230 KV, and Delevan - Vaca #2 230 KV | 2014-01-11 08:00 | 2014-11-01 07:00 | NA | Complete | None | NA
EAGLE MOUNTAIN PUMP STORAGE #3 | 697 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-01-13 01:02 | C04 | Generating Facility Type-1: Hydro; Generating Facility Fuel-1: Water; MWs MW-1: 1400 | 1400 | Full Capacity |  | RIVERSIDE | CA | SCE | Red Bluff Substation 230kV | 2017-07-01 07:00 | 2017-07-01 07:00 | NA | None | None | NA
EDWARDS CREEK GEOTHERMAL PROJECT | 698 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-28 07:00 | C04 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 38 | 38 | Full Capacity |  | CHURCHILL | NV | SCE | Control Substation 115kV bus | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | Complete | None | NA
EE BORREGO II | 699 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-13 14:05 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 45 | 45 | Full Capacity |  | SAN DIEGO | CA | SDGE | Borrego Substation 69kV bus | 2015-06-01 07:00 | 2015-06-01 07:00 | NA | None | None | NA
EE ROSAMOND | 700 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-26 16:12 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | SCE | Rosamond-Del Sur 66kV line | 2015-12-31 08:00 | 2015-12-31 08:00 | NA | Complete | None | NA
EGP SOLAR 1 | 701 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-01-19 14:39 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 28 | 28 | Full Capacity |  | SAN DIEGO | CA | SDGE | Borrego Substation 69kV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
EL SEGUNDO ENERGY CENTER 2 ( FKA EL SEGUNDO ENERGY CENTER-II) | 702 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2017-04-14 07:00 | C04 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 435 | 435 | Full Capacity |  | LOS ANGELES | CA | SCE | El Segundo Substation 230kV Bus | 2017-06-01 07:00 | 2020-03-31 07:00 | NA | Complete | Complete | NA | Executed | IC Request
ENRICO MATSON III | 703 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-17 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | FRESNO | CA | PGAE | Panoche - Oro Loma 115 KV Tap | 2014-06-23 07:00 | 2015-01-01 08:00 | NA | Complete | None | NA
FORT MOJAVE SOLAR FARMS 2 | 704 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-12 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 240 | 240 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Mojave Generating Station 500 kV bus | 2016-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
GIFFEN 1 | 706 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-17 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 17.9 | 17.9 | Full Capacity |  | FRESNO | CA | PGAE | Giffen Substation 70KV | 2014-03-01 08:00 | 2014-03-01 08:00 | NA | Complete | None | NA
GOLDEN HILLS SOLAR FARM | 707 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2013-05-03 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 70 | 70 | Full Capacity |  | STANISLAUS | CA | PGAE | Solado sub 115 KV bus | 2014-07-01 07:00 | 2014-07-01 07:00 | NA | Complete | None | NA
GOLDEN HILLS 1 WIND | 708 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2013-05-03 07:00 | C04 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 50 | 50 | Full Capacity |  | ALAMEDA | CA | PGAE | Tesla - Keslo 230 KV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | Complete | Complete | NA
GOOSE HAVEN ENERGY CENTER | 710 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-12-29 00:05 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 3 | 3 | Full Capacity |  | SOLANO | CA | PGAE | Lambie Switching Station 230 KV | 2013-11-30 08:00 | 2013-11-30 08:00 | NA | None | None | NA
GREAT VALLEY SOLAR | 711 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-30 13:52 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 120 | 120 | Full Capacity |  | TULARE | CA | PGAE | Corcoran-Smyrna 115kV line | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
HARBOR COGENERATION | 712 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-16 22:54 | C04 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 28 | 28 | Full Capacity |  | LOS ANGELES | CA | SCE | Harbor Cogeneration Facility | 2015-05-01 07:00 | 2015-05-01 07:00 | NA | Complete | None | NA
HICKORY SOLAR FARM | 713 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-06-16 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 400 | 400 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley 230kV Sub | 2014-07-01 07:00 | 2014-07-01 07:00 | NA | None | None | NA
HIDDEN HILLS RANCH | 714 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2013-04-26 07:00 | C04 | Generating Facility Type-1: Solar Thermal; Generating Facility Fuel-1: Solar; MWs MW-1: 540 | 540 | Full Capacity |  | NYE | NV | VEA | Crazy Eye Tap Substation 230kV | 2014-06-30 07:00 | 2014-12-01 08:00 | NA | Complete | Complete | NA |  | None
JACOBS CORNER SOLAR | 715 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-12 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 13.5 | 13.5 | Full Capacity |  | KINGS | CA | PGAE | Jacob Corner Substation 70KV Bus | 2013-02-01 08:00 | 2013-02-01 08:00 | NA | None | None | NA
JUNIPER SOLAR FARM | 716 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-22 23:13 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | RIVERSIDE | CA | SCE | Colorado River Substation 230kV Bus | 2014-07-01 07:00 | 2014-07-01 07:00 | NA | Complete | None | NA
KINGSOLAR I | 717 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-17 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KINGS | CA | PGAE | Arco Sub 70 KV Bus | 2013-02-28 08:00 | 2013-06-01 07:00 | NA | Complete | None | NA
KINGSOLAR III | 718 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-17 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KINGS | CA | PGAE | Arco Sub 70 KV Bus | 2013-02-28 08:00 | 2014-06-01 07:00 | NA | Complete | None | NA
LAMBIE ENERGY CENTER | 719 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-12-29 00:06 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 3 | 3 | Full Capacity |  | SOLANO | CA | PGAE | Lambie Switching Station 230 KV | 2013-11-30 08:00 | 2013-11-30 08:00 | NA | None | None | NA
LONE TREE WIND | 721 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-02-22 08:00 | C04 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 299 | 299 | Full Capacity |  | ALAMEDA | CA | PGAE | Tesla - Westley 230 KV line | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
LOOP RANCH WIND | 722 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-01-03 19:34 | C04 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 299 | 299 | Full Capacity |  | KERN | CA | SCE | Windhub Substation 230kV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
MADISON SOLAR | 724 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-02-23 08:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 500 | 500 | Full Capacity |  | KINGS | CA | PGAE | Gates 230 KV Bus | 2017-12-31 08:00 | 2017-12-31 08:00 | NA | None | None | NA
MAGNOLIA SOLAR FARM | 725 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2013-02-07 08:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 90 | 90 | Full Capacity |  | FRESNO | CA | PGAE | Hammond Sub 115 KV | 2014-07-01 07:00 | 2014-07-01 07:00 | NA | Complete | None | NA
MARICOPA CALIFORNIA SOLAR FARMS I | 726 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-02 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | KERN | CA | PGAE | Midway - Wheeler Ridge #1 and #2 230 kV | 2013-10-30 07:00 | 2015-10-20 07:00 | NA | None | None | NA
MARICOPA CALIFORNIA SOLAR FARMS II | 727 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-02 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | KERN | CA | PGAE | Midway - Wheeler Ridge #1 & #2 230 kV | 2013-10-30 07:00 | 2013-10-30 07:00 | NA | None | None | NA
MARTELLA SOLAR | 728 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-06-13 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KINGS | CA | PGAE | 69 KV POI is at a designated google coordinates | 2013-03-01 08:00 | 2013-03-01 08:00 | NA | None | None | NA
MENDOTA SOLAR I | 729 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-17 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 75 | 75 | Full Capacity |  | FRESNO | CA | PGAE | Mendota Sub 115 KV Bus | 2013-10-01 07:00 | 2013-10-01 07:00 | NA | None | None | NA
MESA SOLAR | 730 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-18 19:41 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 500 | 500 | Full Capacity |  | RIVERSIDE | CA | SCE | Colorado River Substation 230kV | 2018-12-31 08:00 | 2018-12-31 08:00 | NA | Complete | None | NA
MIMOSA SOLAR FARM | 731 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-06-22 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 75 | 75 | Full Capacity |  | FRESNO | CA | PGAE | Kearney Sub 230 KV | 2014-07-01 07:00 | 2014-07-01 07:00 | NA | None | None | NA
MOJAVE VIEW SOLAR | 732 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-12 18:03 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 | Full Capacity |  | KERN | CA | SCE | Windhub Substation 230kV bus | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
MONTEREY WIND | 733 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-01-19 08:00 | C04 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 150 | 150 | Full Capacity |  | MONTEREY | CA | PGAE | Coburn Sub 230 KV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
MONTEZUMA WETLANDS | 734 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-17 07:00 | C04 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 250 | 250 | Full Capacity |  | SOLANO | CA | PGAE | Birds Landing Substation 230 kV | 2012-11-01 07:00 | 2012-11-01 07:00 | NA | Complete | None | NA
MOUNT SIGNAL SOLAR FARM III | 735 | 2010-11-02 | 2011-03-31 07:00 | WITHDRAWN | 2011-12-21 21:25 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley Substation 230kV | 2014-06-01 07:00 | 2014-06-01 07:00 | NA | None | None | NA
MULE MOUNTAIN SOLAR PROJECT | 736 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-22 14:42 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | RIVERSIDE | CA | SCE | Colorado River Substation 230kV bus | 2014-01-01 08:00 | 2014-01-01 08:00 | NA | Complete | None | NA
NAS NORTH ISLAND COGENERATION | 737 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2020-01-30 08:00 | C04 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 4.7 | 4.7 | Full Capacity |  | SAN DIEGO | CA | SDGE | North Island Metering Station 69 kV | 2011-12-01 08:00 | 2014-07-14 07:00 | NA | Complete | Complete | NA | Executed
OTAY MESA ENERGY CENTER UPGRADE | 739 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-22 14:20 | C04 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 20 | 20 | Full Capacity |  | SAN DIEGO | CA | SDGE | Otay Mesa Substation | 2013-03-07 08:00 | 2013-03-07 08:00 | NA | Complete | None | NA
SANDY VALLEY PHASE I SEGS (FKA PAHRUMP VALLEY SEGS) | 740 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2013-05-08 07:00 | C04 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 270 | 270 | Full Capacity |  | CLARK | NV | VEA | Crazy Eyes Tap 230kV | 2015-09-30 07:00 | 2016-09-30 07:00 | NA | Complete | Complete | NA |  | None
PATHFINDER RENEWABLE WIND ENERGY | 741 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-18 17:34 | C04 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 3000 | 3000 | Full Capacity |  | PLATTE | WY | SCE | Eldorado Substation 500kV Bus | 2016-03-03 08:00 | 2020-01-01 08:00 | NA | Complete | None | NA
PLAINFIELD SOLAR | 742 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-06-13 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | YOLO | CA | PGAE | Line Tap to 69 KV - Plainfield | 2013-03-01 08:00 | 2013-03-01 08:00 | NA | None | None | NA
BOLTHOUSE SOLAR (FKA PUMPJACK SOLAR) | 743 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-17 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | KERN | CA | PGAE | Morrow Bay - Midway #1 & #2 230 KV | 2015-05-02 07:00 | 2015-05-02 07:00 | NA | None | None | NA
RE ALPINE | 745 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-06-20 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | Coalinga - Gates #1 70 KV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
RE BLUE STAR | 747 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-20 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | PGAE | Smyrna - Semitropic - Midway 115 KV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
RE CANNON | 748 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-20 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | PGAE | Smyrna - Semitropic - Midway 115 KV line | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
RE COBB | 749 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-20 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 5 | 5 | Full Capacity |  | KERN | CA | PGAE | Old River - Kern #1 70 KV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
RE GOLDTOWN | 750 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-06-27 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | SCE | Either Goldtown-Corum or Goldtown-Lancaster 66kV line on Holt St. | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | None | None | NA
RE JAMESON | 751 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2013-03-20 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 5 | 5 | Full Capacity |  | FRESNO | CA | PGAE | Strout SW Station 70kV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | Complete | None | NA
RE LINCOLN | 752 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2014-07-17 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 12 | 12 | Full Capacity |  | KINGS | CA | PGAE | Guernsey - Henrietta 70 KV | 2013-12-31 08:00 | 2014-12-31 08:00 | NA | Complete | Complete | NA
RE MONTEREY | 753 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-20 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 3 | 3 | Full Capacity |  | FRESNO | CA | PGAE | Gates - Coalinga #1 70 KV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
RE OASIS | 754 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-06-27 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 300 | 300 | Full Capacity |  | RIVERSIDE | CA | SCE | 220kV Red Bluff Substation | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | None | None | NA
RE OIL CITY | 755 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-06-20 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | Gates - Coalinga #1 70 KV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
RE PADRE | 756 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-02-28 08:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 60 | 60 | Full Capacity |  | SAN DIEGO | CA | SDGE | Borrego substation 69kV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
RE PALMER | 757 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-06-20 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | Gates - Coalinga #1 70 KV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
RE SOLEDAD | 758 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-06-27 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 19.98 | 19.98 | Full Capacity |  | KERN | CA | SCE | Goldtown-Corum or Goldtown-Lancaster 66kV line | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | None | None | NA
RE TRACTOR | 759 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-06-20 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | Gates - Coalinga #1 70 KV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
RE WILDWOOD | 760 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-20 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | PGAE | Smyrna - Semitropic - Midway #1 115 KV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
RE WILLOW SPRINGS | 761 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-06-27 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | SCE | Cal Cement-Antelope 66kV line | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | None | None | NA
SAGE SOLAR FARM | 762 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2013-05-03 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 70 | 70 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Contra Costa-Delta SW Yard 230kV | 2014-07-01 07:00 | 2014-07-01 07:00 | NA | Complete | None | NA
SAN JOAQUIN 2B | 763 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-17 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | Stroud SW Sta 70 KV | 2013-12-01 08:00 | 2013-12-01 08:00 | NA | None | None | NA
SANTA CATARINA WIND | 764 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-13 15:47 | C04 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 508 | 508 | Full Capacity |  | ENSENADA | MX | SDGE | Imperial Valley Substation 500kV Bus | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | None | None | NA
FRONTIER SOLAR II (FKA SCATEC WESTSIDE SOLAR RANCH II) | 765 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2013-04-26 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 30 | 30 | Full Capacity |  | STANISLAUS | CA | PGAE | Salado - Newman 60 KV | 2013-10-01 07:00 | 2013-10-01 07:00 | NA | Complete | Complete | NA
SILVERTREE GREENWORKS | 766 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-30 15:50 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley Substation 230kV bus | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | Complete | None | NA
SOLDIER FLAT | 767 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-02-23 16:17 | C04 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 400 | 400 | Full Capacity |  | KERN | CA | SCE | Highwind Substation 230kV bus | 2015-07-01 07:00 | 2015-07-01 07:00 | NA | None | None | NA
SUNCREST IMPERIAL SEGS | 770 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-02-16 08:00 | C04 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 1080 | 1080 | Full Capacity |  | IMPERIAL | CA | SDGE | ECO Sub 230kV | 2015-06-30 07:00 | 2015-06-30 07:00 | NA | None | None | NA
TA-EAST LANCASTER | 771 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-02-21 23:55 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 14 | 14 | Full Capacity |  | LOS ANGELES | CA | SCE | Plute-Lancaster 66kV line | 2012-03-03 08:00 | 2013-03-01 08:00 | NA | None | None | NA
TESLA SOLAR FARM | 772 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-02-23 08:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Stanislaus - Manteca #2 115 kV Line | 2014-06-01 07:00 | 2014-06-01 07:00 | NA | None | None | NA
THUNDERHILL SOLAR POWER UNIT 2 | 773 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-17 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 18 | 18 | Full Capacity |  | GLENN | CA | PGAE | Elk Creek 60 KV Tap | 2013-06-01 07:00 | 2013-06-01 07:00 | NA | None | None | NA
TUNGSTEN MOUNTAIN GEOTHERMAL PROJECT | 774 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-26 07:00 | C04 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 38 | 38 | Full Capacity |  | CHURCHILL | NV | SCE | Control Substation 115 kV bus | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | Complete | None | NA
UTICA 25MW PV PROJECT | 776 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-01-26 08:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 25 | 25 | Full Capacity |  | KINGS | CA | PGAE | Tulare Lake - Arco 70 KV | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | None | None | NA
WELLHEAD POWER KERN 3 | 777 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-06-10 07:00 | C04 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 400 | 400 | Full Capacity |  | KERN | CA | SCE | Pastoria-Magunden 230kV line | 2015-07-01 07:00 | 2015-07-01 07:00 | NA | None | None | NA
ZAMORA SOLAR | 780 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-26 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 30 | 30 | Full Capacity |  | YOLO | CA | PGAE | Woodland - Zamora - Rio Oso #2 115kV Bus | 2013-03-01 08:00 | 2013-03-01 08:00 | NA | None | None | NA
ZODIAC SOLAR | 781 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2015-08-06 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 0.1 | 0.1 | Full Capacity |  | SAN DIEGO | CA | SDGE | Barrett-Cameron 69kV line | 2014-12-31 08:00 | 2015-11-30 08:00 | NA | Complete | Complete | NA
CSED BARSTOW ROAD 100 MW PV GENERATING STATION | 782 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-27 15:16 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Jasper Switching Station 220kV bus | 2014-06-01 07:00 | 2014-06-01 07:00 | NA | Complete | None | NA
DAGGETT SOLAR PROJECT | 783 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-11 16:42 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Cool Water Substation 115kV | 2014-06-01 07:00 | 2018-06-01 07:00 | NA | Complete | None | NA
GWF TRACY SOLAR | 784 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-20 15:58 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Schulte sub 115 KV | 2014-06-02 07:00 | 2014-06-02 07:00 | NA | Complete | None | NA
HIGH DESERT SOLAR | 785 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-12 18:03 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 16 | 16 | Full Capacity |  | KERN | CA | SCE | Silver Queen-Goldtown 69kV line | 2013-01-05 08:00 | 2013-01-05 08:00 | NA | None | None | NA
HIGHWAY 58 SOLAR ENERGY PROJECT | 786 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-02-29 08:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 80 | 80 | Full Capacity |  | KERN | CA | SCE | Windhub Substation 66kV | 2014-12-01 08:00 | 2014-12-01 08:00 | NA | None | None | NA
REDDY I | 787 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-17 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 8 | 8 | Full Capacity |  | KERN | CA | PGAE | Arco-Carneras 70 kV Line | 2014-10-07 07:00 | 2015-01-01 08:00 | NA | None | None | NA
ROYAL SOLAR PROJECT | 788 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-12 14:17 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | LOS ANGELES | CA | SCE | Antelope Substation 66kV bus | 2014-06-01 07:00 | 2018-06-01 07:00 | NA | Complete | None | NA
RUGGED SOLAR FARM | 789 | 2011-03-30 | 2011-03-31 07:00 | WITHDRAWN | 2025-03-04 08:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 71.88 | 71.88 | Energy Only | Off-Peak Deliverability | SAN DIEGO | CA | SDGE | Boulevard East Substation 69 kV | 2015-07-31 07:00 | 2025-04-01 07:00 | NA | Complete | Complete | NA | Executed | IC Request
SUNSHINE 3 | 790 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-02-22 16:03 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 45 | 45 | Full Capacity |  | KERN | CA | SCE | Antelope-Rosamond 66kV line | 2014-06-01 07:00 | 2014-06-01 07:00 | NA | None | None | NA
WILDFLOWER GREEN ENERGY FARM- SOLAR | 791 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-12 18:05 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | LOS ANGELES | CA | SCE | Antelope Substation 220kV Bus | 2013-07-31 07:00 | 2013-07-31 07:00 | NA | None | None | NA
SILURIAN VALLEY WIND | 792 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-13 22:32 | C04 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 200 | 200 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Ivanpah Substation 220kV bus | 2014-09-01 07:00 | 2015-12-15 08:00 | NA | Complete | None | NA
TCA SOLAR GOLDTOWN | 793 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-26 16:26 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 75 | 75 | Full Capacity |  | KERN | CA | SCE | Goldtown Substation 66kV Bus | 2013-04-01 07:00 | 2015-12-31 08:00 | NA | Complete | None | NA
TIERRA DEL SOL SOLAR FARM | 794 | 2011-03-30 | 2011-03-31 07:00 | WITHDRAWN | 2015-02-19 08:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 45 | 45 | Full Capacity |  | SAN DIEGO | CA | SDGE | Boulevard East Substation 138kV | 2015-04-30 07:00 | 2016-05-31 07:00 | NA | Complete | Complete | NA
HOLLY RANCH | 797 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2014-04-14 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 0.5 | 0.5 | Full Capacity |  | RIVERSIDE | CA | SCE | Red Bluff Substation 230kV | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | Complete | Complete | NA
SP BLYTHE 1 | 798 | 2010-12-15 | 2011-03-31 07:00 | WITHDRAWN | 2016-11-09 08:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 221 | 221 | Energy Only |  | RIVERSIDE | CA | SCE | Colorado River Substation 230kV | 2014-12-31 08:00 | 2018-09-30 07:00 | NA | Complete | Complete | NA |  | IC Request
ASPIRATION SOLAR D | 799 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2016-07-28 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 0.1 | 0.1 | Full Capacity |  | FRESNO | CA | PGAE | Mendota-San Joaquin-Helm 70kV | 2014-12-31 08:00 | 2015-11-30 08:00 | NA | Complete | Complete | NA |  | None
ASPIRATION SOLAR E | 800 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2016-07-28 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 0.1 | 0.1 | Full Capacity |  | FRESNO | CA | PGAE | Mendota-San Joaquin-Helm 70kV | 2014-12-31 08:00 | 2015-11-30 08:00 | NA | Complete | Complete | NA |  | None
BUTTE SOLAR | 801 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-06-30 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 75 | 75 | Full Capacity |  | BUTTE | CA | PGAE | Butte-Table Mountain 115kV No. 2 | 2014-02-28 08:00 | 2014-02-28 08:00 | NA | None | None | NA
CANDLEWOOD WIND | 802 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-06-23 07:00 | C03 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 150 | 150 | Energy Only |  | IMPERIAL | CA | SDGE | 500kV at Ocotillo Express | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
CENTRAL VALLEY I SEGS | 803 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-30 14:47 | C04 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 1080 | 1080 | Full Capacity |  | KERN | CA | PGAE | Midway - Wheeler Ridge #1 & #2 230 kV | 2015-06-30 07:00 | 2015-06-30 07:00 | NA | None | None | NA
CENTRAL VALLEY II SEGS | 804 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-30 21:30 | C04 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 540 | 540 | Full Capacity |  | KERN | CA | PGAE | Arco Substation 230 KV bus | 2015-06-30 07:00 | 2015-12-01 08:00 | NA | None | None | NA
CITIZEN SOLAR C | 805 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2016-07-28 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 0.1 | 0.1 | Full Capacity |  | FRESNO | CA | PGAE | Mendota-San Joaquin-Helm 69K | 2014-12-31 08:00 | 2015-11-30 08:00 | NA | Complete | Complete | NA |  | None
CITIZEN SOLAR D | 806 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2016-07-28 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 0.1 | 0.1 | Full Capacity |  | FRESNO | CA | PGAE | Mendota-San Joaquin-Helm 70 KV | 2014-12-31 08:00 | 2015-11-30 08:00 | NA | Complete | Complete | NA |  | None
CVH POWER I | 807 | 2011-03-29 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-26 16:08 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 300 | 300 | Full Capacity |  | MARICOPA | AZ | SCE | Harquahala Substation 500kV | 2014-09-15 07:00 | 2014-09-15 07:00 | NA | None | None | NA
CVH POWER II | 808 | 2011-03-29 | 2011-03-31 07:00 | WITHDRAWN | 2011-08-05 23:02 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 700 | 700 | Full Capacity |  | MARICOPA | AZ | SCE | Harquahala Substation 500kV | 2014-09-15 07:00 | 2014-09-15 07:00 | NA | None | None | NA
ELEVATION SOLAR C | 809 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2016-07-28 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 0.1 | 0.1 | Full Capacity |  | FRESNO | CA | PGAE | Stroud switching station 70kV | 2014-12-31 08:00 | 2017-05-30 07:00 | NA | Complete | Complete | NA |  | None
FRESNO SOLAR | 810 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-30 22:44 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | FRESNO | CA | PGAE | Gates-McCall 230kV | 2014-02-28 08:00 | 2014-02-28 08:00 | NA | None | None | NA
GRAHAM SOLAR FARM I EXPANSION | 811 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-17 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | Schindler Substation 115 KV Bus | 2013-06-30 07:00 | 2013-12-25 08:00 | NA | Complete | None | NA
GRAHAM SOLAR FARM II | 812 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-17 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | Schindler Substation 115 KV Bus | 2013-06-30 07:00 | 2013-12-25 08:00 | NA | Complete | None | NA
GRAHAM SOLAR FARM II EXPANSION | 813 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-17 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | Schindler Substation 115 KV Bus | 2013-06-30 07:00 | 2013-12-25 08:00 | NA | Complete | None | NA
INSPIRATION SOLAR C | 814 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2016-07-28 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 0.1 | 0.1 | Full Capacity |  | FRESNO | CA | PGAE | Stroud switching station 70kV | 2014-12-31 08:00 | 2017-05-30 07:00 | NA | Complete | Complete | NA |  | None
INSPIRATION SOLAR E | 815 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2016-07-28 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 0.1 | 0.1 | Full Capacity |  | FRESNO | CA | PGAE | Stroud switching station 70kV | 2014-12-31 08:00 | 2017-05-30 07:00 | NA | Complete | Complete | NA |  | None
INSPIRATION SOLAR F | 816 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2016-07-28 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 0.1 | 0.1 | Full Capacity |  | FRESNO | CA | PGAE | Stroud switching station 70kV | 2014-12-31 08:00 | 2017-05-30 07:00 | NA | Complete | Complete | NA |  | None
JERSEY AVE 20 MW SOLAR PROJECT | 817 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-02-28 08:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | TULARE | CA | PGAE | Henrietta-GWF 115kV | 2012-06-30 07:00 | 2012-06-30 07:00 | NA | None | None | NA
LE GRAND CA 20 MW SOLAR PROJECT | 818 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-30 15:05 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | MERCED | CA | PGAE | Le Grand 115 KV | 2013-06-30 07:00 | 2013-06-30 07:00 | NA | None | None | NA
WESTLANDS LEMOORE SOLAR | 819 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-12 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 | Full Capacity |  | KINGS | CA | PGAE | Gates Substation 500 KV | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | None | None | NA
LIBERTY SOLAR | 820 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2016-07-29 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 0.1 | 0.1 | Full Capacity |  | FRESNO | CA | PGAE | Mendota Sub 115KV Bus | 2014-12-31 08:00 | 2016-12-31 08:00 | NA | Complete | Complete | NA |  | None
MADERA SOLAR | 821 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-29 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 60 | 60 | Full Capacity |  | MADERA | CA | PGAE | Borden Sub 70 KV Bus | 2014-02-28 08:00 | 2014-02-28 08:00 | NA | None | None | NA
WESTSIDE RENEWAL PV PROJECT | 822 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-29 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 110 | 110 | Full Capacity |  | KINGS | CA | PGAE | Gates - Midway 230 KV | 2014-02-28 08:00 | 2014-02-28 08:00 | NA | None | None | NA
NORTH VALLEY SOLAR | 823 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2016-07-28 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 0.1 | 0.1 | Full Capacity |  | FRESNO | CA | PGAE | Oro Loma - Panoche 115 KV | 2014-12-31 08:00 | 2017-05-30 07:00 | NA | Complete | Complete | NA |  | None
PATRIOT SOLAR A | 824 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2016-08-09 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | FRESNO | CA | PGAE | Mendota Sub 115 KV Bus | 2014-12-31 08:00 | 2018-03-31 07:00 | NA | Complete | Complete | NA |  | None
PATRIOT SOLAR B | 825 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2016-08-09 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | FRESNO | CA | PGAE | Mendota Sub 115 KV Bus | 2014-12-31 08:00 | 2018-03-31 07:00 | NA | Complete | Complete | NA |  | None
ORION SOLAR KERN COUNTY 3 | 826 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-06-30 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | PGAE | Westfield Sub 70 KV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
SAN JOAQUIN SOLAR | 827 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-30 22:23 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Bellota - Tesla #2 230 KV | 2014-02-28 08:00 | 2014-02-28 08:00 | NA | None | None | NA
SEMITROPIC SOLAR | 828 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-17 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 | Full Capacity |  | KERN | CA | PGAE | Smyrna Sub 115 KV Bus | 2014-04-30 07:00 | 2014-04-30 07:00 | NA | None | None | NA
SOLANO SOLAR | 830 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-26 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 80 | 80 | Full Capacity |  | SOLANO | CA | PGAE | Vaca - Dixon Sub 115 KV Bus | 2014-02-28 08:00 | 2014-02-28 08:00 | NA | None | None | NA
SONORAN WEST I SEGS | 831 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2013-05-08 07:00 | C04 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 270 | 270 | Full Capacity |  | RIVERSIDE | CA | SCE | Colorado River Substation 230kV | 2016-01-01 08:00 | 2016-10-31 07:00 | NA | Complete | Complete | NA
STANISLAUS SOLAR | 832 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-07-08 14:58 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 75 | 75 | Full Capacity |  | STANISLAUS | CA | PGAE | Tesla - Miller 115 KV | 2014-02-28 08:00 | 2014-02-28 08:00 | NA | None | None | NA
WARTHAN CREEK SOLAR PROJECT | 833 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-30 15:24 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | Coalinga 70 KV | 2013-12-01 08:00 | 2013-12-01 08:00 | NA | None | None | NA
WELLHEAD POWER KERN 1 | 834 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-13 22:29 | C04 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49 | 49 | Full Capacity |  | KERN | CA | SCE | Gorman-Kern River 66kV line | 2013-06-01 07:00 | 2013-06-01 07:00 | NA | Complete | None | NA
WSP 3 | 835 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-07 08:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 800 | 800 | Full Capacity |  | KINGS | CA | PGAE | Gates Sub 500 KV Bus | 2018-02-01 08:00 | 2018-02-01 08:00 | NA | None | None | NA
AREVA SOLAR AZ I | 836 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-26 07:00 | C04 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | YUMA | AZ | SDGE | North Gila Substation 500 kV | 2015-12-01 08:00 | 2015-12-01 08:00 | NA | Complete | None | NA
JACUMBA II SOLAR FARM | 837 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2013-05-08 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | SAN DIEGO | CA | SDGE | East County (ECO) Substation 138kV | 2013-05-01 07:00 | 2016-02-01 08:00 | NA | Complete | None | NA
DESERT HARVEST SOLAR FARM | 839 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-28 16:50 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | IMPERIAL | CA | SCE | Colorado River Substation 230kV bus | 2015-11-30 08:00 | 2015-11-30 08:00 | NA | Complete | None | NA
DESERT QUARTZITE SOLAR | 840 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-22 16:16 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 300 | 300 | Full Capacity |  | RIVERSIDE | CA | SCE | Colorado River Substation 230kV bus | 2015-12-31 08:00 | 2015-12-31 08:00 | NA | Complete | None | NA
HYDER SOLAR ENERGY PROJECT | 841 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-30 15:31 | C04 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 | Full Capacity |  | YUMA | AZ | SDGE | Hassayampa-North Gila 500kV | 2014-09-01 07:00 | 2014-09-01 07:00 | NA | Complete | None | NA
JASPER SEGS (FKA SONORAN WEST II) | 842 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-30 21:29 | C04 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 540 | 540 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Jasper Substation 220kV | 2016-01-01 08:00 | 2016-10-31 07:00 | NA | Complete | None | NA
OAK CREEK SOLAR I | 843 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-26 23:09 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 35.3 | 35.3 | Full Capacity |  | KERN | CA | SCE | 66kV Windhub Substation | 2014-11-30 08:00 | 2013-12-01 08:00 | NA | Complete | None | NA
RE JUNIPER | 844 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2011-06-27 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | SCE | Cal Cement-Antelope 66kV line | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | None | None | NA
SIERRA VIEW SOLAR III | 845 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-23 21:08 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 15 | 15 | Full Capacity |  | KERN | CA | SCE | Corum-Goldtown 69kV line | 2015-09-15 07:00 | 2015-09-15 07:00 | NA | None | None | NA
SOLAR FOUR | 846 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-12 22:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 510 | 510 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley 230-kV Substation | 2017-04-30 07:00 | 2017-04-30 07:00 | NA | None | None | NA
SUN HILL RANCH SOLAR 1 | 847 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-02 15:28 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Kramer-Victor 115kV line | 2013-06-30 07:00 | 2016-01-01 08:00 | NA | Complete | None | NA
VALLE DEL SOL | 848 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-04 17:36 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley Substation 12kV Bus | 2013-12-01 08:00 | 2013-12-01 08:00 | NA | Complete | None | NA
WILLOW SOLAR | 849 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-03 16:03 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | KERN | CA | SCE | Whirlwind Substation 230kV | 2016-12-31 08:00 | 2016-12-31 08:00 | NA | Complete | None | NA
CHALLENGER | 850 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-26 15:52 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 25 | 25 | Full Capacity |  | LOS ANGELES | CA | SCE | Redman-Lancaster 66kV line | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | None | None | NA
COYOTE CANYON | 851 | 2011-03-30 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-06 08:00 | C04 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 70 | 70 | Full Capacity |  | CHURCHILL | NV | SCE | Control Substation 115kV | 2013-08-01 07:00 | 2013-08-01 07:00 | NA | None | None | NA
FAVORITO | 852 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-26 16:16 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 25 | 25 | Full Capacity |  | KERN | CA | SCE | Rosamond-Cal Cement 66kV line | 2014-06-30 07:00 | 2014-06-30 07:00 | NA | None | None | NA
MONOLITH 20 MW (FKA WDAT-BREEZE) | 853 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-13 22:28 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | SCE | Monolith Substation 66kV | 2013-10-01 07:00 | 2014-12-31 08:00 | NA | Complete | None | NA
MURPHY 1 | 854 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-13 22:28 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 37 | 37 | Full Capacity |  | RIVERSIDE | CA | SCE | Blythe Substation 161kV bus | 2014-06-23 07:00 | 2015-01-01 08:00 | NA | Complete | None | NA
TULARE SOLAR | 857 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-03-07 01:11 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | TULARE | CA | SCE | Springville Sub 230 KV Bus | 2014-02-28 08:00 | 2014-02-28 08:00 | NA | None | None | NA
WILD SANDS SOLAR | 858 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-13 22:27 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 21 | 21 | Full Capacity |  | RIVERSIDE | CA | SCE | Devers-Farrel 115kV line | 2012-12-31 08:00 | 2014-09-01 07:00 | NA | Complete | None | NA
LODI 5 | 861 | 2011-03-18 | 2011-03-31 07:00 | WITHDRAWN | 2012-10-31 07:00 | FT | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 5 | 5 | Energy Only |  | SAN JOAQUIN | CA | PGAE | PG&E Valley Springs #2 60 kV Line from Valley Springs to Lockford 60 kV line | 2012-12-15 08:00 | 2012-12-15 08:00 | None | NA | NA | NA
819 HANFORD SOLAR I | 862 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-08-17 07:00 | FT | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 5 | 5 | Energy Only |  | KINGS | CA | PGAE | PG&E Armstrong 70kV switching station at intersection of S 11th Ave. and Idaho Avenue, Hanford, CA. | 2012-06-30 07:00 | 2012-06-30 07:00 | None | NA | NA | NA
LEMOORE WWTP SOLAR | 863 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-18 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 7.8 | 7.8 | Full Capacity |  | KINGS | CA | PGAE | Guernsey - Henrietta 70 KV line | 2012-07-31 07:00 | 2013-03-31 07:00 | NA | Complete | None | NA
MADDOX DAIRY SOLAR | 864 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-18 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 19.9 | 19.9 | Full Capacity |  | FRESNO | CA | PGAE | Stroud 70 KV substation | 2012-08-31 07:00 | 2013-06-30 07:00 | NA | Complete | None | NA
WELLFIELD SOLAR | 865 | 2011-03-31 | 2011-03-31 07:00 | WITHDRAWN | 2012-04-18 07:00 | C04 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 13.4 | 13.4 | Full Capacity |  | KINGS | CA | PGAE | Hardwick 70 KV sub | 2012-07-31 07:00 | 2013-03-31 07:00 | NA | None | None | NA
REDWOOD HOUSE WIND POWER PLANT | 866 | 2011-10-24 | 2011-11-15 08:00 | WITHDRAWN | 2012-05-03 07:00 | C05 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 72 | 72 | Full Capacity |  | HUMBOLDT | CA | PGAE | Humboldt-Bridgeville 115 kV line | 2015-10-01 07:00 | 2015-10-01 07:00 | NA | None | None | NA
WHITEHORSE MOUNTAIN WIND POWER PLANT | 867 | 2011-10-27 | 2011-11-15 08:00 | WITHDRAWN | 2012-01-27 08:00 | C05 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 132 | 132 | Full Capacity |  | SISKIYOU/MODOC | CA | PGAE | Pit#1-Pit#3 230kV line | 2016-10-01 07:00 |  | NA | None | None | NA
CORDELIA HILLS WIND POWER PLANT | 868 | 2011-11-10 | 2011-11-15 08:00 | WITHDRAWN | 2012-08-03 07:00 | C05 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 301 | 301 | Full Capacity |  | NAPA | CA | PGAE | Vaca-Bahia 230kV line | 2016-10-01 07:00 | 2016-10-01 07:00 | NA | None | None | NA
HELM 1 | 869 | 2011-11-15 | 2011-11-15 08:00 | WITHDRAWN | 2014-10-27 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 23 | 23 | Full Capacity |  | FRESNO | CA | PGAE | Helm Substation 70kV Bus | 2015-12-01 08:00 | 2015-12-01 08:00 | NA | Complete | Complete | NA
HYDROGEN ENERGY CALIFORNIA ( HECA ) PROJECT | 870 | 2011-11-10 | 2011-11-15 08:00 | WITHDRAWN | 2013-05-02 07:00 | C05 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Other; MWs MW-1: 340 | 300 | Full Capacity |  | KERN | CA | PGAE | Midway-Wheeler Ridge 230 kV | 2017-09-01 07:00 | 2017-09-01 07:00 | NA | Complete | None | NA
MESA VERDE SOLAR | 871 | 2011-11-15 | 2011-11-15 08:00 | WITHDRAWN | 2013-05-06 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 80 | 80 | Full Capacity |  | RIVERSIDE | CA | SCE | Colorado River Substation 230kV | 2014-03-01 08:00 | 2015-10-31 07:00 | NA | Complete | None | NA
BELRIDGE SOLAR ENERGY PROJECT | 872 | 2011-11-15 | 2011-11-15 08:00 | WITHDRAWN | 2012-07-30 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 75 | 75 | Full Capacity |  | KERN | CA | PGAE | Carneras-Taft 70 kV Line | 2014-12-15 08:00 | 2014-12-15 08:00 | NA | None | None | NA
SUN VALLEY ENERGY CENTER-1 | 873 | 2011-11-09 | 2011-11-15 08:00 | WITHDRAWN | 2013-03-15 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 | Full Capacity |  | MARICOPA | AZ | SCE | Palo Verde-Devers #1 500kV line | 2015-09-30 07:00 | 2016-12-01 08:00 | NA | Complete | None | NA
BLYTHE MESA SOLAR II | 874 | 2011-11-15 | 2011-11-15 08:00 | WITHDRAWN | 2012-02-23 22:40 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 500 | 500 | Full Capacity |  | RIVERSIDE | CA | SCE | Colorado River Substation 230kV | 2015-10-30 07:00 | 2015-10-30 07:00 | NA | None | None | NA
SILVERLEAF SOLAR II | 875 | 2011-11-09 | 2011-11-15 08:00 | WITHDRAWN | 2012-08-02 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 60 | 60 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley Substation 230kV | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | None | None | NA
ZANNON SOLAR | 876 | 2011-12-06 | 2011-11-21 08:00 | WITHDRAWN | 2012-09-19 07:00 | FT | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 5 | 5 | Energy Only |  | SANTA BARBARA | CA | PGAE | Cuyama Substation | 2013-10-13 07:00 | 2013-10-13 07:00 | None | NA | NA | NA
HORSE LAKE | 878 | 2012-03-27 | 2012-04-02 07:00 | WITHDRAWN | 2013-03-07 08:00 | C05 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 51 | 51 | Full Capacity |  | LASSEN | CA | PGAE | Westwood Substation 60kV | 2013-12-31 08:00 | 2013-12-31 08:00 | NA | None | None | NA
LASSEN LODGE HYDROELECTRIC PROJECT EXPANSION | 879 | 2012-03-28 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-15 07:00 | C05 | Generating Facility Type-1: Hydro; Generating Facility Fuel-1: Water; MWs MW-1: 1.35 | 1.35 | Energy Only |  | TEHAMA | CA | PGAE | Volta/South 60 kV | 2013-12-15 08:00 | 2013-12-15 08:00 | NA | None | None | NA
COPPER RAYS SOLAR | 880 | 2012-03-23 | 2012-04-02 07:00 | WITHDRAWN | 2012-07-31 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 180 | 180 | Full Capacity |  | NYE | NV | VEA | Gamebird Substation 138kV | 2013-01-01 08:00 | 2013-01-01 08:00 | NA | None | None | NA |  | None
BLYTHE MESA SOLAR II - C5 | 881 | 2012-03-28 | 2012-04-02 07:00 | WITHDRAWN | 2012-07-25 20:57 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 500 | 500 | Full Capacity |  | RIVERSIDE | CA | SCE | Colorado River Substation 230kV | 2015-10-30 07:00 | 2015-10-30 07:00 | NA | None | None | NA
GREAT VALLEY SOLAR 2 | 882 | 2012-03-23 | 2012-04-02 07:00 | WITHDRAWN | 2012-07-25 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 120 | 120 | Full Capacity |  | TULARE | CA | PGAE | Olive Substation 115 kV | 2015-12-31 08:00 | 2015-12-31 08:00 | NA | None | None | NA
RIPON LM6000 REPOWER | 883 | 2012-03-28 | 2012-04-02 07:00 | WITHDRAWN | 2012-06-22 07:00 | C05 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 11 | 11 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Tesla - Stockton Co-Gen Jct 115 kV Line | 2018-09-01 07:00 | 2018-09-01 07:00 | NA | None | None | NA
SANDY VALLEY SOLAR PROJECT | 884 | 2012-03-29 | 2012-04-02 07:00 | WITHDRAWN | 2012-06-26 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 | Full Capacity |  | NYE | NV | VEA | Crazy Eyes Subsation 230kV | 2018-12-31 08:00 | 2018-12-31 08:00 | NA | None | None | NA |  | None
TRACY DESALINATION AND GREEN ENERGY PROJECT | 886 | 2012-03-30 | 2012-04-02 07:00 | WITHDRAWN | 2012-07-30 07:00 | C05 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Biofuel; MWs MW-1: 15 | 15 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Tracy-Tesla 115kV line | 2014-08-31 07:00 | 2014-08-31 07:00 | NA | None | None | NA
BOULDER SOLAR POWER | 887 | 2012-03-23 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-06 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 300 | 300 | Full Capacity |  | CLARK | NV | SCE | Eldorado Substation 220kV Bus | 2015-01-01 08:00 | 2016-11-01 07:00 | NA | Complete | None | NA |  | None
LUCERNE VALLEY 100 MW PV PLANT | 888 | 2012-03-31 | 2012-04-02 07:00 | WITHDRAWN | 2013-03-13 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Jasper 220 kV | 2015-10-15 07:00 | 2015-10-15 07:00 | NA | Complete | None | NA
SANDY VALLEY PHASE II SEGS | 889 | 2012-03-31 | 2012-04-02 07:00 | WITHDRAWN | 2012-06-19 07:00 | C05 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 540 | 540 | Full Capacity |  | CLARK | NV | SCE | Eldorado Substation 220 kV Bus | 2016-06-30 07:00 | 2016-06-30 07:00 | NA | None | None | NA
BACKUS SOLAR ENERGY | 890 | 2012-03-31 | 2012-04-02 07:00 | WITHDRAWN | 2013-03-29 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 | Full Capacity |  | KERN | CA | SCE | Cal Cement-Rosamond 69kV line | 2014-03-01 08:00 | 2018-08-31 07:00 | NA | Complete | None | NA
TOWNSITE SOLAR PROJECT | 891 | 2012-03-30 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-01 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 180 | 180 | Full Capacity |  | CLARK | NV | SCE | Eldorado Substation 230 kV bus | 2014-06-01 07:00 | 2016-07-01 07:00 | NA | Complete | None | NA
SIBERIA PHASE III SEGS | 892 | 2012-03-31 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-01 07:00 | C05 | Generating Facility Type-1: Solar Thermal; Generating Facility Fuel-1: Solar; MWs MW-1: 140 | 140 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Pisgah Substation 220kV bus | 2015-12-31 08:00 | 2015-12-31 08:00 | NA | Complete | None | NA
HUNTINGTON BEACH | 893 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2017-08-31 07:00 | C05 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 938.612 | 938.61 | Energy Only |  | ORANGE | CA | SCE | Huntington Beach Switching Station 230kV | 2020-06-01 07:00 | 2020-06-01 07:00 | NA | Complete | Complete | NA | Executed | IC Request
PROSPECT ENERGY CENTER | 894 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-02-27 08:00 | C05 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 310 | 310 | Full Capacity |  | YUBA | CA | PGAE | Table Mountain-Rio Oso 230kV circuit | 2017-04-01 07:00 | 2017-04-01 07:00 | NA | None | None | NA
TIERRA DEL SOL II | 895 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2015-02-19 08:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 15 | 15 | Full Capacity |  | SAN DIEGO | CA | SDGE | Boulevard East Substation 138kV | 2014-12-31 08:00 | 2014-12-31 08:00 | NA | Complete | Complete | NA
LOS ROBLES | 896 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-03-25 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | SAN DIEGO | CA | SDGE | Boulevard East Substation 138kV | 2015-09-01 07:00 | 2015-09-01 07:00 | NA | Complete | None | NA
STAGE COACH SOLAR | 897 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2025-01-27 08:00 | C05 | Photovoltaic | Storage |  | Solar | Battery |  | 200 | 50 |  | 200 | Energy Only | Off-Peak Deliverability | SAN BERNARDINO | CA | SCE | Calcite Substation 220kV bus | 2016-12-01 08:00 | 2026-08-01 07:00 | NA | Complete | Complete | NA | Terminated | IC Request
KPP - 45 | 898 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-04-08 07:00 | C05 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 45 | 45 | Full Capacity |  | KERN | CA | PGAE | Famoso Substation 115kV bus | 2014-01-01 08:00 | 2019-09-30 07:00 | NA | Complete | None | NA
DUNNIGAN HILLS | 899 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-15 07:00 | C05 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 100 | 100 | Full Capacity |  | YOLO | CA | PGAE | Ckt I & 2 Delevan-Vaca and Cortina-Vaca 230 kV lines | 2015-08-31 07:00 | 2013-11-30 08:00 | NA | None | None | NA
QUARTZ 2 SOLAR | 902 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-06 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | RIVERSIDE | CA | SCE | Colorado River sub, 230 kV bus | 2016-12-31 08:00 | 2016-12-31 08:00 | NA | Complete | None | NA
DESERT BUTTE SOLAR FARM | 903 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-06 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 387 | 387 | Full Capacity |  | LOS ANGELES | CA | SCE | Lugo-Vincent 500 kV line | 2016-12-20 08:00 | 2016-12-20 08:00 | NA | Complete | None | NA
MULE MOUNTAIN - C5 | 904 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-02-28 08:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | RIVERSIDE | CA | SCE | Colorado River Substation 230kV | 2016-07-01 07:00 | 2016-07-01 07:00 | NA | None | None | NA
BELRIDGE SOLAR ENERGY 2 PROJECT | 905 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2012-07-30 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 80 | 80 | Full Capacity |  | KERN | CA | PGAE | Temblor-Kernridge 115kV line | 2016-06-30 07:00 | 2016-06-30 07:00 | NA | None | None | NA
LUCERNE SOLAR ENERGY - C5 | 906 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2012-08-03 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Jasper Substation 230kV | 2015-05-01 07:00 | 2015-05-01 07:00 | NA | None | None | NA
NEWHALL SOLAR ENERGY PROJECT | 907 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2012-07-30 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 80 | 80 | Full Capacity |  | FRESNO | CA | PGAE | Newhall Substation 115 kV bus | 2013-10-22 07:00 | 2013-10-22 07:00 | NA | None | None | NA
PAHRUMP VALLEY SOLAR (FKA LATHROP WELLS 240MW) | 908 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2015-03-12 07:00 | C05 | Photovoltaic | Steam Turbine |  | Solar | Solar |  | 50 | 160 |  | 210 | Full Capacity |  | NYE | NV | VEA | Crazy Eyes Tap 230kV | 2017-06-01 07:00 | 2019-02-28 08:00 | NA | Complete | Complete | NA |  | None
HONEY LAKE GEOTHERMAL PROJECT | 910 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-15 07:00 | C05 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 20 | 20 | Full Capacity |  | LASSEN | CA | PGAE | Honey Lake Substation 60 kV | 2015-01-01 08:00 | 2016-06-01 07:00 | NA | None | None | NA
SANBORN SOLAR | 912 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2012-06-20 14:54 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | KERN | CA | SCE | Windhub Substation 220kV | 2015-01-01 08:00 | 2015-01-01 08:00 | NA | None | None | NA
QUARTZ 1 SOLAR | 913 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-06 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | RIVERSIDE | CA | SCE | Colorado River Substation 230 kV bus | 2016-12-31 08:00 | 2016-12-31 08:00 | NA | Complete | None | NA
VEA BLACKROCK | 914 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-06 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | NYE | NV | VEA | Vista Substation 138kV | 2014-12-01 08:00 | 2016-03-31 07:00 | NA | Complete | None | NA |  | None
VEA HOMESTEAD | 915 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2012-06-20 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | NYE | NV | VEA | Thousandaire Substation 138kV | 2014-12-01 08:00 | 2014-12-01 08:00 | NA | None | None | NA
STRATFORD SOLAR - C5 | 916 | 2012-03-30 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-15 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KINGS | CA | PGAE | Henrietta-GWF 115 kV Line | 2014-12-01 08:00 | 2014-12-01 08:00 | NA | Complete | None | NA
LEMOORE SOLAR - C5 | 917 | 2012-03-30 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-15 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KINGS | CA | PGAE | Henrietta-GWF 115 kV Line; | 2014-12-01 08:00 | 2014-12-01 08:00 | NA | Complete | None | NA
FIREBAUGH SOLAR - C5 | 918 | 2012-03-30 | 2012-04-02 07:00 | WITHDRAWN | 2012-08-06 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 | Full Capacity |  | FRESNO | CA | PGAE | Mendota Dairyland 115kV | 2015-12-31 08:00 | 2015-12-31 08:00 | NA | None | None | NA
YUHA BASIN SOLAR | 919 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-03-04 08:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 75 | 75 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley Substation 230kV | 2015-01-01 08:00 | 2015-01-01 08:00 | NA | None | None | NA
YERMO SOLAR | 920 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2012-06-20 14:46 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 75 | 75 | Full Capacity |  | KERN | CA | SCE | Coolwater-DunnSiding-Baker Substation 115kV | 2015-01-01 08:00 | 2015-01-01 08:00 | NA | None | None | NA
SPS AS 40MW PV GENERATION FACILITY | 921 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-15 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 40 | 40 | Full Capacity |  | TULARE | CA | PGAE | Alpaugh-Smyrna 115kV Line | 2016-12-01 08:00 | 2016-12-01 08:00 | NA | Complete | None | NA
HIGHWIND POWER PROJECT | 922 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2014-10-13 07:00 | C05 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 291 | 291 | Full Capacity |  | KERN | CA | SCE | Highwind Substation 230kV | 2016-01-01 08:00 | 2017-01-01 08:00 | NA | Complete | Complete | NA
VISTA POWER PROJECT | 923 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-04-17 07:00 | C05 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 402 | 402 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Vista Substation 230kV | 2017-01-01 08:00 | 2018-01-01 08:00 | NA | Complete | None | NA
RED MOUNTAIN WIND ENERGY CENTER - C5 | 924 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2012-08-06 07:00 | C05 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 150 | 150 | Full Capacity |  | MERCED | CA | PGAE | Los Banos-Westly 230 kV Line | 2015-12-01 08:00 | 2015-12-01 08:00 | NA | None | None | NA
TEHACHAPI SPINDLE | 925 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-10 07:00 | C05 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Flywheel; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | SCE | Windhub Substation 230kV bus | 2014-09-30 07:00 | 2014-09-30 07:00 | NA | Complete | None | NA
GOLDEN HILLS POWER | 926 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2014-03-20 07:00 | C05 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 550 | 550 | Full Capacity |  | KERN | CA | SCE | Windhub Substation 230 kV | 2015-03-15 07:00 | 2018-08-06 07:00 | NA | Complete | Complete | NA
TEHACHAPI VALLEY SOLAR I | 927 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2015-06-15 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 45 | 45 | Full Capacity |  | KERN | CA | SCE | Highwind Substation 230kV bus | 2015-01-15 08:00 | 2016-12-01 08:00 | NA | Complete | Complete | NA
DELTA SOLANO WIND | 928 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2014-10-31 07:00 | C05 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 175 | 175 | Full Capacity |  | SOLANO | CA | PGAE | CPN Creed/ Goose Haven Subs - Lambie Switching Station 230 kV | 2015-12-31 08:00 | 2015-12-31 08:00 | NA | Complete | Complete | NA
ENN MOJAVE POWER 1 | 929 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-02 07:00 | C05 | Combustion Turbine | Photovoltaic |  | Natural Gas | Solar |  | 50 | 200 |  | 250 | Full Capacity |  | CLARK | NV | SCE | Mohave-Lugo 500kV line | 2015-12-01 08:00 | 2016-12-31 08:00 | NA | Complete | None | NA
ENN MOJAVE POWER 2 | 930 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-02 07:00 | C05 | Combustion Turbine | Photovoltaic |  | Natural Gas | Solar |  | 50 | 200 |  | 250 | Full Capacity |  | CLARK | NV | SCE | Mohave-Lugo 500kV line | 2015-12-01 08:00 | 2016-12-31 08:00 | NA | Complete | None | NA
ENN MOJAVE POWER 3 | 931 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-02 07:00 | C05 | Photovoltaic | Combustion Turbine |  | Solar | Natural Gas |  | 150 | 150 |  | 300 | Full Capacity |  | CLARK | NV | SCE | Mohave-Eldorado 500kV line | 2015-12-01 08:00 | 2016-12-31 08:00 | NA | Complete | None | NA
ENN MOJAVE POWER 4 | 932 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-02 07:00 | C05 | Combustion Turbine | Photovoltaic |  | Natural Gas | Solar |  | 100 | 200 |  | 300 | Full Capacity |  | CLARK | NV | SCE | Mohave-Eldorado 500kV line | 2015-12-01 08:00 | 2016-12-31 08:00 | NA | Complete | None | NA
WELLHEAD POWER MIDFRUIT CHP | 933 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-15 07:00 | C05 | Generating Facility Type-1: Other; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49 | 49 | Full Capacity |  | KERN | CA | PGAE | Rio Bravo Tomato Substation 115 kV Bus | 2014-04-01 07:00 | 2014-04-01 07:00 | NA | Complete | None | NA
WELLHEAD POWER NELLA CHP | 934 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-15 07:00 | C05 | Generating Facility Type-1: Other; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49 | 49 | Full Capacity |  | MERCED | CA | PGAE | Santa Nella-Canal 70kV line | 2014-04-01 07:00 | 2014-04-01 07:00 | NA | Complete | None | NA
WELLHEAD POWER WOODLAND CHP | 935 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2012-08-06 07:00 | C05 | Generating Facility Type-1: Other; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49 | 49 | Full Capacity |  | YOLO | CA | PGAE | Woodland-Davis 115kV line | 2014-04-01 07:00 | 2014-04-01 07:00 | NA | None | None | NA
COALINGA SOLAR CENTER | 936 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2012-08-06 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | Coalinga 1-Coalinga 2 70kV line | 2015-05-01 07:00 | 2015-05-01 07:00 | NA | None | None | NA
WELLHEAD POWER LEMIETTA CHP | 937 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2013-05-15 07:00 | C05 | Generating Facility Type-1: Other; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49 | 49 | Full Capacity |  | KINGS | CA | PGAE | Lemoore-Henrietta 115kV line | 2014-04-01 07:00 | 2014-04-01 07:00 | NA | Complete | None | NA
TENASKA MOUNTAIN BASIN | 938 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2012-06-15 07:00 | C05 | Generating Facility Type-1: Reciprocating Engine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 300 | 300 | Full Capacity |  | KERN | CA | SCE | Windhub 230 kV bus | 2016-06-01 07:00 | 2016-06-01 07:00 | NA | None | None | NA
ALAMITOS ENERGY CENTER | 939 | 2012-03-13 | 2012-04-02 07:00 | WITHDRAWN | 2012-08-01 07:00 | C05 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 1902.867 | 1902.86 | Full Capacity |  | LOS ANGELES | CA | SCE | Alamitos Switching Station 230kV | 2025-11-01 07:00 | 2025-11-01 07:00 | NA | None | None | NA
PALMAS C5 | 940 | 2012-04-02 | 2012-04-02 07:00 | WITHDRAWN | 2012-06-15 16:13 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 238 | 238 | Full Capacity |  | HYDER | AZ | SDGE | Hassayampa-North Gila 500kV Line | 2014-07-01 07:00 | 2014-07-01 07:00 | NA | None | None | NA
REDONDO BEACH ENERGY PROJECT | 941 | 2012-03-13 | 2012-04-02 07:00 | WITHDRAWN | 2013-11-21 08:00 | C05 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 475.717 | 475.71 | Full Capacity |  | LOS ANGELES | CA | SCE | Redondo Beach Switching Station 230kV | 2019-01-01 08:00 | 2019-01-01 08:00 | NA | Complete | None | NA
MIRAGE SOLAR | 942 | 2012-03-29 | 2012-04-02 07:00 | WITHDRAWN | 2013-03-18 07:00 | C05 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 | Full Capacity |  | KERN | CA | SCE | Kramer Substation 220kV bus | 2016-04-30 07:00 | 2016-04-30 07:00 | NA | Complete | None | NA
LERDO SOLAR | 943 | 2013-04-15 | 2013-04-30 07:00 | WITHDRAWN | 2014-03-04 08:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 | Full Capacity |  | KERN | CA | PGAE | Lerdo 115 kV Substation | 2015-12-01 08:00 | 2015-12-01 08:00 | NA | Complete | None | NA
VALLEY CENTER SOLAR | 944 | 2013-04-15 | 2013-04-30 07:00 | WITHDRAWN | 2015-02-26 08:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | SAN DIEGO | CA | SDGE | Valley Center 69kv Sub | 2015-08-01 07:00 | 2015-07-01 07:00 | NA | Complete | None | NA
GV SOLAR 3 | 947 | 2013-04-24 | 2013-04-30 07:00 | WITHDRAWN | 2014-03-06 08:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 120 | 120 | Full Capacity |  | TULARE | CA | PGAE | Olive Substation 115 kV | 2017-12-01 08:00 | 2017-12-01 08:00 | NA | None | None | NA
BORDER SOLAR | 948 | 2013-04-29 | 2013-04-30 07:00 | WITHDRAWN | 2014-03-07 08:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | SAN DIEGO | CA | SDGE | Border 69 KV Substation | 2015-08-01 07:00 | 2015-08-01 07:00 | NA | None | None | NA
FELIPE SOLAR | 949 | 2013-04-29 | 2013-04-30 07:00 | WITHDRAWN | 2013-07-16 07:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | SAN DIEGO | CA | SDGE | Warners 69kV line | 2015-08-01 07:00 | 2015-08-01 07:00 | NA | None | None | NA
KRAMER SOLAR | 950 | 2013-04-29 | 2013-04-30 07:00 | WITHDRAWN | 2014-03-06 08:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Kramer Substation 230kV | 2016-10-01 07:00 | 2016-10-01 07:00 | NA | Complete | None | NA
LIVERMORE SOLAR | 951 | 2013-04-29 | 2013-04-30 07:00 | WITHDRAWN | 2014-03-04 08:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | ALAMEDA | CA | PGAE | Vasco 60kV Substation | 2015-08-01 07:00 | 2015-08-01 07:00 | NA | None | None | NA
ALGONQUIN POWER SANGER 2 | 955 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2020-04-01 07:00 | C06 | Combined Cycle | Combined Cycle |  | Natural Gas | Natural Gas |  | 60 | 48.3 |  | 48.3 | Full Capacity | Off-Peak Deliverability |  |  | PGAE | Sanger Co-gen 115/13.8kV Sub | 2014-05-01 07:00 | 2020-11-01 07:00 | NA | Complete | Complete | NA | Executed | IC Request
BENICIA WIND | 956 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2014-02-25 08:00 | C06 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 65 | 65 | Full Capacity |  | SOLANO | CA | PGAE | VACA-VACAVILLE-JAMESON-NORTH TOWER 115KV | 2016-12-31 08:00 | 2016-12-31 08:00 | NA | None | None | NA
CALPEAK BORDER OM 2 | 957 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2014-03-20 07:00 | C06 | Generating Facility Type-1: Reciprocating Engine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 205 | 205 | Full Capacity |  | SAN DIEGO | CA | SDGE | Otay Mesa Substation 230kV | 2017-06-01 07:00 | 2017-06-01 07:00 | NA | Complete | None | NA
EL CAJON ENERGY CENTER 2 | 958 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2013-07-01 07:00 | C06 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49.9 | 49.9 | Full Capacity |  | SAN DIEGO | CA | SDGE | 69kV bus of the El Cajon Sub | 2015-01-03 08:00 | 2015-01-03 08:00 | NA | None | None | NA
FOX SOLAR | 959 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2014-03-12 07:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 30 | 30 | Full Capacity |  | SAN DIEGO | CA | SDGE | Crestwood-Boulevard East 69kV line | 2016-12-31 08:00 | 2016-12-31 08:00 | NA | Complete | None | NA
HUNTINGTON BEACH 2 | 960 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2015-09-03 07:00 | C06 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 59.328 | 59.32 | Full Capacity |  | ORANGE | CA | SCE | Huntington Beach Switching Station 230kV | 2020-06-01 07:00 | 2023-01-30 08:00 | NA | Complete | None | NA
LAGUNA SALADA PV POWER PLANT | 961 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2019-08-01 07:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200.62 | 200.62 | Full Capacity |  | BAJA CALIFORNIA | MX | SDGE | Imperial Valley Substation 230kV | 2015-11-01 07:00 | 2020-04-03 07:00 | NA | Complete | Complete | NA | Executed | IC Request
LAKE CLEMENTINE HYDROELECTRIC | 962 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2014-04-25 07:00 | C06 | Generating Facility Type-1: Hydro; Generating Facility Fuel-1: Water; MWs MW-1: 15.5 | 15.5 | Full Capacity |  | PLACER | CA | PGAE | Halsey Substation 60Kv | 2017-01-15 08:00 | 2017-01-15 08:00 | NA | Complete | None | NA
LOST HILLS COGEN | 964 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2014-04-16 07:00 | C06 | Generating Facility Type-1: Other; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 47.821 | 47.82 | Full Capacity |  | KERN | CA | PGAE | Arco-Twisselman 70 kV Line | 2017-03-01 08:00 | 2017-03-31 07:00 | NA | Complete | None | NA
MIDWAY HILLS COGEN | 966 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2014-03-04 08:00 | C06 | Generating Facility Type-1: Other; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 47.821 | 47.82 | Full Capacity |  | KERN | CA | PGAE | Midway-Midsun 115 kV line | 2017-03-31 07:00 | 2017-03-31 07:00 | NA | None | None | NA
GOLDEN OASIS | 967 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2019-04-03 07:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 33 | 33 | Full Capacity |  | KERN | CA | SCE | Whirlwind 230 kV bus | 2016-03-01 08:00 | 2021-04-30 07:00 | NA | Complete | Complete | NA | Executed | IC Request
PIO PICO 2 | 969 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2014-05-09 07:00 | C06 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 110 | 110 | Full Capacity |  | SAN DIEGO | CA | SDGE | Otay Mesa Switchyard 230kV | 2017-04-01 07:00 | 2017-04-01 07:00 | NA | Complete | None | NA
QUARTZ 3 SOLAR | 970 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2019-03-05 08:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Energy Only |  | RIVERSIDE | CA | SCE | Colorado River Substation 230kV bus | 2016-12-31 08:00 | 2021-03-15 07:00 | NA | Complete | Complete | NA | Executed | IC Request
SILVER STATE SOUTH 3 SOLAR | 973 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2013-07-02 07:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | CLARK | NV | SCE | Primm Substation 230kV | 2016-12-31 08:00 | 2016-12-31 08:00 | NA | None | None | NA |  | None
THREE PEAKS WIND | 974 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2014-02-25 08:00 | C06 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 150 | 150 | Full Capacity |  | KINGS | CA | PGAE | Morrow Bay-Gates 230 kV Line | 2016-12-31 08:00 | 2016-12-31 08:00 | NA | None | None | NA
TIMBA SOLAR | 975 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2014-04-17 07:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | STANISLAUS | CA | PGAE | Salado- Newman 60 kV Line #1, Pole No. 3/13 | 2016-12-31 08:00 | 2016-01-30 08:00 | NA | Complete | None | NA
TRANSFER RIDGE WIND | 976 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2014-02-25 08:00 | C06 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 60 | 60 | Full Capacity |  | BUTTE | CA | PGAE | TABLE MTN-RIO OSO 230 KV Line | 2016-12-31 08:00 | 2016-12-31 08:00 | NA | None | None | NA
VENTURA CLEAN ENERGY | 977 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2014-02-24 08:00 | C06 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 778 | 778 | Full Capacity |  | VENTURA | CA | SCE | Santa Clara Substation 230kV bus | 2019-06-01 07:00 | 2019-06-01 07:00 | NA | Complete | None | NA
WP FALLBROOK | 978 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2013-07-01 07:00 | C06 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 99 | 99 | Full Capacity |  | SAN DIEGO | CA | SDGE | Avocado-Monserate 69kV line approx 2.5 mile from Monserate | 2016-05-15 07:00 | 2016-05-15 07:00 | NA | None | None | NA
WP PENDLETON | 979 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2013-07-01 07:00 | C06 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 99 | 99 | Full Capacity |  | SAN DIEGO | CA | SDGE | Pendleton Sub | 2016-05-15 07:00 | 2016-05-15 07:00 | NA | None | None | NA
WP OCEANSIDE | 980 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2013-07-01 07:00 | C06 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 200 | 200 | Full Capacity |  | SAN DIEGO | CA | SDGE | San Luis Rey-Pendleton 69kV line | 2017-05-15 07:00 | 2017-05-15 07:00 | NA | None | None | NA
WP GOLETA (FKA WP OXNARD) | 981 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2013-07-16 07:00 | C06 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 200 | 200 | Full Capacity |  | VENTURA | CA | SCE | Goleta Substation 220kV bus | 2018-05-15 07:00 | 2018-05-15 07:00 | NA | None | None | NA
WP VANDE | 982 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2013-07-01 07:00 | C06 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49.9 | 49.9 | Full Capacity |  | SAN DIEGO | CA | SDGE | San Luis Rey-Stuart 69kV line | 2016-05-15 07:00 | 2016-05-15 07:00 | NA | None | None | NA
WP WALNUT | 983 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2013-07-16 07:00 | C06 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 200 | 200 | Full Capacity |  | LOS ANGELES | CA | SCE | Walnut Substation 230kV | 2017-05-15 07:00 | 2017-05-15 07:00 | NA | None | None | NA
DREW ROAD GENERATION | 984 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2013-07-15 07:00 | C06 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 344 | 344 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley Sub 230kV | 2018-01-01 08:00 | 2018-01-01 08:00 | NA | None | None | NA
RANCHO WISTARIA SOLAR ENERGY CENTER | 985 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2014-03-19 07:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley 230 kV bus | 2016-12-31 08:00 | 2016-12-31 08:00 | NA | None | None | NA
FREMONT VALLEY PRESERVATION | 986 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2014-04-17 07:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 245 | 245 | Full Capacity |  | KERN | CA | SCE | Kramer Substation 230kV | 2015-08-01 07:00 | 2016-11-01 07:00 | NA | Complete | None | NA
PISMO SOLAR | 987 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2014-03-04 08:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | SAN LUIS OBISPO | CA | PGAE | SLO to Oceano 115kV line | 2015-08-01 07:00 | 2015-08-01 07:00 | NA | None | None | NA
MARICOPA WEST SOLAR PV 2 | 988 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2017-03-14 07:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Energy Only |  | KERN | CA | PGAE | Maricopa-Copus 70kV line | 2015-08-01 07:00 | 2017-02-28 08:00 | NA | Complete | Complete | NA | Executed | None
KASSON MANTECA SOLAR | 989 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2015-04-09 07:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Kasson-Manteca 60kV | 2015-08-01 07:00 | 2018-05-01 07:00 | NA | Complete | Complete | NA
CENTER POWER | 990 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2016-06-03 07:00 | C06 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 910 | 910 | Energy Only |  | LOS ANGELES | CA | SCE | Loop Center-Mesa and Center-Olinda 230kV lines | 2018-01-01 08:00 | 2024-08-13 07:00 | NA | Complete | Complete | NA
RIO HONDO POWER | 991 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2014-04-28 07:00 | C06 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 1047 | 1047 | Full Capacity |  | LOS ANGELES | CA | SCE | Rio Hondo Substation 230kV | 2019-01-01 08:00 | 2019-01-01 08:00 | NA | Complete | None | NA
EAST NICOLAUS SOLAR | 992 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2015-05-21 07:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | SUTTER | CA | PGAE | East Nicolaus 60 kV substation | 2015-08-01 07:00 | 2015-08-01 07:00 | NA | Complete | Complete | NA
KINGS SOLAR 4 | 995 | 2013-05-01 | 2013-04-30 07:00 | WITHDRAWN | 2013-07-02 07:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | KINGS | CA | PGAE | Gates-Midway 230kV line | 2016-06-01 07:00 | 2016-06-01 07:00 | NA | None | None | NA
MARICOPA 4 SOLAR PROJECT | 996 | 2013-05-01 | 2013-04-30 07:00 | WITHDRAWN | 2013-07-02 07:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Full Capacity |  | KERN | CA | PGAE | Midway- Wheeler Ridge 230 kV line tap via .5 mile gen tie | 2016-06-01 07:00 | 2016-06-01 07:00 | NA | None | None | NA
STS SOLAR | 997 | 2013-05-01 | 2013-04-30 07:00 | WITHDRAWN | 2015-06-04 07:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 16 | 16 | Full Capacity |  | SONOMA | CA | PGAE | Monte Rio-Fulton 60 kV transmission line | 2015-06-30 07:00 | 2015-09-15 07:00 | NA | Complete | Complete | NA
HYDER VALLEY SOLAR ENERGY | 998 | 2013-05-01 | 2013-04-30 07:00 | WITHDRAWN | 2014-05-01 07:00 | C06 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Solar; MWs MW-1: 300 | 300 | Full Capacity |  | MARICOPA | AZ | SDGE | Proposed switch station on the Hassayama-North Gila Bend 500 kV line | 2018-04-01 07:00 | 2018-04-01 07:00 | NA | Complete | None | NA
BLUE STAR WIND ENERGY CENTER | 999 | 2013-05-01 | 2013-04-30 07:00 | WITHDRAWN | 2013-09-16 07:00 | C06 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 250 | 250 | Full Capacity |  | KERN | CA | PGAE | Caliente Switching Station 230 kV | 2017-01-01 08:00 | 2017-01-01 08:00 | NA | None | None | NA
HECA SCS | 1000 | 2013-05-01 | 2013-04-30 07:00 | WITHDRAWN | 2014-04-24 07:00 | C06 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Other; MWs MW-1: 300 | 300 | Full Capacity |  | KERN | CA | PGAE | Midway-Wheeler Ridge 230 kV Line | 2019-01-01 08:00 | 2019-01-01 08:00 | NA | Complete | None | NA
LASALLE SOLAR PROJECT | 1001 | 2013-05-01 | 2013-04-30 07:00 | WITHDRAWN | 2014-02-27 08:00 | C06 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KINGS | CA | PGAE | Henreitta-GWF 115kV Line | 2016-10-01 07:00 | 2016-10-01 07:00 | NA | Complete | None | NA
DRY CREEK (FKA JASMIN POWER 3) | 1003 | 2013-04-30 | 2013-04-30 07:00 | WITHDRAWN | 2014-04-29 07:00 | C06 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 86 | 86 | Full Capacity |  | KERN | CA | SCE | Vestal-Magunden #2 220kV line | 2017-01-01 08:00 | 2017-01-01 08:00 | NA | Complete | None | NA
CLEARVISTA SOLAR 1 | 1004 | 2013-12-24 | 2014-01-23 08:00 | WITHDRAWN | 2014-07-29 07:00 | FT | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 5 | 5 | Energy Only |  | KERN | CA | SCE | Highwind Substation 220kV | 2014-10-31 07:00 | 2014-10-31 07:00 | None | NA | NA | NA
DIXIE VALLEY 2 | 1006 | 2014-03-28 | 2014-03-28 07:00 | WITHDRAWN | 2014-10-15 07:00 | ISP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 5 | 5 | Energy Only |  | CHURCHILL | NV | SCE | Control Substation 115kV | 2014-10-01 07:00 | 2014-10-01 07:00 | NA | None | None | NA
COYOTE CREEK ENERGY STORAGE | 1007 | 2014-05-01 | 2014-04-30 07:00 | WITHDRAWN | 2015-03-20 07:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20 | Full Capacity |  | SANTA CLARA | CA | PGAE | Los Esteros Substation 115kV | 2019-03-01 08:00 | 2020-01-01 08:00 | NA | Complete | None | NA |  | None
DIABLO ENERGY FACILITY | 1008 | 2014-04-29 | 2014-04-30 07:00 | WITHDRAWN | 2015-01-30 08:00 | C07 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 309 | 309 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Pittsburg Substation 115 kV | 2017-06-01 07:00 | 2017-06-01 07:00 | NA | None | None | NA
DIABLO ENERGY STORAGE | 1009 | 2014-04-29 | 2014-04-30 07:00 | WITHDRAWN | 2015-01-30 08:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Pittsburg Substation 60kV | 2016-06-01 07:00 | 2016-06-01 07:00 | NA | None | None | NA
COLINAS DE ORO | 1011 | 2014-04-28 | 2014-04-30 07:00 | WITHDRAWN | 2021-01-11 08:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 30 | 30 | Full Capacity |  | ALAMEDA | CA | PGAE | Tesla Substation 115kV | 2016-12-01 08:00 | 2021-03-01 08:00 | NA | Complete | Complete | NA | Executed | IC Request
HONEY BEE | 1012 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-01-27 08:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20 | Full Capacity |  | SANTA CLARA | CA | PGAE | FMC Substation 115 kV | 2016-06-01 07:00 | 2016-06-01 07:00 | NA | None | None | NA
LAKE CLEMENTINE HYDROELECTRIC C7 | 1013 | 2014-05-01 | 2014-04-30 07:00 | WITHDRAWN | 2015-02-10 08:00 | C07 | Generating Facility Type-1: Hydro; Generating Facility Fuel-1: Water; MWs MW-1: 15.5 | 15.5 | Full Capacity |  | PLACER | CA | PGAE | Halsey Substation 60 kV | 2018-01-15 08:00 | 2018-01-15 08:00 | NA | None | None | NA
PARADISE CUT | 1014 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2016-11-30 08:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 10 | 10 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Kasson-Louise 60kV Line | 2016-06-01 07:00 | 2016-06-01 07:00 | NA | Complete | Complete | NA |  | IC Request
PLEASANT GROVE GRID STABILIZATION PROJECT | 1015 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-02-03 08:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20 | Full Capacity |  | PLACER | CA | PGAE | Pleasant Grove Substation 115 kV | 2016-12-31 08:00 | 2016-12-31 08:00 | NA | None | None | NA
SGS FREMONT | 1017 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-02-11 08:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 50 | 50 | Full Capacity |  | ALAMEDA | CA | PGAE | Newark Substation 115 kV | 2019-01-01 08:00 | 2019-01-01 08:00 | NA | None | None | NA
SGS LIVERMORE (FKA SGS SOUTH SAN FRANCISCO) | 1018 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-05-11 07:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 50 | 50 | Full Capacity |  | SAN MATEO | CA | PGAE | Las Positas 60 kV | 2019-01-01 08:00 | 2019-01-01 08:00 | NA | Complete | None | NA
SHINGLE SPRINGS GRID STABILIZATION PROJECT | 1019 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-02-19 08:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 40 | 40 | Full Capacity |  | EL DORADO | CA | PGAE | Shingle Springs Substation 115kV | 2016-12-31 08:00 | 2016-12-31 08:00 | NA | None | None | NA
SKY VALLEY WIND | 1020 | 2014-04-28 | 2014-04-30 07:00 | WITHDRAWN | 2015-02-05 08:00 | C07 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 50 | 50 | Full Capacity |  | SOLANO | CA | PGAE | Vaca-Vacaville-Jameson-North Tower 115kV | 2017-12-31 08:00 | 2017-12-31 08:00 | NA | None | None | NA
STOCKTON BIOMASS | 1021 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2018-10-25 07:00 | C07 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Biofuel; MWs MW-1: 5 | 5 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Stockton A #1 line 60 kV, Cogeneration National 60 kV tap | 2016-12-31 08:00 | 2018-02-28 08:00 | NA | Complete | Complete | NA | Executed
TESLA WIND BANK | 1022 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2014-07-02 07:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 30 | 30 | Full Capacity |  | ALAMEDA | CA | PGAE | Patterson Pass 230 kV Substation | 2016-12-01 08:00 | 2016-12-01 08:00 | NA | None | None | NA
UMBARGER EVERGREEN ENERGY STORAGE | 1023 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-04-01 07:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20 | Full Capacity |  | SANTA CLARA | CA | PGAE | Evergreen Substation 60kV | 2016-08-01 07:00 | 2016-08-01 07:00 | NA | Complete | None | NA |  | Failure to Cure Deficiency
VICTOR GRID STABILIZATION PROJECT | 1024 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-02-17 08:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 30 | 30 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Victor Substation 60 kV | 2016-12-31 08:00 | 2016-12-31 08:00 | NA | Complete | None | NA
WATT ENERGY STORAGE | 1025 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-01-27 08:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 15 | 15 | Full Capacity |  | SOLANO | CA | PGAE | Jameson Substation 115 kV | 2017-01-01 08:00 | 2017-01-01 08:00 | NA | None | None | NA
WEBER GRID STABILIZATION PROJECT | 1026 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-06-18 07:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 25 | 25 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Weber Substation 60kV | 2016-12-31 08:00 | 2016-12-31 08:00 | NA | Complete | None | NA
SOUTH LAKE SOLAR | 1030 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2020-05-27 07:00 | C07 | Photovoltaic | Storage |  | Solar | Battery |  | 15 | 5 |  | 20 | Energy Only |  | FRESNO | CA | PGAE | Schindler-Huron-Gates Tap 70kV | 2016-12-15 08:00 | 2021-04-15 07:00 | NA | Complete | Complete | NA | Executed | IC Request
STONECROP | 1031 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2016-09-19 07:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | Gates Substation 230kV | 2016-11-01 07:00 | 2019-07-15 07:00 | NA | Complete | Complete | NA |  | IC Request
BROKEN SPOKE | 1033 | 2014-05-01 | 2014-04-30 07:00 | WITHDRAWN | 2016-04-22 07:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | PGAE | Arco Substation 70 kV | 2016-11-01 07:00 | 2016-11-01 07:00 | NA | Complete | Complete | NA
HIGH NOON | 1034 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-01-27 08:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KINGS | CA | PGAE | Waukena Substation 115kV | 2016-11-01 07:00 | 2016-11-01 07:00 | NA | None | None | NA
MAGELLAN SOLAR | 1035 | 2014-04-25 | 2014-04-30 07:00 | WITHDRAWN | 2015-03-24 07:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | PGAE | Arco Substation 70kV | 2017-12-01 08:00 | 2018-06-01 07:00 | NA | Complete | None | NA |  | IC Request
NEW HECA | 1037 | 2014-04-28 | 2014-04-30 07:00 | WITHDRAWN | 2015-04-01 07:00 | C07 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 300 | 300 | Full Capacity |  | KERN | CA | PGAE | Midway-Wheeler Ridge 230 kV | 2020-01-01 08:00 | 2020-01-31 08:00 | NA | Complete | None | NA
PANDORA SOLAR | 1038 | 2014-04-25 | 2014-04-30 07:00 | WITHDRAWN | 2016-06-03 07:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 60 | 60 | Full Capacity |  | KERN | CA | PGAE | Arco Substation 70kV | 2017-12-01 08:00 | 2018-06-01 07:00 | NA | Complete | Complete | NA |  | Failure to Cure Deficiency
PUMA FORK | 1039 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-01-27 08:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | PGAE | 7th Standard Substation 115 kV | 2016-11-01 07:00 | 2016-11-01 07:00 | NA | None | None | NA
BCS ENERGY STORAGE | 1041 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-01-22 08:00 | C07 | Photovoltaic | Storage |  | Solar | Battery |  | 20 | 20 |  | 20 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley Substation 230 kV | 2015-06-01 07:00 | 2015-06-01 07:00 | NA | None | None | NA
BIG POTRERO | 1042 | 2014-04-29 | 2014-04-30 07:00 | WITHDRAWN | 2015-02-05 08:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | SAN DIEGO | CA | SDGE | Cameron Substation 69 kV | 2016-11-01 07:00 | 2016-11-01 07:00 | NA | None | None | NA
CANASTA | 1043 | 2014-04-29 | 2014-04-30 07:00 | WITHDRAWN | 2015-01-27 08:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | SAN DIEGO | CA | SDGE | Creelman Substation 69 kV | 2016-11-01 07:00 | 2016-11-01 07:00 | NA | None | None | NA
CCI HYBRID POWER | 1044 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2014-07-09 07:00 | C07 | Combustion Turbine | Storage |  | Natural Gas | Battery |  | 448 | 60 |  | 508 | Full Capacity |  | SAN DIEGO | CA | SDGE | Mission-San Luis Rey 230 kV line | 2019-06-01 07:00 | 2019-06-01 07:00 | NA | None | None | NA
ECO ENERGY STORAGE CENTER | 1046 | 2014-04-28 | 2014-04-30 07:00 | WITHDRAWN | 2015-02-16 08:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 10 | 10 | Full Capacity |  | SAN DIEGO | CA | SDGE | East County Substation 138kV | 2016-12-15 08:00 | 2016-12-15 08:00 | NA | None | None | NA
HAWKWIND | 1049 | 2014-04-29 | 2014-04-30 07:00 | WITHDRAWN | 2015-01-27 08:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | SAN DIEGO | CA | SDGE | ECO Substation 138kV | 2016-11-01 07:00 | 2016-11-01 07:00 | NA | None | None | NA
HONEY BADGER | 1050 | 2014-04-29 | 2014-04-30 07:00 | WITHDRAWN | 2016-01-07 08:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | SAN DIEGO | CA | SDGE | Cameron Substation 69kV | 2016-11-01 07:00 | 2016-11-01 07:00 | NA | Complete | None | NA
KEARNY HYBRID POWER | 1051 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-01-26 08:00 | C07 | Storage | Photovoltaic |  | Battery | Solar |  | 30 | 90 |  | 120 | Full Capacity |  | SAN DIEGO | CA | SDGE | Kearny Substation 69kV | 2019-06-01 07:00 | 2019-06-01 07:00 | NA | None | None | NA
MESA ROJO | 1052 | 2014-04-29 | 2014-04-30 07:00 | WITHDRAWN | 2015-01-28 08:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | SAN DIEGO | CA | SDGE | San Ysabel Substation 69kV | 2016-11-01 07:00 | 2016-11-01 07:00 | NA | None | None | NA
MIGUEL ENERGY STORAGE | 1054 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2014-07-07 07:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 150 | 150 | Full Capacity |  | SAN DIEGO | CA | SDGE | Miguel Substation 230kV | 2016-12-31 08:00 | 2016-12-31 08:00 | NA | None | None | NA
NCC HYBRID POWER | 1055 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-01-26 08:00 | C07 | Storage | Combustion Turbine |  | Battery | Natural Gas |  | 60 | 384 |  | 444 | Full Capacity |  | SAN DIEGO | CA | SDGE | San Luis Rey Substation 230 kV | 2019-06-01 07:00 | 2019-06-01 07:00 | NA | None | None | NA
NCI HYBRID POWER | 1056 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-03-20 07:00 | C07 | Photovoltaic | Storage | Combustion Turbine | Solar | Battery | Natural Gas | 30 | 60 | 448 | 538 | Full Capacity |  | SAN DIEGO | CA | SDGE | Talega-Escondido 230kV line | 2019-06-01 07:00 | 2019-06-01 07:00 | NA | Complete | None | NA
OTAY MESA ENERGY CENTER AGP | 1057 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-03-24 07:00 | C07 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 35 | 35 | Full Capacity |  | SAN DIEGO | CA | SDGE | Otay Mesa Switchyard 230 kV | 2016-05-01 07:00 | 2016-05-01 07:00 | NA | Complete | None | NA
SEA LION ENERGY STORAGE | 1059 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-03-30 07:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20 | Full Capacity |  | SAN DIEGO | CA | SDGE | San Luis Rey Substation 69 kV | 2017-01-01 08:00 | 2017-01-01 08:00 | NA | Complete | None | NA
SLW (FKA SHU'LUUK WIND) | 1060 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-04-01 07:00 | C07 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 160 | 160 | Full Capacity |  | SAN DIEGO | CA | SDGE | Boulevard East Substation 138kV | 2017-12-31 08:00 | 2017-12-31 08:00 | NA | Complete | None | NA
WILEY ROAD | 1063 | 2014-04-29 | 2014-04-30 07:00 | WITHDRAWN | 2015-01-28 08:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | SAN DIEGO | CA | SDGE | Salt Creek Substation 69kV | 2016-11-01 07:00 | 2016-11-01 07:00 | NA | None | None | NA
CABALLO LOCO | 1065 | 2014-04-29 | 2014-04-30 07:00 | WITHDRAWN | 2016-06-03 07:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 | Energy Only |  | NYE | NV | VEA | Vista Substation 138kV | 2016-11-01 07:00 | 2019-04-05 07:00 | NA | Complete | Complete | NA |  | Failure to Cure Deficiency
ROADRUNNER | 1066 | 2014-04-29 | 2014-04-30 07:00 | WITHDRAWN | 2018-03-02 08:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 | Energy Only |  | NYE | NV | VEA | Vista Substation 138kV | 2016-11-01 07:00 | 2019-04-05 07:00 | NA | Complete | Complete | NA |  | IC Request
SPRING MOUNTAIN SOLAR | 1067 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-02-17 08:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | NYE | NV | VEA | Gamebird Substation 138kV | 2017-12-01 08:00 | 2017-12-01 08:00 | NA | Complete | None | NA |  | IC Request
SUNSHINE VALLEY SOLAR 3 | 1068 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-02-17 08:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 65 | 65 | Full Capacity |  | NYE | NV | VEA | Valley Substation 138kV | 2017-12-01 08:00 | 2017-12-01 08:00 | NA | Complete | None | NA |  | IC Request
BOULDER SOLAR 3 (FKA: BOULDER SOLAR POWER C7) | 1069 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2016-12-29 08:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 | Energy Only |  | CLARK | NV | SCE | SCE owned Eldorado 220 kV bus | 2016-09-15 07:00 | 2018-08-01 07:00 | NA | Complete | Complete | NA |  | IC Request
JUPITER SOLAR | 1070 | 2014-04-25 | 2014-04-30 07:00 | WITHDRAWN | 2016-06-03 07:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 250 | 250 | Full Capacity |  | RIVERSIDE | CA | SCE | Red Bluff Substation 230 kV | 2017-12-01 08:00 | 2018-12-01 08:00 | NA | Complete | Complete | NA |  | Failure to Cure Deficiency
QUARTZITE SOLAR 7 | 1071 | 2014-05-01 | 2014-04-30 07:00 | WITHDRAWN | 2019-02-21 08:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Energy Only |  | RIVERSIDE | CA | SCE | Colorado River Substation 230 kV | 2016-12-31 08:00 | 2019-12-01 08:00 | NA | Complete | Complete | NA
VERMILLION | 1072 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-01-27 08:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | RIVERSIDE | CA | SCE | Devers Substation 230kV | 2017-11-01 07:00 | 2017-11-01 07:00 | NA | Complete | None | NA |  | IC Request
MISSION ROCK ENERGY CENTER (FKA MISSION ROCK ENERGY CENTER FLEX) | 1073 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-03-24 07:00 | C07 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 305 | 305 | Full Capacity |  | VENTURA | CA | SCE | Santa Clara Substation 230 kV | 2019-03-01 08:00 | 2019-03-01 08:00 | NA | Complete | None | NA
ROSE MEADOW WIND BANK | 1075 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-04-01 07:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 50 | 50 | Full Capacity |  | KERN | CA | SCE | Whirlwind 230kV bus | 2016-12-01 08:00 | 2022-06-01 07:00 | NA | Complete | None | NA
ALAMITOS ENERGY STORAGE | 1077 | 2014-04-29 | 2014-04-30 07:00 | WITHDRAWN | 2015-03-18 07:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 300 | 300 | Full Capacity |  | LOS ANGELES | CA | SCE | Alamitos Switching Station 220kV | 2018-03-01 08:00 | 2018-03-01 08:00 | NA | Complete | None | NA
BIRCH STREET - BATTERY SYSTEM | 1078 | 2014-04-17 | 2014-04-30 07:00 | WITHDRAWN | 2014-06-26 07:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 118 | 118 | Partial Capacity |  | ORANGE | CA | SCE | Ellis-Santiago 220kV line | 2018-05-01 07:00 | 2018-05-01 07:00 | NA | None | None | NA |  | IC Request
BIRCH STREET - COMBINED CYCLE | 1079 | 2014-04-17 | 2014-04-30 07:00 | WITHDRAWN | 2014-06-26 07:00 | C07 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 378 | 378 | Full Capacity |  | ORANGE | CA | SCE | Ellis-Santiago line 220kV | 2018-07-01 07:00 | 2018-07-01 07:00 | NA | None | None | NA
BIRCH STREET GENERATION FACILITY (FKA BIRCH STREET- SIMPLE CYCLE) | 1080 | 2014-04-17 | 2014-04-30 07:00 | WITHDRAWN | 2015-02-03 08:00 | C07 | Combustion Turbine | Storage |  | Natural Gas | Battery |  | 507.4 | 118 |  | 625.4 | Partial Capacity |  | ORANGE | CA | SCE | Ellis-Santiago line 220kV | 2018-03-01 08:00 | 2018-03-01 08:00 | NA | None | None | NA
GRAND AVE - BATTERY SYSTEM | 1081 | 2014-04-29 | 2014-04-30 07:00 | WITHDRAWN | 2014-06-26 07:00 | C07 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 118 | 118 | Partial Capacity |  | ORANGE | CA | SCE | Johanna Switchyard 230 kV | 2018-05-01 07:00 | 2018-05-01 07:00 | NA | None | None | NA |  | IC Request
GRAND AVE- COMBINED CYCLE | 1082 | 2014-04-29 | 2014-04-30 07:00 | WITHDRAWN | 2014-06-26 07:00 | C07 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 378 | 378 | Full Capacity |  | ORANGE | CA | SCE | Johanna Switchyard 230 kV | 2018-07-01 07:00 | 2018-07-01 07:00 | NA | None | None | NA
GRAND AVE GENERATION FACILITY (FKA GRAND AVE SIMPLE CYCLE) | 1083 | 2014-04-29 | 2014-04-30 07:00 | WITHDRAWN | 2015-02-03 08:00 | C07 | Combustion Turbine | Storage |  | Natural Gas | Battery |  | 507.4 | 118 |  | 625.4 | Partial Capacity |  | ORANGE | CA | SCE | Johanna Switchyard 230kV | 2018-07-01 07:00 | 2018-07-01 07:00 | NA | None | None | NA
JOHANNA ENERGY CENTER (FKA JOHANNA ENERGY CENTER LMS) | 1084 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-02-18 08:00 | C07 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 220 | 220 | Full Capacity |  | ORANGE | CA | SCE | Johanna Substation 230 kV | 2019-03-01 08:00 | 2019-03-01 08:00 | NA | None | None | NA
MIRA LOMA HYBRID POWER PROJECT | 1085 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2014-07-17 07:00 | C07 | Combustion Turbine | Storage | Steam Turbine | Natural Gas | Battery | Natural Gas | 455 | 50 | 405 | 910 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Mira Loma Substation 220kV Tap | 2020-06-01 07:00 | 2020-06-01 07:00 | NA | None | None | NA
SANTA ANA ENERGY CENTER | 1087 | 2014-04-28 | 2014-04-30 07:00 | WITHDRAWN | 2015-02-10 08:00 | C07 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 700 | 700 | Full Capacity |  | ORANGE | CA | SCE | Johanna Substation 230 kV | 2018-12-31 08:00 | 2018-12-31 08:00 | NA | Complete | None | NA
VIEJO HYBRID POWER | 1088 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-01-26 08:00 | C07 | Storage | Steam Turbine | Combustion Turbine | Battery | Natural Gas | Natural Gas | 50 | 405 | 455 | 910 | Full Capacity |  | RIVERSIDE | CA | SCE | Chino-Viejo 220 kV line | 2019-06-01 07:00 | 2019-06-01 07:00 | NA | Complete | None | NA |  | IC Request
HIGH DESERT SOLAR PV | 1089 | 2014-04-30 | 2014-04-30 07:00 | WITHDRAWN | 2015-04-01 07:00 | C07 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 89.95 | 89.95 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Desert View Substation 220kV | 2018-08-15 07:00 | 2018-04-30 07:00 | NA | Complete | None | NA
CENTINELA SOLAR ENERGY FACILITY 2MWFT | 1090 | 2014-06-11 | 2014-06-11 07:00 | WITHDRAWN | 2014-09-04 07:00 | FT | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Solar; MWs MW-1: 2 | 2 | Energy Only |  | IMPERIAL | CA | SDGE | Imperial Valley 230kV sub | 2015-01-15 08:00 | 2015-01-15 08:00 | None | NA | NA | NA
WESTLANDS SOLAR FARMS PV2 | 1091 | 2014-05-22 | 2014-05-14 07:00 | WITHDRAWN | 2015-04-24 07:00 | FT | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 1.5 | 1.5 | Energy Only |  | FRESNO | CA | PGAE | Gates-Coalinga 70 kV Line #1 | 2015-02-15 08:00 | 2015-08-01 07:00 | None | NA | NA | NA
PUERTA SOLAR CENTER | 1092 | 2014-01-13 | 2014-08-25 07:00 | WITHDRAWN | 2017-06-06 07:00 | ISP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 49 | 49 | Full Capacity |  | FRESNO | CA | PGAE | Gates-Coalinga #2 70 kV Line | 2015-09-30 07:00 | 2017-08-30 07:00 | NA | None | None | NA |  | IC Request
SWEETWATER ENERGY STORAGE | 1093 | 2014-11-04 | 2014-10-31 07:00 | WITHDRAWN | 2014-12-29 08:00 | FT | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 5 | 5 | Energy Only |  | SAN DIEGO | CA | SDGE | Miguel 69kV | 2016-03-01 08:00 | 2016-03-01 08:00 | Offered | NA | NA | NA
WOODLAND BATTERY PROJECT | 1094 | 2015-02-19 | 2015-03-26 07:00 | WITHDRAWN | 2016-05-05 07:00 | ISP | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 25 | 25 | Full Capacity |  | YOLO | CA | PGAE | 115kV tap on Woodland-Davis 115kV line | 2017-09-01 07:00 | 2017-09-01 07:00 | NA | None | None | NA
BLUE SANDS SOLAR PV | 1095 | 2015-02-05 | 2015-04-07 07:00 | WITHDRAWN | 2015-08-04 07:00 | FT | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 5 | 5 | Energy Only |  | NYE | NV | VEA | Valley Substation 138kV | 2015-12-01 08:00 | 2015-12-01 08:00 | None | NA | NA | NA |  | None
BIRDS LANDING WIND | 1098 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-12-14 08:00 | C08 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 1.84 | 1.84 | Full Capacity |  | SOLANO | CA | PGAE | Birds Landing Substation 230kV | 2016-12-01 08:00 | 2017-12-01 08:00 | NA | None | None | NA |  | IC Request
BRIDGEHEAD ES | 1099 | 2015-04-29 | 2015-04-30 07:00 | WITHDRAWN | 2016-03-02 08:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 103 | 103 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Du Pont Substation 60 kV Bus | 2021-12-31 08:00 | 2021-12-31 08:00 | NA | None | None | NA
BRISBANE ES | 1100 | 2015-04-29 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-17 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 412 | 412 | Full Capacity |  | SAN MATEO | CA | PGAE | Martin Substation 115 kV Bus | 2021-12-31 08:00 | 2021-12-31 08:00 | NA | None | None | NA
COOLEY LANDING BESS | 1101 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-04-15 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20 | Full Capacity |  | SAN MATEO | CA | PGAE | Cooley Landing 60kV Substation | 2017-09-01 07:00 | 2018-06-01 07:00 | NA | None | None | NA |  | IC Request
CORNWALL ENERGY STORAGE | 1102 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-02-22 08:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Pittsburgh - GWF Tap #1 60kV | 2018-06-01 07:00 | 2018-06-01 07:00 | NA | None | None | NA
GEYSERS UNIT 11 RECONNECTION | 1104 | 2015-04-29 | 2015-04-30 07:00 | WITHDRAWN | 2016-02-05 08:00 | C08 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 0.1 | 74 | Full Capacity |  | SONOMA | CA | PGAE | Geysers 17-Fulton 230kV transmission line | 2017-03-03 08:00 | 2017-03-03 08:00 | NA | None | None | NA
GOLDENEYE ENERGY STORAGE CENTER | 1105 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-04-26 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20 | Full Capacity |  | CONTRA COSTA | CA | PGAE | 230 kV bus at the Kelso Substation via the Mariposa Energy 230 kV tie line | 2018-12-01 08:00 | 2021-08-01 07:00 | NA | None | None | NA
FOUNTAIN WIND | 1106 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2026-03-09 07:00 | C08 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 206 | 200 | Full Capacity | Off-Peak Deliverability | SHASTA | CA | PGAE | Pit 1-Cottonwood 230 kV Line | 2020-10-15 07:00 | 2027-09-15 07:00 | NA | Complete | Complete | NA | Executed | IC Request
MOLINO ES | 1107 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-04-29 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 10 | 10 | Full Capacity |  | SONOMA | CA | PGAE | Molino Substation 60kV bus | 2020-03-01 08:00 | 2020-03-01 08:00 | NA | Complete | None | NA
NICOLAUS STORAGE | 1108 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2017-05-31 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 64 | 64 | Full Capacity |  | SUTTER | CA | PGAE | East Nicolaus 115kV Substation | 2020-12-01 08:00 | 2020-12-01 08:00 | NA | None | Complete | NA |  | IC Request
OAKLAND ES | 1110 | 2015-04-29 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-02 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 156 | 153 | Full Capacity |  | ALAMEDA | CA | PGAE | Oakland J 115kV substation bus | 2021-12-31 08:00 | 2021-12-31 08:00 | NA | None | None | NA
POINT ARENA ES | 1112 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-04-29 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 10 | 10 | Full Capacity |  | MENDOCINO | CA | PGAE | Point Arena Substation 60kV | 2020-03-01 08:00 | 2020-03-01 08:00 | NA | Complete | None | NA
SAND HILL WIND 2 | 1114 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-05-02 07:00 | C08 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 52.5 | 52.5 | Full Capacity |  | ALAMEDA | CA | PGAE | Tesla to Delta Switching Yard at the Altamont-Midway Substation | 2017-06-30 07:00 | 2017-06-30 07:00 | NA | Complete | None | NA
SHINGLE SPRINGS ES | 1115 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-04-29 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 10 | 10 | Full Capacity |  | EL DORADO | CA | PGAE | Shingle Springs Substation 115 kV | 2020-03-01 08:00 | 2020-03-01 08:00 | NA | Complete | None | NA
BELTRAN SOLAR | 1118 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-05-02 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 300 | 300 | Full Capacity |  | STANISLAUS | CA | PGAE | Westley-Quinto 230 kV line | 2016-12-01 08:00 | 2018-09-01 07:00 | NA | Complete | None | NA |  | Failure to Cure Deficiency
CENTRAL VALLEY | 1119 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-02-16 08:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 60 | 60 | Full Capacity |  | FRESNO | CA | PGAE | Mendota 115kV substation | 2021-06-01 07:00 | 2021-06-01 07:00 | NA | None | None | NA
CORCORAN 2 BESS ADDITION | 1121 | 2015-04-29 | 2015-04-30 07:00 | WITHDRAWN | 2017-05-16 07:00 | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 19.75 | 3 |  | 19.75 | Full Capacity |  | KINGS | CA | PGAE | Waukena Switching Station 115kV | 2018-12-31 08:00 | 2018-12-31 08:00 | NA | Complete | None | NA |  | IC Request
DOS AMIGOS SOLAR | 1122 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2017-05-03 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 81.8 | 81.8 | Energy Only |  | MERCED | CA | PGAE | Mercy Springs 70 kV Switching Station | 2019-12-31 08:00 | 2020-12-01 08:00 | NA | Complete | None | NA |  | IC Request
FIREBAUGH PANOCHE BESS (FKA PANOCHE ENERGY RELIABILITY CENTER) | 1123 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-03-08 08:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 50 | 50 | Full Capacity |  | FRESNO | CA | PGAE | Panoche-Schindler #2 115 kV Line via the Cheney #1 Tap 115 kV Line | 2018-05-01 07:00 | 2018-05-01 07:00 | NA | None | None | NA
FRESNO SOLAR 1 | 1124 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2015-06-25 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 247 | 247 | Full Capacity |  | FRESNO | CA | PGAE | Helm-Firebaugh 230kV line | 2018-12-31 08:00 | 2018-12-31 08:00 | NA | None | None | NA
GALE SOLAR 1 | 1125 | 2015-04-22 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-02 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 | Full Capacity |  | FRESNO | CA | PGAE | Coalinga No 1 Substation 70kV | 2018-12-31 08:00 | 2018-12-31 08:00 | NA | None | None | NA
HENRIETTA ENERGY STORAGE | 1126 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-01-20 08:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 25 | 25 | Full Capacity |  | KINGS | CA | PGAE | Henrietta Substation - 70kV | 2020-05-01 07:00 | 2020-05-01 07:00 | NA | None | None | NA
LUNA PRISM (FKA: MOON PRISM 2) | 1130 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2018-05-17 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 19.94 | 19.94 | Energy Only |  | FRESNO | CA | PGAE | Tranquility Substation 230kV | 2018-12-31 08:00 | 2020-11-01 07:00 | NA | Complete | Complete | NA |  | IC Request
ENERGY NUEVO STORAGE FARM (FKA NEW KEARNY ENERGY PARK) | 1131 | 2015-04-16 | 2015-04-30 07:00 | WITHDRAWN | 2017-06-06 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Flywheel; MWs MW-1: 20 | 20 | Full Capacity |  | FRESNO | CA | PGAE | New Kearny Substation 70kV bus | 2020-05-01 07:00 | 2020-09-01 07:00 | NA | Complete | None | NA |  | Failure to Cure Deficiency
OLD KEARNEY ES | 1132 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-04-29 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 10 | 10 | Full Capacity |  | FRESNO | CA | PGAE | Kearney Substation 70kV bus | 2020-03-01 08:00 | 2020-03-01 08:00 | NA | Complete | None | NA
OVEJA SOLAR FARM | 1133 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-04-11 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 | Full Capacity |  | MERCED | CA | PGAE | Cantua 115kV substation | 2020-06-01 07:00 | 2020-06-01 07:00 | NA | None | None | NA
QUAIL CREEK SOLAR 1 | 1134 | 2015-04-24 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-02 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 40 | 40 | Full Capacity |  | FRESNO | CA | PGAE | Gates-Coalinga #1 70kV line at Jacalito | 2018-12-31 08:00 | 2018-12-31 08:00 | NA | None | None | NA
WESTLANDS APRICOT | 1137 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2017-05-11 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KINGS | CA | PGAE | Kent SW STA 70 kV | 2016-12-05 08:00 | 2021-10-15 07:00 | NA | None | None | NA |  | None
WESTLANDS ARTICHOKE | 1138 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2017-05-11 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 | Full Capacity |  | KINGS | CA | PGAE | Kent SW STA 70 kV | 2016-12-19 08:00 | 2021-11-03 07:00 | NA | None | None | NA |  | None
WHITE ROCK SOLAR FARM | 1140 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-04-01 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 50 | Full Capacity |  | MERCED | CA | PGAE | Le Grand Substation 115kV | 2020-06-01 07:00 | 2020-06-01 07:00 | NA | Complete | None | NA
ALAMO SPRINGS SOLAR 1 | 1141 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2021-05-17 07:00 | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 80 | 73.6 |  | 80 | Partial Capacity | Off-Peak Deliverability | KERN | CA | PGAE | Arco Substation 70kV | 2018-12-31 08:00 | 2023-12-15 08:00 | NA | Complete | Complete | NA | Executed | Failure to Cure Deficiency
ALGOSO ES | 1142 | 2015-04-29 | 2015-04-30 07:00 | WITHDRAWN | 2016-03-02 08:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 206 | 206 | Full Capacity |  | KERN | CA | PGAE | Magunden 115 kV Substation | 2021-12-31 08:00 | 2021-12-31 08:00 | NA | None | None | NA |  | IC Request
AMERICAN KINGS 2 | 1144 | 2015-04-28 | 2015-04-30 07:00 | WITHDRAWN | 2016-02-26 08:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 120 | 120 | Full Capacity |  | KINGS | CA | PGAE | Henrietta Substation 70kV | 2020-11-01 07:00 | 2020-11-01 07:00 | NA | None | None | NA |  | IC Request
ANCHO CREEK SOLAR | 1145 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-09 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 | Full Capacity |  | KERN | CA | PGAE | Arco 230kV substation | 2018-12-31 08:00 | 2018-12-31 08:00 | NA | None | None | NA |  | IC Request
ATWELL WEST BESS ADDITION | 1146 | 2015-04-29 | 2015-04-30 07:00 | WITHDRAWN | 2017-05-16 07:00 | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 20 | 3 |  | 20 | Full Capacity |  | TULARE | CA | PGAE | Olive switching station - Smynra 115 Kv Line | 2018-12-31 08:00 | 2019-12-31 08:00 | NA | Complete | None | NA |  | IC Request
BASKET RIDGE SOLAR | 1147 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-02-24 08:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 80 | 80 | Full Capacity |  | KERN | CA | PGAE | Famoso Substation 115kV | 2018-12-31 08:00 | 2018-12-31 08:00 | NA | None | None | NA
BRITAIN | 1148 | 2015-04-29 | 2015-04-30 07:00 | WITHDRAWN | 2016-02-26 08:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 21.7 | 21.7 | Full Capacity |  | KERN | CA | PGAE | Arco-Polonio Pass 70 kV line | 2018-03-31 07:00 | 2018-03-31 07:00 | NA | None | None | NA
CARNERAS SOLAR 1 | 1150 | 2015-04-22 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-02 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | PGAE | Blackwell Substation 70kV | 2018-12-31 08:00 | 2018-12-31 08:00 | NA | None | None | NA
KIMBERLINA SOLAR | 1151 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-09 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | KERN | CA | PGAE | Semitropic Substation 115kV | 2018-12-31 08:00 | 2018-12-31 08:00 | NA | None | None | NA |  | IC Request
MARICOPA WEST SOLAR PV 3 | 1152 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-04-25 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | PGAE | Maricopa-Copus 70kV line | 2017-12-31 08:00 | 2017-12-31 08:00 | NA | Complete | None | NA
MORRO BAY WAVE ENERGY PROJECT | 1153 | 2015-04-28 | 2015-04-30 07:00 | WITHDRAWN | 2016-02-17 08:00 | C08 | Generating Facility Type-1: Other; Generating Facility Fuel-1: Water; MWs MW-1: 650 | 650 | Full Capacity |  | SAN LUIS OBISPO | CA | PGAE | Morro Bay PP 230 kV | 2020-03-31 07:00 | 2020-03-31 07:00 | NA | None | None | NA
MOUNT VERNON SOLAR | 1154 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2018-05-16 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 | Energy Only |  | KERN | CA | PGAE | New Wheeler Ridge Junction 115kV substation | 2018-12-31 08:00 | 2020-12-01 08:00 | NA | Complete | Complete | NA |  | IC Request
PERIWINKLE | 1155 | 2015-04-29 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-17 07:00 | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 77.3 | 77.5 |  | 77.5 | Full Capacity |  | KERN | CA | PGAE | Eastshore 115kV Substation | 2018-12-31 08:00 | 2018-12-31 08:00 | NA | None | None | NA
SANTA MARIA ENERGY BESS (FKA SANTA MARIA ENERGY RELIABILITY CENTER) | 1156 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-03-08 08:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 42 | 42 | Full Capacity |  | SANTA BARBARA | CA | PGAE | Santa Maria Cogen 115 kV Tap | 2018-05-01 07:00 | 2018-05-01 07:00 | NA | None | None | NA
ALAMO SPRINGS SOLAR 2 | 1157 | 2015-04-22 | 2015-04-30 07:00 | WITHDRAWN | 2021-05-17 07:00 | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 50 | 46 |  | 50 | Partial Capacity | Off-Peak Deliverability | KERN | CA | PGAE | Arco Substation 70kV | 2018-12-31 08:00 | 2023-12-15 08:00 | NA | Complete | Complete | NA | Executed | Failure to Cure Deficiency
TRAFALGAR | 1159 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2017-05-24 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 21.7 | 21.7 | Full Capacity |  | KINGS | CA | PGAE | Arco-Tulare Lake 70kV line | 2018-03-31 07:00 | 2020-06-30 07:00 | NA | Complete | None | NA |  | IC Request
TROY | 1160 | 2015-04-29 | 2015-04-30 07:00 | WITHDRAWN | 2016-02-26 08:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | PGAE | Arco - Polonio Pass 70kV line | 2018-03-31 07:00 | 2018-03-31 07:00 | NA | None | None | NA
ROYAL (FKA WHEELER INDIGO) | 1161 | 2015-04-29 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-17 07:00 | C08 | Storage | Photovoltaic |  | Battery | Solar |  | 180.5 | 179.8 |  | 180.5 | Full Capacity |  | KERN | CA | PGAE | Wheeler Ridge-Midway 230kV line | 2019-04-01 07:00 | 2019-04-01 07:00 | NA | None | None | NA
WHITE RIVER 3 BESS | 1162 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2017-05-16 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 10 | 10 | Full Capacity |  | TULARE | CA | PGAE | Olive Switching Station 115kV | 2017-12-31 08:00 | 2019-12-31 08:00 | NA | None | None | NA |  | IC Request
WHITE WOLF SOLAR | 1163 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2018-05-16 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Energy Only |  | KERN | CA | PGAE | Lamont 115kV Substation | 2018-12-31 08:00 | 2020-01-31 08:00 | NA | Complete | Complete | NA |  | IC Request
PRIMROSE ENERGY STORAGE CENTER | 1164 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-04-26 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20 | Full Capacity |  | KERN | CA | PGAE | 115kV Rosedale Substation | 2018-12-01 08:00 | 2021-08-01 07:00 | NA | None | None | NA
BANCROFT | 1165 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2017-01-04 08:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20 | Full Capacity |  | SAN DIEGO | CA | SDGE | Spring Valley substation 69 kV bus | 2018-01-01 08:00 | 2019-01-01 08:00 | NA | None | None | NA |  | IC Request
BONSALL RENEWABLE | 1167 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-14 07:00 | C08 | Storage | Photovoltaic |  | Battery | Solar |  | 20 | 64 |  | 84 | Full Capacity |  | SAN DIEGO | CA | SDGE | 0.2 miles from Monsrate Tap on the Monsrate Tap-Pala 69 kV line | 2017-12-31 08:00 | 2017-12-31 08:00 | NA | None | None | NA
CARLSBAD ADVANCED ENERGY STORAGE CENTER | 1168 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-02-23 08:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 40 | 40 | Full Capacity |  | SAN DIEGO | CA | SDGE | Encina Substation 138 kV | 2019-12-31 08:00 | 2019-12-31 08:00 | NA | None | None | NA
HARVEST ENERGY STORAGE PROJECT (FKA OTAY MESA MSS) | 1172 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2015-12-08 08:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Other; MWs MW-1: 110 | 110 | Full Capacity |  | SAN DIEGO | CA | SDGE | Otay Mesa Substation 230 kV bus | 2019-11-30 08:00 | 2019-11-30 08:00 | NA | None | None | NA
HEIRLOOM RENEWABLE | 1173 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-14 07:00 | C08 | Storage | Photovoltaic |  | Battery | Solar |  | 20 | 64 |  | 84 | Full Capacity |  | SAN DIEGO | CA | SDGE | 0.2-mile from Moro hill tap on the Moro Hill Tap - Monserate 69 kV line | 2017-12-31 08:00 | 2017-12-31 08:00 | NA | None | None | NA
JACUMBA RANCH | 1174 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2019-08-16 07:00 | C08 | Storage | Photovoltaic |  | Battery | Solar |  | 10 | 50.25 |  | 60.25 | Energy Only |  | SAN DIEGO | CA | SDGE | East County Substation 138 kV | 2021-06-01 07:00 | 2021-06-01 07:00 | NA | Complete | Complete | NA | In Progress
MARIA PICO ENERGY STORAGE CENTER | 1176 | 2015-04-20 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-08 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 25 | 25 | Full Capacity |  | SAN DIEGO | CA | SDGE | Otay Mesa Switchyard 230 kV | 2018-07-31 07:00 | 2018-07-31 07:00 | NA | None | None | NA
MIDTOWN CANYON ES | 1177 | 2015-04-17 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-06 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 100 | 100 | Full Capacity |  | SAN DIEGO | CA | SDGE | Pala 69kV Substation | 2019-05-01 07:00 | 2019-05-01 07:00 | NA | None | None | NA
MIDTOWN CANYON GAS | 1178 | 2015-04-17 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-06 07:00 | C08 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 507.4 | 507.4 | Full Capacity |  | SAN DIEGO | CA | SDGE | Talega-Escondido 230 kv line | 2019-03-01 08:00 | 2019-03-01 08:00 | NA | None | None | NA
MIGUEL BESS (FKA MIGUEL) | 1179 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-02-09 08:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 30 | 30 | Full Capacity |  | SAN DIEGO | CA | SDGE | Miguel Substation 69kV bus | 2017-07-31 07:00 | 2019-07-31 07:00 | NA | None | None | NA
ORDWAY ENERGY STORAGE (FKA OCEANSIDE BESS) | 1180 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-03-03 08:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 50 | 50 | Full Capacity |  | SAN DIEGO | CA | SDGE | New substations San Luis-Melrose 69 kV | 2019-11-15 08:00 | 2019-11-15 08:00 | NA | None | None | NA |  | None
OTAY MESA BESS | 1181 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-22 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 200 | 200 | Full Capacity |  | SAN DIEGO | CA | SDGE | Otay Mesa Substation 230 kV Bus | 2018-01-01 08:00 | 2018-01-01 08:00 | NA | None | None | NA
OTAY MESA CINCO | 1182 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2015-06-29 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 5 | 5 | Full Capacity |  | SAN DIEGO | CA | SDGE | Border Substation 69kV Alta and Otay Mesa Road | 2017-08-08 07:00 | 2017-08-08 07:00 | NA | None | None | NA
PALA CANYON RENEWABLE (FKA PALA FALLBROOK ENERGY CENTER) | 1183 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-14 07:00 | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 28 | 9 |  | 37 | Full Capacity |  | SAN DIEGO | CA | SDGE | Pala 69kV substation | 2017-12-31 08:00 | 2017-12-31 08:00 | NA | None | None | NA
PALOMAS SOLAR PROJECT | 1184 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-03-04 08:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 200 | 200 | Full Capacity |  | YUMA | AZ | SDGE | Hoodoo Wash Switchyard 500 kV | 2018-12-01 08:00 | 2018-12-01 08:00 | NA | None | None | NA
PIO PICO UNIT 4 | 1185 | 2015-04-20 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-08 07:00 | C08 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 110 | 110 | Full Capacity |  | SAN DIEGO | CA | SDGE | Otay Mesa Switchyard 230 kV | 2018-12-15 08:00 | 2018-12-15 08:00 | NA | None | None | NA
RAINBOW ENERGY CENTER | 1186 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-02-19 08:00 | C08 | Combustion Turbine | Storage |  | Natural Gas | Battery |  | 462 | 61 |  | 523 | Full Capacity |  | SAN DIEGO | CA | SDGE | New Substation to Loop in TL2330 Talega- Escondido 230kV line | 2018-06-30 07:00 | 2018-06-30 07:00 | NA | None | None | NA
STINGRAY ENERGY STORAGE | 1187 | 2015-04-23 | 2015-04-30 07:00 | WITHDRAWN | 2018-03-26 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20 | Full Capacity |  | SAN DIEGO | CA | SDGE | San Luis Rey Substation 69 kV | 2018-01-01 08:00 | 2019-04-01 07:00 | NA | Complete | Complete | NA |  | Failure to Cure Deficiency
STOWE ENERGY STORAGE (FKA POWAY) | 1188 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-08 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 25 | 25 | Full Capacity |  | SAN DIEGO | CA | SDGE | Pomerado Substation 69 kV | 2019-11-15 08:00 | 2019-11-15 08:00 | NA | None | None | NA
TITAN SOLAR | 1190 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-13 07:00 | C08 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 300 | 300 | Full Capacity |  | MARICOPA | AZ | SDGE | Hassayampa 500 kV Substation | 2020-09-30 07:00 | 2020-09-30 07:00 | NA | None | None | NA
EAGLE MOUNTAIN PUMP STORAGE #4 | 1193 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-02-12 08:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Water; MWs MW-1: 1408 | 1408 | Full Capacity |  | RIVERSIDE | CA | SCE | Red Bluff Substation 500 kV | 2022-01-01 08:00 | 2022-01-01 08:00 | NA | Complete | None | NA |  | IC Request
IRISH | 1194 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2017-09-05 07:00 | C08 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 600 | 600 | Energy Only |  | RIVERSIDE | CA | SCE | Colorado River Substation 230kV | 2020-06-01 07:00 | 2020-10-31 07:00 | NA | Complete | Complete | NA |  | IC Request
LEPRECHAUN | 1195 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2015-06-25 07:00 | C08 | Generating Facility Type-1: Combustion Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 49 | 49 | Full Capacity |  | RIVERSIDE | CA | SCE | Blythe Energy Park #1 (BEP1) 230kV | 2020-06-01 07:00 | 2020-06-01 07:00 | NA | None | None | NA |  | IC Request
PALO VERDE ENERGY STORAGE | 1197 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2017-12-29 08:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 400 | 400 | Full Capacity |  | RIVERSIDE | CA | SCE | Red Bluff Switchyard 220kV | 2018-09-01 07:00 | 2020-03-01 08:00 | NA | Complete | Complete | NA |  | IC Request
SIDEWINDER SOLAR | 1199 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-24 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 108.8 | 108.8 | Energy Only |  | RIVERSIDE | CA | SCE | Red Bluff 220kV bus | 2019-12-31 08:00 | 2019-12-31 08:00 | NA | None | None | NA |  | IC Request
HARPER LAKE ENERGY STORAGE | 1202 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-03-10 08:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Other; MWs MW-1: 140 | 140 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Kramer Substation 230kV bus | 2020-08-31 07:00 | 2021-09-01 07:00 | NA | None | None | NA
HIGH DESERT VIEW SOLAR | 1203 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2016-05-03 07:00 | C08 | Photovoltaic | Storage |  | Solar | Battery |  | 136.75 | 30.8 |  | 167.55 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Calcite Substation gen-tie at 230KV | 2018-05-01 07:00 | 2019-05-31 07:00 | NA | None | None | NA
SIENNA | 1205 | 2015-04-29 | 2015-04-30 07:00 | WITHDRAWN | 2016-03-11 08:00 | C08 | Storage | Photovoltaic |  | Battery | Solar |  | 66.7 | 66.5 |  | 66.7 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Coolwater 115kV Substation | 2018-12-31 08:00 | 2018-12-31 08:00 | NA | Complete | None | NA |  | IC Request
TAMPADERO SOLAR | 1206 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2018-05-15 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 150 | 150 | Energy Only |  | SAN BERNARDINO | CA | SCE | Jasper Substation 230kV | 2018-12-31 08:00 | 2021-03-31 07:00 | NA | Complete | Complete | NA |  | IC Request
BRADMORE BESS FKA BRADMORE ES | 1209 | 2015-04-29 | 2015-04-30 07:00 | WITHDRAWN | 2019-05-21 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 412 | 412 | Full Capacity |  | LOS ANGELES | CA | SCE | Antelope 220kV bus | 2021-12-31 08:00 | 2021-12-31 08:00 | NA | Complete | Complete | NA | In Progress | IC Request
FRAZIER ES | 1210 | 2015-04-29 | 2015-04-30 07:00 | WITHDRAWN | 2016-03-11 08:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 420 | 412 | Full Capacity |  | TULARE | CA | SCE | Springville Substation 220kV bus | 2021-12-31 08:00 | 2021-12-31 08:00 | NA | None | None | NA
GOLDEN FIELDS SOLAR 3 | 1213 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2015-07-08 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | KERN | CA | SCE | Whirlwind 230 kV substation | 2018-06-30 07:00 | 2018-06-30 07:00 | NA | None | None | NA |  | IC Request
GOLDEN PRISM | 1214 | 2015-04-30 | 2015-04-30 07:00 | WITHDRAWN | 2019-03-18 07:00 | C08 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 6 | 5.98 | Full Capacity |  | KERN | CA | SCE | Whirlwind Substation 230kV | 2018-06-30 07:00 | 2020-01-31 08:00 | NA | Complete | Complete | NA |  | IC Request
PALMDALE ENERGY | 1216 | 2015-04-29 | 2015-04-30 07:00 | WITHDRAWN | 2019-07-22 07:00 | C08 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 130 | 130 | Full Capacity |  | LOS ANGELES | CA | SCE | Vincent Substation 230 kV bus | 2019-06-01 07:00 | 2022-04-01 07:00 | NA | Complete | Complete | NA | Executed | Failure to Cure Deficiency
NEVADA MOHAVE SOLAR | 1218 | 2015-04-28 | 2015-04-30 07:00 | WITHDRAWN | 2021-01-19 08:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 400 | 400 | Energy Only |  | CLARK | NV | SCE | Jointly-owned Mohave Switchyard 500kV | 2019-12-01 08:00 | 2024-06-15 07:00 | NA | Complete | Complete | NA | In Progress | Failure to Cure Deficiency
SNOW MOUNTAIN SOLAR | 1219 | 2015-04-28 | 2015-04-30 07:00 | WITHDRAWN | 2018-05-22 07:00 | C08 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Energy Only |  | CLARK | NV | GLW | Desert View Substation 230 kV bus | 2018-08-01 07:00 | 2019-06-01 07:00 | NA | Complete | Complete | NA |  | IC Request
MIKADO | 1220 | 2015-04-29 | 2015-04-30 07:00 | WITHDRAWN | 2016-01-21 08:00 | C08 | Storage | Photovoltaic |  | Battery | Solar |  | 103 | 102.5 |  | 103 | Full Capacity |  | IMPERIAL | CA | IID | Liebert 230kV Switchyard | 2018-12-31 08:00 | 2018-12-31 08:00 | NA | None | None | NA |  | IC Request
WGP GEYSERS | 1221 | 2014-12-29 | 2015-02-23 08:00 | WITHDRAWN | 2017-11-28 08:00 | ISP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 35 | 35 | Full Capacity |  | SONOMA | CA | PGAE | Geysers #3 - Cloverdale 115 kV Line | 2018-06-01 07:00 | 2018-06-01 07:00 | NA | None | None | NA | Executed | IC Request
ARROYO REYES SOLAR | 1224 | 2016-04-27 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-03 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 153.3 | 153.3 | Full Capacity |  | KINGS | CA | PGAE | Mustang 230kV Switching Station | 2020-12-01 08:00 | 2020-12-01 08:00 | NA | Complete |  | NA |  | None
CINCO | 1225 | 2016-04-27 | 2016-05-02 07:00 | WITHDRAWN | 2022-04-22 07:00 | C09 | Storage | Photovoltaic |  | Battery | Solar |  | 10.45 | 53.2 |  | 60 | Energy Only | Off-Peak Deliverability | FRESNO | CA | PGAE | Five Points Substation 70 kV | 2019-06-01 07:00 | 2021-12-31 08:00 | NA | Complete | Complete | NA | In Progress | IC Request
CONEJO SOLAR | 1226 | 2016-04-21 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-20 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 102 | 102 | Full Capacity |  | FRESNO | CA | PGAE | 230kV Tranquility Switching Station | 2020-12-01 08:00 | 2020-12-01 08:00 | NA |  |  | NA |  | IC Request
CURRY | 1227 | 2016-04-29 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-01 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 42.2 | 42.1 | Full Capacity |  | FRESNO | CA | PGAE | Schindler Transmission Line Tap 70 kV | 2020-11-01 07:00 | 2020-11-01 07:00 | NA | Complete |  | NA |  | IC Request
EASTERBY ENERGY STORAGE | 1228 | 2016-05-03 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-01 08:00 | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 52.2 | 50.83 | Full Capacity |  | FRESNO | CA | PGAE | Malaga 115kV Bus | 2020-06-01 07:00 | 2020-06-01 07:00 | NA | Complete |  | NA |  | IC Request
SOUTHERN LIGHT SOLAR | 1229 | 2016-04-23 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-13 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 61.62 | 60.85 | Full Capacity |  | FRESNO | CA | PGAE | Coalinga #2 - Coalinga #1 70 kV line Approx. 1.9 miles south of Coalinga #2 and 1 mile east of the project site | 2020-12-31 08:00 | 2020-12-31 08:00 | NA | Complete |  | NA |  | IC Request
GOLDEN RECTANGLE | 1230 | 2016-04-28 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-04 07:00 | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 121.6 | 30.9 |  | 152.2 | Full Capacity |  | FRESNO | CA | PGAE | Tranquility Kearny 230kV | 2021-12-01 08:00 | 2021-12-01 08:00 | NA | Complete |  | NA |  | IC Request
HEARTLAND SOLAR | 1231 | 2016-04-22 | 2016-05-02 07:00 | WITHDRAWN | 2016-07-06 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 1044.7625 | 1043.0705 | Full Capacity |  | FRESNO | CA | PGAE | PANOCHE 230 KV SUB | 2020-12-31 08:00 | 2020-12-31 08:00 | NA | None |  | NA |  | IC Request
HEARTLAND SOLAR-2 | 1232 | 2016-04-22 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-13 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 1044.7625 | 1042.4945 | Full Capacity |  | FRESNO | CA | PGAE | Tranquility Switching Station 230kV | 2020-12-31 08:00 | 2020-12-31 08:00 | NA | Complete |  | NA |  | IC Request
HOBBS ENERGY STORAGE | 1233 | 2016-05-02 | 2016-05-02 07:00 | WITHDRAWN | 2018-05-01 07:00 | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 50.5 | 50.5 | Full Capacity |  | MADERA | CA | PGAE | Borden Substation 70kV | 2018-05-31 07:00 | 2018-05-31 07:00 | NA | Complete | Complete | NA |  | IC Request
HONEYBEE SOLAR | 1234 | 2016-04-21 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-20 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50 | 51 | Full Capacity |  | FRESNO | CA | PGAE | New 115kV Switching Station on the Panoche - Schindler 115kV #1 line | 2020-09-04 07:00 | 2020-09-04 07:00 | NA |  |  | NA |  | IC Request
HUDSON SOLAR 1 | 1235 | 2016-04-21 | 2016-05-02 07:00 | WITHDRAWN | 2021-01-13 08:00 | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 86.64 | 99 |  | 85 | Energy Only |  | FRESNO | CA | PGAE | Panoche Substation 115 kV | 2019-12-31 08:00 | 2024-12-31 08:00 | NA | Complete | Complete | NA | Executed | IC Request
INCA | 1236 | 2016-04-29 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-01 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 105.5 | 105.3 | Full Capacity |  | FRESNO | CA | PGAE | Dairyland-Mendota Transmission Line 115 kV | 2020-11-01 07:00 | 2020-11-01 07:00 | NA | Complete |  | NA |  | IC Request
MAIZEN BLUE SOLAR 1 | 1237 | 2016-04-22 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-04 07:00 | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 82.368 | 20.7 |  | 80.77 | Full Capacity |  | FRESNO | CA | PGAE | Excelsior Switching Station located on the Panoche-Schindler No.1 & 2 115 kV line | 2019-12-31 08:00 | 2019-12-31 08:00 | NA | Complete |  | NA |  | IC Request
MANGO SOLAR | 1238 | 2016-04-28 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-21 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 61 | 61 | Full Capacity |  | FRESNO | CA | PGAE | Jayne Switch Station 70 kV | 2018-12-01 08:00 | 2018-12-01 08:00 | NA | Complete |  | NA |  | IC Request
MEDEIROS SOLAR | 1239 | 2016-05-03 | 2016-05-02 07:00 | WITHDRAWN | 2024-06-18 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 28.35 | 26.5 | Energy Only | Off-Peak Deliverability | MERCED | CA | PGAE | Los Banos-O'Neil PGP 70 kV Line | 2019-08-01 07:00 | 2026-12-31 08:00 | NA | Complete | Complete | NA | Terminated | IC Request
NILES SOLAR 1 | 1240 | 2016-04-21 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-04 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20.52 | 20.22 | Full Capacity |  | KINGS | CA | PGAE | PG&E Corcoran-Guernsey 70 kV line | 2019-12-31 08:00 | 2019-12-31 08:00 | NA | Complete |  | NA |  | IC Request
PELICAN ISLAND | 1241 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-10 08:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 310.791 | 307.624 | Full Capacity |  | FRESNO | CA | PGAE | Midway- Gates 230 kV line | 2020-12-31 08:00 | 2020-12-31 08:00 | NA | Complete |  | NA |  | IC Request
RANCHO FRESNO STORAGE FARM | 1245 | 2016-04-20 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-12 07:00 | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Flywheel; MWs MW-1: 122.4 | 30.6 | Full Capacity |  | FRESNO | CA | PGAE | PG&E Kearney Sub 70 kV | 2021-05-01 07:00 | 2021-05-01 07:00 | NA |  |  | NA |  | IC Request
ROMERO CREEK | 1246 | 2016-04-29 | 2016-05-02 07:00 | WITHDRAWN | 2019-10-31 07:00 | C09 | Storage | Wind Turbine |  | Battery | Wind Turbine |  | 28 | 178.2 |  | 200 | Full Capacity |  | MERCED | CA | PGAE | Quinto Switching Station 230 kV Bus | 2019-12-31 08:00 | 2023-04-28 07:00 | NA | Complete | Complete | NA | In Progress | IC Request
SERENITY SOLAR | 1247 | 2016-04-23 | 2016-05-02 07:00 | WITHDRAWN | 2016-07-06 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 41 | 40.53 | Full Capacity |  | FRESNO | CA | PGAE | Coalinga #1 - San Miguel 70 kV line | 2020-12-31 08:00 | 2020-12-31 08:00 | NA |  |  | NA |  | IC Request
CROWN | 1248 | 2016-04-29 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-01 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 105.5 | 105.3 | Full Capacity |  | FRESNO | CA | PGAE | Dairyland-Mendota 115 kV Line | 2020-11-01 07:00 | 2020-11-01 07:00 | NA | Complete |  | NA |  | IC Request
SEIS PUNTOS SOLAR | 1249 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-17 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 202.922 | 202.922 | Full Capacity |  | FRESNO | CA | PGAE | Excelsior Switch Station 115 kV | 2018-12-01 08:00 | 2018-12-01 08:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
WADY SOLAR | 1250 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-10 08:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 102.75 | 101.97 | Full Capacity |  | MADERA | CA | PGAE | LeGrand - Dairyland 115 kV line | 2020-12-31 08:00 | 2020-12-31 08:00 | NA | Complete |  | NA |  | IC Request
WARRIORS | 1251 | 2016-04-29 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-04 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 42.2 | 42.1 | Full Capacity |  | FRESNO | CA | PGAE | Crescent Switching Station 70kV | 2019-11-01 07:00 | 2019-11-01 07:00 | NA | Complete |  | NA |  | IC Request
WILD WEST SOLAR | 1252 | 2016-04-23 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-10 08:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 71.59 | 71.08 | Full Capacity |  | FRESNO | CA | PGAE | Cantua Substation 115 kV | 2020-12-30 08:00 | 2020-12-30 08:00 | NA | Complete |  | NA |  | IC Request
WOLVERINE SOLAR 1 - FKA YUBA SOLAR 1 | 1253 | 2016-04-18 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-04 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20.52 | 20.2 | Full Capacity |  | FRESNO | CA | PGAE | Stroud 70 kV Switching Station | 2019-12-31 08:00 | 2019-12-31 08:00 | NA | Complete |  | NA |  | IC Request
ALAMO SPRINGS SOLAR 3 | 1254 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-13 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 158.18 | 158.135 | Full Capacity |  | KERN | CA | PGAE | PG&E Arco Substation 70 kV | 2019-07-01 07:00 | 2019-07-01 07:00 | NA | Complete |  | NA |  | IC Request
ALMOND GROVE SOLAR PROJECT | 1255 | 2016-05-02 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-15 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 40 | 40.9 | Full Capacity |  | KERN | CA | PGAE | Antelope Substation 70 kV | 2020-12-31 08:00 | 2020-12-31 08:00 | NA | Complete |  | NA |  | IC Request
CELESTIAL SOLAR 1 | 1256 | 2016-04-23 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-13 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 91.74 | 91.74 | Full Capacity |  | KERN | CA | PGAE | Huron Substation 70 kV | 2020-12-31 08:00 | 2020-12-31 08:00 | NA | Complete |  | NA |  | IC Request
HELIOS PRIME | 1257 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2016-07-06 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 22.37 | 20.29 | Full Capacity |  | KERN | CA | PGAE | Lakeview Substation 70kV | 2020-12-31 08:00 | 2020-12-31 08:00 | NA | Complete |  | NA |  | IC Request
HELIOS SECONDUS | 1258 | 2016-04-27 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-10 08:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 232.16 | 229.16 | Full Capacity |  | KERN | CA | PGAE | Midway-Wheeler Ridge #2 230 kV Line | 2020-12-31 08:00 | 2020-12-31 08:00 | NA |  |  | NA |  | IC Request
ROLLING HILLS SOLAR | 1261 | 2016-04-23 | 2016-05-02 07:00 | WITHDRAWN | 2016-07-06 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 206.27 | 203.635 | Full Capacity |  | KERN | CA | PGAE | Arco Substation 230 kV | 2020-12-30 08:00 | 2020-12-30 08:00 | NA |  |  | NA |  | IC Request
SURYA SOLAR | 1262 | 2016-04-27 | 2016-05-02 07:00 | WITHDRAWN | 2017-04-10 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 158.28 | 157.735 | Full Capacity |  | KERN | CA | PGAE | PG&E Midway Wheeler Ridge 230 kV line | 2019-07-01 07:00 | 2019-07-01 07:00 | NA |  |  | NA |  | IC Request
TENACITY SOLAR | 1263 | 2016-05-02 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-09 08:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 101.3 | 101 | Full Capacity |  | KERN | CA | PGAE | Smyrna Substation 115 kV | 2020-12-31 08:00 | 2020-12-31 08:00 | NA |  |  | NA |  | IC Request
TIERRA DEL ORO | 1264 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-10 08:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 51.15 | 50.75 | Full Capacity |  | KERN | CA | PGAE | SemiTropic 115 KV substation | 2020-12-31 08:00 | 2020-12-31 08:00 | NA |  |  | NA |  | IC Request
TRAFALGAR 2 | 1265 | 2016-04-16 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-16 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20 | 21.1925 | Full Capacity |  | KINGS | CA | PGAE | ARCO-Tulare Lake Line | 2019-03-31 07:00 | 2019-03-31 07:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
APPLE HILL ENERGY STORAGE | 1266 | 2016-05-02 | 2016-05-02 07:00 | WITHDRAWN | 2016-06-22 07:00 | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 50.5 | 50.5 | Full Capacity |  | EL DORADO | CA | PGAE | Apple Hill Substation (PGE) 115kV | 2018-05-31 07:00 | 2018-05-31 07:00 | NA |  |  | NA |  | IC Request
BERRYESSA WIND FARM | 1267 | 2016-04-29 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-01 07:00 | C09 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 158.4 | 158.4 | Full Capacity |  | YOLO | CA | PGAE | Madison 115 kV | 2019-12-31 08:00 | 2019-12-31 08:00 | NA | Complete |  | NA |  | IC Request
CAL SUN | 1268 | 2016-05-02 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-15 07:00 | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 20 | 20.5 |  | 38.5 | Full Capacity |  | ALAMEDA | CA | PGAE | Herdlyn - Tracy 70 kV - Long: -121.577185 Lat: 37.800654 | 2019-09-01 07:00 | 2019-09-01 07:00 | NA | None |  | NA |  | IC Request
CAPETOWN HYBRID | 1269 | 2016-04-29 | 2016-05-02 07:00 | WITHDRAWN | 2020-03-30 07:00 | C09 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 135.3 | 125 | Energy Only |  | HUMBOLDT | CA | PGAE | Bridgeville 115 kV | 2019-12-31 08:00 | 2022-09-15 07:00 | NA | Complete | Complete | NA | Executed | IC Request
CREEKSIDE | 1271 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-17 07:00 | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 418 | 414 | Full Capacity |  | SANTA CLARA | CA | PGAE | Moss Landing - Metcalf 230 kV line | 2020-12-01 08:00 | 2020-12-01 08:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
IG TEHAMA SOLAR | 1273 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-02 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 252.9 | 252.15 | Full Capacity |  | TEHAMA | CA | PGAE | Cottonwood-Delevan 230 kV Line #1 | 2019-06-30 07:00 | 2019-06-30 07:00 | NA | Complete |  | NA |  | IC Request
JOAQUIN SOLAR | 1274 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2016-07-06 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 41.09 | 40.64 | Full Capacity |  | STANISLAUS | CA | PGAE | Crows Landing substation 60 kV | 2020-12-31 08:00 | 2020-12-31 08:00 | NA |  |  | NA |  | IC Request
LAS HERMANAS BESS | 1276 | 2016-05-03 | 2016-05-02 07:00 | WITHDRAWN | 2016-07-22 07:00 | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 110 | 110 | Full Capacity |  | SHASTA | CA | PGAE | Carberry Switching Station 230kV | 2019-05-31 07:00 | 2019-05-31 07:00 | NA |  |  | NA |  | IC Request
NORTHERN PINES | 1278 | 2016-05-02 | 2016-05-02 07:00 | WITHDRAWN | 2019-12-04 08:00 | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 20.6 | 27 |  | 46.018 | Full Capacity |  | LASSEN | CA | PGAE | Westwood 60kV | 2020-12-31 08:00 | 2022-12-01 08:00 | NA | Complete | Complete | NA | Terminated | IC Request
PANEM SOLAR | 1279 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2016-07-27 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20.9 | 20.226 | Full Capacity |  | BUTTE | CA | PGAE | Table Mtn.-Butte #2 115 kV Line | 2019-06-30 07:00 | 2019-06-30 07:00 | NA |  |  | NA |  | None
ROUND HOUSE ENERGY STORAGE | 1280 | 2016-05-03 | 2016-05-02 07:00 | WITHDRAWN | 2016-07-19 07:00 | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20.23 | Full Capacity |  | SAN MATEO | CA | PGAE | PG&E Martin Substation 115kV | 2020-06-01 07:00 | 2020-06-01 07:00 | NA |  |  | NA |  | IC Request
ROYAL SOLAR | 1281 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-10 08:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 102.73 | 101.908 | Full Capacity |  | STANISLAUS | CA | PGAE | Rio Oso - Woodland #1 115 kV line | 2020-12-31 08:00 | 2020-12-31 08:00 | NA |  |  | NA |  | IC Request
SPI QUINCY | 1282 | 2016-04-28 | 2016-05-02 07:00 | WITHDRAWN | 2017-02-21 08:00 | C09 | Generating Facility Type-1: Cogeneration; Generating Facility Fuel-1: Biofuel; MWs MW-1: 35.27 | 24 | Full Capacity |  | PLUMAS | CA | PGAE | SPI 60 kV Tap of PG&E's Caribou Plumas Jct. 60 kV line near Pole 17/12 | 2017-06-01 07:00 | 2017-06-01 07:00 | NA |  |  | NA |  | IC Request
WALKER RIDGE | 1284 | 2016-05-23 | 2016-05-02 07:00 | WITHDRAWN | 2022-09-22 07:00 | C09 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 144.9 | 140.9 | Partial Capacity | Off-Peak Deliverability | LAKE | CA | PGAE | Cortina-Mendocino and Cortina-Eagle Rock 115kV Lines | 2019-02-01 08:00 | 2026-12-16 08:00 | NA | Complete | Complete | NA | Executed | IC Request
BLUE WING RANCH SOLAR | 1285 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2017-04-13 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 205.2 | 203.48 | Full Capacity |  | YUMA | AZ | SDGE | Hoodoo Wash Switchyard 500 kV | 2021-12-31 08:00 | 2021-12-31 08:00 | NA |  |  | NA |  | IC Request
GIGANTES SOLAR | 1286 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-09 08:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 729.6 | 726.41 | Full Capacity |  | IMPERIAL | CA | SDGE | North Gila-Imperial Valley 500 kV line | 2020-12-31 08:00 | 2020-12-31 08:00 | NA |  |  | NA |  | IC Request
MOUNT LAGUNA WIND | 1287 | 2016-04-29 | 2016-05-02 07:00 | WITHDRAWN | 2018-05-22 07:00 | C09 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 207.9 | 207.9 | Full Capacity |  | SAN DIEGO | CA | SDGE | Suncrest - Ocotillo 500 kV line | 2019-12-31 08:00 | 2023-12-01 08:00 | NA | Complete | Complete | NA |  | IC Request
RED WING RANCH SOLAR | 1288 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-09 08:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 205.2 | 203.48 | Full Capacity |  | YUMA | AZ | SDGE | Hoodoo Wash Switchyard 500 kV | 2021-12-31 08:00 | 2021-12-31 08:00 | NA |  |  | NA |  | None
DORADO ENERGY STORAGE | 1289 | 2016-05-04 | 2016-05-02 07:00 | WITHDRAWN | 2016-07-15 07:00 | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 100 | 101 | Full Capacity |  | SAN DIEGO | CA | SDGE | Encina Substation 138kV | 2019-06-01 07:00 | 2019-06-01 07:00 | NA |  |  | NA |  | None
GATEWAY ENERGY STORAGE 2 | 1290 | 2016-04-30 | 2016-05-02 07:00 | WITHDRAWN | 2016-07-22 07:00 | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 200 | 201.2 | Full Capacity |  | SAN DIEGO | CA | SDGE | Otay Mesa substation 230 kV | 2019-08-01 07:00 | 2019-08-01 07:00 | NA |  |  | NA |  | IC Request
OTAYBAT | 1292 | 2016-05-02 | 2016-05-02 07:00 | WITHDRAWN | 2017-01-25 08:00 | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20 | Full Capacity |  | SAN DIEGO | CA | SDGE | Border Substation 69 kV | 2019-03-01 08:00 | 2019-03-01 08:00 | NA |  |  | NA |  | IC Request
SIGNAL PEAK | 1293 | 2016-04-28 | 2016-05-02 07:00 | WITHDRAWN | 2020-07-08 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 400 | 400 | Energy Only |  | YUMA | AZ | SDGE | Hoodoo Wash Switchyard 500 kV | 2021-12-01 08:00 | 2021-12-01 08:00 | NA | Complete | Complete | NA | In Progress
CENTURY SOLAR | 1296 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-09 08:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 310.08 | 306.87 | Full Capacity |  | MARICOPA | AZ | DCRT | Delaney-Colorado River Line 500kV | 2021-12-31 08:00 | 2021-12-31 08:00 | NA | Complete |  | NA |  | IC Request
QUARTZ 9 | 1297 | 2016-04-23 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-09 08:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 153.45 | 153.45 | Full Capacity |  | RIVERSIDE | CA | SCE | Colorado River 230 kV SUB | 2021-12-31 08:00 | 2021-12-31 08:00 | NA |  |  | NA |  | IC Request
HARQUAHALA SOLAR | 1298 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2016-07-19 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 519.382 | 515.126 | Full Capacity |  | MARICOPA | AZ | DCRT | Delaney-Colorado River Line 500kV | 2021-12-31 08:00 | 2021-12-31 08:00 | NA |  |  | NA |  | IC Request
WEST SPRINGS WIND FARM | 1299 | 2016-04-29 | 2016-05-02 07:00 | WITHDRAWN | 2018-03-19 07:00 | C09 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 158.4 | 150 | Full Capacity |  | RIVERSIDE | CA | SCE | El Casco 230 kV | 2019-12-31 08:00 | 2021-02-01 08:00 | NA | Complete | Complete | NA |  | IC Request
DHS OASIS SOLAR | 1300 | 2016-04-30 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-01 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 60.8 | 60 | Full Capacity |  | RIVERSIDE | CA | SCE | Devers 230 kV Substation | 2019-06-30 07:00 | 2019-12-31 08:00 | NA | Complete |  | NA |  | IC Request
SIDEWINDER SOLAR | 1301 | 2016-05-02 | 2016-05-02 07:00 | WITHDRAWN | 2017-04-17 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 120 | 118.5 | Full Capacity |  | RIVERSIDE | CA | SCE | Red Bluff 230kV | 2020-12-31 08:00 | 2020-12-31 08:00 | NA | Complete |  | NA |  | IC Request
LH ENERGY STORAGE | 1303 | 2016-04-30 | 2016-05-02 07:00 | WITHDRAWN | 2016-07-05 07:00 | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 203.7 | 201.5 | Full Capacity |  | LOS ANGELES | CA | SCE | Lighthipe substation Batteries, Inverters, Step Up Transformer and a 220 kV gen tie line | 2020-08-01 07:00 | 2020-08-01 07:00 | NA |  |  | NA |  | IC Request
YERMO SOLAR 1 | 1304 | 2016-04-15 | 2016-05-02 07:00 | WITHDRAWN | 2016-06-29 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 71.136 | 70.736 | Full Capacity |  | SAN BERNADINO | CA | SCE | Cool WaterDunn Siding Baker Mount Pass Ivanpah 115 kV Line | 2019-12-31 08:00 | 2019-12-31 08:00 | NA |  |  | NA |  | IC Request
CALCITE SOLAR 1 | 1305 | 2016-04-22 | 2016-05-02 07:00 | WITHDRAWN | 2021-02-05 08:00 | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 102.85 | 20.7 |  | 100 | Energy Only |  | SAN BERNARDINO | CA | SCE | Calcite 230 kV Line | 2020-08-01 07:00 | 2021-12-31 08:00 | NA | Complete | Complete | NA | In Progress | IC Request
GHOST TOWN SOLAR | 1306 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-09 08:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 205.4 | 203.86 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Kramer 230 KV SUB | 2020-12-31 08:00 | 2020-12-31 08:00 | NA |  |  | NA |  | IC Request
SAND SOLAR | 1307 | 2016-04-25 | 2016-05-02 07:00 | WITHDRAWN | 2018-05-15 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 309.28 | 300 | Full Capacity |  | SAN BERNARDINO | CA | SCE | KRAMER 230 KV SUB | 2020-12-31 08:00 | 2021-12-31 08:00 | NA | Complete | Complete | NA
BARSTOW SOLAR 1 | 1308 | 2016-04-28 | 2016-05-02 07:00 | WITHDRAWN | 2019-03-18 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 211 | 210.94 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Coolwater Substation 115kV | 2019-07-01 07:00 | 2021-06-30 07:00 | NA | Complete | Complete | NA |  | IC Request
SEGS10 SOLAR | 1309 | 2016-04-28 | 2016-05-02 07:00 | WITHDRAWN | 2017-02-14 08:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 81.4 | 81.2 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Kramer 230 kV | 2019-12-31 08:00 | 2019-12-31 08:00 | NA |  |  | NA |  | IC Request
COSO SOLAR 2 | 1310 | 2016-04-27 | 2016-05-02 07:00 | WITHDRAWN | 2017-02-14 08:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 206.7 | 206.5 | Full Capacity |  | INYO | CA | SCE | Kramer 230 kV | 2019-12-31 08:00 | 2019-12-31 08:00 | NA |  |  | NA |  | IC Request
COSO SOLAR 1 | 1311 | 2016-04-28 | 2016-05-02 07:00 | WITHDRAWN | 2017-02-14 08:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 78.2 | 78.2 | Full Capacity |  | INYO | CA | SCE | Kramer 230kV | 2018-12-31 08:00 | 2018-12-31 08:00 | NA |  |  | NA |  | IC Request
WALLER SOLAR FARM | 1315 | 2016-05-02 | 2016-05-02 07:00 | WITHDRAWN | 2017-02-21 08:00 | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 514.8 | 100 |  | 500 | Full Capacity |  | KERN | CA | SCE | Kramer-BLM WEST 230KV line | 2023-05-01 07:00 | 2023-05-01 07:00 | NA |  |  | NA |  | IC Request
HIGH DESERT VIEW SOLAR PROJECT | 1316 | 2016-05-12 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-02 07:00 | C09 | Storage | Photovoltaic |  | Battery | Solar |  | 30 | 136.75 |  | 161.05 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Calcite Substation 230 kV | 2019-05-31 07:00 | 2020-05-01 07:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
GRAPEVINE 1 | 1317 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2017-04-25 07:00 | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 406 | 402 | Full Capacity |  | KERN | CA | SCE | Highwind Substation 230kV | 2020-12-01 08:00 | 2020-12-01 08:00 | NA | Complete |  | NA |  | IC Request
ROSY 9 | 1318 | 2016-04-23 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-02 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 259.842 | 250 | Full Capacity |  | KERN | CA | SCE | WHIRLWIND 230 kV Sub. | 2020-12-31 08:00 | 2020-12-31 08:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
CALIFORNIA CITY SOLAR | 1320 | 2016-04-25 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-02 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 732.0957 | 700 | Full Capacity |  | KERN | CA | SCE | WINDHUB 230 KV SUB | 2020-12-31 08:00 | 2020-12-31 08:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
ALL AMERICAN SOLAR | 1321 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2018-01-11 08:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 414.96 | 400 | Full Capacity |  | KERN | CA | SCE | VESTAL 230 KV SUB | 2020-12-31 08:00 | 2020-12-31 08:00 | NA | Complete | Complete | NA |  | None
SAGEBRUSH SOLAR 1 | 1326 | 2016-04-27 | 2016-05-02 07:00 | WITHDRAWN | 2018-03-19 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 83.3 | 82 | Full Capacity |  | KERN | CA | SCE | Vincent 230 kV Sub. | 2018-12-31 08:00 | 2020-12-15 08:00 | NA | Complete | Complete | NA |  | IC Request
GOLDEN EVENING SOLAR | 1328 | 2016-04-29 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-10 08:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 265.08 | 312.22 | Full Capacity |  | KERN | CA | SCE | SCE Whirlwind Substation | 2019-07-01 07:00 | 2019-07-01 07:00 | NA | Complete |  | NA |  | IC Request
CLOVER ENERGY STORAGE PLANT | 1330 | 2016-05-02 | 2016-05-02 07:00 | WITHDRAWN | 2020-10-16 07:00 | C09 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 300 | 120 | Full Capacity |  | LOS ANGELES | CA | SCE | Antelope Substation 66kV | 2019-06-01 07:00 | 2023-05-15 07:00 | NA | Complete | Complete | NA | Executed | IC Request
CANELLA SOLAR FARM | 1331 | 2016-05-02 | 2016-05-02 07:00 | WITHDRAWN | 2018-04-16 07:00 | C09 | Storage | Photovoltaic |  | Battery | Solar |  | 300 | 309.6 |  | 300 | Full Capacity |  | KERN | CA | SCE | Windhub Substation 230kV | 2019-06-01 07:00 | 2021-10-01 07:00 | NA | Complete | Complete | NA |  | IC Request
LINWOOD SOLAR FARM | 1332 | 2016-05-02 | 2016-05-02 07:00 | WITHDRAWN | 2017-04-19 07:00 | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 205.2 | 200 |  | 205.15 | Full Capacity |  | KERN | CA | SCE | Whirlwind Substation 230kV | 2019-06-01 07:00 | 2019-06-01 07:00 | NA | Complete |  | NA |  | IC Request
EON VISION WIND | 1333 | 2016-05-02 | 2016-05-02 07:00 | WITHDRAWN | 2017-02-28 08:00 | C09 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 280.5 | 277.6 | Full Capacity |  | KERN | CA | SCE | Whirlwind 230 kV Substation | 2019-12-31 08:00 | 2019-12-31 08:00 | NA |  |  | NA |  | IC Request
MISSION ROCK | 1334 | 2016-04-22 | 2016-05-02 07:00 | WITHDRAWN | 2017-05-02 07:00 | C09 | Storage | Gas Turbine |  | Battery | Natural Gas |  | 26.125 | 300 |  | 312 | Full Capacity |  | VENTURA | CA | SCE | Santa Clara Substation 230kV | 2020-10-01 07:00 | 2020-10-01 07:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
SOUTHLAND | 1336 | 2016-04-27 | 2016-05-02 07:00 | WITHDRAWN | 2021-06-11 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 380.1 | 375 | Full Capacity | Off-Peak Deliverability | CLARK | NV | SCE | Mohave Substation 500kV | 2019-12-01 08:00 | 2023-04-26 07:00 | NA | Complete | Complete | NA | In Progress | IC Request
ARIZONA MOHAVE SOLAR | 1337 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2017-03-09 08:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 520.6 | 514.843 | Full Capacity |  | MOHAVE | AZ | SCE | MOHAVE SWITCHYARD 500kV | 2020-12-01 08:00 | 2020-12-01 08:00 | NA | Complete |  | NA |  | IC Request
COPPER MTN SOLAR 5 | 1338 | 2016-04-28 | 2016-05-02 07:00 | WITHDRAWN | 2017-04-17 07:00 | C09 | Photovoltaic | Storage |  | Solar | Battery |  | 256.8 | 20 |  | 256.8 | Full Capacity |  | CLARK | NV | SCE | SCE owned Eldorado bus 230kV | 2023-04-28 07:00 | 2023-04-28 07:00 | NA | Complete |  | NA |  | IC Request
YELLOW PINE 1 | 1340 | 2016-04-20 | 2016-05-02 07:00 | WITHDRAWN | 2016-06-29 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 152.67 | 152.67 | Full Capacity |  | CLARK | NV | VEA | VEA Sandy Valley 138 kV | 2019-12-01 08:00 | 2019-12-01 08:00 | NA |  |  | NA |  | IC Request
PAHRUMP SOLAR | 1342 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2016-07-19 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 87.45 | 86.45 | Full Capacity |  | NYE | NV | VEA | Vista Substation 138 kV bus. | 2020-12-31 08:00 | 2020-12-31 08:00 | NA |  |  | NA |  | IC Request
DESERT OBSIDIAN | 1343 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2016-07-19 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 67.17 | 66.02 | Full Capacity |  | CLARK | NV | VEA | Amargosa Sub 138 kV | 2020-12-31 08:00 | 2020-12-31 08:00 | NA |  |  | NA |  | IC Request
COPPER RAYS | 1344 | 2016-04-26 | 2016-05-02 07:00 | WITHDRAWN | 2017-04-21 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 722.396 | 714.042 | Full Capacity |  | NYE | NV | VEA | Gamebird Substation 230kV | 2021-12-31 08:00 | 2021-12-31 08:00 | NA |  |  | NA |  | IC Request
SOUTH RIDGE | 1345 | 2016-04-28 | 2016-05-02 07:00 | WITHDRAWN | 2017-04-21 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 205.43 | 203.307 | Full Capacity |  | NYE | NV | VEA | Innovation Substation 230kV | 2021-12-31 08:00 | 2021-12-31 08:00 | NA |  |  | NA |  | IC Request
RE PRISM | 1346 | 2016-05-02 | 2016-05-02 07:00 | WITHDRAWN | 2016-07-25 07:00 | C09 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 208.96 | 204.96 | Full Capacity |  | NYE | NV | VEA | Gamebird Substation 230kV | 2019-12-31 08:00 | 2019-12-31 08:00 | NA |  |  | NA |  | IC Request
BIG BREAK ENERGY STORAGE | 1351 | 2017-04-28 | 2017-05-01 07:00 | WITHDRAWN | 2018-02-08 08:00 | C10 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 45 | 39.673 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Contra Costa switchyard 230kV | 2021-06-01 07:00 | 2021-06-01 07:00 | NA | Complete |  | NA |  | IC Request
CAL SUN SOLAR | 1352 | 2017-04-28 | 2017-05-01 07:00 | WITHDRAWN | 2017-07-19 07:00 | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 20 | 20.5 |  | 37.7 | Full Capacity |  | ALAMEDA | CA | PGAE | Herdlyn-Tracy line 70 kV | 2019-09-01 07:00 | 2019-09-01 07:00 | NA |  |  | NA |  | IC Request
CHANSON ENERGY STORAGE FACILITY | 1353 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2018-03-14 07:00 | C10 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 100 | 100 | Full Capacity |  | CALAVERAS | CA | PGAE | Valley Springs Substation 60kV | 2020-10-01 07:00 | 2020-10-01 07:00 | NA | Complete |  | NA |  | IC Request
EAST-BAY-WIND | 1354 | 2017-04-25 | 2017-05-01 07:00 | WITHDRAWN | 2021-05-20 07:00 | C10 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 153.02 | 150 | Energy Only | Off-Peak Deliverability | ALAMEDA | CA | PGAE | Tesla Substation 230kV | 2020-12-01 08:00 | 2023-02-14 08:00 | NA | Complete | Complete | NA | In Progress | IC Request
EXCHEQUER | 1355 | 2017-04-27 | 2017-05-01 07:00 | WITHDRAWN | 2017-05-22 07:00 | C10 | Generating Facility Type-1: Hydro; Generating Facility Fuel-1: Water; MWs MW-1: 112 | 110 | Full Capacity |  | MARIPOSA | CA | PGAE | Exchequer-LeGrand 115 kV | 2019-05-03 07:00 | 2019-05-03 07:00 | NA |  |  | NA |  | IC Request
HAYDON ENERGY STORAGE FACILITY | 1356 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2017-06-22 07:00 | C10 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 60 | 60 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Kyoho Tap 115kV | 2020-10-01 07:00 | 2020-10-01 07:00 | NA |  |  | NA |  | IC Request
KING FLAT WIND FARM 1 | 1357 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2018-03-12 07:00 | C10 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 152.25 | 150 | Full Capacity |  | YOLO | CA | PGAE | Delevan-Vaca No. 2 & No. 3 230kV | 2020-06-01 07:00 | 2020-06-01 07:00 | NA | Complete |  | NA |  | IC Request
KING FLAT WIND FARM 2 | 1358 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2018-03-12 07:00 | C10 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 101.5 | 100 | Full Capacity |  | YOLO | CA | PGAE | Delevan-Vaca No. 2& No. 3 230kV | 2020-06-01 07:00 | 2020-06-01 07:00 | NA | Complete |  | NA |  | IC Request
LUNA MAR | 1359 | 2017-04-27 | 2017-05-01 07:00 | WITHDRAWN | 2018-04-20 07:00 | C10 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 22.99 | 20 | Full Capacity |  | SAN MATEO | CA | PGAE | Half Moon Bay Substation 60kV | 2021-12-31 08:00 | 2021-12-31 08:00 | NA | Complete |  | NA |  | IC Request
OAKLAND ENERGY RELIABILITY CENTER | 1360 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2017-06-23 07:00 | C10 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 101.55 | 100 | Full Capacity |  | ALAMEDA | CA | PGAE | Oakland C Substation 115kV | 2019-12-15 08:00 | 2019-12-15 08:00 | NA | Complete |  | NA |  | IC Request
RIOSA CENTRAL SOLAR | 1361 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2018-03-01 08:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 20.23 | 19.74 | Full Capacity |  | PLACER | CA | PGAE | Smartville-Camp Far West 60kV line | 2020-11-30 08:00 | 2020-11-30 08:00 | NA | Complete |  | NA |  | IC Request
SAGE SOLAR | 1362 | 2017-04-28 | 2017-05-01 07:00 | WITHDRAWN | 2017-07-14 07:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 103.01 | 100 | Full Capacity |  | ALAMEDA | CA | PGAE | Cayetano Substation 230kV | 2020-06-01 07:00 | 2020-06-01 07:00 | NA | Complete |  | NA |  | IC Request
SOURGRASS SOLAR | 1364 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2018-03-01 08:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 380 | 350 | Full Capacity |  | TEHAMA | CA | PGAE | Cottonwood-Delevan #1 230kV | 2020-12-31 08:00 | 2020-12-31 08:00 | NA | Complete |  | NA |  | IC Request
WALTON ENERGY RELIABILITY CENTER | 1365 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2017-06-13 07:00 | C10 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 52.8 | 50 | Full Capacity |  | YUBA | CA | PGAE | Yuba City Cogen tap line-Pease 60kV | 2019-12-15 08:00 | 2019-12-15 08:00 | NA | Complete |  | NA |  | IC Request
WARDENCLYFFE | 1366 | 2017-04-27 | 2017-05-01 07:00 | WITHDRAWN | 2018-04-20 07:00 | C10 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 313.5 | 300 | Full Capacity |  | ALAMEDA | CA | PGAE | Tesla Substation 230kV | 2022-12-31 08:00 | 2022-12-31 08:00 | NA | Complete |  | NA |  | IC Request
WILBUR ENERGY STORAGE | 1368 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2020-03-25 07:00 | C10 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 94.5 | 91.3 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Contra Costa Switchyard 230kV | 2020-10-31 07:00 | 2023-11-13 08:00 | NA | Complete | Complete | NA |  | IC Request
AMERICAN KINGS 10 | 1369 | 2017-04-26 | 2017-05-01 07:00 | WITHDRAWN | 2017-07-14 07:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 155.68 | 150 | Full Capacity |  | FRESNO | CA | PGAE | Mustang Switching Station 230kV | 2021-09-01 07:00 | 2021-09-01 07:00 | NA | Complete |  | NA |  | IC Request
BRUIN SOLAR | 1370 | 2017-04-26 | 2017-05-01 07:00 | WITHDRAWN | 2018-03-01 08:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 51.25 | 50 | Full Capacity |  | FRESNO | CA | PGAE | Mendota Substation 115kV | 2020-05-01 07:00 | 2020-05-01 07:00 | NA | Complete |  | NA |  | IC Request
CALIFORNIA BEAR 6 | 1371 | 2017-04-26 | 2017-05-01 07:00 | WITHDRAWN | 2018-03-01 08:00 | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 22.41 | 22.355 |  | 20 | Full Capacity |  | FRESNO | CA | PGAE | Mendota Substation 115kV | 2021-12-01 08:00 | 2021-12-01 08:00 | NA | Complete |  | NA |  | IC Request
CURRY SOLAR | 1372 | 2017-04-28 | 2017-05-01 07:00 | WITHDRAWN | 2018-03-08 08:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 71.45 | 70 | Full Capacity |  | FRESNO | CA | PGAE | Schindler Substation 70kV | 2020-11-01 07:00 | 2020-11-01 07:00 | NA | Complete |  | NA |  | None
DASOS 10 | 1373 | 2017-04-26 | 2017-05-01 07:00 | WITHDRAWN | 2017-07-14 07:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 209.46 | 200 | Full Capacity |  | MERCED | CA | PGAE | Wilson Substation 230kV | 2020-06-01 07:00 | 2020-06-01 07:00 | NA | Complete |  | NA |  | IC Request
FIREHAWK SOLAR 1 | 1375 | 2017-04-11 | 2017-05-01 07:00 | WITHDRAWN | 2017-06-19 07:00 | C10 | Storage | Photovoltaic |  | Battery | Solar |  | 75 | 75 |  | 75 | Full Capacity |  | KERN | CA | PGAE | Smyrna Substation 115kV | 2020-12-31 08:00 | 2020-12-31 08:00 | NA |  |  | NA |  | IC Request
GOLDEN SQUARE | 1376 | 2017-04-27 | 2017-05-01 07:00 | WITHDRAWN | 2018-04-20 07:00 | C10 | Storage | Photovoltaic |  | Battery | Solar |  | 204.82 | 205.39 |  | 400 | Full Capacity |  | FRESNO | CA | PGAE | Tranquility Switching Station 230 kV | 2021-09-01 07:00 | 2021-09-01 07:00 | NA | Complete |  | NA |  | IC Request
GOLDWICK SOLAR FARM | 1377 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2018-03-14 07:00 | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 100 | 100 |  | 101.44 | Full Capacity |  | STANISLAUS | CA | PGAE | Salado Substation 115kV | 2020-10-01 07:00 | 2020-10-01 07:00 | NA | Complete |  | NA |  | IC Request
KROE HYBRID | 1381 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2018-04-18 07:00 | C10 | Storage | Photovoltaic |  | Battery | Solar |  | 40 | 60 |  | 40.2 | Full Capacity |  | MERCED / FRESNO | CA | PGAE | Mercy Springs Substation 70kV | 2019-11-30 08:00 | 2019-11-30 08:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
LAS CAMAS 2 | 1383 | 2017-04-29 | 2017-05-01 07:00 | WITHDRAWN | 2018-04-18 07:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 102.5 | 101.423 | Full Capacity |  | MERCED | CA | PGAE | Los Banos Substation 230kV | 2021-11-30 08:00 | 2021-11-30 08:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
LOTUS 2 SOLAR FARM | 1384 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2018-03-14 07:00 | C10 | Storage | Photovoltaic |  | Battery | Solar |  | 100 | 100 |  | 102 | Full Capacity |  | MADERA | CA | PGAE | Borden Substation 70kV | 2020-03-01 08:00 | 2020-03-01 08:00 | NA | Complete |  | NA |  | IC Request
VANGUARD SOLAR BESS | 1385 | 2017-04-29 | 2017-05-01 07:00 | WITHDRAWN | 2019-12-19 08:00 | C10 | Storage | Photovoltaic |  | Battery | Solar |  | 47 | 153.315 |  | 150 | Full Capacity |  | FRESNO | CA | PGAE | Mustang Switching Station 230 kV | 2020-07-01 07:00 | 2025-03-31 07:00 | NA | Complete | Complete | NA |  | IC Request
MALLARD ENERGY STORAGE PROJECT | 1386 | 2017-04-28 | 2017-05-01 07:00 | WITHDRAWN | 2017-06-21 07:00 | C10 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 90 | 81.11 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Pittsburg Switchyard 230kV | 2021-06-01 07:00 | 2021-06-01 07:00 | NA |  |  | NA |  | IC Request
PERSEUS SOLAR | 1387 | 2017-04-26 | 2017-05-01 07:00 | WITHDRAWN | 2017-07-14 07:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 208.97 | 206.37 | Full Capacity |  | MERCED | CA | PGAE | Borden Substation 230kV | 2021-08-01 07:00 | 2021-08-01 07:00 | NA | Complete |  | NA |  | IC Request
PUERTA RENEWABLE ENERGY RELIABILITY CENTER | 1388 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2017-07-05 07:00 | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 52 | 52.8 |  | 76.56 | Full Capacity |  | FRESNO | CA | PGAE | Gates-Coalinga #2 70kV | 2019-06-01 07:00 | 2019-06-01 07:00 | NA | Complete |  | NA |  | IC Request
ROMERO CREEK SOLAR | 1390 | 2017-04-28 | 2017-05-01 07:00 | WITHDRAWN | 2018-04-30 07:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 203.96 | 200 | Full Capacity |  | MERCED | CA | PGAE | Quinto Substation 230kV | 2022-12-31 08:00 | 2022-12-31 08:00 | NA | Complete |  | NA
WARRIORS SOLAR | 1392 | 2017-04-28 | 2017-05-01 07:00 | WITHDRAWN | 2020-05-15 07:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 40.69 | 40 | Full Capacity |  | FRESNO | CA | PGAE | Crescent Switching Station 70kV | 2021-11-01 07:00 | 2021-11-01 07:00 | NA | Complete | Complete | NA |  | IC Request
CASSIOPEIA SOLAR | 1393 | 2017-04-26 | 2017-05-01 07:00 | WITHDRAWN | 2017-07-14 07:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 77.04 | 76.12 | Full Capacity |  | KERN | CA | PGAE | Tap on Maricopa-Copus line 70kV | 2021-08-01 07:00 | 2021-08-01 07:00 | NA | Complete |  | NA |  | IC Request
KERRNESS SOLAR | 1395 | 2017-04-28 | 2017-05-01 07:00 | WITHDRAWN | 2018-02-14 08:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 102.39 | 102.29 | Full Capacity |  | MERCED | CA | PGAE | Wilson - Le Grand115kV | 2021-11-01 07:00 | 2021-11-01 07:00 | NA | Complete |  | NA |  | IC Request
LYNX SOLAR | 1396 | 2017-04-28 | 2017-05-01 07:00 | WITHDRAWN | 2017-07-14 07:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 30.91 | 30.42 | Full Capacity |  | SANTA BARBARA | CA | PGAE | Cuyama 2 Substation 70kV | 2021-08-01 07:00 | 2021-08-01 07:00 | NA | Complete |  | NA |  | IC Request
SUN BRILLIANCE | 1399 | 2017-04-30 | 2017-05-01 07:00 | WITHDRAWN | 2017-07-03 07:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 16.35 | 16.345 | Full Capacity |  | KERN | CA | PGAE | Blackwell Substation 70kV | 2019-12-16 08:00 | 2019-12-16 08:00 | NA |  |  | NA |  | IC Request
HIDDEN HILLS SOLAR 1 | 1400 | 2017-04-25 | 2017-05-01 07:00 | WITHDRAWN | 2018-04-16 07:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 305.5 | 266.5 | Full Capacity |  | INYO | CA | GLW | Crazy Eyes Switching Station 230kV | 2021-12-31 08:00 | 2021-12-31 08:00 | NA | Complete |  | NA
WARREN SOLAR 1 | 1401 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2018-05-04 07:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 71.487 | 69.26 | Full Capacity |  | NYE | NV | VEA | Charleston Substation 138kV | 2020-03-01 08:00 | 2020-03-01 08:00 | NA | Complete |  | NA |  | IC Request
HARQUAHALA FLATS | 1403 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2020-06-03 07:00 | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 450 | 450 |  | 450 | Energy Only |  | MARICOPA | AZ | DCRT | Colorado River-Delaney 500kV | 2022-12-16 08:00 | 2022-12-16 08:00 | NA | Complete | Complete | NA
HARQUAHALA SUN | 1404 | 2017-04-28 | 2017-05-01 07:00 | WITHDRAWN | 2018-04-16 07:00 | C10 | Storage | Photovoltaic |  | Battery | Solar |  | 162.5 | 150 |  | 150 | Full Capacity |  | MARICOPA | AZ | DCRT | Delaney-Colorado River 500kV | 2020-06-01 07:00 | 2020-06-01 07:00 | NA | Complete |  | NA |  | IC Request
MESAVILLE SOLAR | 1406 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2020-05-11 07:00 | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 476.33 | 229.9 |  | 675 | Energy Only |  | RIVERSIDE | CA | SCE | Colorado River Substation 230kV | 2021-09-01 07:00 | 2022-01-15 08:00 | NA | Complete | Complete | NA | In Progress | IC Request
QUARTZITE 10 | 1408 | 2017-04-28 | 2017-05-01 07:00 | WITHDRAWN | 2017-07-14 07:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 154.59 | 150 | Full Capacity |  | RIVERSIDE | CA | SCE | Colorado River Substation 230kV | 2023-12-01 08:00 | 2023-12-01 08:00 | NA |  |  | NA |  | IC Request
VERMILLION ENERGY STORAGE | 1409 | 2017-04-28 | 2017-05-01 07:00 | WITHDRAWN | 2018-03-09 08:00 | C10 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 203.7 | 200 | Full Capacity |  | RIVERSIDE | CA | SCE | Devers Substation 220kV | 2021-06-01 07:00 | 2023-06-01 07:00 | NA | Complete |  | NA |  | None
WEST SPRINGS 2 WIND FARM | 1410 | 2017-04-28 | 2017-05-01 07:00 | WITHDRAWN | 2019-10-31 07:00 | C10 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 155.25 | 150 | Full Capacity |  | RIVERSIDE | CA | SCE | Devers-Vista #1 230kV | 2020-06-01 07:00 | 2023-10-15 07:00 | NA | Complete | Complete | NA |  | IC Request
GABRIEL SOLAR 3 | 1411 | 2017-03-15 | 2017-05-01 07:00 | WITHDRAWN | 2018-04-26 07:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 100 | 100 | Full Capacity |  | SAN BERNADINO | CA | SCE | Mira Loma-Walnut 230kV | 2019-12-31 08:00 | 2019-12-31 08:00 | NA |  |  | NA |  | Failure to Cure Deficiency
VICKERS ENERGY STORAGE | 1412 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2019-12-04 08:00 | C10 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 80 | 80 | Full Capacity |  | LOS ANGELES | CA | SCE | La Cienega Substation 230kV | 2021-05-28 07:00 | 2021-11-16 08:00 | NA | Complete | Complete | NA | Terminated
RUBITA | 1415 | 2017-04-28 | 2017-05-01 07:00 | WITHDRAWN | 2020-05-15 07:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 102.18 | 100 | Energy Only |  | SAN BERNARDINO | CA | SCE | Kramer-Inyokern-Randsburg No.1 115kV | 2021-11-01 07:00 | 2023-10-15 07:00 | NA | Complete | Complete | NA |  | IC Request
BLUE MOUNTAIN WIND | 1416 | 2017-04-25 | 2017-05-01 07:00 | WITHDRAWN | 2018-04-20 07:00 | C10 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 108 | 100 | Full Capacity |  | LOS ANGELES | CA | SCE | Antelope Substation 230kV | 2020-12-01 08:00 | 2020-12-01 08:00 | NA | Complete |  | NA |  | IC Request
CALHAWK SOLAR FARM | 1417 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2018-04-16 07:00 | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 100 | 100 |  | 99 | Full Capacity |  | TULARE | CA | SCE | Vestal Substation 230kV | 2020-10-01 07:00 | 2022-06-01 07:00 | NA | Complete |  | NA
CREOSOTE | 1418 | 2017-04-26 | 2017-05-01 07:00 | WITHDRAWN | 2018-02-22 08:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 418.95 | 400 | Full Capacity |  | KERN | CA | SCE | Windhub Substation 230kV | 2021-08-01 07:00 | 2021-08-01 07:00 | NA | Complete |  | NA |  | None
CANELLA 2 SOLAR FARM | 1420 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2018-04-16 07:00 | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 200 | 200 |  | 200 | Full Capacity |  | KERN | CA | SCE | Windhub Substation 230kV | 2020-10-01 07:00 | 2020-10-01 07:00 | NA | Complete |  | NA
JAWBONE WIND ENERGY PROJECT | 1421 | 2017-04-28 | 2017-05-01 07:00 | WITHDRAWN | 2019-07-08 07:00 | C10 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 37.4 | 37.4 | Full Capacity |  | KERN | CA | SCE | Highwind Substation 230kV | 2019-06-01 07:00 | 2021-12-15 08:00 | NA | Complete | Complete | NA
LONGSPUR 10 | 1422 | 2017-04-28 | 2017-05-01 07:00 | WITHDRAWN | 2017-07-14 07:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 263.84 | 250 | Full Capacity |  | KERN | CA | SCE | Rattlesnake Switchyard 230kV | 2021-12-31 08:00 | 2021-12-31 08:00 | NA |  |  | NA |  | IC Request
MUNZ SOLAR 1 | 1423 | 2017-04-04 | 2017-05-01 07:00 | WITHDRAWN | 2018-02-28 08:00 | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 90 | 90 |  | 90 | Full Capacity |  | LOS ANGELES | CA | SCE | Antelope Substation 66kV | 2020-12-31 08:00 | 2020-12-31 08:00 | NA |  |  | NA |  | IC Request
VENTURA ENERGY CENTER | 1425 | 2017-04-28 | 2017-05-01 07:00 | WITHDRAWN | 2018-03-12 07:00 | C10 | Storage | Gas Turbine |  | Battery | Natural Gas |  | 26.125 | 300 |  | 312 | Full Capacity |  | VENTURA | CA | SCE | Santa Clara Substation 230kV | 2020-10-01 07:00 | 2020-10-01 07:00 | NA | Complete |  | NA |  | IC Request
VISION WIND | 1426 | 2017-04-29 | 2017-05-01 07:00 | WITHDRAWN | 2019-10-31 07:00 | C10 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 280.5 | 275 | Full Capacity |  | KERN | CA | SCE | Whirlwind Substation 220kV | 2020-12-31 08:00 | 2023-04-15 07:00 | NA | Complete | Complete | NA |  | IC Request
DARLINGTON BALLEY SOLAR ENERGY 1 | 1427 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2020-03-19 07:00 | C10 | Photovoltaic | Storage |  | Solar | Battery |  | 125 | 60 |  | 125 | Full Capacity |  | MARICOPA | AZ | SDGE | Hassayampa Switchyard 500kV | 2024-04-30 07:00 | 2024-04-30 07:00 | NA | Complete | Complete | NA |  | IC Request
MAVERICK | 1428 | 2017-04-27 | 2017-05-01 07:00 | WITHDRAWN | 2021-03-25 07:00 | C10 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 10 | 10 | Full Capacity |  | SAN DIEGO | CA | SDGE | Miramar GT Switchyard 69kV | 2021-12-31 08:00 | 2021-12-31 08:00 | NA | Complete | Complete | NA |  | IC Request
OCEANSIDE ENERGY STORAGE | 1430 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2018-03-02 08:00 | C10 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 40 | 40 | Full Capacity |  | SAN DIEGO | CA | SDGE | Ocean Ranch Substation | 2021-05-28 07:00 | 2021-05-28 07:00 | NA | Complete |  | NA |  | IC Request
ROSEBUD | 1431 | 2017-04-27 | 2017-05-01 07:00 | WITHDRAWN | 2021-03-25 07:00 | C10 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 10 | 10 | Full Capacity |  | SAN DIEGO | CA | SDGE | Kearny West Substation 69kV | 2021-12-31 08:00 | 2021-12-31 08:00 | NA | Complete | Complete | NA |  | IC Request
SUN STREAMS SOLAR 3 | 1433 | 2017-04-27 | 2017-05-01 07:00 | WITHDRAWN | 2017-06-28 07:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 155.1 | 150 | Full Capacity |  | MARICOPA | AZ | SDGE | Hassayampa Substation 500 kV | 2020-06-01 07:00 | 2020-06-01 07:00 | NA |  |  | NA |  | IC Request
WISTARIA SOLAR 2 | 1436 | 2017-04-28 | 2017-05-01 07:00 | WITHDRAWN | 2017-06-05 07:00 | C10 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 156 | 150 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley Substation 230kV | 2019-12-31 08:00 | 2019-12-31 08:00 | NA |  |  | NA |  | IC Request
WESTSIDE CANAL ENERGY CENTER | 1437 | 2017-05-01 | 2017-05-01 07:00 | WITHDRAWN | 2020-06-10 07:00 | C10 | Storage | Photovoltaic |  | Battery | Solar |  | 400 | 25 |  | 425 | Energy Only |  | IMPERIAL | CA | SDGE | Imperial Valley Substation 230kV | 2021-12-31 08:00 | 2021-12-31 08:00 | NA | Complete | Complete | NA |  | IC Request
PANOCHE ENERGY CENTER | 1438 | 2017-04-28 | 2017-12-15 08:00 | WITHDRAWN | 2018-04-12 07:00 | ISP | Generating Facility Type-1: Gas Turbine; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 432 | 15.6 | Full Capacity |  | FRESNO | CA | PGAE | Panoche Substation | 2018-02-01 08:00 | 2018-02-01 08:00 | NA |  |  | NA |  | IC Request
KERNRIDGE EXPANSION | 1441 | 2018-02-20 | 2018-05-17 07:00 | WITHDRAWN | 2020-09-17 07:00 | ISP | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 17.9 | 0 | Energy Only |  | KERN | CA | PGAE | Kern Ridge Substation 115kV | 2021-01-15 08:00 | 2020-12-15 08:00 | NA | Complete | Complete | NA |  | IC Request
BLACK DIAMOND ENERGY STORAGE 2 | 1445 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-02-27 08:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 200 | 200 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Pittsburg 230kV | 2021-05-01 07:00 | 2021-05-01 07:00 | NA |  |  | NA
BODIE ENERGY STORAGE | 1446 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-02-15 08:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 50.7 | 50 | Full Capacity |  | SUTTER | CA | PGAE | Bogue - Rio Oso 115 kV Line | 2021-07-09 07:00 | 2021-07-09 07:00 | NA |  |  | NA
DERNOPI SOLAR | 1447 | 2018-04-13 | 2018-04-16 07:00 | WITHDRAWN | 2019-02-22 08:00 | C11 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 103.3 | 100 | Full Capacity |  | FRESNO | CA | PGAE | Schindler 115kV | 2021-11-30 08:00 | 2021-11-30 08:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
DESCENDANT RANCH 2 | 1448 | 2018-04-11 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-08 08:00 | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 510 | 513.5 |  | 500 | Full Capacity |  | COLUSA | CA | PGAE | Logan Creek - Delevan Line Tap 230kV | 2023-12-01 08:00 | 2023-12-01 08:00 | NA |  |  | NA |  | IC Request
FALCON ENERGY CENTER | 1449 | 2018-04-13 | 2018-04-16 07:00 | WITHDRAWN | 2019-04-22 07:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 151.2 | 148.84 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Kasson-Lammers 115kV | 2021-09-01 07:00 | 2021-09-01 07:00 | NA | Complete |  | NA |  | IC Request
GAUCHO STORAGE | 1450 | 2018-04-13 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-11 07:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 32.4 | 30.8 | Full Capacity |  | SANTA BARBARA | CA | PGAE | Cabrillo Substation 115kV | 2021-12-01 08:00 | 2021-12-01 08:00 | NA | Complete |  | NA |  | IC Request
HOLOCRYSTALLINE ENERGY CENTER | 1451 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-02-26 08:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 40 | 40 | Full Capacity |  | SAN MATEO | CA | PGAE | Bair Substation 60kV bus | 2021-12-01 08:00 | 2021-12-01 08:00 | NA | Complete |  | NA |  | IC Request
HOOD 2 | 1452 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-04-29 07:00 | C11 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 220 | 200 | Full Capacity |  | STANISLAUS | CA | PGAE | Q1244 Switching Station 230kV | 2022-12-31 08:00 | 2022-12-31 08:00 | NA | Complete |  | NA |  | IC Request
HOOD 3 | 1453 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-04-30 07:00 | C11 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 220 | 200 | Full Capacity |  | STANISLAUS | CA | PGAE | Q1244 Switching Station 230kV | 2022-12-31 08:00 | 2022-12-31 08:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
MONTARA | 1458 | 2018-04-12 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-08 08:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 65 | 65 | Full Capacity |  | ALAMEDA | CA | PGAE | Eastshore Station 115kV | 2020-07-01 07:00 | 2020-07-01 07:00 | NA |  |  | NA |  | IC Request
PINTO PASS | 1460 | 2018-04-12 | 2018-04-16 07:00 | WITHDRAWN | 2022-09-01 07:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20 | 20 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Christie Substation 60kV | 2021-12-31 08:00 | 2023-12-31 08:00 | NA | Complete | Complete | NA | Executed | IC Request
SEAPORT STORAGE | 1462 | 2018-04-12 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-08 08:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 41.8 | 40 | Full Capacity |  | ALAMEDA | CA | PGAE | Oakland Station C 115kV | 2022-12-01 08:00 | 2022-12-01 08:00 | NA |  |  | NA |  | IC Request
STAR GL STORAGE 2 | 1464 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-04-30 07:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 45.8 | 45 | Full Capacity |  | SUTTER | CA | PGAE | Greenleaf #1 Tap 115 kV | 2021-12-01 08:00 | 2021-12-01 08:00 | NA |  |  | NA |  | Failure to Cure Deficiency
STARGAZE SOLAR BESS | 1465 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-02-25 08:00 | C11 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 153.5 | 150 | Full Capacity |  | ALAMEDA | CA | PGAE | Cayetano Substation 230kV | 2021-12-01 08:00 | 2021-12-01 08:00 | NA |  |  | NA |  | IC Request
TIERRA BUENA ENERGY CENTER | 1466 | 2018-04-13 | 2018-04-16 07:00 | WITHDRAWN | 2019-04-22 07:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 74.3513 | 74.3513 | Full Capacity |  | SUTTER | CA | PGAE | Pease 60kV | 2021-09-01 07:00 | 2021-09-01 07:00 | NA | Complete |  | NA |  | IC Request
TUNITAS | 1467 | 2018-04-13 | 2018-04-16 07:00 | WITHDRAWN | 2019-02-25 08:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 50 | 50 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Kasson Station 60kV | 2020-07-01 07:00 | 2020-07-01 07:00 | NA |  |  | NA |  | IC Request
ATLAS | 1468 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2018-08-29 07:00 | C11 | Photovoltaic | Storage |  | Solar | Battery |  | 1036.8 | 1036.8 |  | 1000 | Full Capacity |  | FRESNO | CA | PGAE | Los Banos - Gates #3 500kV line | 2022-12-31 08:00 | 2022-12-31 08:00 | NA | None |  | NA |  | IC Request
BERRYDALE STORAGE | 1469 | 2018-04-12 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-08 08:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 41.8 | 40 | Full Capacity |  | ALAMEDA | CA | PGAE | Birds Landing 230kV | 2022-12-01 08:00 | 2022-12-01 08:00 | NA |  |  | NA |  | IC Request
CASY SOLAR | 1471 | 2018-04-13 | 2018-04-16 07:00 | WITHDRAWN | 2019-05-07 07:00 | C11 | Photovoltaic | Storage |  | Solar | Battery |  | 203.5 | 104 |  | 200 | Energy Only |  | FRESNO | CA | PGAE | Tranquility 230kV | 2022-06-15 07:00 | 2022-06-15 07:00 | NA | Complete |  | NA
DEL RANCHO | 1473 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-01-16 08:00 | C11 | Photovoltaic | Storage |  | Solar | Battery |  | 102.6 | 102.6 |  | 100 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Kelso Switching Station 230kV | 2021-12-31 08:00 | 2021-12-31 08:00 | NA | Complete |  | NA |  | IC Request
GEMINI WIND NORTH | 1474 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-04-22 07:00 | C11 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 2005.8 | 2005.8 | Full Capacity |  | N/A | CA | PGAE | Diablo Canyon Power Plant 500kV | 2025-03-31 07:00 | 2025-03-31 07:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
GONZAGA RIDGE WIND FARM 2 | 1475 | 2018-04-17 | 2018-04-16 07:00 | WITHDRAWN | 2019-04-10 07:00 | C11 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 61.28 | 58.63 | Full Capacity |  | MERCED | CA | PGAE | Los Banos Substation 70kV | 2020-12-21 08:00 | 2020-12-21 08:00 | NA | Complete |  | NA |  | IC Request
GREEN MEZZO | 1476 | 2018-04-12 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-08 08:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 204.1 | 200 | Full Capacity |  | SOLANO | CA | PGAE | Birds Landing Switchyard 230kV | 2022-12-01 08:00 | 2022-12-01 08:00 | NA |  |  | NA |  | IC Request
HEARTLAND 3 | 1477 | 2018-04-11 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-07 08:00 | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 51.169 | 154.89 |  | 150 | Full Capacity |  | FRESNO | CA | PGAE | Tranquility Switching Station 230kV | 2022-12-30 08:00 | 2022-12-30 08:00 | NA | Complete |  | NA |  | IC Request
HUDSON SOLAR 2 | 1478 | 2018-04-12 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-07 08:00 | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 102 | 102 |  | 80 | Energy Only |  | FRESNO | CA | PGAE | Panoche Substation 115kV | 2022-06-30 07:00 | 2022-06-30 07:00 | NA | Complete |  | NA |  | IC Request
KEY STORAGE 2 | 1480 | 2018-04-11 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-08 08:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 309.3 | 300 | Full Capacity |  | FRESNO | CA | PGAE | Gates Sub 230kV | 2024-12-01 08:00 | 2024-12-01 08:00 | NA |  |  | NA |  | IC Request
KINGSTON ENERGY STORAGE | 1481 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-04-30 07:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 50.74 | 50 | Full Capacity |  | MADERA | CA | PGAE | Borden Substation 70kV | 2021-07-09 07:00 | 2021-07-09 07:00 | NA |  |  | NA |  | Failure to Cure Deficiency
MERCATOR | 1482 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-02-04 08:00 | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 518.4 | 518.4 |  | 500 | Full Capacity |  | FRESNO | CA | PGAE | Tranquillity SS 230kV | 2021-12-31 08:00 | 2021-12-31 08:00 | NA | None |  | NA
PANIOLO SOLAR | 1483 | 2018-04-13 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-11 07:00 | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 19.8 | 52.2 |  | 50.3 | Full Capacity |  | FRESNO | CA | PGAE | Jayne Switching Station 70kV | 2021-12-01 08:00 | 2021-12-01 08:00 | NA |  |  | NA |  | IC Request
PLACID | 1485 | 2018-04-10 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-06 08:00 | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 90 | 180 |  | 200 | Full Capacity |  | FRESNO | CA | PGAE | Mendota Substation 115kV | 2021-05-01 07:00 | 2021-05-01 07:00 | NA | Complete |  | NA |  | IC Request
ROCKFISH STORAGE 1 | 1486 | 2018-04-11 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-08 08:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 510 | 500 | Full Capacity |  | MONTEREY | CA | PGAE | Moss Landing 230kV | 2023-12-01 08:00 | 2023-12-01 08:00 | NA |  |  | NA |  | IC Request
ROCKFISH STORAGE 2 | 1487 | 2018-04-11 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-08 08:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 510 | 500 | Full Capacity |  | MONTEREY | CA | PGAE | Moss Landing 230kV | 2024-12-01 08:00 | 2024-12-01 08:00 | NA |  |  | NA |  | IC Request
SAGEBERRY SOLAR | 1488 | 2018-04-11 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-06 08:00 | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 92.08 | 311.885 |  | 300 | Full Capacity |  | FRESNO | CA | PGAE | Gates Substation 230kV | 2022-12-30 08:00 | 2022-12-30 08:00 | NA | Complete |  | NA |  | IC Request
STEPHEN | 1489 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-13 07:00 | C11 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 102.73 | 100 | Full Capacity |  | FRESNO | CA | PGAE | Schindler Substation 115kV | 2022-06-01 07:00 | 2022-06-01 07:00 | NA |  |  | NA |  | IC Request
TEMETTATE ADVANCED CAES | 1490 | 2018-04-13 | 2018-04-16 07:00 | WITHDRAWN | 2019-02-28 08:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Other; MWs MW-1: 100 | 100 | Full Capacity |  | SAN LUIS OBISPO | CA | PGAE | Mesa 230kV | 2024-06-01 07:00 | 2024-06-01 07:00 | NA | Complete |  | NA |  | IC Request
TEPONA OFF-SHORE WIND | 1491 | 2018-04-14 | 2018-04-16 07:00 | WITHDRAWN | 2025-08-25 07:00 | C11 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 161.925 | 156 | Energy Only | Off-Peak Energy Only | HUMBOLDT | CA | PGAE | Humboldt 115 kV | 2024-10-01 07:00 | 2034-10-01 07:00 | NA | Complete | Complete | NA |  | IC Request
WINDCHARGER ESS | 1492 | 2018-04-12 | 2018-04-16 07:00 | WITHDRAWN | 2021-04-09 07:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 150 | 150 | Full Capacity |  | SOLANO | CA | PGAE | Birds Landing Substation 230kV | 2021-12-01 08:00 | 2021-12-01 08:00 | NA | Complete | Complete | NA |  | IC Request
CASTLE WIND OFFSHORE | 1494 | 2018-05-30 | 2018-04-16 07:00 | WITHDRAWN | 2019-04-08 07:00 | C11 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 576 | 559.3 | Full Capacity |  | SAN LUIS OBISPO | CA | PGAE | Morro Bay Substation 230kV | 2025-03-30 07:00 | 2025-03-30 07:00 | NA | Complete |  | NA |  | IC Request
HOLLY | 1497 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-13 07:00 | C11 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 40.825 | 40 | Full Capacity |  | KINGS | CA | PGAE | Corcoran-Guernsey 70kV line | 2021-11-01 07:00 | 2021-11-01 07:00 | NA |  |  | NA |  | IC Request
HOOD 1 | 1498 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-07 08:00 | C11 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 110 | 100 | Full Capacity |  | TULARE | CA | PGAE | Olive Switching Substation 115kV | 2022-12-31 08:00 | 2022-12-31 08:00 | NA | Complete |  | NA |  | IC Request
LIMON ENERGY PARK | 1500 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-06 08:00 | C11 | Photovoltaic | Storage |  | Solar | Battery |  | 128.35 | 25 |  | 125 | Full Capacity |  | KERN | CA | PGAE | Midway Substation 230kV | 2020-12-01 08:00 | 2020-12-01 08:00 | NA | Complete |  | NA |  | IC Request
MAMMOTH ENERGY STORAGE | 1501 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-04-25 07:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 101.4 | 100 | Full Capacity |  | KERN | CA | PGAE | Midway Substation 115kV | 2021-07-09 07:00 | 2021-07-09 07:00 | NA |  |  | NA |  | IC Request
MAVERICKS | 1502 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-02-25 08:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 300 | 300 | Full Capacity |  | ALAMEDA | CA | PGAE | Newark Station 230kV | 2021-07-01 07:00 | 2021-07-01 07:00 | NA |  |  | NA |  | IC Request
PINTAIL ENERGY STORAGE | 1503 | 2018-04-13 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-05 08:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 100 | 100 | Full Capacity |  | SONOMA | CA | PGAE | Lakeville 230kV | 2021-06-30 07:00 | 2021-06-30 07:00 | NA |  |  | NA |  | IC Request
PISTACHIO ENERGY PARK | 1504 | 2018-04-17 | 2015-04-16 07:00 | WITHDRAWN | 2019-03-06 08:00 | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 37 | 153.5 |  | 150 | Full Capacity |  | KERN | CA | PGAE | Arco-Midway & Gates-Midway 230kV | 2020-12-01 08:00 | 2020-12-01 08:00 | NA | Complete |  | NA |  | IC Request
POLELINE SOLAR ENERGY CENTER | 1505 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-04-30 07:00 | C11 | Photovoltaic | Storage |  | Solar | Battery |  | 61.005 | 41.4 |  | 99.995 | Full Capacity |  | MERCED/FRESNO | CA | PGAE | Mercy Springs 70kV | 2021-12-01 08:00 | 2021-12-01 08:00 | NA |  |  | NA |  | Failure to Cure Deficiency
POSEIDON | 1506 | 2018-04-17 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-06 08:00 | C11 | Photovoltaic | Storage |  | Solar | Battery |  | 206 | 50 |  | 200 | Full Capacity |  | KERN | CA | PGAE | Bitterwater Switching Station 230kV | 2020-12-01 08:00 | 2020-12-01 08:00 | NA | Complete |  | NA |  | IC Request
CORTES | 1508 | 2018-04-14 | 2018-04-16 07:00 | WITHDRAWN | 2019-04-18 07:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 500 | 500 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Chino Substation 230kV bus | 2021-07-01 07:00 | 2021-12-22 08:00 | NA | Complete |  | NA |  | IC Request
ARROW | 1509 | 2018-04-10 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-11 07:00 | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 29.47 | 225 |  | 250 | Full Capacity |  | KERN | CA | SCE | Whirlwind Substation 230kV | 2022-01-02 08:00 | 2024-10-01 07:00 | NA |  |  | NA
CLEANPOWER SOLAR | 1511 | 2018-04-13 | 2018-04-16 07:00 | WITHDRAWN | 2019-04-30 07:00 | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 37.7 | 37.7 |  | 37.5 | Partial Capacity |  | LOS ANGELES | CA | SCE | Neenach Substation 66kV | 2020-12-15 08:00 | 2020-12-15 08:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
DRY CREEK SOLAR | 1512 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-07 08:00 | C11 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 110 | 100 | Full Capacity |  | KERN | CA | SCE | Magunden-Vestal #1 230kV line | 2022-12-31 08:00 | 2022-12-31 08:00 | NA | None |  | NA |  | IC Request
HIGHLINE SOLAR ENERGY CENTER | 1513 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-02-26 08:00 | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 40 | 80 |  | 74.9 | Full Capacity |  | KERN | CA | SCE | Highwind Substation 230kV | 2021-12-01 08:00 | 2021-12-01 08:00 | NA |  |  | NA |  | IC Request
LONGSPUR 11 | 1514 | 2018-04-11 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-12 07:00 | C11 | Photovoltaic | Storage |  | Solar | Battery |  | 182.46 | 51.093 |  | 175 | Full Capacity |  | KERN | CA | SCE | Whirlwind Substation 230kV | 2022-12-30 08:00 | 2022-12-30 08:00 | NA |  |  | NA |  | IC Request
MCGRATH ENERGY CENTER 1 | 1515 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-02-26 08:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 100 | 100 | Full Capacity |  | VENTURA | CA | SCE | Mandalay-Santa Clara 220kV | 2020-12-01 08:00 | 2020-12-01 08:00 | NA |  |  | NA |  | IC Request
SAGEBRUSH SOLAR 5 | 1517 | 2018-04-13 | 2018-04-16 07:00 | WITHDRAWN | 2019-04-30 07:00 | C11 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 223.56 | 200 | Full Capacity |  | KERN | CA | SCE | Vincent Substation 230kV | 2022-12-31 08:00 | 2022-12-31 08:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
BIG BEAR WIND | 1520 | 2018-04-14 | 2018-04-16 07:00 | WITHDRAWN | 2018-07-31 07:00 | C11 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 199 | 199 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Victor Substation 230kV | 2022-12-01 08:00 | 2022-12-01 08:00 | NA |  |  | NA |  | IC Request
MOORHEN ENERGY STORAGE | 1521 | 2018-04-13 | 2018-04-16 07:00 | WITHDRAWN | 2019-04-08 07:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 200 | 200 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Lugo Substation 220kV | 2021-06-30 07:00 | 2022-11-30 08:00 | NA | Complete |  | NA |  | IC Request
PORTHOS SOLAR | 1523 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2019-04-10 07:00 | C11 | Photovoltaic | Storage |  | Solar | Battery |  | 900 | 900 |  | 900 | Full Capacity |  | RIVERSIDE | CA | SCE | Eldorado Substation 500kV | 2022-12-31 08:00 | 2022-12-31 08:00 | NA | Complete |  | NA |  | IC Request
SUNVALE SOLAR FARM | 1524 | 2018-04-16 | 2018-04-16 07:00 | WITHDRAWN | 2020-05-14 07:00 | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 600 | 600 |  | 600 | Full Capacity |  | CLARK | NV | SCE | Eldorado Substation 500kV | 2022-10-01 07:00 | 2022-10-01 07:00 | NA | Complete |  | NA |  | IC Request
IRON HILLS PUMPED STORAGE | 1525 | 2018-04-12 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-08 08:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Pumped-Storage hydro; MWs MW-1: 1407 | 1400 | Full Capacity |  | RIVERSIDE | CA | SCE | Red Bluff Substation 500kV | 2025-04-10 07:00 | 2025-04-10 07:00 | NA |  |  | NA |  | IC Request
SILVERWING | 1527 | 2018-04-12 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-12 07:00 | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 156 | 156 |  | 150 | Full Capacity |  | RIVERSIDE | CA | SCE | Devers Substation 230kV | 2021-12-31 08:00 | 2022-12-31 08:00 | NA |  |  | NA |  | IC Request
WINDY WASH SOLAR | 1528 | 2018-04-13 | 2018-04-16 07:00 | WITHDRAWN | 2025-06-23 07:00 | C11 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 79 | 79 | Energy Only | Off-Peak Deliverability | RIVERSIDE | CA | SCE | Devers Substation 220kV | 2021-06-30 07:00 | 2022-12-31 08:00 | NA | Complete | Complete | NA |  | Failure to Cure Deficiency
PITCHFORK ENERGY | 1530 | 2018-04-12 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-08 08:00 | C11 | Storage | Photovoltaic |  | Battery | Solar |  | 510 | 513.5 |  | 500 | Full Capacity |  | MARICOPA | AZ | DCRT | Delaney Substation 500kV | 2024-12-01 08:00 | 2024-12-01 08:00 | NA |  |  | NA |  | IC Request
SAN VICENTE ENERGY STORAGE FACILITY | 1533 | 2018-04-03 | 2018-04-16 07:00 | WITHDRAWN | 2019-03-11 07:00 | C11 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Pumped-Storage hydro; MWs MW-1: 500 | 500 | Full Capacity |  | SAN DIEGO | CA | SDGE | Sycamore Canyon Substation 230kV | 2025-04-03 07:00 | 2025-04-03 07:00 | NA | Complete |  | NA
GONZAGA RIDGE WIND FARM 3 | 1535 | 2018-04-17 | 2018-04-16 07:00 | WITHDRAWN | 2019-02-22 08:00 | C11 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 76 | 117.405 | Full Capacity |  | MERCED | CA | PGAE | Los Banos-Pacheco 70 kV Line via Dinosaur Point Tap 70 kV Line | 2020-12-21 08:00 | 2020-12-21 08:00 | NA |  |  | NA |  | IC Request
CAMPTONVILLE BIOPOWER | 1536 | 2018-09-27 | 2018-12-06 08:00 | WITHDRAWN | 2019-03-12 07:00 | FT | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Biofuel; MWs MW-1: 3.371 | 3 | Energy Only |  | YUBA | CA | PGAE | COLGATE-CHALLENGE | 2021-04-20 07:00 | 2021-04-20 07:00 |  | NA | NA | NA |  | None
CAMPTONVILLE BIOPOWER1 | 1537 | 2019-03-04 | 2019-04-05 07:00 | WITHDRAWN | 2020-03-17 07:00 | ISP | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Biofuel; MWs MW-1: 5.5 | 5 | Full Capacity |  | YUBA | CA | PGAE | COLGATE-CHALLENGE 60kV | 2022-03-18 07:00 | 2022-03-18 07:00 | NA |  |  | NA
KUIPER ENERGY STORAGE | 1538 | 2018-11-19 | 2019-04-05 07:00 | WITHDRAWN | 2020-02-27 08:00 | ISP | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 40.5 | 40 | Full Capacity |  | SONOMA | CA | PGAE | Geysers #3 Cloverdale 115 kV line | 2021-12-31 08:00 | 2021-12-31 08:00 | NA |  |  | NA
BRIGHT STAR HYBRID | 1541 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2020-04-10 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 356.796 | 361.74 |  | 350 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Brighton-Bellota 230kV | 2022-12-31 08:00 | 2022-12-31 08:00 | NA | Complete |  | NA |  | IC Request
CAPETOWN 2 HYBRID | 1542 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2020-04-28 07:00 | C12 | Storage | Wind Turbine |  | Battery | Wind Turbine |  | 50.875 | 54.6 |  | 100 | Full Capacity |  | HUMBOLDT | CA | PGAE | Bridgeville Substation 115kV | 2021-06-30 07:00 | 2021-06-30 07:00 | NA | Complete |  | NA |  | IC Request
BEAUCHAMP 2 SOLAR | 1543 | 2019-04-04 | 2019-04-15 07:00 | WITHDRAWN | 2020-03-04 08:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 150 | 75 |  | 150 | Full Capacity |  | COLUSA | CA | PGAE | Cortina Substation 115kV | 2023-12-01 08:00 | 2023-12-01 08:00 | NA | Complete |  | NA |  | IC Request
RANCHERO SOLAR | 1544 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-15 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 150 | 300 |  | 300 | Full Capacity |  | COLUSA | CA | PGAE | Delevan Substation 230kV | 2023-12-01 08:00 | 2023-12-01 08:00 | NA |  |  | NA |  | IC Request
MARESTE BESS | 1545 | 2019-04-12 | 2019-04-15 07:00 | WITHDRAWN | 2020-04-09 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 99 | 99 | Full Capacity |  | ALAMEDA | CA | PGAE | Grant Eastshore #1 115kV | 2023-05-31 07:00 | 2023-05-31 07:00 | NA |  |  | NA |  | IC Request
TATTON STORAGE 1 | 1546 | 2019-04-14 | 2019-04-15 07:00 | WITHDRAWN | 2020-02-14 08:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 30.58 | 30 | Full Capacity |  | MENDOCINO | CA | PGAE | Elk-Gualala 60 kV | 2021-12-01 08:00 | 2021-12-01 08:00 | NA | Complete |  | NA
BRADMOOR SOLAR | 1547 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-10 07:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 361.74 | 356.796 |  | 350 | Full Capacity |  | SOLANO | CA | PGAE | Lambie SW Station-Birds Landing 230kV | 2022-12-31 08:00 | 2022-12-31 08:00 | NA |  |  | NA
LORINER STORAGE | 1548 | 2019-04-06 | 2019-04-15 07:00 | WITHDRAWN | 2021-02-17 08:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 30.48 | 30 | Full Capacity |  | SANTA CLARA | CA | PGAE | Morgan Hill Substation 115kV | 2022-11-30 08:00 | 2022-11-30 08:00 | NA | Complete | Complete | NA |  | IC Request
MIRANDA ESS | 1549 | 2019-04-04 | 2019-04-15 07:00 | WITHDRAWN | 2020-04-09 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 200 | 200 | Full Capacity |  | SANTA CLARA | CA | PGAE | Los Esteros Substation 115kV | 2023-12-01 08:00 | 2023-12-01 08:00 | NA | Complete |  | NA |  | IC Request
MABU BESS | 1551 | 2019-04-13 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-06 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 100.4 | 100 | Full Capacity |  | SANTA CLARA | CA | PGAE | Mabury Tap 115kV | 2023-05-31 07:00 | 2023-05-31 07:00 | NA |  |  | NA |  | IC Request
HERCULIS | 1554 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2020-02-27 08:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 101.2 | 100 | Full Capacity |  | ALAMEDA | CA | PGAE | Oakland J-Grant 115kV | 2022-12-31 08:00 | 2022-12-31 08:00 | NA | Complete |  | NA
STEEL CITY ENERGY STORAGE | 1555 | 2019-04-04 | 2019-04-15 07:00 | WITHDRAWN | 2020-04-29 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 650 | 650 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Pittsburg Substation 230kV | 2022-04-01 07:00 | 2025-06-30 07:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
SPINDRIFT HYBRID SOLAR | 1556 | 2019-04-06 | 2019-04-15 07:00 | WITHDRAWN | 2020-02-28 08:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 101.725 | 101.725 |  | 100 | Full Capacity |  | SUTTER | CA | PGAE | Rio Oso Substation 115kV | 2022-11-30 08:00 | 2022-11-30 08:00 | NA | Complete |  | NA
HYDASPES | 1558 | 2019-04-04 | 2018-04-15 07:00 | WITHDRAWN | 2023-08-17 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 41.436 | 40.562 |  | 40 | Energy Only | Off-Peak Energy Only | STANISLAUS | CA | PGAE | Miller #1 115 kV Line | 2022-12-31 08:00 | 2022-12-31 08:00 | NA | Complete | Complete | NA | In Progress
TEMPEST GENERATION | 1559 | 2019-04-08 | 2019-04-15 07:00 | WITHDRAWN | 2020-02-10 08:00 | C12 | Wind Turbine | Storage |  | Wind Turbine | Battery |  | 1568 | 319.35 |  | 1500 | Full Capacity |  | HUMBOLDT | CA | PGAE | Round Mountain Substation 500kV | 2025-10-31 07:00 | 2025-10-31 07:00 | NA | Complete |  | NA |  | IC Request
NIKOLA NORTE | 1560 | 2019-04-13 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-06 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 61.256 | 244.26 |  | 240 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Tesla-Stagg 230kV | 2023-04-15 07:00 | 2023-04-15 07:00 | NA |  |  | NA |  | IC Request
TESOSTER | 1561 | 2019-04-13 | 2019-04-15 07:00 | WITHDRAWN | 2020-02-25 08:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 61.256 | 244.26 |  | 240 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Tesla-Weber 230kV | 2023-04-15 07:00 | 2023-04-15 07:00 | NA | Complete |  | NA |  | IC Request
NIKOVASTER | 1562 | 2019-04-13 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-06 07:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 244.26 | 61.256 |  | 240 | Full Capacity |  | STANISLAUS | CA | PGAE | Tesla-Westley 230kV | 2023-04-15 07:00 | 2023-04-15 07:00 | NA |  |  | NA |  | IC Request
BAY SUNSHINE HYBRID SOLAR | 1563 | 2019-04-15 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-09 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 50.805 | 50.805 |  | 50 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Tesla Substation 115kV | 2022-11-30 08:00 | 2022-11-30 08:00 | NA |  |  | NA |  | IC Request
TRIM BESS | 1564 | 2019-04-13 | 2019-04-15 07:00 | WITHDRAWN | 2020-02-25 08:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 100.4 | 100 | Full Capacity |  | SANTA CLARA | CA | PGAE | Trimble Substation 115kV | 2023-05-31 07:00 | 2023-05-31 07:00 | NA | Complete |  | NA |  | IC Request
TYRE | 1566 | 2019-04-04 | 2019-04-15 07:00 | WITHDRAWN | 2020-03-03 08:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 55.729 | 55.656 |  | 55 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Valley Springs #2 60 kV | 2022-12-31 08:00 | 2022-12-31 08:00 | NA | Complete |  | NA
TRIGO | 1567 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-10 07:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 153.08 | 77.34 |  | 150 | Full Capacity |  | MADERA | CA | PGAE | Borden Substation 230kV | 2023-12-15 08:00 | 2023-12-15 08:00 | NA |  |  | NA |  | IC Request
OSO ROJO WEST | 1569 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-10 07:00 | C12 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 65.7825 | 65 | Full Capacity |  | FRESNO | CA | PGAE | Coalinga Cogen Tap 70kV | 2021-07-31 07:00 | 2021-07-31 07:00 | NA |  |  | NA |  | IC Request
CARBONERA 1 HYBRID SOLAR | 1570 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-17 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 50 | 50.75 |  | 50 | Full Capacity |  | FRESNO | CA | PGAE | Coalinga#1-San Miguel 70 kV | 2022-11-30 08:00 | 2022-11-30 08:00 | NA |  |  | NA |  | IC Request
EASTSIDE | 1571 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-10 07:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 82.29 | 41.89 |  | 80 | Full Capacity |  | MERCED | CA | PGAE | El Nido Substation 115kV | 2023-12-15 08:00 | 2023-12-15 08:00 | NA |  |  | NA |  | IC Request
POPPY | 1572 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2020-04-22 07:00 | C12 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 184.5 | 190 | Full Capacity |  | FRESNO | CA | PGAE | Gates Substation 230kV | 2021-07-31 07:00 | 2022-11-30 08:00 | NA | Complete |  | NA |  | IC Request
BOYCE SOLAR HYBRID | 1573 | 2019-04-15 | 2019-04-15 07:00 | WITHDRAWN | 2020-04-29 07:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 27.5 | 27.5 |  | 23 | Energy Only |  | FRESNO | CA | PGAE | Jayne Substation 70kV | 2022-07-16 07:00 | 2022-07-16 07:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
BIG DUCK STORAGE | 1574 | 2019-04-15 | 2019-04-15 07:00 | WITHDRAWN | 2020-02-11 08:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 462 | 400 | Full Capacity |  | FRESNO | CA | PGAE | Panoche Substation 230 kV | 2022-07-01 07:00 | 2022-07-01 07:00 | NA | Complete |  | NA |  | IC Request
ASH TREE HYBRID SOLAR | 1575 | 2019-04-15 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-09 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 202.877 | 202.877 |  | 200 | Full Capacity |  | FRESNO | CA | PGAE | Gates Substation 230kV | 2022-11-30 08:00 | 2022-11-30 08:00 | NA |  |  | NA |  | IC Request
DRY GRAPE HYBRID SOLAR | 1576 | 2019-04-15 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-09 07:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 202.76 | 200 |  | 200 | Full Capacity |  | FRESNO | CA | PGAE | Gates Substation 230kV | 2022-11-30 08:00 | 2022-11-30 08:00 | NA |  |  | NA |  | IC Request
IRRIGOSA | 1577 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-09 07:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 153.08 | 77.34 |  | 150 | Full Capacity |  | MADERA | CA | PGAE | Gregg Substation 230kV | 2023-12-15 08:00 | 2023-12-15 08:00 | NA |  |  | NA |  | IC Request
JOURNEY STORAGE | 1578 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2020-02-27 08:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 354.88 | 350 | Full Capacity |  | KINGS | CA | PGAE | Henrietta Substation 230kV | 2022-12-31 08:00 | 2022-12-31 08:00 | NA |  |  | NA |  | IC Request
ROBIN SOLAR HYBRID | 1579 | 2019-04-04 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-10 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 30.25 | 30.25 |  | 27 | Full Capacity |  | MONTEREY | CA | PGAE | Soledad Substation 60kV | 2022-12-16 08:00 | 2022-12-16 08:00 | NA |  |  | NA |  | IC Request
STEVINSON | 1580 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-10 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 31.88 | 66.94 |  | 65 | Full Capacity |  | MERCED | CA | PGAE | Livingston Substation 115kV | 2023-12-15 08:00 | 2023-12-15 08:00 | NA |  |  | NA |  | IC Request
PINEBROOK SOLAR HYBRID ENERGY CENTER | 1581 | 2019-04-01 | 2019-04-15 07:00 | WITHDRAWN | 2020-04-14 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 1537 | 1537 |  | 1500 | Full Capacity |  | FRESNO | CA | PGAE | Los Banos-Gates #1 500 kV | 2024-11-01 07:00 | 2024-11-01 07:00 | NA | Complete |  | NA |  | IC Request
SUGARLOAF HYBRID SOLAR | 1582 | 2019-04-09 | 2019-04-15 07:00 | WITHDRAWN | 2020-03-09 07:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 152.8 | 150 |  | 150 | Full Capacity |  | FRESNO | CA | PGAE | Panoche Substation 230kV | 2022-11-30 08:00 | 2022-11-30 08:00 | NA | Complete |  | NA |  | IC Request
CORCAIR HYBRID SOLAR | 1583 | 2019-04-09 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-08 07:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 91.35 | 90 |  | 90 | Full Capacity |  | KINGS | CA | PGAE | Waukena Substation 115kV | 2022-11-30 08:00 | 2022-11-30 08:00 | NA |  |  | NA |  | IC Request
RIVIERA SOLAR | 1584 | 2018-12-27 | 2019-04-15 07:00 | WITHDRAWN | 2020-02-12 08:00 | C12 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 75 | 75 | Full Capacity |  | MADERA | CA | PGAE | Wilson-Oro Loma 115 kv | 2022-12-31 08:00 | 2022-12-31 08:00 | NA |  |  | NA
STORM | 1585 | 2019-04-08 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-10 07:00 | C12 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 50.8 | 50 | Full Capacity |  | KERN | CA | PGAE | Olive SW Station-Smyrna 115kV | 2021-07-31 07:00 | 2021-07-31 07:00 | NA |  |  | NA |  | IC Request
ARCTURUS | 1586 | 2019-04-04 | 2019-04-15 07:00 | WITHDRAWN | 2025-03-03 08:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 152.29 | 151.794 |  | 150 | Energy Only | Off-Peak Energy Only | KERN | CA | PGAE | Arco 230 kV | 2022-12-30 08:00 | 2026-11-03 08:00 | NA | Complete | Complete | NA | Executed | IC Request
LAS BRISAS OFFSHORE WIND | 1588 | 2019-04-15 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-18 07:00 | C12 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 1187.5 | 1145 | Full Capacity |  | SAN LUIS OBISPO | CA | PGAE | Diablo Canyon Switching Station 500kV | 2026-04-01 07:00 | 2026-04-01 07:00 | NA |  |  | NA |  | IC Request
NIMITZ 1 GENERATION | 1589 | 2019-04-06 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-18 07:00 | C12 | Storage | Wind Turbine |  | Battery | Wind Turbine |  | 319.35 | 1568 |  | 1500 | Full Capacity |  | SAN LUIS OBISPO | CA | PGAE | Diablo Canyon-Gates 500kV | 2024-10-31 07:00 | 2024-10-31 07:00 | NA |  |  | NA |  | IC Request
NIMITZ 2 GENERATION | 1590 | 2019-04-08 | 2019-04-15 07:00 | WITHDRAWN | 2020-02-10 08:00 | C12 | Wind Turbine | Storage |  | Wind Turbine | Battery |  | 1568 | 319.35 |  | 1500 | Full Capacity |  | SAN LUIS OBISPO | CA | PGAE | Diablo Canyon-Gates 500kV | 2026-04-01 07:00 | 2026-04-01 07:00 | NA | Complete |  | NA |  | IC Request
CHAMISE | 1591 | 2019-04-04 | 2019-04-15 07:00 | WITHDRAWN | 2023-08-30 07:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 55.9 | 21.8 |  | 55 | Energy Only | Off-Peak Energy Only | KERN | CA | PGAE | Midway-Tupman-Rio Bravo-Renfro 115 kV | 2022-12-31 08:00 | 2024-12-31 08:00 | NA | Complete | Complete | NA | In Progress | IC Request
OATFIELD HYBRID SOLAR | 1592 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2020-03-13 07:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 500 | 500 |  | 500 | Full Capacity |  | KINGS | CA | PGAE | Gates-Templeton 230 kV | 2022-11-30 08:00 | 2022-11-30 08:00 | NA | Complete |  | NA |  | IC Request
GRAND LAKE HYBRID SOLAR | 1594 | 2019-04-15 | 2019-04-15 07:00 | WITHDRAWN | 2022-06-06 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 250 | 254 |  | 250 | Energy Only | Off-Peak Energy Only | KINGS | CA | PGAE | Gates-Midway 230kV | 2023-11-30 08:00 | 2023-11-30 08:00 | NA | Complete | Complete | NA |  | Failure to Cure Deficiency
PEONY | 1595 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2020-03-12 07:00 | C12 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 358.875 | 350 | Full Capacity |  | KERN | CA | PGAE | Midway 230kV | 2021-07-31 07:00 | 2022-11-30 08:00 | NA | Complete |  | NA |  | IC Request
OSO ROJO GOLF COURSE | 1597 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2020-03-02 08:00 | C12 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 139.7 | 138 | Full Capacity |  | KERN | CA | PGAE | Midway-Wheeler Ridge 230kV | 2021-07-31 07:00 | 2021-07-31 07:00 | NA | Complete |  | NA |  | IC Request
AGUA AMARGA WIND | 1598 | 2019-04-12 | 2019-04-15 07:00 | WITHDRAWN | 2020-02-21 08:00 | C12 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 403.2 | 400 | Full Capacity |  | SAN LUIS OBISPO | CA | PGAE | SOLARSS Switching Station | 2023-10-31 07:00 | 2023-10-31 07:00 | NA | Complete |  | NA |  | IC Request
LION ROCK OFFSHORE WIND | 1599 | 2019-04-15 | 2019-04-15 07:00 | WITHDRAWN | 2020-04-01 07:00 | C12 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 627 | 605 | Full Capacity |  | SAN LUIS OBISPO | CA | PGAE | Morro Bay Substation 230kV | 2026-04-01 07:00 | 2026-04-01 07:00 | NA | Complete |  | NA |  | IC Request
SEAWOLF GENERATION | 1600 | 2019-04-08 | 2019-04-15 07:00 | WITHDRAWN | 2020-02-10 08:00 | C12 | Storage | Wind Turbine |  | Battery | Wind Turbine |  | 319.35 | 1568 |  | 1500 | Full Capacity |  | SAN LUIS OBISPO | CA | PGAE | Midway-Diablo Canyon #2 | 2024-10-31 07:00 | 2024-10-31 07:00 | NA | Complete |  | NA |  | IC Request
FAMILIA HYBRID SOLAR | 1601 | 2019-04-15 | 2019-04-15 07:00 | WITHDRAWN | 2020-03-13 07:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 202.5 | 202.5 |  | 200 | Full Capacity |  | MARICOPA | CA | PGAE | Midway-Wheeler Ridge #2 230kV | 2022-11-30 08:00 | 2022-11-30 08:00 | NA |  |  | NA |  | IC Request
FOKUS RENEWABLE ENERGY CENTER | 1602 | 2019-04-13 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-19 07:00 | C12 | Storage | Photovoltaic | Wind Turbine | Battery | Solar | Wind Turbine | 151.6 | 152.4 | 168 | 150 | Full Capacity |  | KERN | CA | SCE | Highwind Substation 230kV | 2023-12-15 08:00 | 2023-12-15 08:00 | NA |  |  | NA |  | IC Request
RIGAL | 1603 | 2019-04-08 | 2019-04-15 07:00 | WITHDRAWN | 2020-03-04 08:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 202.98 | 202.998 |  | 200 | Full Capacity |  | KERN | CA | SCE | Inyokern-Randsburg 115 kV | 2022-12-31 08:00 | 2022-12-31 08:00 | NA |  |  | NA
CAYENNE ENERGY STORAGE | 1605 | 2019-04-16 | 2019-04-15 07:00 | WITHDRAWN | 2020-02-26 08:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 102.1 | 100 | Full Capacity |  | LOS ANGELES | CA | SCE | Chino Substation 220kV | 2022-12-16 08:00 | 2022-12-16 08:00 | NA |  |  | NA |  | IC Request
ELLIS BESS | 1606 | 2019-04-10 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-17 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 203.41 | 200 | Full Capacity |  | ORANGE | CA | SCE | Ellis Substation 220kV | 2021-10-31 07:00 | 2021-10-31 07:00 | NA |  |  | NA |  | IC Request
RANCHO 2 ENERGY STORAGE | 1607 | 2019-04-09 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-18 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 250 | 250 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Etiwanda Substation 230kV | 2023-01-01 08:00 | 2023-01-01 08:00 | NA |  |  | NA |  | IC Request
HINSON BESS | 1609 | 2019-04-10 | 2019-04-15 07:00 | WITHDRAWN | 2020-04-13 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 308.102 | 300 | Full Capacity |  | LOS ANGELES | CA | SCE | Hinson Substation 220kV | 2021-10-31 07:00 | 2022-08-01 07:00 | NA | Complete |  | NA |  | IC Request
SUPERBA STORAGE 1 | 1610 | 2019-04-11 | 2019-04-15 07:00 | WITHDRAWN | 2020-04-29 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 305 | 300 | Full Capacity |  | ORANGE | CA | SCE | Johanna Substation 230 kV | 2021-12-01 08:00 | 2021-12-01 08:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
SPEEDWAY ESS | 1612 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2021-11-17 08:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 200 | 200 | Full Capacity | Off-Peak Deliverability | LOS ANGELES | CA | SCE | Rio Hondo Substation 230kV | 2023-12-01 08:00 | 2024-04-15 07:00 | NA | Complete | Complete | NA
TRESTLES ENERGY STORAGE | 1613 | 2019-04-16 | 2019-04-15 07:00 | WITHDRAWN | 2020-02-27 08:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 433.752 | 400 | Full Capacity |  | LOS ANGELES | CA | SCE | Rio Hondo Substation 220kV | 2022-12-16 08:00 | 2022-12-16 08:00 | NA |  |  | NA |  | IC Request
CITADEL ESS | 1614 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-15 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 200 | 200 | Full Capacity |  | ORANGE | CA | SCE | Johanna Substation 230 kV | 2023-12-01 08:00 | 2023-12-01 08:00 | NA |  |  | NA |  | IC Request
HIGHWIND ENERGY CENTER | 1616 | 2019-04-13 | 2019-04-15 07:00 | WITHDRAWN | 2020-02-27 08:00 | C12 | Storage | Wind Turbine | Photovoltaic | Battery | Wind Turbine | Solar | 28.38 | 64.8 | 51.75 | 115 | Full Capacity |  | KERN | CA | SCE | Highwind Substation 230kV | 2023-12-31 08:00 | 2023-12-31 08:00 | NA |  |  | NA |  | IC Request
DORADUS | 1618 | 2019-04-04 | 2019-04-15 07:00 | WITHDRAWN | 2020-03-04 08:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 202.998 | 202.998 |  | 200 | Full Capacity |  | KERN | CA | SCE | Magunden-Pastoria 230kV | 2022-12-31 08:00 | 2022-12-31 08:00 | NA | Complete |  | NA |  | IC Request
ROCKY HILL SOLAR | 1620 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2020-03-11 07:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 102.04 | 51.56 |  | 100 | Full Capacity |  | TULARE | CA | SCE | Rector Substation 230kV | 2023-12-15 08:00 | 2023-12-15 08:00 | NA |  |  | NA
YELLOW HAY HYBRID SOLAR | 1621 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2020-03-06 08:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 200 | 200 |  | 200 | Full Capacity |  | TULARE | CA | SCE | Magunden-Springville #1 220 kV | 2022-11-30 08:00 | 2022-11-30 08:00 | NA |  |  | NA |  | IC Request
BARRENSPRING | 1622 | 2019-04-13 | 2019-04-15 07:00 | WITHDRAWN | 2020-02-27 08:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 64.17 | 244.26 |  | 240 | Full Capacity |  | TULARE | CA | SCE | Springville-Rector 220kV line | 2023-04-15 07:00 | 2023-04-15 07:00 | NA | Complete |  | NA |  | IC Request
TRIUMPH SOLAR | 1623 | 2019-04-04 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-15 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 150 | 300 |  | 300 | Full Capacity |  | TULARE | CA | SCE | Vestal Substation 230 kV | 2023-12-01 08:00 | 2023-12-01 08:00 | NA |  |  | NA |  | IC Request
VESTAL VALLEY | 1624 | 2019-04-13 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-26 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 64.17 | 244.26 |  | 240 | Full Capacity |  | TULARE | CA | SCE | Vestal Substation 220kV | 2023-04-15 07:00 | 2023-04-15 07:00 | NA |  |  | NA |  | IC Request
SAGEBRUSH 6 HYBRID | 1626 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2020-04-29 07:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 116.0186 | 113.96 |  | 200 | Full Capacity |  | KERN | CA | SCE | Vincent Substation 230kV | 2022-12-01 08:00 | 2022-12-01 08:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
UNA LAKE SOLAR | 1627 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-10 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 615.9 | 627 |  | 600 | Full Capacity |  | LOS ANGELES | CA | SCE | Vincent Substation 230kV | 2022-12-31 08:00 | 2022-12-31 08:00 | NA |  |  | NA |  | IC Request
FORT TEJON SOLAR | 1628 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2021-05-05 07:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 310.2 | 306.26 |  | 300 | Full Capacity | Off-Peak Deliverability | LOS ANGELES | CA | SCE | Vincent Substation 230kV | 2023-12-31 08:00 | 2026-08-15 07:00 | NA | Complete | Complete | NA
DRACO SOLAR | 1630 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-15 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 125 | 250 |  | 250 | Full Capacity |  | KERN | CA | SCE | Whirlwind Substation 230 kV | 2023-12-01 08:00 | 2023-12-01 08:00 | NA |  |  | NA
DESERT FLOWER WIND FARM | 1633 | 2019-04-13 | 2019-04-15 07:00 | WITHDRAWN | 2019-11-07 08:00 | C12 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 86.4 | 85 | Full Capacity |  | KERN | CA | SCE | Windhub Substation 230 kV | 2023-12-31 08:00 | 2023-12-31 08:00 | NA |  |  | NA
GARCES HYBRID SOLAR | 1634 | 2019-04-15 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-23 07:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 203.434 | 200 |  | 200 | Full Capacity |  | KERN | CA | SCE | Windhub Substation 230 kV | 2022-11-30 08:00 | 2022-11-30 08:00 | NA |  |  | NA |  | IC Request
YEAGER HYBRID SOLAR | 1635 | 2019-04-15 | 2019-04-15 07:00 | WITHDRAWN | 2020-03-13 07:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 406.56 | 406.56 |  | 400 | Full Capacity |  | KERN | CA | SCE | Windhub Substation 500kV | 2022-11-30 08:00 | 2022-11-30 08:00 | NA |  |  | NA |  | IC Request
SOLO | 1637 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2020-03-26 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 518.4 | 518.4 |  | 500 | Full Capacity |  | RIVERSIDE | CA | SCE | Colorado River Substation 500kV | 2022-12-31 08:00 | 2022-12-31 08:00 | NA | Complete |  | NA
VENTUS RENEWABLE ENERGY CENTER | 1638 | 2019-04-12 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-19 07:00 | C12 | Photovoltaic | Wind Turbine | Storage | Solar | Wind Turbine | Battery | 208.527 | 229.6 | 204.93 | 200 | Full Capacity |  | RIVERSIDE | CA | SCE | Devers Substation 230kV | 2023-12-15 08:00 | 2023-12-15 08:00 | NA |  |  | NA |  | IC Request
CONSECHA | 1639 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-10 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 100.98 | 100 | Full Capacity |  | RIVERSIDE | CA | SCE | Devers Substation 230kV | 2022-12-31 08:00 | 2022-12-31 08:00 | NA |  |  | NA |  | IC Request
SUNNYNOOK SOLAR CENTER | 1640 | 2019-04-12 | 2019-04-15 07:00 | WITHDRAWN | 2020-04-14 07:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 514.35 | 514.35 |  | 500 | Full Capacity |  | RIVERSIDE | CA | SCE | Devers-San Bernardino Line 230 kV | 2023-06-01 07:00 | 2026-09-01 07:00 | NA | Complete |  | NA |  | IC Request
SAN BERNARDINO BESS | 1644 | 2019-04-10 | 2019-04-15 07:00 | WITHDRAWN | 2020-04-13 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 308.1 | 300 | Full Capacity |  | SAN BERNARDINO | CA | SCE | San Bernardino Substation 220kV | 2021-10-31 07:00 | 2022-08-01 07:00 | NA | Complete |  | NA |  | IC Request
BULLHEAD SOLAR | 1648 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2020-03-04 08:00 | C12 | Photovoltaic | Storage |  | Solar | Battery |  | 400 | 200 |  | 400 | Full Capacity |  | CLARK | NV | SCE | Mohave Substation 500kV | 2023-12-01 08:00 | 2023-12-01 08:00 | NA |  |  | NA |  | IC Request
BLACK HILLS PLAYA A SOLAR | 1651 | 2019-04-12 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-24 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 51.15 | 102.3 |  | 100 | Full Capacity |  | CLARK | NV | GLW | Sloan Canyon Switching Station 230kV | 2023-12-15 08:00 | 2023-12-15 08:00 | NA |  |  | NA
BLACK HILLS PLAYA B SOLAR | 1652 | 2019-04-12 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-24 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 51.15 | 102.3 |  | 100 | Full Capacity |  | CLARK | NV | GLW | Sloan Canyon Switching Station 230 kV | 2023-12-15 08:00 | 2023-12-15 08:00 | NA |  |  | NA |  | IC Request
SLOAN ENERGY CENTER | 1653 | 2019-04-13 | 2019-04-15 07:00 | WITHDRAWN | 2020-03-12 07:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 118.56 | 459.54 |  | 448 | Full Capacity |  | CLARK | NV | GLW | Sloan Canyon Switching Station 230kV | 2023-05-31 07:00 | 2023-05-31 07:00 | NA | Complete |  | NA |  | IC Request
GYPSY ESS | 1656 | 2019-04-04 | 2019-04-15 07:00 | WITHDRAWN | 2021-05-19 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 200 | 200 | Full Capacity | Off-Peak Deliverability | SAN DIEGO | CA | SDGE | Bay-Boulevard 230kV | 2023-12-01 08:00 | 2023-09-01 07:00 | NA | Complete | Complete | NA |  | IC Request
CARDINAL STORAGE | 1658 | 2019-04-01 | 2019-04-15 07:00 | WITHDRAWN | 2022-04-18 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 200 | 200 | Energy Only | Off-Peak Deliverability | IMPERIAL | CA | SDGE | Imperial Valley Substation 230kV | 2023-06-30 07:00 | 2028-10-12 07:00 | NA | Complete | Complete | NA |  | IC Request
PRIMAVERA STORAGE | 1659 | 2019-04-04 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-15 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 200 | 200 | Full Capacity |  | SAN DIEGO | CA | SDGE | ECO 230kV | 2023-12-01 08:00 | 2023-12-01 08:00 | NA |  |  | NA |  | IC Request
OBSIDIAN STORAGE | 1661 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2024-03-13 07:00 | C12 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 300 | 300 | Energy Only | Off-Peak Deliverability | BAJA CALIFORNIA | MX | SDGE | East County Substation 230 kV | 2024-12-01 08:00 | 2029-09-26 07:00 | NA | Complete | Complete | NA |  | IC Request
VOLTA DE MEXICALI | 1664 | 2019-03-29 | 2019-04-15 07:00 | WITHDRAWN | 2025-09-06 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 500 | 500 | Energy Only |  | SONORA | MX | SDGE | Imperial Valley Substation 230 kV | 2021-12-31 08:00 | 2035-03-10 08:00 | NA | Complete | Complete | NA |  | IC Request
SALTON SOLAR | 1666 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2020-03-04 08:00 | C12 | Storage | Photovoltaic |  | Battery | Solar |  | 210.6 | 421.2 |  | 400 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley Substation 230kV | 2023-12-01 08:00 | 2023-12-01 08:00 | NA | Complete |  | NA
SUFFOLK STORAGE | 1668 | 2019-04-12 | 2019-04-15 07:00 | WITHDRAWN | 2020-04-28 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 51 | 50 | Full Capacity |  | SAN DIEGO | CA | SDGE | Mesa Heights Substation 69kV | 2021-12-01 08:00 | 2021-12-01 08:00 | NA | Complete |  | NA |  | IC Request
MARINE DEPOT | 1671 | 2019-04-16 | 2019-04-15 07:00 | WITHDRAWN | 2025-04-28 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 26.6 | 25 | Energy Only |  | SAN DIEGO | CA |  | Point Loma Substation 69 kV | 2021-12-31 08:00 | 2026-10-20 07:00 | NA | Complete | Complete | NA |  | IC Request
BOULDER OAKS HYBRID | 1672 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2020-04-13 07:00 | C12 | Wind Turbine | Storage |  | Wind Turbine | Battery |  | 205.8 | 205 |  | 400 | Full Capacity |  | SAN DIEGO | CA | SDGE | ECO-Miguel 500kV | 2021-09-30 07:00 | 2023-06-01 07:00 | NA | Complete |  | NA |  | IC Request
SV ENERGY STORAGE FACILITY | 1674 | 2019-04-12 | 2019-04-15 07:00 | WITHDRAWN | 2020-04-24 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Pumped-Storage hydro; MWs MW-1: 500 | 500 | Full Capacity |  | SAN DIEGO | CA | SDGE | Sycamore Canyon Substation 230kV | 2026-04-01 07:00 | 2026-04-01 07:00 | NA |  |  | NA |  | IC Request
CHAPARREL STORAGE | 1676 | 2019-04-05 | 2019-04-15 07:00 | WITHDRAWN | 2019-07-15 07:00 | C12 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 50 | 50 | Full Capacity |  | SAN DIEGO | CA | SDGE | Warners Substation 69kV | 2023-12-01 08:00 | 2023-12-01 08:00 | NA |  |  | NA |  | IC Request
SYCAMORE EXPANSION | 1677 | 2019-06-12 | 2020-04-01 07:00 | WITHDRAWN | 2020-11-06 08:00 | ISP | Generating Facility Type-1: Cogeneration; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 60 | 60 | Full Capacity |  | KERN | CA | SCE | Magunden | 2019-12-01 08:00 | 2019-12-01 08:00 | NA |  |  | NA
BRISBANE ENERGY STORAGE | 1682 | 2020-04-10 | 2020-04-15 07:00 | WITHDRAWN | 2021-04-08 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 253.6895 | 250 | Full Capacity |  | SAN MATEO | CA | PGAE | Martin | 2023-10-15 07:00 | 2023-10-15 07:00 | NA |  |  | NA |  | IC Request
AQUEDUCT ENERGY STORAGE | 1683 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2025-09-22 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 102.25 | 100 | Energy Only | Off-Peak Deliverability | CONTRA COSTA | CA | PGAE | Contra Costa-Delta 230 kV Line | 2023-12-31 08:00 | 2026-04-30 07:00 | NA | Complete | Complete | NA | Executed | IC Request
CAPETOWN 3 HYBRID | 1684 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2021-04-08 07:00 | C13 | Wind Turbine | Storage |  | Wind Turbine | Battery |  | 97.2 | 61.0139 |  | 150 | Full Capacity | Off-Peak Deliverability | HUMBOLDT | CA | PGAE | Bridgeville Substation 115kV | 2023-12-01 08:00 | 2023-12-01 08:00 | NA |  |  | NA
CHIA ESS | 1685 | 2020-04-07 | 2020-04-15 07:00 | WITHDRAWN | 2021-04-02 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 300 | 300 | Full Capacity |  | ALAMEDA | CA | PGAE | Cayetano Substation 230kV | 2025-12-01 08:00 | 2025-12-01 08:00 | NA | Complete |  | NA |  | IC Request
CHICKAREE HYBRID SOLAR | 1686 | 2020-04-01 | 2020-04-15 07:00 | WITHDRAWN | 2021-05-25 07:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 86.7 | 86.7 |  | 85 | Full Capacity | Off-Peak Deliverability | BUTTE | CA | PGAE | Table Mountain Substation 115kV | 2023-12-31 08:00 | 2023-12-31 08:00 | NA | Complete |  | NA |  | IC Request
CROSSROADS STORAGE | 1688 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2024-04-04 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 312.96 | 299.99 | Energy Only |  | SHASTA | CA | PGAE | Round Mountain 230 kV | 2024-11-30 08:00 | 2027-04-01 07:00 | NA | Complete | Complete | NA
CROWSWEST | 1689 | 2020-04-07 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-19 07:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 20.2 | 10 |  | 20 | Full Capacity | Off-Peak Deliverability | STANISLAUS | CA | PGAE | Crow Creek Switching Station 60kV | 2023-12-30 08:00 | 2023-12-30 08:00 | NA | Complete |  | NA |  | IC Request
FORTIS | 1691 | 2020-04-09 | 2020-04-15 07:00 | WITHDRAWN | 2025-05-14 07:00 | C13 | Wind Turbine | Storage | Photovoltaic | Wind Turbine | Battery | Solar | 207.2 | 203.94 | 205.02 | 200 | Energy Only | Off-Peak Deliverability | SOLANO | CA | PGAE | Birds Landing 230 kV | 2024-12-15 08:00 | 2028-02-11 08:00 | NA | Complete | Complete | NA | Executed
INTREPID ENERGY | 1692 | 2020-04-12 | 2020-04-15 07:00 | WITHDRAWN | 2021-04-09 07:00 | C13 | Wind Turbine | Storage |  | Wind Turbine | Battery |  | 1568 | 319.356 |  | 1500.12 | Full Capacity | Off-Peak Deliverability | HUMBOLDT | CA | PGAE | Round Mountain Substation 500kV | 2027-04-15 07:00 | 2027-04-15 07:00 | NA |  |  | NA
MARIPOSA ENERGY BESS | 1693 | 2020-04-14 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-27 07:00 | C13 | Storage | Gas Turbine |  | Battery | Natural Gas |  | 26.21 | 14.1 |  | 34.1 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Mariposa Energy Center 230kV | 2027-03-31 07:00 | 2027-03-31 07:00 | NA |  |  | NA |  | Failure to Cure Deficiency
MAYA | 1694 | 2020-04-14 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-22 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 102.8 | 40 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Pittsburg Substation 60kV | 2023-12-31 08:00 | 2023-12-31 08:00 | NA | Complete |  | NA |  | IC Request
MEADOWS ENERGY STORAGE | 1695 | 2020-04-14 | 2020-04-15 07:00 | WITHDRAWN | 2024-06-05 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 102 | 101.2 | Energy Only |  | PLACER | CA | PGAE | Atlantic 60 kV | 2023-06-15 07:00 | 2025-01-29 08:00 | NA | Complete | Complete | NA
MENARD ENERGY STORAGE | 1696 | 2020-04-14 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-25 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 950.4 | 900 | Full Capacity |  | SOLANO | CA | PGAE | Vaca-Dixon Substation 500kV | 2023-08-01 07:00 | 2023-08-01 07:00 | NA |  |  | NA |  | IC Request
MUIR STORAGE | 1697 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-10 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 305.25 | 300 | Full Capacity |  | MARIN | CA | PGAE | Ignacio Substation 230kV | 2025-10-30 07:00 | 2025-10-30 07:00 | NA |  |  | NA |  | IC Request
MIRANDA ESS 2 | 1698 | 2020-04-07 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-07 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 300 | 300 | Full Capacity |  | SANTA CLARA | CA | PGAE | Los Esteros Substation 115kV | 2024-12-01 08:00 | 2024-12-01 08:00 | NA |  |  | NA |  | IC Request
GREASEWOOD HYBRID | 1699 | 2020-04-09 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-07 07:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 326.6129 | 166.905 |  | 300 | Full Capacity | Off-Peak Deliverability | COLUSA | CA | PGAE | Delevan-Vaca #3 230kV line | 2023-12-01 08:00 | 2023-12-01 08:00 | NA |  |  | NA |  | IC Request
NORTH BAY ENERGY STORAGE | 1700 | 2020-04-14 | 2020-04-15 07:00 | WITHDRAWN | 2024-11-01 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 102.75 | 100 | Energy Only |  | SONOMA | CA | PGAE | Lakeville 60 kV | 2023-06-01 07:00 | 2027-03-18 07:00 | NA | Complete | Complete | NA | Executed | IC Request
ORIGIN ENERGY STORAGE | 1701 | 2020-04-14 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-15 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 102 | 101.1 | Full Capacity |  | SHASTA | CA | PGAE | Cottonwood Substation 115kV | 2023-06-15 07:00 | 2023-06-15 07:00 | NA |  |  | NA
RAILYARD ENERGY STORAGE | 1703 | 2020-04-10 | 2020-04-15 07:00 | WITHDRAWN | 2021-04-08 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 150.929 | 150 | Full Capacity |  | SANTA CLARA | CA | PGAE | New Switchyard on Los Esteros-Trimble Line 115kV | 2023-10-15 07:00 | 2023-10-15 07:00 | NA |  |  | NA
SPARTAN ENERGY STORAGE | 1704 | 2020-04-14 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-27 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 152.2875 | 150 | Full Capacity |  | SUTTER | CA | PGAE | Rio Oso Substation 115kV | 2023-09-01 07:00 | 2023-09-01 07:00 | NA |  |  | NA |  | Failure to Cure Deficiency
STEEL CITY BATTERY STORAGE | 1705 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2026-02-09 08:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 675 | 220 | Energy Only |  | CONTRA COSTA | CA | PGAE | Pittsburg 230 kV | 2025-06-30 07:00 | 2029-03-01 08:00 | NA | Complete | Complete | NA | Executed | IC Request
TRAILWAYS ENERGY STORAGE | 1706 | 2020-04-14 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-15 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 102 | 101.2 | Full Capacity |  | BUTTE | CA | PGAE | Paradise Substation 115kV | 2023-07-15 07:00 | 2023-07-15 07:00 | NA |  |  | NA
OWL CLAW HYBRID SOLAR | 1707 | 2020-04-01 | 2020-04-15 07:00 | WITHDRAWN | 2020-06-11 07:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 86.6 | 86.6 |  | 84.9 | Full Capacity | Off-Peak Deliverability | SAN JOAQUIN | CA | PGAE | Camanche 115kV Tap via the Camanche Powerhouse Station 115kV | 2023-12-31 08:00 | 2023-12-31 08:00 | NA |  |  | NA |  | IC Request
QUICKSILVER ENERGY STORAGE | 1708 | 2020-04-14 | 2020-04-15 07:00 | WITHDRAWN | 2020-06-16 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 250 | 250 | Full Capacity |  | SANTA CLARA | CA | PGAE | Metcalf Substation 230kV | 2024-08-01 07:00 | 2024-08-01 07:00 | NA |  |  | NA |  | IC Request
ALBA | 1710 | 2020-04-03 | 2020-04-15 07:00 | WITHDRAWN | 2021-04-12 07:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 154.838 | 77.638 |  | 150 | Full Capacity | Off-Peak Deliverability | FRESNO | CA | PGAE | Mendota Substation 115kV | 2023-10-31 07:00 | 2023-10-31 07:00 | NA |  |  | NA |  | IC Request
ALLIUM | 1711 | 2020-04-10 | 2020-04-15 07:00 | WITHDRAWN | 2021-04-14 07:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 114.5529 | 114.5529 |  | 110 | Full Capacity | Off-Peak Deliverability | SAN BENITO | CA | PGAE | Hollister Substation 115kV | 2023-12-01 08:00 | 2023-12-01 08:00 | NA |  |  | NA |  | IC Request
APRICOT ENERGY STORAGE | 1712 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2021-04-07 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 30.6 | 30 | Full Capacity |  | FRESNO | CA | PGAE | Cheney #1 Tap 115kV Line | 2023-07-01 07:00 | 2023-07-01 07:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
COMAL FLATS 1 | 1714 | 2020-04-02 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-30 07:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 202.5 | 202.5 |  | 200 | Full Capacity | Off-Peak Deliverability | FRESNO | CA | PGAE | Gates Substation 230kV | 2024-09-30 07:00 | 2024-09-30 07:00 | NA | Complete |  | NA |  | IC Request
EDGEWOOD SOLAR HYBRID | 1715 | 2020-04-02 | 2020-04-15 07:00 | WITHDRAWN | 2021-04-09 07:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 1700 | 1700 |  | 1700 | Full Capacity | Off-Peak Deliverability | FRESNO | CA | PGAE | Los Banos - Gates #1 500kV line | 2024-11-01 07:00 | 2024-11-01 07:00 | NA |  |  | NA |  | IC Request
FERRY HYBRID SOLAR | 1716 | 2020-04-07 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-08 07:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 50 | 102.2 |  | 100 | Full Capacity | Off-Peak Deliverability | MADERA | CA | PGAE | Dairyland - Mendota 115kV line | 2023-11-30 08:00 | 2023-11-30 08:00 | NA |  |  | NA |  | IC Request
FOXGLOVE HYBRID SOLAR | 1717 | 2020-04-01 | 2020-04-15 07:00 | WITHDRAWN | 2020-12-03 08:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 102.5 | 102.5 |  | 100 | Full Capacity | Off-Peak Deliverability | MADERA | CA | PGAE | Borden Substation 70kV | 2023-12-31 08:00 | 2023-12-31 08:00 | NA |  |  | NA
HENSLEY HYBRID SOLAR | 1719 | 2020-04-07 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-08 07:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 50 | 101.8 |  | 100 | Full Capacity | Off-Peak Deliverability | MADERA | CA | PGAE | Chowchilla-Kerckhoff #2 115kV lin3 | 2023-11-30 08:00 | 2023-11-30 08:00 | NA |  |  | NA |  | IC Request
ICEBERG ENERGY STORAGE | 1720 | 2020-04-14 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-03 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 31.7579 | 30 | Full Capacity |  | MONTEREY | CA | PGAE | Spence Substation 60kV | 2022-07-01 07:00 | 2022-07-01 07:00 | NA |  |  | NA |  | IC Request
MILKY WAY HYBRID SOLAR | 1721 | 2020-04-10 | 2020-04-15 07:00 | WITHDRAWN | 2021-04-12 07:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 175 | 355.2 |  | 350 | Full Capacity | Off-Peak Deliverability | KINGS | CA | PGAE | Gates- Templeton 230kV line | 2023-11-30 08:00 | 2023-11-30 08:00 | NA |  |  | NA |  | IC Request
MORTIMER SOLAR HYBRID | 1722 | 2020-04-01 | 2020-04-15 07:00 | WITHDRAWN | 2021-04-09 07:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 250 | 250 |  | 250 | Full Capacity | Off-Peak Deliverability | KINGS | CA | PGAE | Mustang Switching Station 230kV | 2024-04-01 07:00 | 2024-04-01 07:00 | NA | Complete |  | NA |  | IC Request
POLVADERO HYBRID SOLAR | 1723 | 2020-04-07 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-03 07:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 51.9 | 25 |  | 50 | Full Capacity | Off-Peak Deliverability | FRESNO | CA | PGAE | Jayne Sw Sta-Coalinga #1 70kV line | 2023-11-30 08:00 | 2023-11-30 08:00 | NA |  |  | NA |  | IC Request
ROCK DOVE 1 ENERGY CENTER | 1724 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2021-05-21 07:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 387.94 | 312.96 |  | 300 | Full Capacity | Off-Peak Deliverability | KERN | CA | PGAE | Arco - Midway 230kV line | 2024-11-30 08:00 | 2024-11-30 08:00 | NA | Complete |  | NA
ROCK DOVE 2 ENERGY CENTER | 1725 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2020-06-18 07:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 387.94 | 312.96 |  | 300 | Full Capacity | Off-Peak Deliverability | KERN | CA | PGAE | Gates - Midway 230kV line | 2025-11-30 08:00 | 2025-11-30 08:00 | NA |  |  | NA |  | IC Request
TORANA HYBRID SOLAR | 1726 | 2020-04-01 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-25 07:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 102.5 | 102.5 |  | 100 | Full Capacity | Off-Peak Deliverability | MERCED | CA | PGAE | Los Banos Substation 70kV | 2023-12-31 08:00 | 2023-12-31 08:00 | NA | Complete |  | NA |  | IC Request
TURON ENERGY STORAGE | 1727 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2020-06-25 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 71.45 | 70 | Full Capacity |  | FRESNO | CA | PGAE | Gates - Coalinga #2 Line 70kV | 2023-07-01 07:00 | 2023-07-01 07:00 | NA |  |  | NA |  | IC Request
ANACAPA | 1729 | 2020-04-03 | 2020-04-15 07:00 | WITHDRAWN | 2021-05-12 07:00 | C13 | Storage | Solar Thermal |  | Battery | Solar |  | 103.202 | 206.2 |  | 200 | Full Capacity | Off-Peak Deliverability | SANTA BARBARA | CA | PGAE | Sisquoc Substation 115kV | 2023-10-31 07:00 | 2023-10-31 07:00 | NA |  |  | NA |  | IC Request
AUSTIN ES | 1730 | 2019-10-15 | 2020-04-15 07:00 | WITHDRAWN | 2023-05-05 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 203.6 | 200 | Full Capacity |  | SAN LUIS OBISPO | CA | PGAE | Morro Bay Substation 230kV | 2024-12-01 08:00 | 2024-12-01 08:00 | NA | Complete | Complete | NA |  | IC Request
BLACK BEAR ENERGY STORAGE 1 | 1731 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2021-05-28 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 102 | 100 | Full Capacity | Off-Peak Deliverability | SAN LUIS OBISPO | CA | PGAE | Mesa Substation 115kV | 2023-02-01 08:00 | 2023-02-01 08:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
BLACK BEAR ENERGY STORAGE 2 | 1732 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2021-05-28 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 102 | 100 | Full Capacity | Off-Peak Deliverability | SAN LUIS OBISPO | CA | PGAE | Mesa Substation 230kV | 2023-02-01 08:00 | 2023-02-01 08:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
BLUFF TRAIL STORAGE | 1733 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2023-11-20 08:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 632.44 | 500 | Energy Only |  | SAN LUIS OBISPO | CA | PGAE | Mesa Substation 230kV | 2024-11-30 08:00 | 2027-08-10 07:00 | NA | Complete | Complete | NA | In Progress | Failure to Cure Deficiency
FREEBORN | 1734 | 2020-04-04 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-07 07:00 | C13 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 27.3 | 27 | Full Capacity | Off-Peak Deliverability | KERN | CA | PGAE | Midway-Taft 115kV line | 2023-12-30 08:00 | 2023-12-30 08:00 | NA |  |  | NA
HANSON ENERGY CENTER | 1735 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-21 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 30.8 | 30 | Full Capacity |  | SANTA BARBARA | CA | PGAE | Santa Maria Cogen Tap 115kV Line | 2023-07-01 07:00 | 2023-07-01 07:00 | NA |  |  | NA |  | IC Request
KAIROS HYBRID | 1737 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2021-05-06 07:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 179.4 | 359.352 |  | 350 | Full Capacity | Off-Peak Deliverability | KERN | CA | PGAE | Midway Substation 230kV | 2025-10-30 07:00 | 2025-10-30 07:00 | NA |  |  | NA |  | IC Request
LIGHTHOUSE WIND | 1738 | 2020-04-01 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-25 07:00 | C13 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 1456 | 1400 | Full Capacity | Off-Peak Deliverability | SAN LUIS OBISPO | CA | PGAE | Diablo Canyon Switching Station 500kV | 2027-03-01 08:00 | 2027-03-01 08:00 | NA |  |  | NA |  | IC Request
PECHO ENERGY STORAGE | 1739 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2025-01-30 08:00 | C13 | Storage | Other |  | Battery | Other |  | 108 | 520 |  | 500 | Partial Capacity | Off-Peak Deliverability | SAN LUIS OBISPO | CA | PGAE | Morro Bay 230 kV | 2023-06-01 07:00 | 2031-01-24 08:00 | NA | Complete | Complete | NA | Terminated | IC Request
ROBIN 2 | 1741 | 2020-04-08 | 2020-04-15 07:00 | WITHDRAWN | 2021-05-03 07:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 103.95 | 204.12 |  | 200 | Full Capacity | Off-Peak Deliverability | SAN LUIS OBISPO | CA | PGAE | Morro Bay Solar Sw Sta #2 230kV | 2023-12-01 08:00 | 2023-12-01 08:00 | NA | Complete |  | NA |  | IC Request
ROBIN 3 | 1742 | 2020-04-08 | 2020-04-15 07:00 | WITHDRAWN | 2021-04-02 07:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 79.2 | 155.925 |  | 150 | Full Capacity | Off-Peak Deliverability | SAN LUIS OBISPO | CA | PGAE | Temblor - San Luis Obispo 115kV line | 2023-12-01 08:00 | 2023-12-01 08:00 | NA |  |  | NA
SAGRARIO | 1743 | 2020-04-02 | 2020-04-15 07:00 | WITHDRAWN | 2021-04-12 07:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 51.401 | 103.456 |  | 100 | Full Capacity | Off-Peak Deliverability | KERN | CA | PGAE | Old River Substation 70kV | 2023-10-31 07:00 | 2023-10-31 07:00 | NA |  |  | NA |  | IC Request
VERBENA | 1746 | 2020-04-10 | 2020-04-15 07:00 | WITHDRAWN | 2021-04-13 07:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 123.5965 | 123.5965 |  | 120 | Full Capacity | Off-Peak Deliverability | KERN | CA | PGAE | Tupman Substation 115kV | 2023-12-01 08:00 | 2023-12-01 08:00 | NA |  |  | NA |  | IC Request
VINSON ENERGY | 1747 | 2020-04-08 | 2020-04-15 07:00 | WITHDRAWN | 2021-04-09 07:00 | C13 | Wind Turbine | Storage |  | Wind Turbine | Battery |  | 1568 | 319.35 |  | 1499.94 | Full Capacity | Off-Peak Deliverability | SAN LUIS OBISPO | CA | PGAE | Diablo-Gates 500kV line | 2027-04-13 07:00 | 2027-04-13 07:00 | NA |  |  | NA
WESTERN COAST WIND 1 | 1748 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-30 07:00 | C13 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 1021.125 | 1000 | Full Capacity | Off-Peak Deliverability | SAN LUIS OBISPO | CA | PGAE | Diablo Canyon - Morro Bay 230 kV and Diablo Canyon - Mesa 230 kV Lines | 2027-04-07 07:00 | 2027-04-07 07:00 | NA | Complete |  | NA |  | IC Request
WHALE ROCK ENERGY | 1749 | 2020-04-13 | 2020-04-15 07:00 | WITHDRAWN | 2025-06-16 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 75 | 299.65 | Energy Only | Off-Peak Deliverability | SAN LUIS OBISPO | CA | PGAE | Caliente 230 kV | 2024-12-31 08:00 | 2031-04-27 07:00 | NA | Complete | Complete | NA | In Progress | IC Request
ARIZONA A1 | 1752 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2021-05-03 07:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 1572.2 | 2072.52 |  | 2000 | Full Capacity | Off-Peak Deliverability | MARICOPA | AZ | DCRT | Delaney Substation 500kV | 2025-02-05 08:00 | 2025-02-05 08:00 | NA | Complete |  | NA |  | IC Request
LA PAZ | 1753 | 2020-04-02 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-18 07:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 526.68 | 415.96 |  | 500 | Full Capacity | Off-Peak Deliverability | MARICOPA | AZ | DCRT | Delaney - Colorado River 500kV line | 2024-12-01 08:00 | 2024-12-01 08:00 | NA |  |  | NA |  | IC Request
PAPAGO | 1754 | 2020-04-11 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-19 07:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 307.188 | 306.18 |  | 300 | Full Capacity | Off-Peak Deliverability | MARICOPA | AZ | DCRT | Delaney Substation 500kV | 2023-10-31 07:00 | 2023-10-31 07:00 | NA | Complete |  | NA |  | IC Request
AMETHYST SOLAR | 1755 | 2020-04-06 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-06 07:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 100 | 200 |  | 200 | Full Capacity | Off-Peak Deliverability | RIVERSIDE | CA | SCE | Colorado River Substation 230kV | 2023-12-01 08:00 | 2023-12-01 08:00 | NA |  |  | NA |  | IC Request
ASTRA | 1756 | 2020-04-09 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-23 07:00 | C13 | Storage | Wind Turbine | Photovoltaic | Battery | Wind Turbine | Solar | 205.92 | 207.2 | 206.59 | 200 | Full Capacity | Off-Peak Deliverability | RIVERSIDE | CA | SCE | BLYTHE SUBSTATION 161kV | 2024-12-15 08:00 | 2024-12-15 08:00 | NA |  |  | NA |  | IC Request
ETERNAL PUMPED STORAGE | 1759 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2023-12-21 08:00 | C13 | Storage | Storage |  | Pumped-Storage hydro | Battery |  | 1407 | 1400 |  | 1400 | Energy Only |  | RIVERSIDE | CA | SCE | Red Bluff Substation 500kV | 2026-12-01 08:00 | 2026-12-01 08:00 | NA | Complete | Complete | NA |  | Failure to Cure Deficiency
FORTUNA | 1760 | 2020-04-11 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-24 07:00 | C13 | Wind Turbine | Storage | Photovoltaic | Wind Turbine | Battery | Solar | 207.2 | 205.92 | 206.59 | 200 | Full Capacity | Off-Peak Deliverability | RIVERSIDE | CA | SCE | DEVERS SUBSTATION 220kV | 2024-12-15 08:00 | 2024-12-15 08:00 | NA | Complete |  | NA |  | IC Request
GRISEDALE STORAGE 1 | 1762 | 2020-04-13 | 2020-04-15 07:00 | WITHDRAWN | 2021-05-10 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 510 | 500 | Full Capacity | Off-Peak Deliverability | RIVERSIDE | CA | SCE | Devers Substation 230kV | 2022-11-15 08:00 | 2022-11-15 08:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
PORTA | 1763 | 2020-04-09 | 2020-04-15 07:00 | WITHDRAWN | 2025-11-20 08:00 | C13 | Storage | Photovoltaic | Wind Turbine | Battery | Solar | Wind Turbine | 204.16 | 203.76 | 207.2 | 200 | Energy Only | Off-Peak Deliverability | RIVERSIDE | CA | SCE | DEVERS SUBSTATION 220kV | 2024-12-15 08:00 | 2029-01-31 08:00 | NA | Complete | Complete | NA |  | IC Request
BULLDOG ENERGY STORAGE | 1765 | 2020-04-14 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-12 08:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 408.07 | 400 | Full Capacity |  | LOS ANGELES | CA | SCE | Rio Hondo Substation 220kV | 2023-06-01 07:00 | 2023-06-01 07:00 | NA |  |  | NA |  | IC Request
HAMMOCK STORAGE | 1767 | 2020-04-02 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-01 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 152.5 | 150 | Full Capacity |  | LOS ANGELES | CA | SCE | El Nido Substation 230kV | 2023-12-31 08:00 | 2023-12-31 08:00 | NA |  |  | NA |  | IC Request
SPEEDWAY ESS 2 | 1769 | 2020-04-07 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-06 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 300 | 300 | Full Capacity |  | LOS ANGELES | CA | SCE | Rio Hondo Substation 230kV | 2024-12-01 08:00 | 2024-12-01 08:00 | NA |  |  | NA |  | IC Request
SWAN ESS | 1770 | 2020-04-07 | 2020-04-15 07:00 | WITHDRAWN | 2021-04-26 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 300 | 300 | Full Capacity | Off-Peak Deliverability | SAN BERNARDINO | CA | SCE | Mira Loma Substation 230kV | 2025-12-01 08:00 | 2025-12-01 08:00 | NA | Complete |  | NA |  | IC Request
LEO WOLF ENERGY CENTER | 1771 | 2020-04-13 | 2020-04-15 07:00 | WITHDRAWN | 2020-09-08 07:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 508.56 | 508.56 |  | 500 | Full Capacity | Off-Peak Deliverability | SAN BERNARDINO | CA | SCE | Kramer Junction Substation 230kV | 2024-11-30 08:00 | 2024-11-30 08:00 | NA |  |  | NA
LUZEN SOLAR ENERGY CENTER | 1772 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2020-06-30 07:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 156.48 | 156.48 |  | 150 | Full Capacity | Off-Peak Deliverability | SAN BERNARDINO | CA | SCE | Kramer Junction Substation 115kV | 2022-11-30 08:00 | 2022-11-30 08:00 | NA |  |  | NA |  | IC Request
OXFORD | 1773 | 2020-04-14 | 2020-04-15 07:00 | WITHDRAWN | 2020-06-30 07:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 78.378 | 78.378 |  | 75 | Full Capacity | Off-Peak Deliverability | KERN | CA | SCE | Kramer-Inyokern-Randsburg #1 115kV line | 2023-12-31 08:00 | 2023-12-31 08:00 | NA |  |  | NA |  | IC Request
VENTOSO | 1776 | 2020-04-11 | 2020-04-15 07:00 | WITHDRAWN | 2025-11-14 08:00 | C13 | Wind Turbine | Photovoltaic | Storage | Wind Turbine | Solar | Battery | 212.18 | 206.59 | 204.16 | 200 | Energy Only | Off-Peak Deliverability | SAN BERNARDINO | CA | SCE | COOLWATER SUBSTATION 115kV | 2024-12-15 08:00 | 2027-10-01 07:00 | NA | Complete | Complete | NA | Executed | IC Request
ALLEGRO HYBRID SOLAR | 1777 | 2020-04-09 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-08 07:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 152.4 | 75 |  | 150 | Full Capacity | Off-Peak Deliverability | KERN | CA | SCE | Highwind Substation 220kV | 2023-11-30 08:00 | 2023-11-30 08:00 | NA |  |  | NA |  | IC Request
ALTA 20 WIND | 1778 | 2020-04-14 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-10 08:00 | C13 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 257.6 | 250 | Full Capacity | Off-Peak Deliverability | KERN | CA | SCE | Windhub Substation 230kV | 2023-10-15 07:00 | 2025-12-15 08:00 | NA | Complete |  | NA |  | IC Request
BOBCAT ENERGY STORAGE | 1780 | 2020-04-10 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-05 08:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 75 | 75 | Full Capacity |  | LOS ANGELES | CA | SCE | Antelope Substation 66kV | 2022-07-01 07:00 | 2022-07-01 07:00 | NA |  |  | NA |  | IC Request
CENTRAL COAST WIND 1 | 1781 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-07 07:00 | C13 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 771.75 | 750 | Full Capacity | Off-Peak Deliverability | SANTA BARBARA | CA | SCE | Goleta Substation 230kV | 2027-04-07 07:00 | 2027-04-07 07:00 | NA |  |  | NA |  | IC Request
KEYHOLE WIND 2 | 1785 | 2020-04-06 | 2020-04-15 07:00 | WITHDRAWN | 2020-06-25 07:00 | C13 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 100 | 100 | Full Capacity | Off-Peak Deliverability | KERN | CA | SCE | Whirlwind Substation 230kV | 2024-12-01 08:00 | 2024-12-01 08:00 | NA |  |  | NA |  | IC Request
LONGHORN 1 | 1786 | 2020-04-02 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-11 08:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 405.8 | 405.8 |  | 400 | Full Capacity | Off-Peak Deliverability | KERN | CA | SCE | Windhub Substation 230kV | 2024-09-30 07:00 | 2024-09-30 07:00 | NA |  |  | NA |  | IC Request
LYCKA SOLAR | 1787 | 2020-04-11 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-18 07:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 122.512 | 464.42 |  | 460 | Full Capacity | Off-Peak Deliverability | TULARE | CA | SCE | Springville Substation 230kV | 2024-04-15 07:00 | 2024-04-15 07:00 | NA | Complete |  | NA |  | IC Request
METEORITE SOLAR | 1788 | 2020-04-06 | 2020-04-15 07:00 | WITHDRAWN | 2021-04-26 07:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 400 | 200 |  | 400 | Full Capacity | Off-Peak Deliverability | KERN | CA | SCE | Whirlwind Substation 230 kV | 2024-12-01 08:00 | 2024-12-01 08:00 | NA | Complete |  | NA |  | IC Request
VALOREM | 1793 | 2020-04-11 | 2020-04-15 07:00 | WITHDRAWN | 2021-05-10 07:00 | C13 | Storage | Wind Turbine | Photovoltaic | Battery | Wind Turbine | Solar | 203.94 | 207.2 | 208.08 | 200 | Full Capacity | Off-Peak Deliverability | KERN | CA | SCE | HIGHWIND SUBSTATION 230kV | 2024-12-15 08:00 | 2024-12-15 08:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
VENADO VALLEY 1 | 1794 | 2020-04-02 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-12 08:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 305.2 | 305.2 |  | 300 | Full Capacity | Off-Peak Deliverability | ROSAMOND | CA | SCE | WhirlWind Substation 230kV | 2024-09-30 07:00 | 2024-09-30 07:00 | NA |  |  | NA |  | IC Request
BONANZA SOLAR 2 | 1797 | 2020-04-06 | 2020-04-15 07:00 | WITHDRAWN | 2021-04-26 07:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 300 | 150 |  | 300 | Full Capacity | Off-Peak Deliverability | CLARK/NYE | NV | GLW | Innovation Substation 230kV | 2024-12-01 08:00 | 2024-12-01 08:00 | NA | Complete |  | NA |  | IC Request
AMPCHAMP STORAGE | 1802 | 2020-04-02 | 2020-04-15 07:00 | WITHDRAWN | 2023-05-05 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20.8 | 20 | Energy Only |  | SAN DIEGO | CA | SDGE | Otay Substation 69 kV | 2023-12-31 08:00 | 2024-12-08 08:00 | NA | Complete | Complete | NA |  | IC Request
BLUEGILL STORAGE | 1803 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-09 08:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 81.375 | 80 | Full Capacity |  | SAN DIEGO | CA | SDGE | Loop Loveland - Los Coches 69kV line | 2025-10-30 07:00 | 2025-10-30 07:00 | NA |  |  | NA |  | IC Request
BOULDER OAKS HYBRID 2 | 1804 | 2020-04-13 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-10 08:00 | C13 | Wind Turbine | Storage |  | Wind Turbine | Battery |  | 205.8 | 205 |  | 400 | Full Capacity | Off-Peak Deliverability | SAN DIEGO | CA | SDGE | New Switchyard to loop the ECO-Miguel 500 kV Line | 2023-12-01 08:00 | 2023-12-01 08:00 | NA |  |  | NA |  | IC Request
BRADSHAW ENERGY STORAGE | 1805 | 2020-04-14 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-16 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 75 | 75 | Full Capacity |  | SAN DIEGO | CA | SDGE | Miramar-Scripps 69kV line | 2022-06-01 07:00 | 2022-06-01 07:00 | NA |  |  | NA |  | IC Request
CARROLL CANYON ENERGY STORAGE | 1807 | 2020-04-10 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-10 08:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 154.1405 | 150 | Full Capacity |  | SAN DIEGO | CA | SDGE | Eastgate Substation 69kV | 2023-10-15 07:00 | 2023-10-15 07:00 | NA |  |  | NA |  | IC Request
COASTWOOD ENERGY STORAGE | 1808 | 2020-04-14 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-15 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 101.9 | 101.1 | Full Capacity |  | SAN DIEGO | CA | SDGE | Shadowridge Substation 138kV | 2023-07-15 07:00 | 2023-07-15 07:00 | NA |  |  | NA |  | IC Request
CUCKOO ENERGY STORAGE | 1809 | 2020-04-14 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-03 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 30 | 30 | Full Capacity |  | SAN DIEGO | CA | SDGE | Borrego Substation 69kV | 2022-07-01 07:00 | 2022-07-01 07:00 | NA |  |  | NA |  | IC Request
DUCK PILOT STORAGE | 1811 | 2020-04-02 | 2020-04-15 07:00 | WITHDRAWN | 2023-04-20 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 101.9 | 100 | Full Capacity |  | SAN DIEGO | CA | SDGE | Los Coches Substation 138 kV | 2023-12-31 08:00 | 2024-12-08 08:00 | NA | Complete | Complete | NA | In Progress | IC Request
GYPSY ESS 2 | 1813 | 2020-04-07 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-06 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 300 | 300 | Full Capacity |  | SAN DIEGO | CA | SDGE | Bay Boulevard 230kV | 2024-12-01 08:00 | 2024-12-01 08:00 | NA |  |  | NA
HEDIONDA ENERGY STORAGE | 1814 | 2020-04-01 | 2020-04-15 07:00 | WITHDRAWN | 2025-04-17 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 160 | 160 | Energy Only |  | SAN DIEGO | CA |  | Encina Substation 138 kV | 2023-03-31 07:00 | 2024-02-08 08:00 | NA | Complete | Complete | NA |  | IC Request
HINTON ENERGY STORAGE | 1815 | 2020-03-31 | 2020-04-15 07:00 | WITHDRAWN | 2024-03-11 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 103.275 | 100 | Partial Capacity |  | SAN DIEGO | CA | SDGE | Creelman Substation 69 kV | 2023-06-01 07:00 | 2024-12-08 08:00 | NA | Complete | Complete | NA |  | Failure to Cure Deficiency
OTAY MESA ENERGY CENTER EXPANSION | 1816 | 2020-04-09 | 2020-04-15 07:00 | WITHDRAWN | 2021-03-17 07:00 | C13 | Generating Facility Type-1: Combined Cycle; Generating Facility Fuel-1: Natural Gas; MWs MW-1: 26.37 | 26.37 | Full Capacity |  | SAN DIEGO | CA | SDGE | Otay Mesa Substation 230kV | 2022-05-01 07:00 | 2022-05-01 07:00 | NA |  |  | NA |  | IC Request
POWWOW | 1817 | 2020-04-01 | 2020-04-15 07:00 | WITHDRAWN | 2021-05-10 07:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 33.5 | 202.23 |  | 200 | Full Capacity | Off-Peak Deliverability | SAN DIEGO | CA | SDGE | Oceanside Tap - Stuart Tap 69kV (TL690C ) | 2022-06-20 07:00 | 2022-06-20 07:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
SANYO AVE STORAGE 1 | 1819 | 2020-04-14 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-27 07:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 82.6 | 80 | Full Capacity |  | SAN DIEGO | CA | SDGE | Border-Salt Creek 69kV line | 2023-09-01 07:00 | 2023-09-01 07:00 | NA |  |  | NA |  | Failure to Cure Deficiency
SEGURO STORAGE | 1821 | 2020-04-15 | 2020-04-15 07:00 | WITHDRAWN | 2026-01-07 08:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 407 | 400 | Partial Capacity |  | SAN DIEGO | CA | SDGE | Escondido Substation 230 kV | 2025-10-30 07:00 | 2032-05-14 07:00 | NA | Complete | Complete | NA | Executed | IC Request
SUN STREAMS 4 | 1822 | 2020-04-02 | 2020-04-15 07:00 | WITHDRAWN | 2024-04-08 07:00 | C13 | Photovoltaic | Storage |  | Solar | Battery |  | 225.04 | 225.04 |  | 215 | Energy Only | Off-Peak Deliverability | MARICOPA | AZ | SDGE | Hassayampa Common Bus 500 kV | 2021-12-31 08:00 | 2024-06-01 07:00 | NA | Complete | Complete | NA |  | Failure to Cure Deficiency
SUN STREAMS 5 | 1823 | 2020-04-02 | 2020-04-15 07:00 | WITHDRAWN | 2024-06-10 07:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 473.76 | 473.76 |  | 450 | Energy Only | Off-Peak Deliverability | MARICOPA | AZ | SDGE | Hassayampa Common Bus 500 kV | 2023-06-30 07:00 | 2025-06-01 07:00 | NA | Complete | Complete | NA |  | IC Request
VIKING ENERGY STORAGE | 1825 | 2020-04-14 | 2020-04-15 07:00 | WITHDRAWN | 2024-01-10 08:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 101.9 | 101.1 | Energy Only |  | SAN DIEGO | CA | SDGE | Ocean Ranch Substation 69 kV | 2023-07-15 07:00 | 2024-11-09 08:00 | NA | Complete | Complete | NA |  | Failure to Cure Deficiency
VULCAN 2 | 1826 | 2020-04-02 | 2020-04-15 07:00 | WITHDRAWN | 2020-07-06 07:00 | C13 | Storage | Photovoltaic |  | Battery | Solar |  | 252.6 | 252.6 |  | 250 | Full Capacity | Off-Peak Deliverability | MARICOPA | AZ | SDGE | Hassayampa Switchyard Common Bus 500kV | 2024-09-30 07:00 | 2024-09-30 07:00 | NA |  |  | NA |  | IC Request
BIG HORN ENERGY STORAGE | 1827 | 2020-04-05 | 2020-04-15 07:00 | WITHDRAWN | 2024-02-21 08:00 | C13 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 425.1 | 400 | Full Capacity |  | IMPERIAL | CA | SDGE | Imperial Valley Substation 230kV | 2024-07-01 07:00 | 2024-07-01 07:00 | NA |  |  | NA |  | IC Request
WELLHEAD POWER PANOCHE, LLC | 1828 | 2019-12-24 | 2020-07-14 07:00 | WITHDRAWN | 2025-08-18 07:00 | FT | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 5 | 5 | Energy Only |  | FRESNO | CA | PGAE | Panoche 115 kV | 2021-04-01 07:00 | 2021-04-01 07:00 |  | NA | NA | NA |  | IC Request
OAKLAND ES UNIT 3 | 1830 | 2020-10-26 | 2020-12-21 08:00 | WITHDRAWN | 2023-12-05 08:00 | ISP | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 55.65 | 55 | Full Capacity |  | ALAMEDA | CA | PGAE | Oakland C Sub via Oakland C-Turbine 115 kV Line | 2022-05-01 07:00 | 2024-01-01 08:00 | NA | Complete | Complete | NA
MIDLAND ES | 1831 | 2020-12-08 | 2021-02-26 08:00 | WITHDRAWN | 2025-09-24 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 405.4 | 400 | Full Capacity |  | SAN LUIS OBISPO | CA | PGAE | Morro Bay 230 kV | 2024-11-01 07:00 | 2032-03-01 08:00 | NA | Complete | Complete | NA |  | Failure to Cure Deficiency
GOAL LINE RELIABILITY | 1832 | 2021-02-08 | 2021-04-15 07:00 | WITHDRAWN | 2024-07-08 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 51.375 | 50 | Full Capacity |  | SAN DIEGO | CA | SDGE | Escondido Substation 69 kV | 2023-05-30 07:00 | 2026-07-05 07:00 | NA | Complete | Complete | NA |  | IC Request
BLYTHE BESS | 1833 | 2021-02-25 | 2021-03-23 07:00 | WITHDRAWN | 2021-08-25 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 510.21 | 122.5 | Full Capacity |  | RIVERSIDE | CA | SCE | Julian Hinds Substation 230 kV | 2022-07-22 07:00 | 2022-07-22 07:00 | NA |  |  | NA |  | IC Request
BRIX ENERGY STORAGE | 1836 | 2021-03-22 | 2021-04-19 07:00 | WITHDRAWN | 2024-05-31 07:00 | ISP | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 213.55 | 200 | Energy Only |  | SONOMA | CA | PGAE | Fulton 115 kV | 2023-06-01 07:00 | 2027-06-01 07:00 | NA | Complete | Complete | NA | Terminated
TAMALPAIS ENERGY STORAGE | 1837 | 2021-04-03 | 2021-04-15 07:00 | WITHDRAWN | 2025-08-18 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 313.7932 | 300 | Full Capacity |  | MARIN | CA | PGAE | Ignacio 115 kV | 2025-06-01 07:00 | 2030-06-18 07:00 | NA | Complete | Complete | NA |  | Failure to Cure Deficiency
BOREALIS ENERGY STORAGE | 1838 | 2021-04-02 | 2021-04-15 07:00 | WITHDRAWN | 2025-08-18 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 313.7932 | 300 | Full Capacity |  | SONOMA | CA | PGAE | Lakeville 115 kV | 2025-06-01 07:00 | 2030-06-18 07:00 | NA | Complete | Complete | NA |  | Failure to Cure Deficiency
NEWTON | 1839 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2021-09-01 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 61.85 | 60 | Full Capacity | Off-Peak Deliverability | EL DORADO | CA | PGAE | Apple Hill Substation 115 kV | 2024-11-01 07:00 | 2024-11-01 07:00 | NA |  |  | NA |  | IC Request
GENOA ENERGY STORAGE | 1840 | 2021-04-07 | 2021-04-15 07:00 | WITHDRAWN | 2025-09-24 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 252 | 250 | Full Capacity |  | NAPA | CA | PGAE | Vaca-Lakeville #1 230 kV Line | 2024-08-01 07:00 | 2031-12-19 08:00 | NA | Complete | Complete | NA |  | Failure to Cure Deficiency
SCENIC ENERGY STORAGE | 1841 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-23 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 40.4 | 40 | Full Capacity |  | LAKE | CA | PGAE | Konocti Substation 60 kV | 2025-01-01 08:00 | 2025-01-01 08:00 | NA | Complete |  | NA |  | IC Request
KANOA SOLAR | 1844 | 2021-04-07 | 2021-04-15 07:00 | WITHDRAWN | 2024-11-26 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 159.418 | 160.3789 |  | 150 | Full Capacity | Off-Peak Deliverability | GLENN | CA | PGAE | Logan Creek-Delevan 230 kV Line | 2025-10-01 07:00 | 2031-03-20 07:00 | NA | Complete | Complete | NA |  | IC Request
NORTH BAY ENERGY STORAGE 2 | 1845 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2024-11-01 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 102.2112 | 100 | Full Capacity |  | SONOMA | CA | PGAE | Lakeville 60 kV | 2023-06-01 07:00 | 2028-04-17 07:00 | NA | Complete | Complete | NA
JUGLANS ENERGY STORAGE | 1847 | 2021-04-12 | 2021-04-15 07:00 | WITHDRAWN | 2025-08-06 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 710.6 | 700 | Full Capacity |  | SOLANO | CA | PGAE | Vaca-Dixon 500 kV | 2024-06-30 07:00 | 2031-02-02 08:00 | NA | Complete | Complete | NA |  | IC Request
MYRTLE | 1848 | 2021-04-12 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-14 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 26.784 | 189.3015 |  | 210 | Full Capacity | Off-Peak Deliverability | SONOMA | CA | PGAE | Santa Rosa-Corona 115 kV line | 2025-10-30 07:00 | 2025-10-30 07:00 | NA | Complete |  | NA
SUNRIDGE STORAGE | 1849 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-16 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 213.8451 | 200 | Full Capacity | Off-Peak Deliverability | SACRAMENTO | CA | PGAE | Gold Hill-Eight Mile Road 230 kV | 2026-12-31 08:00 | 2026-12-31 08:00 | NA | None |  | NA |  | IC Request
BLUE BIRD | 1851 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-09 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 110.84 | 120.62 |  | 100 | Full Capacity | Off-Peak Deliverability | SUTTER | CA | PGAE | Rio Oso Substation 115 kV | 2024-11-30 08:00 | 2024-11-30 08:00 | NA | Complete |  | NA |  | IC Request
BULL RUN | 1852 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2024-07-24 07:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 225 | 232.1 |  | 225 | Full Capacity |  | BUTTE | CA | PGAE | Table Mountain 115 kV | 2024-12-31 08:00 | 2030-12-03 08:00 | NA | Complete | Complete | NA |  | IC Request
BULL RUN 2 ES | 1853 | 2021-04-12 | 2021-04-15 07:00 | WITHDRAWN | 2024-07-24 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 205.1 | 200 | Full Capacity |  | BUTTE | CA | PGAE | Table Mountain 115 kV | 2024-12-31 08:00 | 2030-12-03 08:00 | NA | Complete | Complete | NA |  | IC Request
TRES RIOS ENERGY CENTER | 1855 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-16 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 90.304 | 165.3 |  | 250 | Full Capacity | Off-Peak Deliverability | YUBA | CA | PGAE | Table Mtn-Rio Oso 230 kV | 2025-03-01 08:00 | 2025-03-01 08:00 | NA | Complete |  | NA
BLITZ ENERGY STORAGE | 1857 | 2021-04-15 | 2021-04-15 07:00 | WITHDRAWN | 2024-12-05 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 213.55 | 200 | Full Capacity |  | SONOMA | CA | PGAE | Fulton 115 kV | 2023-06-01 07:00 | 2029-10-04 07:00 | NA | Complete | Complete | NA |  | IC Request
GRINDSTONE CREEK SOLAR | 1858 | 2021-04-15 | 2021-04-15 07:00 | WITHDRAWN | 2025-08-28 07:00 | C14 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 142.85 | 140 | Full Capacity | Off-Peak Deliverability | TEHAMA | CA | PGAE | Cottonwood-Delevan #1 and #2 230 kV | 2024-08-31 07:00 | 2031-07-19 07:00 | NA | Complete | Complete | NA |  | IC Request
MEADOW RIDGE SOLAR AND BATTERY | 1860 | 2021-04-16 | 2021-04-15 07:00 | WITHDRAWN | 2024-05-03 07:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 93.5 | 19.992 |  | 75 | Full Capacity | Off-Peak Deliverability | SHASTA | CA | PGAE | Pit 1-Cottonwood 230 kV Line | 2024-12-31 08:00 | 2034-02-01 08:00 | NA | Complete |  | NA
OSITO ENERGY | 1861 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-29 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 306.55 | 306.55 |  | 300 | Full Capacity | Off-Peak Deliverability | PLACER | CA | PGAE | Rio Oso-Atlantic 230 kV/Rio Oso-Gold Hill 230 kV | 2024-09-01 07:00 | 2024-09-01 07:00 | NA | Complete |  | NA |  | IC Request
VERBENA ENERGY STORAGE | 1862 | 2021-04-15 | 2021-04-15 07:00 | WITHDRAWN | 2026-02-13 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 50.5 | 49.2 | Full Capacity |  | SUTTER | CA | PGAE | at Switch 125 outside Harter Sub | 2023-12-31 08:00 | 2028-03-01 08:00 | NA | Complete | Complete | NA |  | IC Request
STONY CREEK STORAGE | 1863 | 2021-04-15 | 2021-04-15 07:00 | WITHDRAWN | 2025-08-28 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 251.9 | 250 | Full Capacity | Off-Peak Deliverability | TEHAMA | CA | PGAE | Cottonwood-Delevan #1 and #2 230 kV | 2024-08-31 07:00 | 2031-07-19 07:00 | NA | Complete | Complete | NA |  | IC Request
VELAS | 1867 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2025-08-01 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 462.57 | 450 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Schulte 115 kV | 2024-11-01 07:00 | 2031-08-18 07:00 | NA | Complete | Complete | NA |  | IC Request
COPERNICUS | 1868 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-08 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 153.1 | 152.8 |  | 150 | Full Capacity | Off-Peak Deliverability | TBD | CA | PGAE | Coburn Substation 230 kV | 2024-11-01 07:00 | 2024-11-01 07:00 | NA | Complete |  | NA |  | IC Request
FIFE | 1869 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-11 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 101.6226 | 100 | Full Capacity |  | ALAMEDA | CA | PGAE | Grant - Eastshore #2 line 115 kV | 2024-06-30 07:00 | 2024-06-30 07:00 | NA |  |  | NA |  | IC Request
BALSAM | 1870 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-11 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 150 | 153.5 |  | 150 | Full Capacity | Off-Peak Deliverability | ALAMEDA COUNTY | CA | PGAE | Grant - Eastshore #2 115 kV line | 2024-06-30 07:00 | 2024-06-30 07:00 | NA |  |  | NA |  | IC Request
STAGELINE ENERGY STORAGE | 1871 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2026-01-14 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 213.55 | 200 | Full Capacity |  | BUTTE | CA | PGAE | Palermo 115 kV | 2024-06-01 07:00 | 2030-11-18 08:00 | NA | Complete | Complete | NA |  | IC Request
BEOWULF ENERGY STORAGE | 1873 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2024-07-02 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 95.8 | 95 | Full Capacity |  | SANTA CLARA | CA | PGAE | Evergreen 115 kV | 2024-08-01 07:00 | 2034-03-19 07:00 | NA | Complete | Complete | NA |  | IC Request
COMMANDER ENERGY STORAGE | 1874 | 2021-04-07 | 2021-04-15 07:00 | WITHDRAWN | 2025-08-04 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 504 | 500 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Pittsburg 230 kV | 2024-08-01 07:00 | 2032-07-19 07:00 | NA | Complete | Complete | NA |  | IC Request
JAGUAR ENERGY STORAGE | 1877 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2025-08-04 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 252 | 250 | Full Capacity |  | ALAMEDA | CA | PGAE | Grant-Eastshore #1 115 kV Line | 2024-08-01 07:00 | 2034-01-18 08:00 | NA | Complete | Complete | NA |  | IC Request
LANYARD ENERGY STORAGE | 1878 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-06 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 201.6 | 200 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Pittsburg-Kirker-Columbia Steel 115kV Line | 2024-08-01 07:00 | 2024-08-01 07:00 | NA | Complete |  | NA |  | IC Request
MOONSTONE ENERGY STORAGE | 1879 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-06 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 504 | 500 | Full Capacity |  | ALAMEDA | CA | PGAE | Tassajara - Newark 230 kV | 2024-08-01 07:00 | 2024-08-01 07:00 | NA | Complete |  | NA |  | IC Request
LACUNA ENERGY STORAGE | 1882 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-02 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 226.8 | 225 | Full Capacity |  | ALAMEDA | CA | PGAE | Dumbarton-Newark 115 kV line | 2024-08-01 07:00 | 2024-08-01 07:00 | NA | Complete |  | NA |  | IC Request
BLUE OAK STORAGE | 1883 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-06 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 615.6 | 600 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Tesla-Tracy #1 230 kV line | 2025-10-30 07:00 | 2025-10-30 07:00 | NA | Complete |  | NA
ZIETZ STORAGE | 1884 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-09 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 105.7884 | 100 | Full Capacity |  | SANTA CLARA | CA | PGAE | Llagas Substation 115 kV | 2025-10-01 07:00 | 2025-10-01 07:00 | NA |  |  | NA |  | IC Request
LENNY STORAGE | 1885 | 2021-04-07 | 2021-04-15 07:00 | WITHDRAWN | 2021-09-28 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 159.2303 | 150 | Full Capacity | Off-Peak Deliverability | ALAMEDA | CA | PGAE | Newark Substation 230 kV | 2025-10-01 07:00 | 2025-10-01 07:00 | NA |  |  | NA
HADSELVILLE | 1886 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-18 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 407.42 | 408.4 |  | 400 | Full Capacity | Off-Peak Deliverability | STANISLAUS | CA | PGAE | Bellota-Warnerville and Bellota Cottle Lines 230 kV | 2025-06-01 07:00 | 2025-06-01 07:00 | NA | Complete |  | NA |  | IC Request
DOLORES | 1888 | 2021-04-07 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-18 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 509.8 | 500 | Full Capacity |  | SAN CLARA | CA | PGAE | Los Esteros Substation 230 kV | 2025-06-01 07:00 | 2025-06-01 07:00 | NA | Complete |  | NA |  | IC Request
HALIFAX | 1890 | 2021-04-07 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-04 07:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 50.8 | 101.72 |  | 100 | Full Capacity | Off-Peak Deliverability | CONTRA COSTA | CA | PGAE | Herdlyn-Balfour 60kV line | 2024-12-15 08:00 | 2024-12-15 08:00 | NA | None |  | NA
HARMONY STORAGE 1 | 1891 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-14 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 165.048 | 160 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Fibreboard tap 115 kV | 2025-10-30 07:00 | 2025-10-30 07:00 | NA | Complete |  | NA
HEMMINGS STORAGE | 1893 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-09 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 105.8348 | 100 | Full Capacity |  | SANTA CLARA | CA | PGAE | Piercy Substation 115 kV | 2025-10-01 07:00 | 2025-10-01 07:00 | NA | Complete |  | NA |  | IC Request
ADA ENERGY STORAGE | 1894 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2024-07-02 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 505.2 | 500 | Full Capacity |  | SANTA CLARA | CA | PGAE | Monta Vista 230 kV | 2024-08-01 07:00 | 2034-03-19 07:00 | NA | Complete | Complete | NA |  | IC Request
SODIS STORAGE | 1897 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-18 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 112.4 | 110 | Full Capacity |  | STANISLAUS | CA | PGAE | Crows Landing Substation 60 kV | 2024-12-15 08:00 | 2024-12-15 08:00 | NA | None |  | NA |  | IC Request
NIGHTSHADE | 1898 | 2021-04-02 | 2021-04-15 07:00 | WITHDRAWN | 2024-04-09 07:00 | C14 | Gas Turbine | Storage |  | Natural Gas | Battery |  | 9.4 | 27 |  | 34.1 | Full Capacity | Off-Peak Deliverability | CONTRA COSTA | CA | PGAE | Kelso 230 kV | 2027-03-31 07:00 | 2027-03-31 07:00 | NA | Complete |  | NA
STONEMAN | 1899 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-12 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 224.986 | 220 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Pittsburg Substation 230 kV | 2024-11-01 07:00 | 2024-11-01 07:00 | NA | Complete |  | NA |  | IC Request
TIMBER ENERGY STORAGE | 1901 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-17 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 213.55 | 200 | Full Capacity |  | PLACER | CA | PGAE | Atlantic Substation 230 kV | 2024-06-01 07:00 | 2024-06-01 07:00 | NA | Complete |  | NA |  | IC Request
TOLEDO STORAGE | 1902 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-09 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 213.1488 | 200 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Contra Costa Substation 230 kV | 2025-10-01 07:00 | 2025-10-01 07:00 | NA | Complete |  | NA |  | IC Request
ADRIAN STORAGE | 1905 | 2021-04-13 | 2021-04-15 07:00 | WITHDRAWN | 2024-07-02 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 55.5 | 41.1 | Full Capacity |  | SAN MATEO | CA | PGAE | Millbrae 60 kV | 2025-07-01 07:00 | 2031-10-18 07:00 | NA | Complete | Complete | NA |  | IC Request
ALVISO ENERGY STORAGE | 1906 | 2021-04-15 | 2021-04-15 07:00 | WITHDRAWN | 2024-06-28 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 256.29 | 250 | Full Capacity |  | SANTA CLARA | CA | PGAE | Los Esteros 230 kV | 2025-06-01 07:00 | 2032-12-18 08:00 | NA | Complete | Complete | NA |  | IC Request
CROW CREEK BATTERY 1 | 1907 | 2021-04-07 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-02 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 21.8295 | 0 | Full Capacity |  | STANISLAUS | CA | PGAE | Crow Creek Switching Station 60 kV | 2024-05-01 07:00 | 2024-05-01 07:00 | NA | None |  | NA |  | IC Request
RUBY ENERGY STORAGE | 1908 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-12 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 151.2 | 150 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Sobrante - Standard Oil Switching Stn #1 115 kV Line | 2024-08-01 07:00 | 2024-08-01 07:00 | NA | Complete |  | NA |  | IC Request
STOMPER STORAGE | 1909 | 2021-04-10 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-09 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 151.2 | 150 | Full Capacity |  | ALAMEDA | CA | PGAE | Oakland J - Grant 115 kV line | 2024-10-31 07:00 | 2024-10-31 07:00 | NA | Complete |  | NA
STARBURST STORAGE | 1910 | 2021-04-13 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-01 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 40.36 | 40 | Full Capacity |  | SAN MATEO | CA | PGAE | Dixon Landing - McKee 115 kV line | 2025-07-01 07:00 | 2025-07-01 07:00 | NA | Complete |  | NA
OVERLAKE STORAGE | 1913 | 2021-04-13 | 2021-04-15 07:00 | WITHDRAWN | 2024-07-02 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 62.6 | 46.5 | Full Capacity |  | ALAMEDA | CA | PGAE | Dumbarton-Newark 115 kV Line | 2025-07-01 07:00 | 2034-02-18 08:00 | NA | Complete | Complete | NA |  | IC Request
STIRLING BRIDGE | 1916 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2024-03-27 07:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 257.35 | 250 |  | 250 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Bellota 115 kV | 2024-12-31 08:00 | 2031-03-03 08:00 | NA | Complete | Complete | NA |  | IC Request
STIRLING BRIDGE 2 ES | 1917 | 2021-04-12 | 2021-04-15 07:00 | WITHDRAWN | 2024-03-27 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 102.6 | 100 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Bellota 115 kV | 2024-12-31 08:00 | 2031-03-03 08:00 | NA | Complete | Complete | NA |  | IC Request
EMPEROR STORAGE | 1923 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-04 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 152.2 | 150 | Full Capacity |  | SANTA CLARA | CA | PGAE | FMC Substation 115 kV | 2024-12-15 08:00 | 2024-12-15 08:00 | NA | Complete |  | NA |  | IC Request
EPPS STORAGE | 1924 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2024-03-25 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 305 | 300 | Full Capacity |  | CONTRA COSTA | CA | PGAE | Moraga 230 kV | 2023-12-15 08:00 | 2026-03-31 07:00 | NA | Complete |  | NA |  | IC Request
ESTANISLAU SOLAR STORAGE | 1925 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-29 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 407.85 | 407.85 |  | 400 | Full Capacity | Off-Peak Deliverability | SAN JOAQUIN | CA | PGAE | Bellota-Warnerville 230 kV | 2024-09-01 07:00 | 2024-09-01 07:00 | NA | Complete |  | NA |  | IC Request
VALLEY GREEN | 1926 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-10 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 204.07 | 200 | Full Capacity |  | SANTA CRUZ | CA | PGAE | Green Valley Substation 115 kV | 2024-09-01 07:00 | 2024-09-01 07:00 | NA | Complete |  | NA |  | IC Request
BOA VISTA STORAGE | 1927 | 2021-04-15 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-18 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Other; MWs MW-1: 108.7 | 101.5 | Full Capacity |  | SAN BENITO | CA | PGAE | San Benito - Hollister 115kV line | 2025-12-15 08:00 | 2025-12-15 08:00 | NA | Complete |  | NA
CAZADORES STORAGE | 1929 | 2021-04-10 | 2021-04-15 07:00 | WITHDRAWN | 2025-08-04 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 151.3 | 150 | Full Capacity |  | SAN JOAQUIN | CA | PGAE | Lammers 115 kV | 2024-10-31 07:00 | 2032-08-19 07:00 | NA | Complete | Complete | NA |  | IC Request
BULLDOG STORAGE | 1931 | 2021-03-24 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-19 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 178.192 | 175 | Full Capacity |  | FRESNO | CA | PGAE | West Fresno Substation 115 kV | 2025-06-01 07:00 | 2025-06-01 07:00 | NA | None |  | NA
THREE ROCKS | 1936 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-15 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 439.084 | 439.084 |  | 425 | Full Capacity | Off-Peak Deliverability | TBD | CA | PGAE | Helm Substation 230 kV | 2024-11-01 07:00 | 2024-11-01 07:00 | NA | Complete |  | NA |  | IC Request
MARNIER | 1937 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-12 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 154.362 | 154.362 |  | 150 | Full Capacity | Off-Peak Deliverability | MERCED | CA | PGAE | Le Grand Substation 115 kV | 2024-11-01 07:00 | 2024-11-01 07:00 | NA | Complete |  | NA |  | IC Request
BOBCAT | 1938 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2021-08-17 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 178.881 | 175 | Full Capacity | Off-Peak Deliverability | TBD | CA | PGAE | El Capitan Substation 115 kV | 2024-11-01 07:00 | 2024-11-01 07:00 | NA |  |  | NA |  | IC Request
MUSCAT | 1939 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-15 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 772.245 | 750 | Full Capacity |  | TBD | CA | PGAE | McCall Substation 230 kV | 2024-11-01 07:00 | 2024-11-01 07:00 | NA | Complete |  | NA |  | IC Request
WHITE RABBIT | 1940 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2025-04-09 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 150 | 150 | Energy Only | Off-Peak Deliverability | FRESNO | CA | PGAE | Mendota 115 kV | 2024-11-01 07:00 | 2030-07-18 07:00 | NA | Complete | Complete | NA | Executed | IC Request
DAHLIA SOLAR | 1941 | 2021-04-03 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-23 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 204.8 | 204.8 |  | 200 | Full Capacity | Off-Peak Deliverability | KINGS | CA | PGAE | Helm Substation 230 kV | 2026-06-01 07:00 | 2026-06-01 07:00 | NA | Complete |  | NA
NORTHLINE | 1942 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-15 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 105.735 | 105.735 |  | 100 | Full Capacity | Off-Peak Deliverability | MERCED COUNTY | CA | PGAE | Los Banos-Livingston-Canal 70 kV Line | 2024-06-30 07:00 | 2024-06-30 07:00 | NA |  |  | NA |  | IC Request
WINGTIP SOLAR 2 | 1944 | 2021-04-02 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-30 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 561.5 | 561.5 |  | 550 | Full Capacity | Off-Peak Deliverability | MERCED | CA | PGAE | Los Banos Substation 500 kV | 2027-06-01 07:00 | 2027-06-01 07:00 | NA | Complete |  | NA
MENILLES | 1945 | 2021-04-05 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-15 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 255.5 | 255.5 |  | 250 | Full Capacity | Off-Peak Deliverability | FRESNO COUNTY | CA | PGAE | Panoche - Tranquility #1 230 kV line | 2024-06-30 07:00 | 2024-06-30 07:00 | NA |  |  | NA |  | IC Request
ELBRUS ENERGY STORAGE | 1946 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-30 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 101.1 | 100 | Full Capacity |  | MERCED | CA | PGAE | Le Grand Substation 115 kV | 2025-01-01 08:00 | 2025-01-01 08:00 | NA | Complete |  | NA |  | IC Request
HEKLA ENERGY STORAGE | 1947 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-13 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 100.93 | 100 | Full Capacity |  | FRESNO | CA | PGAE | Huron Substation 70 kV | 2025-01-01 08:00 | 2025-01-01 08:00 | NA | Complete |  | NA |  | IC Request
TRIVOR ENERGY STORAGE | 1948 | 2021-04-05 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-13 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 151.42 | 150 | Full Capacity |  | MERCED | CA | PGAE | El Nido Substation 115 kV | 2025-01-01 08:00 | 2025-01-01 08:00 | NA | Complete |  | NA |  | IC Request
EE K BATTERY 1 | 1950 | 2021-04-07 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-02 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 20.4 | 0 | Full Capacity |  | KINGS | CA | PGAE | Kent Sw Sta-Tulare Lake 70 kV | 2024-05-01 07:00 | 2024-05-01 07:00 | NA | Complete |  | NA |  | IC Request
EXCELSIOR BATTERY 1 | 1951 | 2021-04-07 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-02 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 62.37 | 0 | Full Capacity |  | FRESNO | CA | PGAE | Excelsior Switching Station 115 kV | 2024-05-01 07:00 | 2024-05-01 07:00 | NA | Complete |  | NA |  | IC Request
SOLITUDE HYBRID | 1957 | 2021-04-12 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-23 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 116.233 | 115.745 |  | 114.9992 | Full Capacity | Off-Peak Deliverability | FRESNO | CA | PGAE | Panoche Substation 230 kV | 2024-06-16 07:00 | 2024-06-16 07:00 | NA | Complete |  | NA
LAS CAMAS 4 | 1960 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2025-09-04 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 100 | 100 | Full Capacity |  | MERCED | CA | PGAE | Los Banos 230 kV | 2025-05-07 07:00 | 2028-04-01 07:00 | NA | Complete | Complete | NA |  | IC Request
OLIVOS | 1961 | 2021-04-03 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-15 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 360.198 | 350 | Full Capacity |  | TBD | CA | PGAE | Gregg Substation 230 kV | 2024-11-01 07:00 | 2024-11-01 07:00 | NA |  |  | NA |  | IC Request
ALBACORE ESS | 1964 | 2021-04-13 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-23 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 70.88 | 70 | Full Capacity |  | KINGS | CA | PGAE | Guernsey - Henrietta 70kV line | 2024-11-30 08:00 | 2024-11-30 08:00 | NA | Complete |  | NA
NORMANDY | 1965 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-28 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 61.8 | 60 |  | 60 | Full Capacity |  | KINGS | CA | PGAE | Guernsey Substation 70 kV | 2024-12-31 08:00 | 2024-12-31 08:00 | NA | Complete |  | NA |  | IC Request
NORTE VISTA | 1967 | 2021-04-15 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-28 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 192.73 | 192.73 |  | 189.91 | Full Capacity | Off-Peak Deliverability | FRESNO | CA | PGAE | Gates Substation 230 kV | 2024-07-31 07:00 | 2024-07-31 07:00 | NA | Complete |  | NA |  | IC Request
YORKTOWN | 1969 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2024-07-24 07:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 87.5 | 87.5 |  | 85 | Full Capacity |  | KINGS | CA | PGAE | Corcoran 70 kV | 2024-12-31 08:00 | 2029-12-03 08:00 | NA | Complete | Complete | NA |  | IC Request
BUTTERCUP HYBRID SOLAR | 1970 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2026-03-24 07:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 131.43 | 65.47 |  | 130 | Full Capacity | Off-Peak Deliverability | MERCED | CA | PGAE | Le Grand 115 kV | 2024-11-30 08:00 | 2032-03-04 08:00 | NA | Complete | Complete | NA |  | IC Request
STORYBOOK | 1971 | 2021-04-13 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-18 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 204.07 | 200 | Full Capacity |  | FRESNO | CA | PGAE | Kearney Substation 230 kV | 2024-09-01 07:00 | 2024-09-01 07:00 | NA | Complete |  | NA |  | IC Request
KRATOS BESS | 1972 | 2021-04-15 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-21 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 213.55 | 200 | Full Capacity |  | KINGS | CA | PGAE | Panoche Substation 115 kV | 2024-06-01 07:00 | 2024-06-01 07:00 | NA | Complete |  | NA |  | IC Request
SWEETBRIER HYBRID SOLAR | 1974 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2023-08-29 07:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 60.6 | 30.22 |  | 60 | Full Capacity | Off-Peak Deliverability | MONTEREY | CA | PGAE | California Flats Switching Station 230 kV | 2024-11-30 08:00 | 2024-11-30 08:00 | NA | Complete |  | NA |  | IC Request
TAVA FLATS | 1976 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-18 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 202.5 | 202.5 |  | 200 | Full Capacity | Off-Peak Deliverability | FRESNO | CA | PGAE | Gates Substation 230 kV | 2024-09-30 07:00 | 2024-09-30 07:00 | NA | Complete |  | NA |  | IC Request
ESTRADA STORAGE | 1978 | 2021-03-24 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-19 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 101.9 | 100 | Full Capacity |  | KERN | CA | PGAE | Lamont Substation 115 kV | 2025-06-01 07:00 | 2025-06-01 07:00 | NA | None |  | NA
APPELLATION | 1979 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-07 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 514.83 | 500 | Full Capacity |  | TBD | CA | PGAE | Templeton Substation 230 kV | 2024-11-01 07:00 | 2024-11-01 07:00 | NA | Complete |  | NA |  | IC Request
AIRFIELD | 1981 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-02 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 102.3049 | 101.7915 |  | 100 | Full Capacity | Off-Peak Deliverability | KERN | CA | PGAE | Semitropic - Midway #1 115 kV | 2024-12-31 08:00 | 2024-12-31 08:00 | NA |  |  | NA |  | IC Request
RESPIRE | 1982 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-02 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 101.7635 | 102.254 |  | 100 | Full Capacity | Off-Peak Deliverability | KERN | CA | PGAE | MIDWAY-TUPMAN-RIO BRAVO-RENFRO 115 kV | 2024-12-31 08:00 | 2024-12-31 08:00 | NA |  |  | NA |  | IC Request
HOG ISLAND | 1984 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-02 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 153.54 | 153.54 |  | 150 | Full Capacity | Off-Peak Deliverability | TULARE COUNTY | CA | PGAE | Olive Switch Station - Smyrna 115 kV line | 2024-06-30 07:00 | 2024-06-30 07:00 | NA |  |  | NA |  | IC Request
FINKE RIVER | 1985 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-02 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 150 | 153.5 |  | 150 | Full Capacity | Off-Peak Deliverability | KERN COUNTY | CA | PGAE | Kern - Old River #1 70 kV line | 2024-06-30 07:00 | 2024-06-30 07:00 | NA |  |  | NA |  | IC Request
ROWAN | 1986 | 2021-03-25 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-02 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 101.7808 | 102.2971 |  | 100 | Full Capacity | Off-Peak Deliverability | KERN | CA | PGAE | Symrna-Semitropic-Midway 115 kV Line | 2024-12-31 08:00 | 2024-12-31 08:00 | NA |  |  | NA |  | IC Request
THUNDER | 1988 | 2021-04-02 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-17 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 101.781 | 102.2885 |  | 100 | Full Capacity | Off-Peak Deliverability | KERN | CA | PGAE | Lamont Substation 115 kV | 2024-12-31 08:00 | 2028-04-11 07:00 | NA | Complete |  | NA |  | IC Request
ROSEBOWL | 1989 | 2021-04-05 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-16 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 151.6 | 150 | Full Capacity |  | KERN COUNTY | CA | PGAE | Kern PP Substation 115KV | 2024-06-30 07:00 | 2024-06-30 07:00 | NA |  |  | NA |  | IC Request
SHEATH STORAGE | 1990 | 2021-04-05 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-16 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 101 | 100 | Full Capacity |  | KERN COUNTY | CA | PGAE | Midway Substation 230 kV | 2024-06-30 07:00 | 2024-06-30 07:00 | NA |  |  | NA |  | IC Request
SALIX | 1991 | 2021-04-05 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-16 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 100 | 102.1 |  | 100 | Full Capacity | Off-Peak Deliverability | KERN COUNTY | CA | PGAE | Midway Substation 230 kV | 2024-06-30 07:00 | 2024-06-30 07:00 | NA |  |  | NA |  | IC Request
CALLINAN SOLAR AND STORAGE | 1992 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2025-08-01 07:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 159.4008 | 160.3879 |  | 150 | Full Capacity | Off-Peak Deliverability | KERN | CA | PGAE | Arco 230 kV | 2025-10-01 07:00 | 2031-02-18 08:00 | NA | Complete | Complete | NA |  | IC Request
AURUM MINE | 1993 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-16 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 101.6291 | 100 | Full Capacity |  | KERN | CA | PGAE | Bear Mountain - Bear Mountain Tap 115 kV line | 2024-06-30 07:00 | 2024-06-30 07:00 | NA |  |  | NA |  | IC Request
BRECKENRIDGE | 1996 | 2021-04-07 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-17 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 76.5 | 75 | Full Capacity |  | KERN | CA | PGAE | Lamont Substation 115 kV | 2025-06-01 07:00 | 2025-06-01 07:00 | NA | Complete |  | NA |  | IC Request
HIGH PLAINS STORAGE | 1997 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-18 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 406.142 | 400 | Full Capacity |  | SAN LUIS OBISPO | CA | PGAE | Caliente Switching Station 230 kV | 2024-04-01 07:00 | 2024-04-01 07:00 | NA | Complete |  | NA |  | IC Request
ISLAY | 1998 | 2021-04-07 | 2021-04-15 07:00 | WITHDRAWN | 2025-08-18 07:00 | C14 | Storage | Wind Turbine |  | Battery | Wind Turbine |  | 756.054 | 1518.472 |  | 1500 | Full Capacity | Off-Peak Deliverability | SAN LUIS OBISPO | CA | PGAE | Diablo Canyon 500 kV | 2028-04-01 07:00 | 2034-08-16 07:00 | NA | Complete | Complete | NA |  | Failure to Cure Deficiency
LEGACY | 1999 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-07 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 101.72 | 52.9 |  | 98 | Full Capacity | Off-Peak Deliverability | KERN | CA | PGAE | Wheeler Ridge-Tejon 70 kV Line | 2024-12-15 08:00 | 2024-12-15 08:00 | NA | Complete |  | NA
FLYWAY SOLAR | 2000 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-14 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 113.325 | 113.325 |  | 110 | Full Capacity | Off-Peak Deliverability | KERN | CA | PGAE | Berrenda "C" Tap 70 kV | 2024-10-30 07:00 | 2024-10-30 07:00 | NA | Complete |  | NA
FOUNTAIN HYBRID | 2002 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-05 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 196.56 | 196.56 |  | 140 | Full Capacity | Off-Peak Deliverability | TULARE | CA | PGAE | Alpaugh Substation 115 kV | 2025-10-30 07:00 | 2025-10-30 07:00 | NA |  |  | NA
BUCKAROO SOLAR STORAGE | 2003 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-29 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 102.2814 | 103.1744 |  | 100 | Full Capacity | Off-Peak Deliverability | KERN | CA | PGAE | Kern - Old River #2 70 kV | 2024-06-01 07:00 | 2024-06-01 07:00 | NA |  |  | NA |  | IC Request
EUROPA ENERGY CENTER | 2005 | 2021-04-07 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-07 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 307.1 | 300 |  | 300 | Full Capacity | Off-Peak Deliverability | KERN | CA | PGAE | Gates - Midway 230 KV Line | 2025-06-01 07:00 | 2025-06-01 07:00 | NA | None |  | NA
CALLOWAY BESS | 2006 | 2021-04-12 | 2021-04-15 07:00 | WITHDRAWN | 2024-12-13 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 92.07 | 82.9 | Full Capacity |  | KERN | CA | PGAE | 7th Standard 115 kV | 2024-06-01 07:00 | 2029-09-16 07:00 | NA | Complete | Complete | NA |  | IC Request
WATER CANYON WIND | 2007 | 2021-04-02 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-12 08:00 | C14 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 1028.94 | 1000 | Full Capacity | Off-Peak Deliverability | SAN LUIS OBISPO | CA | PGAE | Diablo Canyon Switching Station 500 kV | 2028-03-31 07:00 | 2028-03-31 07:00 | NA | Complete |  | NA
SALINAN ENERGY | 2008 | 2021-04-11 | 2021-04-15 07:00 | WITHDRAWN | 2025-05-13 07:00 | C14 | Wind Turbine | Storage |  | Wind Turbine | Battery |  | 1190 | 319.35 |  | 1148.37 | Full Capacity | Off-Peak Deliverability | SAN LUIS OBISPO | CA | PGAE | Diablo-Gates 500 kV Line | 2028-04-11 07:00 | 2032-09-17 07:00 | NA | Complete | Complete | NA |  | IC Request
SHOVELNOSE ENERGY STORAGE | 2009 | 2021-04-07 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-28 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 75 | 75 | Full Capacity |  | SAN LUIS OBISPO | CA | PGAE | Callender SW STA 115 kV | 2023-05-01 07:00 | 2023-05-01 07:00 | NA | None |  | NA |  | IC Request
CANNAE | 2010 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2025-03-27 07:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 118.5 | 115 |  | 115 | Full Capacity |  | KERN | CA | PGAE | Midway 115 kV | 2024-12-31 08:00 | 2030-12-03 08:00 | NA | Complete | Complete | NA |  | IC Request
GRAN VISTA | 2011 | 2021-04-15 | 2011-04-15 07:00 | WITHDRAWN | 2022-12-28 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 139.7 | 139.7 |  | 137.85 | Full Capacity | Off-Peak Deliverability | KERN | CA | PGAE | Midway-Wheeler Ridge #1 230 kV | 2024-07-31 07:00 | 2024-07-31 07:00 | NA | Complete |  | NA |  | IC Request
SEAGLASS OFFSHORE WIND | 2012 | 2021-04-15 | 2021-04-15 07:00 | WITHDRAWN | 2024-11-26 08:00 | C14 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 628.65 | 606.0588 | Full Capacity | Off-Peak Deliverability | SAN LUIS OBISPO | CA | PGAE | Morro Bay 230 kV | 2028-03-01 08:00 | 2032-06-01 07:00 | NA | Complete | Complete | NA |  | IC Request
ANDROMEDA | 2013 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2025-09-24 07:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 172.835 | 172.835 |  | 160 | Full Capacity | Off-Peak Deliverability | TULARE | CA | PGAE | Alpaugh 115 kV | 2026-12-31 08:00 | 2029-04-10 07:00 | NA | Complete | Complete | NA |  | Failure to Cure Deficiency
BRAVO WIND | 2014 | 2021-04-12 | 2021-04-15 07:00 | WITHDRAWN | 2024-06-17 07:00 | C14 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 1464.6 | 1400 | Full Capacity | Off-Peak Deliverability | SAN LUIS OBISPO | CA | PGAE | Diablo Canyon 500 kV | 2028-03-01 08:00 | 2034-02-17 08:00 | NA | Complete | Complete | NA |  | IC Request
CHERRYBLOSSOM HYBRID SOLAR | 2016 | 2021-04-15 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-10 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 65.46 | 131.4 |  | 130 | Full Capacity | Off-Peak Deliverability | SAN LUIS OBISPO | CA | PGAE | Solar Switching Station 230 kV | 2024-11-30 08:00 | 2024-11-30 08:00 | NA | Complete |  | NA
ARIELLA SOLAR | 2017 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2026-03-04 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 163.268 | 163.268 |  | 160 | Energy Only | Off-Peak Deliverability | TULARE | CA | PGAE | Olive 115 kV | 2023-12-31 08:00 | 2030-12-17 08:00 | NA | Complete | Complete | NA | Terminated | IC Request
SUR VISTA | 2019 | 2021-04-15 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-28 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 358.875 | 358.875 |  | 352.09 | Full Capacity | Off-Peak Deliverability | KERN | CA | PGAE | Midway Substation 230 kV | 2024-07-31 07:00 | 2024-07-31 07:00 | NA | Complete |  | NA |  | IC Request
RED STAR GRIZZLY OFFSHORE WIND | 2020 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-05 08:00 | C14 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 1039.5 | 1000 | Full Capacity | Off-Peak Deliverability | SAN LUIS OBISPO | CA | PGAE | Diablo Canyon Substation 500 kV | 2028-04-13 07:00 | 2028-04-13 07:00 | NA | Complete |  | NA |  | IC Request
LA PAZ 2 | 2021 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-09 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 516.7638 | 516.7638 |  | 500 | Full Capacity | Off-Peak Deliverability | MARICOPA | AZ | DCRT | Cielo Azul Substation 500 kV | 2028-04-01 07:00 | 2028-04-01 07:00 | NA |  |  | NA |  | IC Request
BRENDA RENEWABLE ENERGY COMPLEX | 2024 | 2021-04-02 | 2021-04-15 07:00 | WITHDRAWN | 2021-08-09 07:00 | C14 | Generating Facility Type-1: Photovoltaic; Generating Facility Fuel-1: Solar; MWs MW-1: 357.53 | 350 | Full Capacity | Off-Peak Deliverability | LA PAZ | AZ | DCRT | TWL Series Compensation Station 500 kV | 2025-12-31 08:00 | 2025-12-31 08:00 | NA |  |  | NA |  | IC Request
ADOBE FLATS | 2026 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-07 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 508.56 | 515.08 |  | 500 | Full Capacity | Off-Peak Deliverability | LA PAZ | AZ | DCRT | Cielo Azul Substation 500 kV | 2025-11-30 08:00 | 2025-11-30 08:00 | NA |  |  | NA |  | IC Request
PRIMROSE HYBRID | 2028 | 2021-04-13 | 2021-04-15 07:00 | WITHDRAWN | 2021-08-12 07:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 452.918 | 458.659 |  | 449.9969 | Full Capacity | Off-Peak Deliverability | MARICOPA | AZ | DCRT | Delaney Substation 500 kV | 2025-06-16 07:00 | 2025-06-16 07:00 | NA |  |  | NA |  | IC Request
EMPIRE | 2030 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-28 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 1646.568 | 1600 | Full Capacity |  | SAN BERNADINO | CA | SCE | Etiwanda Substation 230 kV | 2024-11-01 07:00 | 2024-11-01 07:00 | NA |  |  | NA |  | IC Request
MARLEY | 2031 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2025-10-31 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 206.091 | 200 | Full Capacity |  | RIVERSIDE | CA | SCE | Wildlife Substation 230 kV | 2024-11-01 07:00 | 2032-06-26 07:00 | NA | Complete | Complete | NA |  | IC Request
HUB CITY ENERGY STORAGE | 2034 | 2021-04-03 | 2021-04-15 07:00 | WITHDRAWN | 2025-11-13 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 261 | 250 | Partial Capacity |  | RIVERSIDE COUNTY | CA | SCE | Devers 220kV | 2025-06-01 07:00 | 2031-01-01 08:00 | NA | Complete | Complete | NA |  | Failure to Cure Deficiency
PELAGIC ENERGY STORAGE | 2035 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-13 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 404.1 | 400 | Full Capacity |  | RIVERSIDE | CA | SCE | Devers Substation 220 kV | 2024-08-01 07:00 | 2024-08-01 07:00 | NA | Complete |  | NA |  | IC Request
SARGASSO STORAGE | 2037 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2025-11-07 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 202.8 | 200 | Full Capacity |  | SAN BERNARDINO | CA | SCE | San Bernadino 230 kV | 2024-12-15 08:00 | 2032-05-26 07:00 | NA | Complete | Complete | NA |  | IC Request
RED ARCH HYBRID SOLAR | 2038 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2021-08-10 07:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 303.856 | 303.856 |  | 300 | Full Capacity | Off-Peak Deliverability | KERN | CA | SCE | Devers-El Casco line 230kV | 2025-12-15 08:00 | 2025-12-15 08:00 | NA |  |  | NA |  | IC Request
GARGANTUA STORAGE | 2040 | 2021-04-07 | 2021-04-15 07:00 | WITHDRAWN | 2021-08-16 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 253.2 | 250 | Full Capacity | Off-Peak Deliverability | RIVERSIDE | CA | SCE | Mirage Substation 230 kV | 2024-12-15 08:00 | 2024-12-15 08:00 | NA |  |  | NA |  | IC Request
PICADOR ENERGY STORAGE | 2043 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2025-10-13 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 252 | 250 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Etiwanda Substation 230 kV | 2024-08-01 07:00 | 2032-05-26 07:00 | NA | Complete | Complete | NA |  | IC Request
NATURA | 2044 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-03 07:00 | C14 | Storage | Photovoltaic | Wind Turbine | Battery | Solar | Wind Turbine | 207.92 | 207.92 | 207.2 | 200 | Full Capacity | Off-Peak Deliverability | RIVERSIDE | CA | SCE | DEVERS SUBSTATION 220 kV | 2025-12-15 08:00 | 2025-12-15 08:00 | NA |  |  | NA
ASHANTI HYBRID SOLAR | 2046 | 2021-04-12 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-02 07:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 325.1 | 325.1 |  | 320 | Full Capacity | Off-Peak Deliverability | RIVERSIDE | CA | SCE | Eagle Mountain Substation 220 kV | 2024-12-15 08:00 | 2024-12-15 08:00 | NA | Complete |  | NA |  | IC Request
LONGMEADOW HYBRID SOLAR | 2047 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-02 07:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 227.899 | 227.899 |  | 225 | Full Capacity | Off-Peak Deliverability | RIVERSIDE COUNTY | CA | SCE | Red Bluff Substation 220 kV | 2024-12-15 08:00 | 2024-12-15 08:00 | NA | Complete |  | NA |  | IC Request
ARDILLA | 2049 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2025-10-02 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 410.76 | 400 | Full Capacity |  | RIVERSIDE | CA | SCE | Devers Substation 230kV | 2025-11-30 08:00 | 2032-04-26 07:00 | NA | Complete | Complete | NA |  | IC Request
ETERNAL 2 | 2050 | 2021-04-13 | 2021-04-15 07:00 | WITHDRAWN | 2025-08-14 07:00 | C14 | Storage | Storage |  | Pumped-Storage hydro | Battery |  | 1417 | 1434.4 |  | 1400 | Energy Only | Off-Peak Deliverability | RIVERSIDE | CA | SCE | Red Bluff Substation 500 kV | 2026-12-01 08:00 | 2031-11-26 08:00 | NA | Complete | Complete | NA
SALVADOR | 2051 | 2021-04-13 | 2021-04-15 07:00 | WITHDRAWN | 2025-10-21 07:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 65 | 404.8 |  | 400 | Full Capacity | Off-Peak Deliverability | RIVERSIDE | CA | SCE | MIRAGE Substation 220 kV | 2025-12-15 08:00 | 2030-12-26 08:00 | NA | Complete | Complete | NA |  | IC Request
GOODALL STORAGE | 2053 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2021-09-13 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 510 | 500 | Full Capacity | Off-Peak Deliverability | SAN BERNARDINO | CA | SCE | Vista - Mira Loma 230 kV line | 2023-12-15 08:00 | 2023-12-15 08:00 | NA |  |  | NA |  | IC Request
GOLDENSTAR ENERGY STORAGE | 2054 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2022-10-31 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 213.55 | 200 | Full Capacity |  | LOS ANGELES | CA | SCE | Antelope Substation 220 kV | 2024-06-01 07:00 | 2024-06-01 07:00 | NA | Complete |  | NA |  | IC Request
QUERCUS | 2056 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2024-12-12 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 405.6634 | 400 | Full Capacity |  | LOS ANGELES | CA | SCE | Pardee-Vincent No1 230kV Line | 2024-06-30 07:00 | 2034-12-26 08:00 | NA | Complete | Complete | NA |  | IC Request
RESONATE | 2057 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-02 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 307.7 | 307.7 |  | 300 | Full Capacity | Off-Peak Deliverability | LOS ANGELES COUNTY | CA | SCE | WHIRLWIND Substation 230 kV | 2024-06-30 07:00 | 2024-06-30 07:00 | NA |  |  | NA |  | IC Request
FOUR CREEKS ENERGY STORAGE | 2058 | 2021-04-02 | 2021-04-15 07:00 | WITHDRAWN | 2025-09-09 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 261 | 250 | Full Capacity |  | TULARE | CA | SCE | Rector Substation 230 kV | 2025-06-01 07:00 | 2030-07-01 07:00 | NA | Complete | Complete | NA |  | IC Request
GILMORE SOLAR | 2063 | 2021-04-07 | 2021-04-15 07:00 | WITHDRAWN | 2021-09-28 07:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 214.9928 | 214.9928 |  | 200 | Full Capacity | Off-Peak Deliverability | TULARE | CA | SCE | Vestal Substation 230 kV | 2025-10-01 07:00 | 2025-10-01 07:00 | NA |  |  | NA |  | IC Request
BELLEFIELD SOLAR 4 | 2065 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-30 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 508.67 | 508.67 |  | 500 | Full Capacity | Off-Peak Deliverability | KERN | CA | SCE | Windhub Substation 500 kV | 2025-07-31 07:00 | 2025-07-31 07:00 | NA | Complete |  | NA |  | IC Request
WINOKA HYBRID SOLAR | 2067 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2021-08-10 07:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 253.88 | 253.88 |  | 250 | Full Capacity | Off-Peak Deliverability | KERN | CA | SCE | Highwind Substation 230 kV | 2024-12-15 08:00 | 2024-12-15 08:00 | NA |  |  | NA |  | IC Request
ADASTRA HYBRID SOLAR | 2069 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-30 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 354.6 | 354.6 |  | 350 | Full Capacity | Off-Peak Deliverability | TULARE | CA | SCE | Springville Substation 230 kV | 2025-12-15 08:00 | 2025-12-15 08:00 | NA |  |  | NA |  | IC Request
COLIMA HYBRID SOLAR | 2070 | 2021-04-06 | 2021-04-05 07:00 | WITHDRAWN | 2022-12-01 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 606.048 | 606.048 |  | 600 | Full Capacity | Off-Peak Deliverability | KERN | CA | SCE | Pastoria Substation 230 kV | 2024-12-15 08:00 | 2026-04-15 07:00 | NA |  |  | NA |  | IC Request
CONLOUGE SOLAR | 2071 | 2021-04-07 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-04 07:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 214.6866 | 213.7549 |  | 200 | Full Capacity | Off-Peak Deliverability | TULARE | CA | SCE | Springville Substation 230 kV | 2025-10-01 07:00 | 2025-10-01 07:00 | NA | Complete |  | NA |  | IC Request
DUPONT STORAGE | 2072 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-04 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 159.2593 | 150 | Full Capacity |  | VENTURA | CA | SCE | Moorpark Substation 230 kV | 2025-10-01 07:00 | 2025-10-01 07:00 | NA | Complete |  | NA |  | IC Request
ALPINE STORAGE | 2073 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-20 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 79.474 | 79 | Full Capacity |  | LOS ANGELES | CA | SCE | Neenach Substation 66 kV | 2024-04-01 07:00 | 2026-04-01 07:00 | NA | Complete |  | NA |  | IC Request
ALTA 1 STORAGE | 2074 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2021-09-10 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 150.79 | 150 | Full Capacity | Off-Peak Deliverability | KERN | CA | SCE | Windhub Substation 230 kV | 2024-04-01 07:00 | 2024-04-01 07:00 | NA |  |  | NA |  | IC Request
FAIRMONT SOLAR I | 2075 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2024-04-08 07:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 12 | 37.8 |  | 20 | Full Capacity | Off-Peak Deliverability | LOS ANGELES | CA | SCE | Antelope-Neenach 66kV line | 2023-12-15 08:00 | 2023-12-15 08:00 | NA | Complete |  | NA |  | IC Request
MICHELANGELO | 2076 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-15 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 204.5175 | 200 | Full Capacity |  | VENTURA | CA | SCE | Moorpark Substation 230 kV | 2024-11-01 07:00 | 2024-11-01 07:00 | NA |  |  | NA |  | IC Request
HUXLEY SOLAR | 2077 | 2021-04-02 | 2021-04-15 07:00 | WITHDRAWN | 2021-10-12 07:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 335.7 | 335.7 |  | 325 |  | Off-Peak Deliverability | LOS ANGELES | CA | SCE | Vincent Substation 230 kV | 2027-06-01 07:00 | 2027-06-01 07:00 | NA |  |  | NA
SLATE MOUNTAIN SOLAR | 2079 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-11 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 82.8 | 82.1 |  | 80 | Full Capacity | Off-Peak Deliverability | TULARE | CA | SCE | Springville Substation 230 kV | 2025-10-30 07:00 | 2027-12-01 08:00 | NA | Complete |  | NA |  | IC Request
RANGELAND SOLAR | 2080 | 2021-04-12 | 2021-04-15 07:00 | WITHDRAWN | 2025-08-29 07:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 113.832 | 102.672 |  | 210 | Full Capacity | Off-Peak Deliverability | LOS ANGELES | CA | SCE | Antelope- Magunden #2 230 kV line | 2024-10-30 07:00 | 2033-08-26 07:00 | NA | Complete | Complete | NA |  | IC Request
QUAIL LAKE STORAGE | 2083 | 2021-04-13 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-21 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 151.2 | 150 | Full Capacity |  | LOS ANGELES | CA | SCE | Bailey Substation 230 kV | 2025-11-01 07:00 | 2025-11-01 07:00 | NA | Complete |  | NA |  | IC Request
SOLAR FARM ENERGY CENTER | 2084 | 2021-04-12 | 2021-04-15 07:00 | WITHDRAWN | 2022-10-31 07:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 410.76 | 410.76 |  | 400 | Full Capacity | Off-Peak Deliverability | TULARE | CA | SCE | Rector Substation 230kV | 2026-11-30 08:00 | 2026-11-30 08:00 | NA |  |  | NA |  | IC Request
BISON PEAK | 2086 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2023-02-08 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Pumped-Storage hydro; MWs MW-1: 506 | 500 | Full Capacity |  | KERN | CA | SCE | WINDHUB Substation 230 kV | 2025-12-31 08:00 | 2025-12-31 08:00 | NA | Complete |  | NA |  | Failure to Cure Deficiency
EDISON DRIVE ENERGY STORAGE | 2087 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2022-08-26 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 672 | 660 | Full Capacity |  | VENTURA | CA | SCE | Moorpark Substation 230 kV | 2024-01-01 08:00 | 2024-01-01 08:00 | NA |  |  | NA |  | IC Request
AMARYLLIS SOLAR | 2088 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2021-09-15 07:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 215.4124 | 214.0983 |  | 200 | Full Capacity | Off-Peak Deliverability | TULARE | CA | SCE | Vestal Substation 220 kV | 2026-12-31 08:00 | 2026-12-31 08:00 | NA |  |  | NA |  | IC Request
GWENT STORAGE 2 | 2090 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2025-10-28 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 473 | 465 | Full Capacity |  | VENTURA | CA | SCE | Moorpark Substation 230 kV | 2023-12-15 08:00 | 2033-01-26 08:00 | NA | Complete | Complete | NA |  | IC Request
MAATHAI | 2091 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2025-11-18 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 256 | 250 | Full Capacity |  | LOS ANGELES | CA | SCE | Vincent Substation 230 kV | 2023-12-15 08:00 | 2033-01-26 08:00 | NA | Complete | Complete | NA | In Progress | IC Request
YEAGER MUSTANG | 2093 | 2021-04-15 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-24 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 407.63 | 407.63 |  | 400 | Full Capacity | Off-Peak Deliverability | KERN | CA | SCE | Whirlwind-Windhub 500 kV | 2024-09-01 07:00 | 2027-09-01 07:00 | NA | Complete |  | NA |  | IC Request
FITZGIBBONS SOLAR | 2094 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2021-08-09 07:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 200 | 200 |  | 200 | Full Capacity | Off-Peak Deliverability | SAN BERNARDINO | CA | SCE | Pisgah Substation 230 kV | 2025-10-01 07:00 | 2025-10-01 07:00 | NA |  |  | NA
LAKEY SOLAR | 2095 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-10 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 200 | 200 |  | 200 | Full Capacity | Off-Peak Deliverability | SAN BERNARDINO | CA | SCE | Victor Substation 230 kV | 2025-10-01 07:00 | 2025-10-01 07:00 | NA |  |  | NA |  | IC Request
CUERNO GRANDE WIND | 2098 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2024-12-11 08:00 | C14 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 150 | 150 | Full Capacity | Off-Peak Deliverability | SAN BERNARDINO | CA | SCE | Lugo-Pisgah 230 kV | 2025-10-01 07:00 | 2035-04-10 07:00 | NA | Complete | Complete | NA |  | IC Request
GRAVEL HILLS WIND & SOLAR | 2099 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-10 08:00 | C14 | Wind Turbine | Photovoltaic |  | Wind Turbine | Solar |  | 150 | 150 |  | 150 | Full Capacity | Off-Peak Deliverability | KERN | CA | SCE | Kramer Substation 230 kV | 2025-10-01 07:00 | 2025-10-01 07:00 | NA |  |  | NA |  | IC Request
SOUZA SOLAR | 2100 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2021-09-28 07:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 213.8183 | 214.808 |  | 200 | Full Capacity | Off-Peak Deliverability | LOS ANGELES | CA | SCE | Vincent-Lugo 500 kV line | 2025-10-01 07:00 | 2025-10-01 07:00 | NA |  |  | NA
ALTILIUM ENERGY STORAGE | 2102 | 2021-04-13 | 2021-04-15 07:00 | WITHDRAWN | 2021-09-09 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 404.25 | 400 | Full Capacity | Off-Peak Deliverability | SAN BERNADINO | CA | SCE | Victor Substation 230 kV | 2025-08-01 07:00 | 2025-08-01 07:00 | NA |  |  | NA |  | IC Request
PEARL GEOTHERMAL | 2106 | 2021-04-15 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-09 08:00 | C14 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 200 | 200 | Full Capacity |  | ESMERALDA COUNTY | NV | SCE | Control Substation 115 kV | 2025-02-01 08:00 | 2027-09-10 07:00 | NA | Complete |  | NA |  | IC Request
SUMMIT HYBRID | 2107 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-23 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 206.091 | 206.091 |  | 200 | Full Capacity | Off-Peak Deliverability | SAN BERNARDINO | CA | SCE | Kramer-Victor #1 230 kV line | 2025-06-01 07:00 | 2025-06-01 07:00 | NA |  |  | NA |  | IC Request
RED DIAMOND SOLAR | 2108 | 2021-09-30 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-03 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 61.9 | 61.9 |  | 60 | Full Capacity | Off-Peak Deliverability | SAN BERNARDINO | CA | SCE | Tortilla Substation 115 kV | 2025-10-30 07:00 | 2028-04-10 07:00 | NA |  |  | NA |  | IC Request
ADAGIO | 2109 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2025-11-19 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 405.6634 | 400 | Full Capacity |  | LOS ANGELES | CA | SCE | Hinson Substation 230 kV | 2024-06-30 07:00 | 2032-04-28 07:00 | NA | Complete | Complete | NA |  | IC Request
FLEA FLICKER ENERGY STORAGE | 2110 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2024-07-31 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 213.55 | 200 | Full Capacity |  | LOS ANGELES | CA | SCE | Vincent Substation 230 kV | 2024-06-01 07:00 | 2033-01-26 08:00 | NA | Complete | Complete | NA |  | Failure to Cure Deficiency
MAGNOLIA | 2112 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-07 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 405.6565 | 400 | Full Capacity |  | RIVERSIDE | CA | SCE | Mira Loma Substation 230 kV | 2024-06-30 07:00 | 2032-04-09 07:00 | NA |  |  | NA |  | IC Request
SPROUT | 2118 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-17 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 405.7509 | 400 | Full Capacity |  | LOS ANGELES | CA | SCE | Center S Substation 230 kV | 2024-06-30 07:00 | 2030-10-11 07:00 | NA |  |  | NA |  | IC Request
RISU | 2119 | 2021-04-05 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-16 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 252.6 | 250 | Full Capacity |  | ORANGE COUNTY | CA | SCE | Villa Park Substation 230 kV | 2024-06-30 07:00 | 2030-10-11 07:00 | NA |  |  | NA |  | IC Request
VOLTRON | 2120 | 2021-04-05 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-02 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 306 | 306 |  | 300 | Full Capacity | Off-Peak Deliverability | LOS ANGELES COUNTY | CA | SCE | Laguna Bell Substation 230 kV Substation | 2024-06-30 07:00 | 2024-06-30 07:00 | NA |  |  | NA |  | IC Request
JACIVA ENERGY STORAGE | 2122 | 2021-04-07 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-13 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 403.5 | 400 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Mira Loma Substation 230 kV | 2024-08-01 07:00 | 2024-08-01 07:00 | NA | Complete |  | NA |  | IC Request
SPINDLE ENERGY STORAGE | 2123 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-13 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 504.2 | 500 | Full Capacity |  | LOS ANGELES | CA | SCE | La Cienega Substation 230 kV | 2024-08-01 07:00 | 2024-08-01 07:00 | NA | Complete |  | NA |  | IC Request
FUERTE ENERGY STORAGE | 2126 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-18 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 554.4 | 550 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Mira Loma - Chino 230 #1 230 kV | 2024-08-01 07:00 | 2024-08-01 07:00 | NA | Complete |  | NA |  | IC Request
OTROS ALAMITOS ENERGY STORAGE | 2127 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2025-09-16 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 241.5 | 236 | Full Capacity |  | LOS ANGELES | CA | SCE | Alamitos 220 kV | 2025-10-30 07:00 | 2031-08-26 07:00 | NA | Complete | Complete | NA |  | IC Request
MANUEL STORAGE | 2128 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-13 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 150 | 150 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Chino Substation 230 kV | 2025-10-01 07:00 | 2025-10-01 07:00 | NA | Complete |  | NA |  | IC Request
LAS PILAS | 2130 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-13 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 204.5175 | 200 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Mira Loma Substation 230 kV | 2024-11-01 07:00 | 2024-11-01 07:00 | NA |  |  | NA |  | IC Request
RANGER | 2132 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-15 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 102.26 | 100 | Full Capacity |  | LOS ANGELES | CA | SCE | Laguna Bell Substation 230 kV | 2024-11-01 07:00 | 2024-11-01 07:00 | NA |  |  | NA |  | IC Request
LIVE OAK STORAGE | 2133 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2021-09-23 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 358.4412 | 350 | Full Capacity | Off-Peak Deliverability | SAN BERNARDINO | CA | SCE | San Bernadino 220 kV | 2024-06-01 07:00 | 2024-06-01 07:00 | NA |  |  | NA |  | IC Request
LOPEZ BESS | 2134 | 2021-04-12 | 2021-04-15 07:00 | WITHDRAWN | 2024-12-13 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 171.738 | 162.9 | Full Capacity |  | LOS ANGELES | CA | SCE | Sylmar-Gould line 230 kV | 2024-06-01 07:00 | 2033-06-26 07:00 | NA | Complete | Complete | NA |  | IC Request
CATHODE | 2135 | 2021-04-12 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-08 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 300 | 300 | Full Capacity |  | LOS ANGELES | CA | SCE | Hinson Substation 220kV | 2024-06-01 07:00 | 2024-06-01 07:00 | NA |  |  | NA |  | IC Request
MT BALDY ENERGY STORAGE | 2137 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2024-07-01 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 512.58 | 500 | Full Capacity |  | SAN BERNARDINO | CA | SCE | Mira Loma Substation 230 kV | 2025-06-01 07:00 | 2031-02-26 08:00 | NA | Complete | Complete | NA |  | IC Request
SEPARATOR UNIT 2 | 2138 | 2021-04-12 | 2021-04-15 07:00 | WITHDRAWN | 2024-05-22 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 300 | 300 | Full Capacity |  | ORANGE | CA | SCE | SERRANO Substation 220 kV | 2024-06-01 07:00 | 2031-01-26 08:00 | NA | Complete | Complete | NA |  | IC Request
ALUM GEOTHERMAL | 2143 | 2021-04-15 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-09 08:00 | C14 | Generating Facility Type-1: Steam Turbine; Generating Facility Fuel-1: Geothermal; MWs MW-1: 530 | 427.3 | Full Capacity |  | ESMERALDA COUNTY | NV | VEA | Beatty Substation 138 kV | 2025-02-01 08:00 | 2025-02-01 08:00 | NA | Complete |  | NA |  | IC Request
LAVA RIDGE WIND | 2151 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-13 08:00 | C14 | Storage | Wind Turbine |  | Battery | Wind Turbine |  | 510.1785 | 1156.1 |  | 1050 | Full Capacity | Off-Peak Deliverability | LINCOLN | ID | DSLK | Harry Allen-Eldorado 500 kV | 2024-06-01 07:00 | 2025-12-01 08:00 | NA |  |  | NA |  | IC Request
SALMON FALLS WIND | 2152 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-13 08:00 | C14 | Storage | Wind Turbine |  | Battery | Wind Turbine |  | 520 | 836.28 |  | 800 | Full Capacity | Off-Peak Deliverability | TWIN FALLS | ID | DSLK | Harry Allen-Eldorado 500 kV | 2025-06-01 07:00 | 2026-12-01 08:00 | NA | Complete |  | NA |  | IC Request
AMBER RAY | 2155 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-17 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 303.7533 | 300 | Full Capacity |  | SAN DIEGO | CA | SDGE | Chicarita Substation 138 kV | 2024-06-30 07:00 | 2027-04-12 07:00 | NA | Complete |  | NA |  | IC Request
SCIURUS | 2156 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-17 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 304.1932 | 300 | Full Capacity |  | ORANGE | CA | SDGE | Trabuco Substation 138 kV | 2024-06-30 07:00 | 2028-09-09 07:00 | NA | Complete |  | NA |  | IC Request
PALADIN | 2158 | 2021-04-01 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-11 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 304.1228 | 300 | Full Capacity |  | ORANGE | CA | SDGE | Rancho Mission Viejo Substation 138 kV | 2024-06-30 07:00 | 2024-06-30 07:00 | NA |  |  | NA |  | IC Request
BERNARDO ENERGY STORAGE | 2159 | 2021-04-02 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-23 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 157 | 150 | Full Capacity |  | SAN DIEGO | CA | SDGE | Artesian Ranch Substation 69 kV | 2025-06-01 07:00 | 2025-06-01 07:00 | NA |  |  | NA |  | IC Request
OLD STEEL BRIDGE BESS | 2160 | 2021-04-05 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-23 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 157 | 150 | Full Capacity |  | SAN DIEGO | CA | SDGE | Jamacha - Miguel 69 kV Line | 2025-06-01 07:00 | 2025-06-01 07:00 | NA |  |  | NA |  | IC Request
PAVION | 2163 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-18 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 400 | 400 | Full Capacity |  | SAN DIEGO | CA | SDGE | Talega Substation 230 kV | 2026-06-01 07:00 | 2026-06-01 07:00 | NA |  |  | NA |  | IC Request
PETREL STORAGE | 2164 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-16 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 51.099 | 50 | Full Capacity |  | SAN DIEGO | CA | SDGE | Friars Substation 138 kV | 2024-12-15 08:00 | 2024-12-15 08:00 | NA |  |  | NA |  | IC Request
TOWER 1 ENERGY STORAGE | 2165 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2025-09-08 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 105 | 100 | Full Capacity |  | SAN DIEGO | CA | SDGE | Ocean Ranch Substation 69 kV | 2025-06-01 07:00 | 2029-02-05 08:00 | NA | Complete | Complete | NA |  | IC Request
LAGO DOMINGO SOLAR | 2168 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-14 08:00 | C14 | Storage | Photovoltaic |  | Battery | Solar |  | 82.35 | 82.35 |  | 80 | Full Capacity | Off-Peak Deliverability | SAN DIEGO | CA | SDGE | Boulevard East Substation 69 kV | 2025-10-30 07:00 | 2025-10-30 07:00 | NA |  |  | NA |  | IC Request
SPANISH TABLE | 2169 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-13 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 100.8 | 100 | Full Capacity |  | SAN DIEGO | CA | SDGE | Border - Border Tap 69 kV | 2024-05-31 07:00 | 2024-05-31 07:00 | NA | Complete |  | NA |  | IC Request
JAPATUL VALLEY STORAGE | 2170 | 2021-04-11 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-09 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 308.2086 | 300 | Full Capacity |  | SAN DIEGO | CA | SDGE | Suncrest Substation 230 kV | 2024-12-31 08:00 | 2024-12-31 08:00 | NA |  |  | NA |  | IC Request
WEST HILLS ENERGY STORAGE | 2171 | 2021-04-07 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-23 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 261 | 250 | Full Capacity |  | SAN DIEGO | CA | SDGE | Sycamore Canyon Substation 230 kV | 2025-06-01 07:00 | 2025-06-01 07:00 | NA |  |  | NA |  | IC Request
HYDER | 2172 | 2021-04-06 | 2021-04-15 07:00 | WITHDRAWN | 2024-12-13 08:00 | C14 | Photovoltaic | Storage |  | Solar | Battery |  | 823.85 | 823.85 |  | 800 | Full Capacity | Off-Peak Deliverability | MARICOPA | AZ | SDGE | Hoodoo Wash - Hassayampa 500 kV Line | 2025-06-01 07:00 | 2035-06-05 07:00 | NA | Complete | Complete | NA
CHARGER STORAGE | 2174 | 2021-04-08 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-29 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 615.756 | 600 | Full Capacity |  | SAN DIEGO | CA | SDGE | Otay Mesa Switchyard 230 kV | 2025-10-30 07:00 | 2025-10-30 07:00 | NA |  |  | NA |  | IC Request
WINGED DOVE STORAGE | 2175 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2023-01-13 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 408.5 | 400 | Full Capacity |  | YUMA | AZ | SDGE | Hoodoo Wash Switchyard 500 kV | 2025-04-15 07:00 | 2028-03-11 08:00 | NA | Complete |  | NA |  | IC Request
BIERSTADT ENERGY STORAGE | 2179 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-09 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 100.365 | 99.99 | Full Capacity |  | SAN DIEGO | CA | SDGE | Border Substation 69 kV | 2024-06-01 07:00 | 2024-06-01 07:00 | NA |  |  | NA |  | IC Request
PINSCHER ENERGY STORAGE | 2181 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2024-07-17 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 150.521 | 149.91 | Full Capacity |  | SAN DIEGO | CA | SDGE | Carrizo Gorge Switchyard 138 kV | 2024-06-01 07:00 | 2029-02-05 08:00 | NA | Complete | Complete | NA |  | IC Request
TAYLOR STORAGE | 2182 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2025-07-17 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 101.9 | 100 | Energy Only |  | SAN DIEGO | CA | SDGE | Chicarita Substation 138 kV | 2025-11-01 07:00 | 2029-12-01 08:00 | NA | Complete | Complete | NA |  | IC Request
HELIX STORAGE | 2183 | 2021-04-09 | 2021-04-15 07:00 | WITHDRAWN | 2021-08-20 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 81.6 | 80 | Full Capacity | Off-Peak Deliverability | SAN DIEGO | CA | SDGE | Spring Valley Substation 69 kV | 2025-11-01 07:00 | 2025-11-01 07:00 | NA |  |  | NA |  | IC Request
AMBERJACK ENERGY STORAGE | 2184 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2025-09-03 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 100.6499 | 100 | Full Capacity |  | SAN DIEGO | CA | SDGE | Loveland - Alpine 69 kV Line | 2024-11-30 08:00 | 2034-02-05 08:00 | NA | Complete | Complete | NA
EOLICA DE RUMOROSA | 2187 | 2021-04-13 | 2021-04-15 07:00 | WITHDRAWN | 2024-06-18 07:00 | C14 | Generating Facility Type-1: Wind Turbine; Generating Facility Fuel-1: Wind Turbine; MWs MW-1: 940.8 | 900 | Full Capacity | Off-Peak Deliverability | TECATE BAJA CALIFORNIA MEXICO | CA | SDGE | East County Substation 500 kV | 2028-03-31 07:00 | 2035-05-05 07:00 | NA | Complete | Complete | NA |  | IC Request
GERANIUM ENERGY STORAGE | 2188 | 2021-04-15 | 2021-04-15 07:00 | WITHDRAWN | 2026-02-13 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 51.4 | 50 | Full Capacity |  | SAN DIEGO | CA | SDGE | Miguel Substation 69 kV | 2023-12-31 08:00 | 2029-02-05 08:00 | NA | Complete | Complete | NA |  | IC Request
LA FUENTE ENERGY STORAGE | 2189 | 2021-04-14 | 2021-04-15 07:00 | WITHDRAWN | 2022-12-18 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 105.9831 | 100 | Full Capacity |  | SAN DIEGO | CA | SDGE | Otay Mesa Switchyard 230 kV | 2024-06-01 07:00 | 2024-06-01 07:00 | NA |  |  | NA |  | IC Request
HERMES ENERGY STORAGE | 2190 | 2021-04-15 | 2021-04-15 07:00 | WITHDRAWN | 2021-09-03 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 154.6 | 150 | Full Capacity | Off-Peak Deliverability | SAN DIEGO | CA | SDGE | Border Substation 69 kV | 2024-06-01 07:00 | 2024-06-01 07:00 | NA |  |  | NA |  | IC Request
FREIGHT ENERGY STORAGE | 2191 | 2021-04-15 | 2021-04-15 07:00 | WITHDRAWN | 2022-11-03 07:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 51.75 | 50 | Full Capacity |  | SAN DIEGO | CA | SDGE | Border Substation 69 kV | 2025-06-01 07:00 | 2025-06-01 07:00 | NA |  |  | NA |  | IC Request
PAJARO VALLEY STORAGE | 2192 | 2021-04-13 | 2021-04-15 07:00 | WITHDRAWN | 2026-02-04 08:00 | C14 | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 102.04 | 100 | Full Capacity |  | SAN DIEGO | CA | SDGE | Salt Creek Substation 69 kV | 2024-09-01 07:00 | 2030-03-05 08:00 | NA | Complete | Complete | NA |  | IC Request
VENTANA ENERGY STORAGE | 2193 | 2021-11-19 | 2022-06-03 07:00 | WITHDRAWN | 2022-08-11 07:00 | ISP | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 254.3 | 250 | Full Capacity | Off-Peak Deliverability | SAN BERNARDINO | CA | SCE | Lugo | 2024-06-01 07:00 | 2024-06-01 07:00 | NA |  |  | NA |  | IC Request
PRONGHORN ENERGY STORAGE | 2194 | 2022-05-07 | 2022-06-13 07:00 | WITHDRAWN | 2022-08-18 07:00 | ISP | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 122.6 | 120 | Full Capacity | Off-Peak Deliverability | LOS ANGELES | CA | SCE | Antelope | 2026-06-01 07:00 | 2026-06-01 07:00 | NA |  |  | NA |  | IC Request
MALAGA BESS | 2196 | 2022-09-10 | 2023-01-04 08:00 | WITHDRAWN | 2024-11-27 08:00 | ISP | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 46.28 | 44 | Full Capacity | Off-Peak Deliverability | FRESNO | CA | PGAE | Malaga 115 kV | 2024-11-06 08:00 | 2024-11-06 08:00 | NA |  |  | NA
VENTANA RELIABILITY PROJECT | 2197 | 2022-09-29 | 2023-01-11 08:00 | WITHDRAWN | 2023-04-05 07:00 | ISP | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 254.3 | 250 | Full Capacity | Off-Peak Deliverability | SAN BERNARDINO | CA | SCE | Lugo | 2024-06-01 07:00 | 2024-06-01 07:00 | NA |  |  | NA |  | Failure to Cure Deficiency
VISTA RELIABILITY | 2198 | 2022-10-14 | 2023-01-31 08:00 | WITHDRAWN | 2023-04-05 07:00 | ISP | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 254.3 | 250 | Full Capacity | Off-Peak Deliverability | LOS ANGELES | CA | SCE | Vincent | 2024-06-01 07:00 | 2024-06-01 07:00 | NA |  |  | NA |  | Failure to Cure Deficiency
TUNGSTEN BESS | 2199 | 2023-01-31 | 2023-03-02 08:00 | WITHDRAWN | 2024-11-27 08:00 | ISP | Generating Facility Type-1: Storage; Generating Facility Fuel-1: Battery; MWs MW-1: 126 | 120 | Full Capacity | Off-Peak Deliverability | SAN BERNARDINO | CA | SCE | Victor Substation 230 kV | 2026-05-01 07:00 | 2026-05-01 07:00 | NA |  |  | NA
The contents of these pages are subject to change without notice. Decisions based on information contained within the California ISO's web site are the visitor's sole responsibility.